## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CTN-ITP-021 - Ride Quality for Pavements | itp |  |  |  |  | CTN-ITP-021 - Ride Quality for Pavements
checkpoint | 1.1 - Plant and Equipment
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Plant and equipment used in the Works are appropriate to achieve specification requirements
label | Reference Documents - N/A
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.1 - Measurement of Ride Quality
label | Frequency - Each lot
label | Acceptance Criteria - The Contractor shall comply with the requirements for both the Maximum Individual Lane Roughness and Maximum Mean Lane Roughness as follows:
label | (a) Individual Lane Roughness
label | ○ Where an Individual Lane Roughness Value in any 100 m sub-section is greater than the specified Maximum Individual Lane Roughness Value specified in Table 180.092, the Contractor shall rectify work within the sub-section to comply with this requirement. The minimum length of rectification work undertaken shall be 100 m.
label | ○ All rectified 100 m sub-sections shall be re-tested following completion of rectification work.
label | (b) Mean Lane Roughness
label | ○ Where the Mean Lane Roughness Value of a lot is greater than the Mean Lane Roughness specified in Table 180.092, the work shall be rectified unless the Superintendent agrees to accept the work at a reduced payment. Where the lot is to be rectified, the minimum length for any rectification work undertaken shall be 100 m. Where the Superintendent agrees to accept the lot at a reduced payment, a deduction to the contract sum shall be made in accordance with Clause 180.06.
label | ○ The Contractor shall re-test the lot following completion of any rectification work.
label | Reference Documents - 180.05, Table 180.092
label | Inspection / Test Method - Measure
label | Record of conformity - Test Report
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: