## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Foreman and Site Manager Job planning Prior to meeting PM |  |  |  |  | Yes | Foreman and Site Manager Job planning Prior to meeting PM | 07d005bc-7552-4663-8712-bc94eb258852
checkpoint-no-status |  |  | checkpoint | Foreman and Site Manager Job planning Prior to meeting PM
text | 30dc9a7d-112e-5731-b0d9-65314f6cd77f |  | textbox | Project details:
text | 6c0b0e93-af96-5422-bf8c-29b8b1fe0280 |  | textbox | Client:
text | 19327e34-5b33-5505-ae35-5c17a0240c59 |  | textbox | Address:
text | 3874c4d8-3533-5b41-87eb-87555e86cbe1 |  | textbox | Other:
text | 6304ed4b-369a-5d2d-9c57-f171afd2857a |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review plans, including engineer set and build question sheet
checkpoint-status |  |  | checkpoint | Go over PM's Job schedule
checkpoint-status |  |  | checkpoint | Identify key dates
checkpoint-status |  |  | checkpoint | Deliveries
checkpoint-status |  |  | checkpoint | QA's
checkpoint-status |  |  | checkpoint | Inspections
checkpoint-status |  |  | checkpoint | Pour dates
checkpoint-status |  |  | checkpoint | Identify materials used
checkpoint-status |  |  | checkpoint | DPM
checkpoint-status |  |  | checkpoint | Steel
checkpoint-status |  |  | checkpoint | Mebrane type
checkpoint-status |  |  | checkpoint | Boxing required
checkpoint-status |  |  | checkpoint | Identify survey plan and Heights
checkpoint-status |  |  | checkpoint | Identify waterproofing locations and where DPM ends
checkpoint-status |  |  | checkpoint | If we have footing outside of building lines, top of footings in these loctions need to be at least 200 mm below FFL
checklist-flat |  |  | checklist | 3 Site Manager and Foreman job planning prior to meeting PM (SM / F) |  |  |  |  | Yes | 3 Site Manager and Foreman job planning prior to meeting PM (SM / F) | 0d4a747f-0ab7-4788-a8da-843cdee69421
checkpoint-no-status |  |  | checkpoint | Foreman and Site Manager Job planning Prior to meeting PM
text | ac23d3b9-e511-5433-bcee-32be0de9e9c4 |  | textbox | Project details:
text | 57bc8ccf-fbfb-52f1-bee6-2fee40e82172 |  | textbox | Client:
text | 184c0ccd-a80d-55fd-a357-099ea21489f3 |  | textbox | Address:
text | 6a1d6b49-af64-527c-82f9-794c67a356ef |  | textbox | Other:
text | 0870a453-152c-5d5b-b6a3-fccd28f7a563 |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review plans, including engineer set and build question sheet
checkpoint-status |  |  | checkpoint | Go over PM's Job schedule
checkpoint-status |  |  | checkpoint | Identify key dates
checkpoint-status |  |  | checkpoint | Deliveries
checkpoint-status |  |  | checkpoint | QA's
checkpoint-status |  |  | checkpoint | Inspections
checkpoint-status |  |  | checkpoint | Pour dates
checkpoint-status |  |  | checkpoint | Identify materials used
checkpoint-status |  |  | checkpoint | DPM
checkpoint-status |  |  | checkpoint | Steel
checkpoint-status |  |  | checkpoint | Mebrane type
checkpoint-status |  |  | checkpoint | Boxing required
checkpoint-status |  |  | checkpoint | Identify survey plan and Heights
checkpoint-status |  |  | checkpoint | Identify waterproofing locations and where DPM ends
checkpoint-status |  |  | checkpoint | If we have footing outside of building lines, top of footings in these loctions need to be at least 200 mm below FFL
checklist-flat |  |  | checklist | 4 Site Manager and Foreman Question Sheet (SM / F) |  |  |  |  | Yes | 4 Site Manager and Foreman Question Sheet (SM / F) | 0e48b3c1-ebb0-41c4-b6ff-09da351dfb79
checkpoint-status |  |  | checkpoint | Do you understand profile and survey setout or do you require more information?
checkpoint-status |  |  | checkpoint | Are your survey marks off grid lines or building lines?
button | 89e9ef06-ef9f-51dd-b0f9-58a8ccdc593f |  | button |  | Grid lines, Building Lines
checkpoint-status |  |  | checkpoint | Item Details
boolean | 50aad029-2878-5d05-9e55-257f17afa42d |  | tickbox | Do you understand all heights?
boolean | 4736bd63-a094-5d61-8be7-7b72923b0508 |  | tickbox | Do you have all dimensions?
text | d089dffd-d1fa-57de-a4c2-81d236c7707f |  | textbox | What formwork are you using for each component of the job?
checkpoint-status |  |  | checkpoint | Has the formwork and bracing been organised to be onsite before you require it?
checkpoint-status |  |  | checkpoint | Material Details
text | 6e0b9a80-0365-506c-af91-4f26b65f7c60 |  | textbox | Where have your materials been ordered from?
date | f5032521-914d-526a-8c25-71c43c75285e |  | date | What date do you expect your materials to be delivered?
checkpoint-status |  |  | checkpoint | Have all materials been ordered to site or do you need to pickup materials? If so, notify your van.
button | daca5fd2-9a9f-5f4c-afcc-fa46dc6d139a |  | button |  | To Site, Pickup
checkpoint-status |  |  | checkpoint | Key Dates
text | 399c32ac-558c-58e6-8da1-70cf96580c6e |  | textbox | Identify key dates to make
text | 8206f5b4-7236-5262-aa38-7175e42a1091 |  | textbox | Identify inspection dates
checkpoint-status |  |  | checkpoint | DPM & Waterproofing
text | 582fdbda-10c5-56ba-a0c1-1c105d8ad446 |  | textbox | What DPM and tape required?
boolean | c7af4209-4fe2-5628-beb5-19113fd22cb4 |  | tickbox | Has this been ordered?
text | 14e258ec-bc88-5d04-8025-e1d2aeff0b48 |  | textbox | Waterproofing - Identify waterproofing location
boolean | 70811c16-c6ef-5593-93cf-3bbd151e007f |  | tickbox | Make sure digout accounts for waterproofers
boolean | cdb985d1-4e7e-5444-af47-bb4a4b129bf6 |  | tickbox | Go over van load out list with your van
boolean | 85453de5-65f8-509f-a597-4ec274aac047 |  | tickbox | Has your van got everything needed for the job
text | b74310be-1cf0-55b7-bb5f-27bec9297924 |  | textbox | Rebates
text | b18186f8-217a-52d3-b425-da29e9e609d3 |  | textbox | Profile timber and walls
checklist-flat |  |  | checklist | 6 Site Manager and Foreman’s Job planning (SM / F) |  |  |  |  | Yes | 6 Site Manager and Foreman’s Job planning (SM / F) | 13fb59b3-8dc6-4902-beec-12f5830b278d
checkpoint-no-status |  |  | checkpoint | Project Details
text | 03d3792b-1e64-5035-8f2b-276a17dd964e |  | textbox | Project Details:
text | a7993000-4957-5037-b227-34c443b2d970 |  | textbox | Client:
text | e1c64352-2f35-50ab-9e9e-65ba8f1b20c7 |  | textbox | Address:
text | 3e6b7e68-b152-5960-b125-a19a59f947ff |  | textbox | Other:
text | 8483ea4e-5624-5721-9aab-429185631e11 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Job built from start to finish - Compare with Program
checkpoint-status |  |  | checkpoint | Design issues noted and send to client
checkpoint-status |  |  | checkpoint | Site Specific OTWC requirements - Send to client
checkpoint-status |  |  | checkpoint | Master Program built and send to client
label | 9d71563a-3f42-5216-8209-263509693b11 |  | note | To include materials drop offs
label | 195bbfc8-0918-53a8-9a7c-7068daeeaa06 |  | note | To include formwork required
label | 62f289c3-a78c-5447-b16e-d9b7ff59d8c7 |  | note | To include concrete bookings
label | f4bf7936-e1a8-58bb-92a9-d9bbcf0d24a3 |  | note | To include inspections
checkpoint-status |  |  | checkpoint | Concrete bookings insert into Concrete Schedule
checkpoint-status |  |  | checkpoint | Material bookings into Material Schedule
checkpoint-status |  |  | checkpoint | Site Manager to get a copy of the Job Schedule
checkpoint-status |  |  | checkpoint | Schedule to have Toolbox Meeting
checklist-flat |  |  | checklist | 5 PM handover to Site Manager and Forman (PM / SM / F) |  |  |  |  | Yes | 5 PM handover to Site Manager and Forman (PM / SM / F) | 22b13cbf-27e1-488f-8485-26e747c6974b
checkpoint-status |  |  | checkpoint | Have you reviewed Plans/Job Schedule?
checkpoint-status |  |  | checkpoint | Do you understand survey markout grids? Building lines?
checkpoint-status |  |  | checkpoint | Heights:
text | 4f480cad-db9b-5509-ba57-ab62a60d57ca |  | textbox | Footing Depth
text | c904af7a-6d78-5a85-a991-95fa1544e798 |  | textbox | Bottom of footing measurement
text | dec5f034-f412-5a80-8fc8-0b7ebc40f316 |  | textbox | Top of footing measurement
text | be202197-73b2-5816-8317-dcf1d78ba7f4 |  | textbox | Finish Floor Line (FFL)
text | 7fab818c-ebbc-5f19-91e6-acb454628b4a |  | textbox | Block wall heights
text | 85b94ec1-0a7f-5647-8eab-5ca6cfc87dc1 |  | textbox | Insitu wall heights
checkpoint-status |  |  | checkpoint | Have you got all dimensions?
checkpoint-status |  |  | checkpoint | Show Foreman complicated components of Job and solutions
checkpoint-status |  |  | checkpoint | DPM require/tape
checkpoint-status |  |  | checkpoint | Waterproofing locations, explain importance of larger digout in these locations:
label | 9f86dfec-4d54-5ede-ad0b-d310ffeab4ad |  | note | Go over Engineer Details
label | 870fb9b1-1349-5e3c-95c4-885891d5ca89 |  | note | Go over Building Methodology
label | 50785104-99cc-5ad5-a321-4945a67b191c |  | note | Go over Key dates
label | 907df799-a127-51e1-9ed8-c60ee1e45084 |  | note | Go over size of team
label | f23537f6-c3b8-586a-8279-52bcb2e652b3 |  | note | Go over rebates
label | f1de7315-2ba2-531b-9152-e736015979af |  | note | Go over penetrations
checkpoint-status |  |  | checkpoint | Materials to site
checkpoint-status |  |  | checkpoint | What has been allowed/ and what hasn't
checkpoint-status |  |  | checkpoint | What needs to be taken to site
checkpoint-status |  |  | checkpoint | Any other points/discussion:
checklist-flat |  |  | checklist | 1 Job estimation handover (QS / PM) |  |  |  |  | Yes | 1 Job estimation handover (QS / PM) | 24cf0f59-ab36-4da6-bf09-355fc03cc096
checkpoint-no-status |  |  | checkpoint | Project Details
text | ebcd3623-ffa4-5d68-9007-1a8496065bde |  | textbox | Project Details:
text | c6504904-116a-5605-876a-f06029b2abdc |  | textbox | Client:
text | b6283aac-b4ac-5258-9830-8f6f2fee499d |  | textbox | Address:
text | 8af42d01-ce1e-559d-8434-251aa680e78c |  | textbox | Other:
text | 86e11169-6e47-5565-8fc4-e35d9c61dd6c |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Estimator and Project Team - Discuss quoted job (QS/PM)
checkpoint-status |  |  | checkpoint | Critical tags discussed
checkpoint-status |  |  | checkpoint | Any tender ageement with subcontractors and supplier discussed and documented. (Who are the subcontractors and suppliers)
checkpoint-status |  |  | checkpoint | Tender and risks and opportunities discussed with project team
checkpoint-status |  |  | checkpoint | P&G Allowances
checkpoint-status |  |  | checkpoint | Tender discuss and approved by relevant person/s
checkpoint-status |  |  | checkpoint | Formwork / Propping / Rebates allowed for Job
checkpoint-status |  |  | checkpoint | Program and Labour allowances for each phase of the job
checkpoint-status |  |  | checkpoint | Any other job information that needs to be handed over.
checklist-flat |  |  | checklist | 8 Site inspection Pre-job start Site Manager and Foreman (SM / F) |  |  |  |  | Yes | 8 Site inspection Pre-job start Site Manager and Foreman (SM / F) | 4b472336-e037-4388-b72b-b5f61a40d8ea
checkpoint-no-status |  |  | checkpoint | Site Inspection Pre Job Starting - Site Manager and Foreman
text | b7e8e567-2e6e-5d58-8c82-66b8761857d9 |  | textbox | Project Details:
text | 04b1d1bb-e2f9-51ed-98bb-93e3aefaf793 |  | textbox | Client:
text | 7f484c2c-6fd4-5935-80cc-2ef5d0155687 |  | textbox | Address:
text | 438c8484-00e2-570e-95cb-4dffe08da225 |  | textbox | Other:
text | 9b006481-13e6-5970-b0cd-53b4fadd7235 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Traffic management required for our job scope?
checkpoint-status |  |  | checkpoint | If so, has the client been informed and agreed it will be in place for our start date?
checkpoint-status |  |  | checkpoint | Have materials been dropped off?
checkpoint-status |  |  | checkpoint | If not, contact suppliers, let them know where you want materials delivered and what is delivery time and date:
checkpoint-status |  |  | checkpoint | Identify workstations
checkpoint-status |  |  | checkpoint | Pod cutting station outside of slab
checkpoint-status |  |  | checkpoint | Steel bending and cutting station
checkpoint-status |  |  | checkpoint | Timber cutting station
checkpoint-status |  |  | checkpoint | Skip bin onsite?
checkpoint-status |  |  | checkpoint | Portaloo onsite?
checkpoint-status |  |  | checkpoint | Power to site?
checkpoint-status |  |  | checkpoint | Water to site?
checkpoint-status |  |  | checkpoint | Site box and work drawings?
checkpoint-status |  |  | checkpoint | If none of the above are onsite and are needed for us, has client been informed?
checkpoint-status |  |  | checkpoint | Boundary and survey set outs/pegs been done?
checkpoint-status |  |  | checkpoint | Cut heights and locations as OTWC requirements?
checkpoint-status |  |  | checkpoint | If not, has client been informed and start date been changed for the problem to be sorted?
checkpoint-status |  |  | checkpoint | OTWC vehicle parking confirmed with client & the location has been identified?
checkpoint-status |  |  | checkpoint | Any other issues that need to be brought up to client?
checkpoint-status |  |  | checkpoint | If so, has client been informed?
checklist-flat |  |  | checklist | Site Inspection Pre Job Starting - Site Manager and Foreman |  |  |  |  | Yes | Site Inspection Pre Job Starting - Site Manager and Foreman | 5b798b98-819e-449e-9822-1a47d477938f
checkpoint-no-status |  |  | checkpoint | Site Inspection Pre Job Starting - Site Manager and Foreman
text | e3aac975-cfa6-5499-bc5e-5837ad382d60 |  | textbox | Project Details:
text | ae0472df-bf75-5a90-a4ce-80da5281a471 |  | textbox | Client:
text | 091248a0-d8df-5267-8158-d0bc3ba0529a |  | textbox | Address:
text | 5cc98935-2241-5706-8892-cc69a3c2301e |  | textbox | Other:
text | e7119dfb-1114-5f44-91bc-1a05828414b3 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Traffic management required for our job scope?
checkpoint-status |  |  | checkpoint | If so, has the client been informed and agreed it will be in place for our start date?
checkpoint-status |  |  | checkpoint | Have materials been dropped off?
checkpoint-status |  |  | checkpoint | If not, contact suppliers, let them know where you want materials delivered and what is delivery time and date:
checkpoint-status |  |  | checkpoint | Identify workstations
checkpoint-status |  |  | checkpoint | Pod cutting station outside of slab
checkpoint-status |  |  | checkpoint | Steel bending and cutting station
checkpoint-status |  |  | checkpoint | Timber cutting station
checkpoint-status |  |  | checkpoint | Skip bin onsite?
checkpoint-status |  |  | checkpoint | Portaloo onsite?
checkpoint-status |  |  | checkpoint | Power to site?
checkpoint-status |  |  | checkpoint | Water to site?
checkpoint-status |  |  | checkpoint | Site box and work drawings?
checkpoint-status |  |  | checkpoint | If none of the above are onsite and are needed for us, has client been informed?
checkpoint-status |  |  | checkpoint | Boundary and survey set outs/pegs been done?
checkpoint-status |  |  | checkpoint | Cut heights and locations as OTWC requirements?
checkpoint-status |  |  | checkpoint | If not, has client been informed and start date been changed for the problem to be sorted?
checkpoint-status |  |  | checkpoint | OTWC vehicle parking confirmed with client & the location has been identified?
checkpoint-status |  |  | checkpoint | Any other issues that need to be brought up to client?
checkpoint-status |  |  | checkpoint | If so, has client been informed?
checklist-flat |  |  | checklist | 2.1 Slab Installation Methodology |  |  |  |  | Yes | 2.1 Slab Installation Methodology | 722610e0-b7c5-4389-b5f0-b3c47e968931
checkpoint-no-status |  |  | checkpoint | What is FFL
checkpoint-status |  |  | checkpoint | Set Profiles to 30 mm above FFL and stransfer gridlines onto profiles
checkpoint-status |  |  | checkpoint | Set up stringlines, check measurements and diagonals
checkpoint-status |  |  | checkpoint | Clean / wash down all footings and Block wall header blocks
checkpoint-status |  |  | checkpoint | Check all prep heights are within tolerance
checkpoint-status |  |  | checkpoint | Set Edgebeam and Rebates set to FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Set correct Edgebeam face running down correct gridlines (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Joinery Rebates set to required depths (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Garage Rebate set as per client requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All waratahs have starter caps on (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Site Cleaned / Rubbish in bin/ Materials located in centralised locations/ Ready for Plumbers?
checkpoint-status |  |  | checkpoint | Steel and Pod cutting loctions outside of pad established (centralise all rubbish to one location)
checkpoint-status |  |  | checkpoint | Pods have been cut outside the slab
checkpoint-status |  |  | checkpoint | All steel has minimum bottom cover (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from form work (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All bends tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps minimum lap requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from form work and rebates (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minum cover from services (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Stringline run and left up in multiple places to prove cover from FFL to top of Mesh for engineer and council (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates set to correct depth from FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Floor checked all over to make sure no steel is above FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Thickening measurement as per plan and same top and bottom (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM up to edgebeam (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Services taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inside pad free from rubbish (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Starter caps on all waratahs or exposed starters (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Rubbish in bins and site cleaned up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess boxing and steel stacked neatly and out of lay teams way, ready for pick up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Nothing around the slab and in way of Lay team (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess pods and pod rubbish been collected or supplier been called to pick up
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates in correct slab position (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Formwork Sprayed with form release (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team been organised
checklist-flat |  |  | checklist | 2 Job handover to Site Manager and Foreman (PM) |  |  |  |  | Yes | 2 Job handover to Site Manager and Foreman (PM) | 76db13df-91e2-4819-bb05-d14f5e6020cd
checkpoint-no-status |  |  | checkpoint | Project Details:
text | e12219f0-c25a-5aa0-900b-5a7396a1c9e4 |  | textbox | Client:
text | d9cf5765-fe9e-5192-a87c-4642374f7334 |  | textbox | Address:
text | e3e481fa-9af4-5c50-a7a8-f2d6b4cec8c2 |  | textbox | Other:
text | 4de3f32a-b051-58b7-812a-5a3206ffb00b |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Send Foreman Job Question Sheet
checkpoint-status |  |  | checkpoint | Get Foreman to review plans before coming in to see you
checkpoint-status |  |  | checkpoint | Have Master Schedule sent
checkpoint-status |  |  | checkpoint | Have survey serout and plan sent
checkpoint-status |  |  | checkpoint | Make sure Foreman knows if we are working off grids or building lines
checkpoint-status |  |  | checkpoint | Make sure they know heights
text | 8b5b8633-4883-561a-88df-c45cc207ab15 |  | textbox | Footings height:
text | fa1599aa-56bf-5c49-8176-0ecd16cfff8e |  | textbox | Block/wall heights:
text | beb4bf44-7293-573a-be59-957fdd9ba411 |  | textbox | Finish floor levels:
text | 6d67fe3a-e901-555d-90f3-7ed63d9ecc1f |  | textbox | Lift pit levels:
text | a9d0b22f-f480-5fd1-8ecd-2a9347babcc4 |  | textbox | Finish Ground Levels (for footings outside of building lines)
checkpoint-status |  |  | checkpoint | DPM require
checkpoint-status |  |  | checkpoint | Waterproofing areas
checkpoint-status |  |  | checkpoint | Formworks and bracing required and what was quoted
checklist-flat |  |  | checklist | Foreman's Job Planning |  |  |  |  | Yes | Foreman's Job Planning | 7c37c2b9-3b09-4fab-913c-f770d77389f0
checkpoint-no-status |  |  | checkpoint | Foreman's Job Planning
text | dd79810e-7537-5a78-bd4b-bac8d6822992 |  | textbox | Project Details:
text | cfc6641a-e658-592f-9dcf-4177c8b55534 |  | textbox | Client:
text | 5d17ed81-f44a-5bed-860f-c6de39cff22a |  | textbox | Address:
text | 89f6cd5e-2b57-5b2e-9df5-9a620344182e |  | textbox | Other:
text | dee635b6-8c91-56af-a0b6-9db3624562f7 |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review Master Schedule
checkpoint-status |  |  | checkpoint | Plan Days / Weeks according to Master schedule; Labour size and tasks to complete
checkpoint-status |  |  | checkpoint | Bring your team in for and go over job with them, explain the job file
checkpoint-status |  |  | checkpoint | Make sure Van is loaded with everything it will need for the job
checkpoint-status |  |  | checkpoint | Team book and load trailer as required, day prior to job starting
checkpoint-status |  |  | checkpoint | Remember Monday morning Toolboxes and Friday debriefs
checklist-flat |  |  | checklist | 3.2 Footing Pre Pour Quality Assurance |  |  |  |  | Yes | 3.2 Footing Pre Pour Quality Assurance | 7ea42101-48f9-4b05-b786-434b22a0aa3b
checkpoint-status |  |  | checkpoint | Check all top of footing heights and make sure they are as per plan? Label as footing engineer detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | All footing depths as per plan? Label as per engineer footing detail( Multiple photos required)
checkpoint-status |  |  | checkpoint | All footing widths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Specified DPM used in footings? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All DPM laps taped? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Waterproofing membrane in required parts of footing? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel bottom minimum bottom cover achieved in all places (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel minimum side cover achieved in all places (Boxing or to earth)(Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends all tied? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends as per minimum lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Bottom mat of footing spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Top mat spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect bottom mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continous bent steel to connect top mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | Where footings step up, have Z bends and horizontals been installed as per engineer design. (Multiple photos required)
checkpoint-status |  |  | checkpoint | On step ups, form work set to footing depth and no more? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter Line been profiles and set as per engineer requirements from block / earth face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Starters within 5 mm of engineer plans from block face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter spacings set as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter lap for post concrete pour, set to have minimum steel lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Height pegs or nails installed and sprayed for Lay team (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Footings clear from rubbish and dirt (Multiple photos required)
checkpoint-status |  |  | checkpoint | All waratahs and starters have starter caps on (Multiple photos required)
checkpoint-status |  |  | checkpoint | All excess steel / materials stored neatly and out of lay and blockie teams way? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Access for concrete pump clear
checkpoint-status |  |  | checkpoint | All rubbish in bin or removed from site
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team has been organised
checklist-flat |  |  | checklist | 7 Foreman Job Checklist (F) |  |  |  |  | Yes | 7 Foreman Job Checklist (F) | 876eb3f5-1c86-41cc-989f-fd5d2b52b164
checkpoint-status |  |  | checkpoint | Job file formed
checkpoint-status |  |  | checkpoint | Plans reviewed and required details printed and laminated?
label | e8ac362b-6fca-5007-bb45-18f7ffdf3d41 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Survey markout plan printed and laminated?
label | 3228dbd6-19db-5320-9d03-d32392066f13 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All heights printed and kaminated?
label | 916b3141-f2f4-5f0f-b552-a23f27d65601 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Job Master Schedule printed and laminated? (if schedule changes, throw away old and add new)
label | 042f8a5d-b808-5ef3-97ba-ca17f1b383ad |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Amounts
label | 0a46c74c-bb54-5fb9-84fe-aef3b62615d2 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Dockets
label | 000c92f4-f2c5-5d07-b4e8-30d04ce1f102 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Toolboxes
label | 77ef8af0-5958-5a50-bec7-819aa50c494c |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | SSSP
label | 3d0420b0-e384-5776-81a6-e131d6a34627 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Waterproofing markout
label | 307d7155-05e4-5f96-9636-71d9e29db038 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | PM - Foreman handover printed
label | b33b4150-5854-5d2e-b451-80d455611d9b |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All Qas printed
label | b781dea1-e226-5df2-bbad-3f2f6f02e4c6 |  | note | Add to Job File
checklist-flat |  |  | checklist | 0 Pricing Pre-Start Meeting |  |  |  |  | Yes | 0 Pricing Pre-Start Meeting | a45c1f1b-bc09-4143-9cac-d62721464e3d
checkpoint-no-status |  |  | checkpoint | Pricing Pre-Start Meeting
text | 98215756-676c-5c7b-976e-02fcc4f77520 |  | textbox | Project Details:
text | 1f3bcaae-99e9-517c-b5d6-7c2048ea8705 |  | textbox | Client:
text | bc79498f-6f61-5651-9c69-25261ae5fe42 |  | textbox | Address:
text | e519a35f-d84e-5e97-b005-b900be47677b |  | textbox | Other:
text | 3c5f87d6-49e0-5a5c-9626-727508ec2400 |  | textbox | Attendance:
text | 91d9c0bc-02d3-5845-8d62-d4ae0dd9e0ed |  | textbox | Tender Manager:
text | 41680006-7206-57bb-a076-7e44d8c881bb |  | textbox | Tender Status:
text | 76386736-8056-5cbe-84a1-362c28dc78a3 |  | textbox | Tender submission due date:
text | 8b43314b-6559-58a4-ad6b-38e185349cd9 |  | textbox | Job Details/Scope:
checkpoint-status |  |  | checkpoint | Has a Client Programme be provided?
checkpoint-status |  |  | checkpoint | Suppliers & Subcontractors Identified:
checkpoint-status |  |  | checkpoint | Have the documents been uploaded to Sharepoint?
checkpoint-status |  |  | checkpoint | A tasks list & a Project Programme (Project Manager):
checkpoint-status |  |  | checkpoint | Tender Clarifications/RFI's Required:
checkpoint-status |  |  | checkpoint | Risks or Opportunities:
checkpoint-status |  |  | checkpoint | Pre Submission meeting date scheduled:
checkpoint-status |  |  | checkpoint | Is a meeting with the client required? (At this stage)
checklist-flat |  |  | checklist | 2.2 Footing Methodology |  |  |  |  | Yes | 2.2 Footing Methodology | be8e2013-285e-4969-bbad-a03b6b8b7ecb
checkpoint-status |  |  | checkpoint | Set profiles to above Footing FFL
checkpoint-status |  |  | checkpoint | Surveyor to install grids on profiles (No builder to set a gridline)
checkpoint-status |  |  | checkpoint | Surveyor to mark Block side of grid line with an X on profile both sides
checkpoint-status |  |  | checkpoint | Install all stringlines
checkpoint-status |  |  | checkpoint | Measure all walls and confirm measurements within tolerance of plan measurements
checkpoint-status |  |  | checkpoint | Check diagonals
checkpoint-status |  |  | checkpoint | Transfer grids to ground and mark out each footing as per engineer dimension
checkpoint-status |  |  | checkpoint | Confirm all top of footing heights and make sure they are as per plan? Label as per footing engineer detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Confirm footing depths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Confirm footing widths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Specified DPM used in footings? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Dig out footings
checkpoint-status |  |  | checkpoint | Confirm all footing depths as per plans and within tolerable deep to begin building footing
checkpoint-status |  |  | checkpoint | Confirm all footing tops as per plans and within tolerable deep to begin building footing
checkpoint-status |  |  | checkpoint | Box footings where required
checkpoint-status |  |  | checkpoint | Insert DPM into footings where required
checkpoint-status |  |  | checkpoint | All DPM laps taped? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Waterproofing membrane in required parts of footing? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel out bottom mat as per singeer plans
checkpoint-status |  |  | checkpoint | Steel bottom minimum bottom cover achieved in all places (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel minimum side cover achieved in all places (Boxing or to earth)(Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends all tied? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends as per minimum lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Bottom mat of footing spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Top mat spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect bottom mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect top mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | Where footings step up, have Z bends and horizontals been installed as per engineer design. (Multiple photos required)
checkpoint-status |  |  | checkpoint | On step ups, form work set to footing depth and no more? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter Line been profiled and set as per engineer requirements from block / earth face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Starters with in 5 mm of engineer plans from block face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter spacings set as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter lap for post concrete pour, set to have minimum steel lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Height pegs or nails installed and sprayed for Lay team (Multiple photos required)
checkpoint-status |  |  | checkpoint | All footings clear from rubbish and dirt (Multiple photos required)
checkpoint-status |  |  | checkpoint | All waratahs and starters have starter caps on (Multiple photos required)
checkpoint-status |  |  | checkpoint | All excess steel / materials stored neatly and out of lay and blockie team way? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Access for concrete pump clears
checkpoint-status |  |  | checkpoint | All rubbish in bin or removed from site
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photos required)
checkpoint-status |  |  | checkpoint | Hand over to lay team been organised
checklist-flat |  |  | checklist | 3.1 Slab Pre pour Quality Assurance |  |  |  |  | Yes | 3.1 Slab Pre pour Quality Assurance | cd2057b8-940c-457d-8d44-aa525f2fbdf3
checkpoint-no-status |  |  | checkpoint | What is FFL
checkpoint-status |  |  | checkpoint | Edgebeam / Rebates set to FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Edgebeam running down correct gridlines (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Joinery Rebates set to required depths
checkpoint-status |  |  | checkpoint | Garage Rebate set as per client requirements
checkpoint-status |  |  | checkpoint | Inslab rebates in correct slab position (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates set to correct depth from FFL
checkpoint-status |  |  | checkpoint | Formwork Sprayed with form release (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum bottom cover (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from form work (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All bends tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps minimum lap requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from form work and rebates (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minum cover from services (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Stringline run and left up in multiple places to prove cover from FFL to top of Mesh for engineer and council (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Floor checked all over to make sure no steel is above FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Thickening measurement as per plan and same top and bottom (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Pods been cut outside the slab
checkpoint-status |  |  | checkpoint | All DPM taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM up to edgebeam (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Services taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inside pad free from rubbish (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Starter caps on all waratahs or exposed starters (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Rubbish in bins and site cleaned up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess boxing and steel stacked neatly and out of lay teams way, ready for pick up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Nothing around the slab and in way of Lay team (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess pods and pod rubbish been collected or supplier been called to pick up
checkpoint-status |  |  | checkpoint | Site in clean and respectable state (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team has been organised