## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | 1 Job estimation handover (QS / PM) |  |  |  |  | Yes | 1 Job estimation handover (QS / PM) | 3186d598-87da-42b6-914c-184cda7bb875
checkpoint-no-status |  |  | checkpoint | Project Details
text | 24736087-d9fd-585b-a36f-e97985d5aabb |  | textbox | Project Details:
text | d129dd4c-a90a-55c7-b5fc-02499ac1f899 |  | textbox | Client:
text | efaef4c6-aaa6-5eeb-88e4-afd04fc98e98 |  | textbox | Address:
text | 9aacfaf7-8738-5d03-b9fb-02e98810c999 |  | textbox | Other:
text | 1fe6a14c-0d6a-58d9-98a9-8d82495adb7f |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Estimator and Project Team - Discuss quoted job (QS/PM)
checkpoint-status |  |  | checkpoint | Critical tags discussed
checkpoint-status |  |  | checkpoint | Any tender ageement with subcontractors and supplier discussed and documented. (Who are the subcontractors and suppliers)
checkpoint-status |  |  | checkpoint | Tender and risks and opportunities discussed with project team
checkpoint-status |  |  | checkpoint | P&G Allowances
checkpoint-status |  |  | checkpoint | Tender discuss and approved by relevant person/s
checkpoint-status |  |  | checkpoint | Formwork / Propping / Rebates allowed for Job
checkpoint-status |  |  | checkpoint | Program and Labour allowances for each phase of the job
checkpoint-status |  |  | checkpoint | Any other job information that needs to be handed over.
checklist-flat |  |  | checklist | 6 Site Manager and Foreman’s Job planning (SM / F) |  |  |  |  | Yes | 6 Site Manager and Foreman’s Job planning (SM / F) | 3d3118bb-149f-4e4f-be54-fa04325c6f94
checkpoint-no-status |  |  | checkpoint | Project Details
text | 2c50bf3a-342d-5eff-a51b-ac2e0bba7b28 |  | textbox | Project Details:
text | b4c6268d-b85e-5e9c-9e8c-13ef80005373 |  | textbox | Client:
text | 513e755e-bdcc-5897-9e26-ecab15b62599 |  | textbox | Address:
text | cf7858b9-9a5c-52ff-b4ec-c07b91334bbf |  | textbox | Other:
text | c82ec84e-035b-5ae8-828b-b126390225ab |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Job built from start to finish - Compare with Program
checkpoint-status |  |  | checkpoint | Design issues noted and send to client
checkpoint-status |  |  | checkpoint | Site Specific OTWC requirements - Send to client
checkpoint-status |  |  | checkpoint | Master Program built and send to client
label | 61b365ff-a10a-5610-8bec-4f353d534895 |  | note | To include materials drop offs
label | 99d49ea6-5db2-5adc-afb3-b47333b48152 |  | note | To include formwork required
label | 85f44236-2321-5802-95aa-03ae0883d57f |  | note | To include concrete bookings
label | 3a59e325-cbdc-5e6e-9871-daba5a7b6591 |  | note | To include inspections
checkpoint-status |  |  | checkpoint | Concrete bookings insert into Concrete Schedule
checkpoint-status |  |  | checkpoint | Material bookings into Material Schedule
checkpoint-status |  |  | checkpoint | Site Manager to get a copy of the Job Schedule
checkpoint-status |  |  | checkpoint | Schedule to have Toolbox Meeting
checklist-flat |  |  | checklist | 3.2 Footing Pre Pour Quality Assurance |  |  |  |  | Yes | 3.2 Footing Pre Pour Quality Assurance | 4ef92d41-90ee-4aee-b72d-4c0e2c3c2d49
checkpoint-status |  |  | checkpoint | Check all top of footing heights and make sure they are as per plan? Label as footing engineer detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | All footing depths as per plan? Label as per engineer footing detail( Multiple photos required)
checkpoint-status |  |  | checkpoint | All footing widths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Specified DPM used in footings? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All DPM laps taped? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Waterproofing membrane in required parts of footing? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel bottom minimum bottom cover achieved in all places (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel minimum side cover achieved in all places (Boxing or to earth)(Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends all tied? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends as per minimum lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Bottom mat of footing spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Top mat spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect bottom mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continous bent steel to connect top mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | Where footings step up, have Z bends and horizontals been installed as per engineer design. (Multiple photos required)
checkpoint-status |  |  | checkpoint | On step ups, form work set to footing depth and no more? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter Line been profiles and set as per engineer requirements from block / earth face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Starters within 5 mm of engineer plans from block face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter spacings set as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter lap for post concrete pour, set to have minimum steel lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Height pegs or nails installed and sprayed for Lay team (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Footings clear from rubbish and dirt (Multiple photos required)
checkpoint-status |  |  | checkpoint | All waratahs and starters have starter caps on (Multiple photos required)
checkpoint-status |  |  | checkpoint | All excess steel / materials stored neatly and out of lay and blockie teams way? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Access for concrete pump clear
checkpoint-status |  |  | checkpoint | All rubbish in bin or removed from site
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team has been organised
checklist-flat |  |  | checklist | 3 Site Manager and Foreman job planning prior to meeting PM (SM / F) |  |  |  |  | Yes | 3 Site Manager and Foreman job planning prior to meeting PM (SM / F) | 54d4fb37-374d-41b8-94c0-b6dd0fa293a3
checkpoint-no-status |  |  | checkpoint | Foreman and Site Manager Job planning Prior to meeting PM
text | 3dc34ec2-023c-5094-a4fa-0d97a69e56a5 |  | textbox | Project details:
text | a49bc54b-38d0-5dbd-aa1e-59f4ba81d8ed |  | textbox | Client:
text | bf70dfc2-b6eb-5cbe-893b-914ae9421aba |  | textbox | Address:
text | f97ec8bb-3cff-5bc5-9d74-5852e784c2f4 |  | textbox | Other:
text | 2d1f8802-ca0d-5543-b0d9-70d8320dadaf |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review plans, including engineer set and build question sheet
checkpoint-status |  |  | checkpoint | Go over PM's Job schedule
checkpoint-status |  |  | checkpoint | Identify key dates
checkpoint-status |  |  | checkpoint | Deliveries
checkpoint-status |  |  | checkpoint | QA's
checkpoint-status |  |  | checkpoint | Inspections
checkpoint-status |  |  | checkpoint | Pour dates
checkpoint-status |  |  | checkpoint | Identify materials used
checkpoint-status |  |  | checkpoint | DPM
checkpoint-status |  |  | checkpoint | Steel
checkpoint-status |  |  | checkpoint | Mebrane type
checkpoint-status |  |  | checkpoint | Boxing required
checkpoint-status |  |  | checkpoint | Identify survey plan and Heights
checkpoint-status |  |  | checkpoint | Identify waterproofing locations and where DPM ends
checkpoint-status |  |  | checkpoint | If we have footing outside of building lines, top of footings in these loctions need to be at least 200 mm below FFL
checklist-flat |  |  | checklist | 0 Pricing Pre-Start Meeting |  |  |  |  | Yes | 0 Pricing Pre-Start Meeting | 66321274-a4a4-428b-a752-e8373f8c515f
checkpoint-no-status |  |  | checkpoint | Pricing Pre-Start Meeting
text | 98215756-676c-5c7b-976e-02fcc4f77520 |  | textbox | Project Details:
text | 1f3bcaae-99e9-517c-b5d6-7c2048ea8705 |  | textbox | Client:
text | bc79498f-6f61-5651-9c69-25261ae5fe42 |  | textbox | Address:
text | e519a35f-d84e-5e97-b005-b900be47677b |  | textbox | Other:
text | 3c5f87d6-49e0-5a5c-9626-727508ec2400 |  | textbox | Attendance:
text | 91d9c0bc-02d3-5845-8d62-d4ae0dd9e0ed |  | textbox | Tender Manager:
text | 41680006-7206-57bb-a076-7e44d8c881bb |  | textbox | Tender Status:
text | 76386736-8056-5cbe-84a1-362c28dc78a3 |  | textbox | Tender submission due date:
text | 8b43314b-6559-58a4-ad6b-38e185349cd9 |  | textbox | Job Details/Scope:
checkpoint-status |  |  | checkpoint | Has a Client Programme be provided?
checkpoint-status |  |  | checkpoint | Suppliers & Subcontractors Identified:
checkpoint-status |  |  | checkpoint | Have the documents been uploaded to Sharepoint?
checkpoint-status |  |  | checkpoint | A tasks list & a Project Programme (Project Manager):
checkpoint-status |  |  | checkpoint | Tender Clarifications/RFI's Required:
checkpoint-status |  |  | checkpoint | Risks or Opportunities:
checkpoint-status |  |  | checkpoint | Pre Submission meeting date scheduled:
checkpoint-status |  |  | checkpoint | Is a meeting with the client required? (At this stage)
checklist-flat |  |  | checklist | 2.1 Slab Installation Methodology |  |  |  |  | Yes | 2.1 Slab Installation Methodology | 70b4038d-20a2-49f6-bfb6-d64a2625f1b0
checkpoint-no-status |  |  | checkpoint | What is FFL
checkpoint-status |  |  | checkpoint | Set Profiles to 30 mm above FFL and stransfer gridlines onto profiles
checkpoint-status |  |  | checkpoint | Set up stringlines, check measurements and diagonals
checkpoint-status |  |  | checkpoint | Clean / wash down all footings and Block wall header blocks
checkpoint-status |  |  | checkpoint | Check all prep heights are within tolerance
checkpoint-status |  |  | checkpoint | Set Edgebeam and Rebates set to FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Set correct Edgebeam face running down correct gridlines (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Joinery Rebates set to required depths (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Garage Rebate set as per client requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All waratahs have starter caps on (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Site Cleaned / Rubbish in bin/ Materials located in centralised locations/ Ready for Plumbers?
checkpoint-status |  |  | checkpoint | Steel and Pod cutting loctions outside of pad established (centralise all rubbish to one location)
checkpoint-status |  |  | checkpoint | Pods have been cut outside the slab
checkpoint-status |  |  | checkpoint | All steel has minimum bottom cover (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from form work (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All bends tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps minimum lap requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from form work and rebates (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minum cover from services (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Stringline run and left up in multiple places to prove cover from FFL to top of Mesh for engineer and council (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates set to correct depth from FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Floor checked all over to make sure no steel is above FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Thickening measurement as per plan and same top and bottom (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM up to edgebeam (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Services taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inside pad free from rubbish (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Starter caps on all waratahs or exposed starters (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Rubbish in bins and site cleaned up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess boxing and steel stacked neatly and out of lay teams way, ready for pick up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Nothing around the slab and in way of Lay team (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess pods and pod rubbish been collected or supplier been called to pick up
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates in correct slab position (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Formwork Sprayed with form release (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team been organised
checklist-flat |  |  | checklist | 7 Foreman Job Checklist (F) |  |  |  |  | Yes | 7 Foreman Job Checklist (F) | 7738ef24-860e-426c-9070-4425ff99dc79
checkpoint-status |  |  | checkpoint | Job file formed
checkpoint-status |  |  | checkpoint | Plans reviewed and required details printed and laminated?
label | eb5e8918-8070-5277-b7a3-de2cc3b7c02e |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Survey markout plan printed and laminated?
label | e941210c-d0f9-5362-baa0-0d668dcf1c28 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All heights printed and kaminated?
label | 542b507d-19a1-5538-ac98-d0e4488956c6 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Job Master Schedule printed and laminated? (if schedule changes, throw away old and add new)
label | c7c0ab61-a91c-59c2-b33e-3a1733ca92b9 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Amounts
label | cb8a1f0e-491e-5fa9-bd4d-7988e0b3e530 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Dockets
label | b93f644b-450e-51d0-847f-cc4c606276e3 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Toolboxes
label | cfc11173-cb30-5201-b2ef-f18e9e67863d |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | SSSP
label | ae98c9a9-6d9b-5d39-a4b7-8ed5d227d2ba |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Waterproofing markout
label | 4143c9a4-4a64-5eac-b6e3-ae5c6678c61c |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | PM - Foreman handover printed
label | b12f94fd-a880-5573-90c4-da3f34a3e12b |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All Qas printed
label | 7c6131e4-d8d7-50fe-bcb4-ba3c65ce5f98 |  | note | Add to Job File
checklist-flat |  |  | checklist | 4 Site Manager and Foreman Question Sheet (SM / F) |  |  |  |  | Yes | 4 Site Manager and Foreman Question Sheet (SM / F) | 79d5c2f9-8d1f-440c-835a-7fe03789ef7c
checkpoint-status |  |  | checkpoint | Do you understand profile and survey setout or do you require more information?
checkpoint-status |  |  | checkpoint | Are your survey marks off grid lines or building lines?
button | 4fa3c385-4bf9-5155-b849-1c9dce3c2cd5 |  | button |  | Grid lines, Building Lines
checkpoint-status |  |  | checkpoint | Item Details
boolean | 4e0fd3a3-3514-55d9-9dfb-a5bd34b325fb |  | tickbox | Do you understand all heights?
boolean | a38bd4f7-0f8c-57b4-9dd5-ee6919d5d806 |  | tickbox | Do you have all dimensions?
text | 59f439cf-4959-5a9a-9922-46e1d9866f2f |  | textbox | What formwork are you using for each component of the job?
checkpoint-status |  |  | checkpoint | Has the formwork and bracing been organised to be onsite before you require it?
checkpoint-status |  |  | checkpoint | Material Details
text | 09cfd836-edf4-5aed-9f12-1e19e38becac |  | textbox | Where have your materials been ordered from?
date | a73d5fdf-3464-5751-b4bf-20ddbbeaecff |  | date | What date do you expect your materials to be delivered?
checkpoint-status |  |  | checkpoint | Have all materials been ordered to site or do you need to pickup materials? If so, notify your van.
button | 574d2775-8d1e-5997-97f5-003d2e62f797 |  | button |  | To Site, Pickup
checkpoint-status |  |  | checkpoint | Key Dates
text | 78cdf6f8-dc43-5952-bbb5-499996f73b00 |  | textbox | Identify key dates to make
text | 8fde372b-4041-5659-9d7d-4989995291bf |  | textbox | Identify inspection dates
checkpoint-status |  |  | checkpoint | DPM & Waterproofing
text | b30e429d-1b39-594c-a791-ff07b0789305 |  | textbox | What DPM and tape required?
boolean | 0bdab218-ab8c-574c-b32e-f675e6f072d8 |  | tickbox | Has this been ordered?
text | e75f377d-0b3d-56ce-ae04-34157f5f5273 |  | textbox | Waterproofing - Identify waterproofing location
boolean | 3fbe98dc-eaa8-5a48-9285-9b2dd0117c9c |  | tickbox | Make sure digout accounts for waterproofers
boolean | f8c4b411-52f7-5608-b374-19036994d882 |  | tickbox | Go over van load out list with your van
boolean | fdcfdb55-fedd-506e-9e9e-272f87567d7a |  | tickbox | Has your van got everything needed for the job
text | 9432c6c3-c22f-55dd-b944-9205c4cdf76c |  | textbox | Rebates
text | ecd5406d-3eb5-5c6d-b205-7547ed75d6dd |  | textbox | Profile timber and walls
checklist-flat |  |  | checklist | 2 Job handover to Site Manager and Foreman (PM) |  |  |  |  | Yes | 2 Job handover to Site Manager and Foreman (PM) | 96cbe900-6821-4e4e-b569-8b2cb6344b68
checkpoint-no-status |  |  | checkpoint | Project Details:
text | a77e9584-3234-573b-b2a5-bc390e4439dc |  | textbox | Client:
text | 5a878eb2-2f4c-52da-bc70-3cbe0e67972f |  | textbox | Address:
text | 10a2d461-41f6-5195-9f39-b0fb26dfa206 |  | textbox | Other:
text | 09ee0e9e-9c64-5ffb-836e-e460cb937f58 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Send Foreman Job Question Sheet
checkpoint-status |  |  | checkpoint | Get Foreman to review plans before coming in to see you
checkpoint-status |  |  | checkpoint | Have Master Schedule sent
checkpoint-status |  |  | checkpoint | Have survey serout and plan sent
checkpoint-status |  |  | checkpoint | Make sure Foreman knows if we are working off grids or building lines
checkpoint-status |  |  | checkpoint | Make sure they know heights
text | a108b31d-0e29-591c-93cf-57f48d90e4d8 |  | textbox | Footings height:
text | 0aef1b51-0ce3-569b-967d-476c73bcbb39 |  | textbox | Block/wall heights:
text | 3ef81e33-1543-513f-9673-0d2cec0a826c |  | textbox | Finish floor levels:
text | e1a88fa7-b4b4-598f-af4b-6d08f9fb6968 |  | textbox | Lift pit levels:
text | 2afe723c-7b18-506e-b944-eab8c27a7a53 |  | textbox | Finish Ground Levels (for footings outside of building lines)
checkpoint-status |  |  | checkpoint | DPM require
checkpoint-status |  |  | checkpoint | Waterproofing areas
checkpoint-status |  |  | checkpoint | Formworks and bracing required and what was quoted
checklist-flat |  |  | checklist | 5 PM handover to Site Manager and Forman (PM / SM / F) |  |  |  |  | Yes | 5 PM handover to Site Manager and Forman (PM / SM / F) | a109cd64-f770-4d2e-af9e-c5bc08eaee5b
checkpoint-status |  |  | checkpoint | Have you reviewed Plans/Job Schedule?
checkpoint-status |  |  | checkpoint | Do you understand survey markout grids? Building lines?
checkpoint-status |  |  | checkpoint | Heights:
text | 5878188c-d5bc-5824-9fee-3f042917a99b |  | textbox | Footing Depth
text | 8cf4b1c2-6374-5927-bda4-0a8215a6a613 |  | textbox | Bottom of footing measurement
text | 123b6db7-aabe-5c1b-9c9a-387e8a2f8003 |  | textbox | Top of footing measurement
text | f2f49905-4984-53e2-a911-1867cf78b84e |  | textbox | Finish Floor Line (FFL)
text | 8cce9da7-7d18-5020-9cf2-9978c70e7f03 |  | textbox | Block wall heights
text | a5b6543b-e084-5a1c-90a7-619e80e15603 |  | textbox | Insitu wall heights
checkpoint-status |  |  | checkpoint | Have you got all dimensions?
checkpoint-status |  |  | checkpoint | Show Foreman complicated components of Job and solutions
checkpoint-status |  |  | checkpoint | DPM require/tape
checkpoint-status |  |  | checkpoint | Waterproofing locations, explain importance of larger digout in these locations:
label | b1b281b8-34a7-56c7-9bfb-f893592054dc |  | note | Go over Engineer Details
label | b452060d-b708-5259-ade4-e9bfe77b64a8 |  | note | Go over Building Methodology
label | 684f57f6-542a-535b-a866-4a492c13bbbb |  | note | Go over Key dates
label | 9f30bde2-0c01-5e79-9a5b-ea44cfa43fe8 |  | note | Go over size of team
label | 43c66eed-275f-5de4-b92d-de605655e2c7 |  | note | Go over rebates
label | a4ca39af-38e3-5868-b818-480c820fd4d6 |  | note | Go over penetrations
checkpoint-status |  |  | checkpoint | Materials to site
checkpoint-status |  |  | checkpoint | What has been allowed/ and what hasn't
checkpoint-status |  |  | checkpoint | What needs to be taken to site
checkpoint-status |  |  | checkpoint | Any other points/discussion:
checklist-flat |  |  | checklist | Foreman and Site Manager Job planning Prior to meeting PM |  |  |  |  | Yes | Foreman and Site Manager Job planning Prior to meeting PM | a4908942-cfb9-4aed-b1ec-8f2ea5f8505a
checkpoint-no-status |  |  | checkpoint | Foreman and Site Manager Job planning Prior to meeting PM
text | 30dc9a7d-112e-5731-b0d9-65314f6cd77f |  | textbox | Project details:
text | 6c0b0e93-af96-5422-bf8c-29b8b1fe0280 |  | textbox | Client:
text | 19327e34-5b33-5505-ae35-5c17a0240c59 |  | textbox | Address:
text | 3874c4d8-3533-5b41-87eb-87555e86cbe1 |  | textbox | Other:
text | 6304ed4b-369a-5d2d-9c57-f171afd2857a |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review plans, including engineer set and build question sheet
checkpoint-status |  |  | checkpoint | Go over PM's Job schedule
checkpoint-status |  |  | checkpoint | Identify key dates
checkpoint-status |  |  | checkpoint | Deliveries
checkpoint-status |  |  | checkpoint | QA's
checkpoint-status |  |  | checkpoint | Inspections
checkpoint-status |  |  | checkpoint | Pour dates
checkpoint-status |  |  | checkpoint | Identify materials used
checkpoint-status |  |  | checkpoint | DPM
checkpoint-status |  |  | checkpoint | Steel
checkpoint-status |  |  | checkpoint | Mebrane type
checkpoint-status |  |  | checkpoint | Boxing required
checkpoint-status |  |  | checkpoint | Identify survey plan and Heights
checkpoint-status |  |  | checkpoint | Identify waterproofing locations and where DPM ends
checkpoint-status |  |  | checkpoint | If we have footing outside of building lines, top of footings in these loctions need to be at least 200 mm below FFL
checklist-flat |  |  | checklist | Site Inspection Pre Job Starting - Site Manager and Foreman |  |  |  |  | Yes | Site Inspection Pre Job Starting - Site Manager and Foreman | b03366b3-6a17-4603-b9d5-8bc4384b3ed3
checkpoint-no-status |  |  | checkpoint | Site Inspection Pre Job Starting - Site Manager and Foreman
text | e3aac975-cfa6-5499-bc5e-5837ad382d60 |  | textbox | Project Details:
text | ae0472df-bf75-5a90-a4ce-80da5281a471 |  | textbox | Client:
text | 091248a0-d8df-5267-8158-d0bc3ba0529a |  | textbox | Address:
text | 5cc98935-2241-5706-8892-cc69a3c2301e |  | textbox | Other:
text | e7119dfb-1114-5f44-91bc-1a05828414b3 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Traffic management required for our job scope?
checkpoint-status |  |  | checkpoint | If so, has the client been informed and agreed it will be in place for our start date?
checkpoint-status |  |  | checkpoint | Have materials been dropped off?
checkpoint-status |  |  | checkpoint | If not, contact suppliers, let them know where you want materials delivered and what is delivery time and date:
checkpoint-status |  |  | checkpoint | Identify workstations
checkpoint-status |  |  | checkpoint | Pod cutting station outside of slab
checkpoint-status |  |  | checkpoint | Steel bending and cutting station
checkpoint-status |  |  | checkpoint | Timber cutting station
checkpoint-status |  |  | checkpoint | Skip bin onsite?
checkpoint-status |  |  | checkpoint | Portaloo onsite?
checkpoint-status |  |  | checkpoint | Power to site?
checkpoint-status |  |  | checkpoint | Water to site?
checkpoint-status |  |  | checkpoint | Site box and work drawings?
checkpoint-status |  |  | checkpoint | If none of the above are onsite and are needed for us, has client been informed?
checkpoint-status |  |  | checkpoint | Boundary and survey set outs/pegs been done?
checkpoint-status |  |  | checkpoint | Cut heights and locations as OTWC requirements?
checkpoint-status |  |  | checkpoint | If not, has client been informed and start date been changed for the problem to be sorted?
checkpoint-status |  |  | checkpoint | OTWC vehicle parking confirmed with client & the location has been identified?
checkpoint-status |  |  | checkpoint | Any other issues that need to be brought up to client?
checkpoint-status |  |  | checkpoint | If so, has client been informed?
checklist-flat |  |  | checklist | 8 Site inspection Pre-job start Site Manager and Foreman (SM / F) |  |  |  |  | Yes | 8 Site inspection Pre-job start Site Manager and Foreman (SM / F) | b8b012ff-b35a-4a45-aae1-d993d8c8a44a
checkpoint-no-status |  |  | checkpoint | Site Inspection Pre Job Starting - Site Manager and Foreman
text | 1f1da044-cad7-5c3e-9b54-3ac882245997 |  | textbox | Project Details:
text | 25bdf3f0-7dbf-5017-b6f5-d0e3fbb5b74a |  | textbox | Client:
text | 993298b8-cb0b-52b6-989b-b34669ca1a42 |  | textbox | Address:
text | 33882a80-bf36-589b-9117-4abab627be72 |  | textbox | Other:
text | 06e81ea6-14f5-508f-bed0-3f9721e5c302 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Traffic management required for our job scope?
checkpoint-status |  |  | checkpoint | If so, has the client been informed and agreed it will be in place for our start date?
checkpoint-status |  |  | checkpoint | Have materials been dropped off?
checkpoint-status |  |  | checkpoint | If not, contact suppliers, let them know where you want materials delivered and what is delivery time and date:
checkpoint-status |  |  | checkpoint | Identify workstations
checkpoint-status |  |  | checkpoint | Pod cutting station outside of slab
checkpoint-status |  |  | checkpoint | Steel bending and cutting station
checkpoint-status |  |  | checkpoint | Timber cutting station
checkpoint-status |  |  | checkpoint | Skip bin onsite?
checkpoint-status |  |  | checkpoint | Portaloo onsite?
checkpoint-status |  |  | checkpoint | Power to site?
checkpoint-status |  |  | checkpoint | Water to site?
checkpoint-status |  |  | checkpoint | Site box and work drawings?
checkpoint-status |  |  | checkpoint | If none of the above are onsite and are needed for us, has client been informed?
checkpoint-status |  |  | checkpoint | Boundary and survey set outs/pegs been done?
checkpoint-status |  |  | checkpoint | Cut heights and locations as OTWC requirements?
checkpoint-status |  |  | checkpoint | If not, has client been informed and start date been changed for the problem to be sorted?
checkpoint-status |  |  | checkpoint | OTWC vehicle parking confirmed with client & the location has been identified?
checkpoint-status |  |  | checkpoint | Any other issues that need to be brought up to client?
checkpoint-status |  |  | checkpoint | If so, has client been informed?
checklist-flat |  |  | checklist | 3.1 Slab Pre pour Quality Assurance |  |  |  |  | Yes | 3.1 Slab Pre pour Quality Assurance | db48dc34-ce75-477e-8a40-d0b305d5748c
checkpoint-no-status |  |  | checkpoint | What is FFL
checkpoint-status |  |  | checkpoint | Edgebeam / Rebates set to FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Edgebeam running down correct gridlines (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Joinery Rebates set to required depths
checkpoint-status |  |  | checkpoint | Garage Rebate set as per client requirements
checkpoint-status |  |  | checkpoint | Inslab rebates in correct slab position (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates set to correct depth from FFL
checkpoint-status |  |  | checkpoint | Formwork Sprayed with form release (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum bottom cover (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from form work (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All bends tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps minimum lap requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from form work and rebates (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minum cover from services (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Stringline run and left up in multiple places to prove cover from FFL to top of Mesh for engineer and council (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Floor checked all over to make sure no steel is above FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Thickening measurement as per plan and same top and bottom (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Pods been cut outside the slab
checkpoint-status |  |  | checkpoint | All DPM taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM up to edgebeam (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Services taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inside pad free from rubbish (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Starter caps on all waratahs or exposed starters (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Rubbish in bins and site cleaned up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess boxing and steel stacked neatly and out of lay teams way, ready for pick up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Nothing around the slab and in way of Lay team (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess pods and pod rubbish been collected or supplier been called to pick up
checkpoint-status |  |  | checkpoint | Site in clean and respectable state (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team has been organised
checklist-flat |  |  | checklist | Foreman's Job Planning |  |  |  |  | Yes | Foreman's Job Planning | e20065c0-5e7e-4c33-93a6-3310e6595e8b
checkpoint-no-status |  |  | checkpoint | Foreman's Job Planning
text | dd79810e-7537-5a78-bd4b-bac8d6822992 |  | textbox | Project Details:
text | cfc6641a-e658-592f-9dcf-4177c8b55534 |  | textbox | Client:
text | 5d17ed81-f44a-5bed-860f-c6de39cff22a |  | textbox | Address:
text | 89f6cd5e-2b57-5b2e-9df5-9a620344182e |  | textbox | Other:
text | dee635b6-8c91-56af-a0b6-9db3624562f7 |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review Master Schedule
checkpoint-status |  |  | checkpoint | Plan Days / Weeks according to Master schedule; Labour size and tasks to complete
checkpoint-status |  |  | checkpoint | Bring your team in for and go over job with them, explain the job file
checkpoint-status |  |  | checkpoint | Make sure Van is loaded with everything it will need for the job
checkpoint-status |  |  | checkpoint | Team book and load trailer as required, day prior to job starting
checkpoint-status |  |  | checkpoint | Remember Monday morning Toolboxes and Friday debriefs
checklist-flat |  |  | checklist | 2.2 Footing Methodology |  |  |  |  | Yes | 2.2 Footing Methodology | fa5d4369-2c7b-4db2-a657-684a34b68553
checkpoint-status |  |  | checkpoint | Set profiles to above Footing FFL
checkpoint-status |  |  | checkpoint | Surveyor to install grids on profiles (No builder to set a gridline)
checkpoint-status |  |  | checkpoint | Surveyor to mark Block side of grid line with an X on profile both sides
checkpoint-status |  |  | checkpoint | Install all stringlines
checkpoint-status |  |  | checkpoint | Measure all walls and confirm measurements within tolerance of plan measurements
checkpoint-status |  |  | checkpoint | Check diagonals
checkpoint-status |  |  | checkpoint | Transfer grids to ground and mark out each footing as per engineer dimension
checkpoint-status |  |  | checkpoint | Confirm all top of footing heights and make sure they are as per plan? Label as per footing engineer detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Confirm footing depths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Confirm footing widths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Specified DPM used in footings? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Dig out footings
checkpoint-status |  |  | checkpoint | Confirm all footing depths as per plans and within tolerable deep to begin building footing
checkpoint-status |  |  | checkpoint | Confirm all footing tops as per plans and within tolerable deep to begin building footing
checkpoint-status |  |  | checkpoint | Box footings where required
checkpoint-status |  |  | checkpoint | Insert DPM into footings where required
checkpoint-status |  |  | checkpoint | All DPM laps taped? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Waterproofing membrane in required parts of footing? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel out bottom mat as per singeer plans
checkpoint-status |  |  | checkpoint | Steel bottom minimum bottom cover achieved in all places (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel minimum side cover achieved in all places (Boxing or to earth)(Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends all tied? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends as per minimum lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Bottom mat of footing spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Top mat spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect bottom mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect top mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | Where footings step up, have Z bends and horizontals been installed as per engineer design. (Multiple photos required)
checkpoint-status |  |  | checkpoint | On step ups, form work set to footing depth and no more? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter Line been profiled and set as per engineer requirements from block / earth face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Starters with in 5 mm of engineer plans from block face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter spacings set as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter lap for post concrete pour, set to have minimum steel lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Height pegs or nails installed and sprayed for Lay team (Multiple photos required)
checkpoint-status |  |  | checkpoint | All footings clear from rubbish and dirt (Multiple photos required)
checkpoint-status |  |  | checkpoint | All waratahs and starters have starter caps on (Multiple photos required)
checkpoint-status |  |  | checkpoint | All excess steel / materials stored neatly and out of lay and blockie team way? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Access for concrete pump clears
checkpoint-status |  |  | checkpoint | All rubbish in bin or removed from site
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photos required)
checkpoint-status |  |  | checkpoint | Hand over to lay team been organised