## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | 5 PM handover to Site Manager and Forman (PM / SM / F) |  |  |  |  | Yes | 5 PM handover to Site Manager and Forman (PM / SM / F) | 186f706c-6d5b-450e-bfe3-7fbdea022a91
checkpoint-status |  |  | checkpoint | Have you reviewed Plans/Job Schedule?
checkpoint-status |  |  | checkpoint | Do you understand survey markout grids? Building lines?
checkpoint-status |  |  | checkpoint | Heights:
text | 91fe918f-7a18-54a9-9bf3-a2def6c85c2a |  | textbox | Footing Depth
text | e72f292c-de3d-57bb-b7fa-eeb394cd33f5 |  | textbox | Bottom of footing measurement
text | c6d80153-4f21-5b24-beb2-bb09f946a747 |  | textbox | Top of footing measurement
text | 46d3e52c-0c46-5c78-8943-a4c114325dd2 |  | textbox | Finish Floor Line (FFL)
text | a393b889-d574-5554-9e56-ec6b46e54526 |  | textbox | Block wall heights
text | 65ae608e-7052-59d3-b924-ddce457e2f0a |  | textbox | Insitu wall heights
checkpoint-status |  |  | checkpoint | Have you got all dimensions?
checkpoint-status |  |  | checkpoint | Show Foreman complicated components of Job and solutions
checkpoint-status |  |  | checkpoint | DPM require/tape
checkpoint-status |  |  | checkpoint | Waterproofing locations, explain importance of larger digout in these locations:
label | 3db91c2b-c87f-560d-8af3-3113783f21ac |  | note | Go over Engineer Details
label | 8e103226-5681-511c-b5e7-b891af00f1fb |  | note | Go over Building Methodology
label | 56811765-bab3-5db1-b9c0-fd082eafa7a2 |  | note | Go over Key dates
label | 292fa177-b714-5dac-9983-431e98f5ba94 |  | note | Go over size of team
label | 3caf1746-82c1-5dc5-ad25-92afa855fe7f |  | note | Go over rebates
label | ebca8760-cb96-5f5d-b55b-98d5561475b2 |  | note | Go over penetrations
checkpoint-status |  |  | checkpoint | Materials to site
checkpoint-status |  |  | checkpoint | What has been allowed/ and what hasn't
checkpoint-status |  |  | checkpoint | What needs to be taken to site
checkpoint-status |  |  | checkpoint | Any other points/discussion:
checklist-sectioned |  |  | checklist | Foreman Job Checklist (Insitu Walls) |  |  |  |  | Yes | Foreman Job Checklist (Insitu Walls) | 1b425302-81ba-43ae-9661-edc5f85f05ed
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Job file made?
checkpoint-status |  |  | checkpoint | Profile/Establish?
text | eecc9b2e-dc28-5612-8ebe-29a2db1273cb |  | textbox | Profile timber head to site or need to be loaded?
button | 05bb82c8-f459-5cbf-89d1-a30e8222f3f3 |  | button |  | To site, To be loaded
text | 12f1d739-8831-5cd7-a3d6-27eb740861d0 |  | textbox | Waratahs need/loaded?
text | e0c854f1-7ef3-5e5f-b9f0-e3335220c0d8 |  | textbox | Surveyor time on site?
boolean | e21ac154-7b34-5db4-8f50-7a2097084a7f |  | tickbox | Survey markout plan laminated?
checkpoint-group |  |  | section | Forklift
checkpoint-status |  |  | checkpoint | 3-phase plus onsite?
checkpoint-status |  |  | checkpoint | Formwork lay down areas identified?
checkpoint-group |  |  | section | Formwork
checkpoint-no-status |  |  | checkpoint | Doka delivery date?
date | b924329b-f4ca-5b22-ad36-e5079103b54f |  | date
boolean | 2cadb08c-4081-5a8f-a222-da6153477b22 |  | tickbox | Doka engineer plan laminated?
checkpoint-status |  |  | checkpoint | Doka heights laminated?
checkpoint-status |  |  | checkpoint | Conduit and plugs ordered?
checkpoint-status |  |  | checkpoint | Wall chairs ordered
checkpoint-status |  |  | checkpoint | Form release ordered?
checkpoint-status |  |  | checkpoint | Steel delivery dates?
checkpoint-status |  |  | checkpoint | Steel delivery tags printed?
checkpoint-status |  |  | checkpoint | Concrete blocks ordered (if required)?
checkpoint-status |  |  | checkpoint | Chalk lines
checkpoint-status |  |  | checkpoint | Lasers/spare batteries
checkpoint-status |  |  | checkpoint | Dazzle
checkpoint-status |  |  | checkpoint | Access to CONQA for QA forms?
checklist-flat |  |  | checklist | 3.1 Slab Pre pour Quality Assurance |  |  |  |  | Yes | 3.1 Slab Pre pour Quality Assurance | 22c7e95d-a7db-46ab-95e0-94f7710dc112
checkpoint-no-status |  |  | checkpoint | What is FFL
checkpoint-status |  |  | checkpoint | Edgebeam / Rebates set to FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Edgebeam running down correct gridlines (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Joinery Rebates set to required depths
checkpoint-status |  |  | checkpoint | Garage Rebate set as per client requirements
checkpoint-status |  |  | checkpoint | Inslab rebates in correct slab position (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates set to correct depth from FFL
checkpoint-status |  |  | checkpoint | Formwork Sprayed with form release (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum bottom cover (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from form work (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All bends tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps minimum lap requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from form work and rebates (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minum cover from services (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Stringline run and left up in multiple places to prove cover from FFL to top of Mesh for engineer and council (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Floor checked all over to make sure no steel is above FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Thickening measurement as per plan and same top and bottom (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Pods been cut outside the slab
checkpoint-status |  |  | checkpoint | All DPM taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM up to edgebeam (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Services taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inside pad free from rubbish (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Starter caps on all waratahs or exposed starters (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Rubbish in bins and site cleaned up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess boxing and steel stacked neatly and out of lay teams way, ready for pick up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Nothing around the slab and in way of Lay team (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess pods and pod rubbish been collected or supplier been called to pick up
checkpoint-status |  |  | checkpoint | Site in clean and respectable state (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team has been organised
checklist-sectioned |  |  | checklist | Foreman Job Checklist (Slabs) |  |  |  |  | Yes | Foreman Job Checklist (Slabs) | 24fd8de3-3954-438b-b752-43687bc52453
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Job file made?
checkpoint-status |  |  | checkpoint | Profile/Establish?
text | 17b63276-faa8-5d9d-a0b0-df3bdfed98ba |  | textbox | Profile timber head to site or need to be loaded?
button | 9d00a571-acb0-59ac-aaca-007a4174fc7a |  | button |  | To site, To be loaded
text | 99aba052-af32-5860-ae08-b2d02bd9ebe2 |  | textbox | Waratahs need/loaded?
text | ccdc14d3-1fae-5538-88cc-83815d349e32 |  | textbox | Surveyor time on site?
boolean | 292ac4c3-8e8e-5e53-abf0-3cd692ce9e19 |  | tickbox | Survey markout plan laminated?
checkpoint-group |  |  | section | Forklift
checkpoint-status |  |  | checkpoint | 3-phase plus onsite?
checkpoint-status |  |  | checkpoint | Formwork lay down areas identified?
checkpoint-group |  |  | section | Formwork
checkpoint-no-status |  |  | checkpoint | Doka delivery date?
date | 2b671bc4-aa55-5a63-96e5-2d18e23af795 |  | date
boolean | 61f54e39-b753-57c4-8eab-fb3d0d070fcb |  | tickbox | Doka engineer plan laminated?
checkpoint-status |  |  | checkpoint | Doka heights laminated?
checkpoint-status |  |  | checkpoint | Conduit and plugs ordered?
checkpoint-status |  |  | checkpoint | Wall chairs ordered
checkpoint-status |  |  | checkpoint | Form release ordered?
checkpoint-status |  |  | checkpoint | Steel delivery dates?
checkpoint-status |  |  | checkpoint | Steel delivery tags printed?
checkpoint-status |  |  | checkpoint | Concrete blocks ordered (if required)?
checkpoint-status |  |  | checkpoint | Chalk lines
checkpoint-status |  |  | checkpoint | Lasers/spare batteries
checkpoint-status |  |  | checkpoint | Dazzle
checkpoint-status |  |  | checkpoint | Access to CONQA for QA forms?
checklist-flat |  |  | checklist | Friday Toolbox Meeting - End of Day |  |  |  |  | Yes | Friday Toolbox Meeting - End of Day | 28da8681-1f57-4064-8f16-50d92efe3730
checkpoint-status |  |  | checkpoint | Details Complete (pass once all relevant details are inputted below)
text | b3088db4-33c2-5db5-a667-1063dc018fef |  | textbox | Go over van load out list
text | ed7ba273-c6dd-56a0-b820-66c6a228c673 |  | textbox | Make sure by the end of day the van is 100% load out for Monday (Inform Office)
text | 677781f5-bb7f-5df8-a6cc-14a415c8b4d8 |  | textbox | Something that didn't go well for the week?
text | 34031d92-6074-5afc-a566-d392c0ff6428 |  | textbox | Something that went well for the week?
text | 7f90bf91-8716-570b-ac7b-f290143d04f0 |  | textbox | What can we learn from the week to do safer?
text | ae4058c2-b71d-59b7-8ce5-77701c3bbb6d |  | textbox | Overall recap from the team for the week.
text | 97ad3b7a-4c56-5b28-be64-683555af93b9 |  | textbox | Write down feedback both positive and negative.
text | 07612eb9-f3f8-538e-b4ce-ab00a289d765 |  | textbox | What do we require for next week? (Inform Office)
holdpoint |  |  | signoff | Toolbox conducted by:
checklist-flat |  |  | checklist | Job Estimation Handover to Project Team |  |  |  |  | Yes | Job Estimation Handover to Project Team | 2a0bc0d4-f62c-4003-8c02-00a6fbcc72e7
checkpoint-no-status |  |  | checkpoint | Project Details
text | 7935097c-d7d4-58a4-9a69-f34f828cf986 |  | textbox | Project Details:
text | 37be894c-aae0-521f-be39-cfc7370fc823 |  | textbox | Client:
text | bfa6f74e-1179-5a63-908d-5323af3433f3 |  | textbox | Address:
text | e50bc661-959d-505a-b8ff-6d2e2b655cd5 |  | textbox | Other:
text | 38f84940-9ad5-5bd8-9e3d-d2a2d377358f |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Estimator and Project Team - Discuss quoted job (QS/PM)
checkpoint-status |  |  | checkpoint | Critical tags discussed
checkpoint-status |  |  | checkpoint | Any tender ageement with subcontractors and supplier discussed and documented. (Who are the subcontractors and suppliers)
checkpoint-status |  |  | checkpoint | Tender and risks and opportunities discussed with project team
checkpoint-status |  |  | checkpoint | P&G Allowances
checkpoint-status |  |  | checkpoint | Tender discuss and approved by relevant person/s
checkpoint-status |  |  | checkpoint | Formwork / Propping / Rebates allowed for Job
checkpoint-status |  |  | checkpoint | Program and Labour allowances for each phase of the job
checkpoint-status |  |  | checkpoint | Any other job information that needs to be handed over.
checklist-flat |  |  | checklist | Foreman and Site Manager Job planning Prior to meeting PM |  |  |  |  | Yes | Foreman and Site Manager Job planning Prior to meeting PM | 2e9f7308-8a6d-42fe-9213-c22d68efc2bf
checkpoint-no-status |  |  | checkpoint | Foreman and Site Manager Job planning Prior to meeting PM
text | 30dc9a7d-112e-5731-b0d9-65314f6cd77f |  | textbox | Project details:
text | 6c0b0e93-af96-5422-bf8c-29b8b1fe0280 |  | textbox | Client:
text | 19327e34-5b33-5505-ae35-5c17a0240c59 |  | textbox | Address:
text | 3874c4d8-3533-5b41-87eb-87555e86cbe1 |  | textbox | Other:
text | 6304ed4b-369a-5d2d-9c57-f171afd2857a |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review plans, including engineer set and build question sheet
checkpoint-status |  |  | checkpoint | Go over PM's Job schedule
checkpoint-status |  |  | checkpoint | Identify key dates
checkpoint-status |  |  | checkpoint | Deliveries
checkpoint-status |  |  | checkpoint | QA's
checkpoint-status |  |  | checkpoint | Inspections
checkpoint-status |  |  | checkpoint | Pour dates
checkpoint-status |  |  | checkpoint | Identify materials used
checkpoint-status |  |  | checkpoint | DPM
checkpoint-status |  |  | checkpoint | Steel
checkpoint-status |  |  | checkpoint | Mebrane type
checkpoint-status |  |  | checkpoint | Boxing required
checkpoint-status |  |  | checkpoint | Identify survey plan and Heights
checkpoint-status |  |  | checkpoint | Identify waterproofing locations and where DPM ends
checkpoint-status |  |  | checkpoint | If we have footing outside of building lines, top of footings in these loctions need to be at least 200 mm below FFL
checklist-flat |  |  | checklist | 2.1 Slab Installation Methodology |  |  |  |  | Yes | 2.1 Slab Installation Methodology | 36acc24f-2648-42a2-b80f-b71fd36291d5
checkpoint-no-status |  |  | checkpoint | What is FFL
checkpoint-status |  |  | checkpoint | Set Profiles to 30 mm above FFL and stransfer gridlines onto profiles
checkpoint-status |  |  | checkpoint | Set up stringlines, check measurements and diagonals
checkpoint-status |  |  | checkpoint | Clean / wash down all footings and Block wall header blocks
checkpoint-status |  |  | checkpoint | Check all prep heights are within tolerance
checkpoint-status |  |  | checkpoint | Set Edgebeam and Rebates set to FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Set correct Edgebeam face running down correct gridlines (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Joinery Rebates set to required depths (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Garage Rebate set as per client requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All waratahs have starter caps on (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Site Cleaned / Rubbish in bin/ Materials located in centralised locations/ Ready for Plumbers?
checkpoint-status |  |  | checkpoint | Steel and Pod cutting loctions outside of pad established (centralise all rubbish to one location)
checkpoint-status |  |  | checkpoint | Pods have been cut outside the slab
checkpoint-status |  |  | checkpoint | All steel has minimum bottom cover (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from form work (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All bends tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps minimum lap requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from form work and rebates (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minum cover from services (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Stringline run and left up in multiple places to prove cover from FFL to top of Mesh for engineer and council (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates set to correct depth from FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Floor checked all over to make sure no steel is above FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Thickening measurement as per plan and same top and bottom (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM up to edgebeam (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Services taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inside pad free from rubbish (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Starter caps on all waratahs or exposed starters (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Rubbish in bins and site cleaned up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess boxing and steel stacked neatly and out of lay teams way, ready for pick up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Nothing around the slab and in way of Lay team (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess pods and pod rubbish been collected or supplier been called to pick up
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates in correct slab position (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Formwork Sprayed with form release (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team been organised
checklist-flat |  |  | checklist | 1 Job estimation handover (QS / PM) |  |  |  |  | Yes | 1 Job estimation handover (QS / PM) | 3828f5bb-dd24-4968-9726-362a92700824
checkpoint-no-status |  |  | checkpoint | Project Details
text | f53c42b9-da54-54b0-bc43-a320519065b8 |  | textbox | Project Details:
text | 192bfc33-d733-5795-9fd9-d9aef53cd623 |  | textbox | Client:
text | 4a2377e4-3d0f-5532-8993-98fb2bbda6e0 |  | textbox | Address:
text | c0fddcfb-d904-5ddf-8c18-ed70fd5e6aa9 |  | textbox | Other:
text | 87a01179-f626-5b16-bf76-10d552667cb2 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Estimator and Project Team - Discuss quoted job (QS/PM)
checkpoint-status |  |  | checkpoint | Critical tags discussed
checkpoint-status |  |  | checkpoint | Any tender ageement with subcontractors and supplier discussed and documented. (Who are the subcontractors and suppliers)
checkpoint-status |  |  | checkpoint | Tender and risks and opportunities discussed with project team
checkpoint-status |  |  | checkpoint | P&G Allowances
checkpoint-status |  |  | checkpoint | Tender discuss and approved by relevant person/s
checkpoint-status |  |  | checkpoint | Formwork / Propping / Rebates allowed for Job
checkpoint-status |  |  | checkpoint | Program and Labour allowances for each phase of the job
checkpoint-status |  |  | checkpoint | Any other job information that needs to be handed over.
checklist-sectioned |  |  | checklist | PPE Check |  |  |  |  | Yes | PPE Check | 3da5d1c0-508c-4fda-9cf7-cb10b6320b8a
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | bd91ab13-5765-5b58-ae55-39154f707f6d |  | textbox | Employee:
date | 110a7435-1219-51a4-9147-d8b1d707bf73 |  | date | Date:
text | c07e5dc2-a9cf-5b21-b312-e1919cc75d65 |  | textbox | Conducted by:
text | c0f5d9a6-8e1d-5f7d-8b3b-7104ae643043 |  | textbox | Overall Comment:
checkpoint-group |  |  | section | Standard Issue PPE
checkpoint-status |  |  | checkpoint | Steel cap boots in good/working condition?
checkpoint-status |  |  | checkpoint | Hard hat is in good/working condition?
checkpoint-status |  |  | checkpoint | High visibility clothing is in good/working condition?
checkpoint-status |  |  | checkpoint | Hearing protection in good/working condition?
checkpoint-status |  |  | checkpoint | Glasses are in good/working condition?
checkpoint-status |  |  | checkpoint | Gloves are in good/working condition?
checkpoint-group |  |  | section | Additional PPE
checkpoint-status |  |  | checkpoint | Mask or Respirator
checkpoint-status |  |  | checkpoint | Harness check
date | 0842d41d-1c8c-5a34-a693-ee830a8c7812 |  | date | Date of harness certification:
holdpoint |  |  | signoff | Signature:
checklist-flat |  |  | checklist | Foreman Job File Checklist |  |  |  |  | Yes | Foreman Job File Checklist | 43aff45d-733f-4931-a32e-0b01b159af70
checkpoint-status |  |  | checkpoint | Job file formed
checkpoint-status |  |  | checkpoint | Plans reviewed and required details printed and laminated?
label | 23f2ac62-715b-5519-95d3-7b607d33bbd2 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Survey markout plan printed and laminated?
label | 5fa326e8-471f-57b2-98ee-2bd1a0514ca3 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All heights printed and kaminated?
label | 0f964301-49f7-5fdf-b98d-deec471ae64e |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Job Master Schedule printed and laminated? (if schedule changes, throw away old and add new)
label | 7dc8dec2-4e8f-51e6-b665-f947a262e362 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Amounts
label | f3d0dced-a4a0-5fc6-b5c1-37a84f1ec6cd |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Dockets
label | 99c2a1fc-d39b-5659-98fb-ff7f4741792b |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Toolboxes
label | dc38249a-430a-5bf3-94cf-1c01301cf65d |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | SSSP
label | 105aaf5e-1a98-5b6a-b900-2b05bb466603 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Waterproofing markout
label | b51b8ccf-b7e5-538f-b570-987625afe305 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | PM - Foreman handover printed
label | d194b1b5-da53-58da-bca5-7b0c34298d8c |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All Qas printed
label | da9ff54a-52f2-5232-8627-6b2fe59d7f67 |  | note | Add to Job File
checklist-sectioned |  |  | checklist | Foreman Job Checklist (Footings) |  |  |  |  | Yes | Foreman Job Checklist (Footings) | 491d2bed-40f1-4e5d-9ae8-89a5467839b9
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Job file made?
checkpoint-status |  |  | checkpoint | Profile/Establish?
text | 1126bc25-ec36-5070-991c-4fc50ee767e9 |  | textbox | Profile timber head to site or need to be loaded?
button | 63d00798-242a-5c5b-ba52-5faa044d774a |  | button |  | To site, To be loaded
text | 6f38acca-a6cd-5a60-9155-6e6870c77b8a |  | textbox | Waratahs need/loaded?
text | 9dbf2751-d203-588a-9e06-935f8b5c457a |  | textbox | Surveyor time on site?
boolean | dc80bf69-e89a-50d7-b46b-5548b2522679 |  | tickbox | Survey markout plan laminated?
checkpoint-group |  |  | section | Footings
checkpoint-no-status |  |  | checkpoint | Digger time on site?
text | 1217ee98-7921-59b4-9198-d47ed8967f41 |  | textbox
checkpoint-no-status |  |  | checkpoint | Boxing timber delivered? or loaded?
button | 9e9acd7d-2600-5c0a-a67b-c4ec0c4c5fb2 |  | button |  | Delivered,Loaded
checkpoint-status |  |  | checkpoint | Waratah loaded?
checkpoint-no-status |  |  | checkpoint | DPM Delivered or loaded?
button | 8b82967e-5358-587a-9749-a9c65b4e4bf4 |  | button |  | Delivered,Loaded
checkpoint-no-status |  |  | checkpoint | Steel delivery date?
date | 279f17a1-c5b6-5c8a-bcc7-29831524f081 |  | date
boolean | 18bab47e-8bba-5b53-a3d0-44f2f783e201 |  | tickbox | Steel takeoff form printed?
boolean | bfbbe3a3-c0a4-59be-9369-bb22017a5c1e |  | tickbox | Chairs being delivered?
boolean | d47f5e5a-4077-57ae-9bbe-fa9440800ceb |  | tickbox | Waterproofing areas marked/printed/laminated?
checkpoint-group |  |  | section | Van load out
checkpoint-status |  |  | checkpoint | Laser and spare batteries
checkpoint-status |  |  | checkpoint | Dazzle
checkpoint-status |  |  | checkpoint | String lines
checkpoint-status |  |  | checkpoint | Nails
checkpoint-status |  |  | checkpoint | Tie wires
checkpoint-status |  |  | checkpoint | All other relevant rools required?
checklist-sectioned |  |  | checklist | Vehicle Inspection |  |  |  |  | Yes | Vehicle Inspection | 51b4ece8-37dc-4831-8baa-9a3cb1b36804
checkpoint-group |  |  | section | Vehicle Details
checkpoint-no-status |  |  | checkpoint | Vehicle Details
text | c025dd6a-e07b-5e2a-b756-5e6d10c405d5 |  | textbox | Licence Plate:
text | c45b4822-3eb9-57ca-8ea9-e3fb95f84653 |  | textbox | Conducted by:
text | 926b7917-a9ef-50d5-9a09-0878c00f17d1 |  | textbox | Overall Comment:
checkpoint-group |  |  | section | Vehicle Exterior
checkpoint-status |  |  | checkpoint | Tyres in good condition and inflated?
checkpoint-status |  |  | checkpoint | Showing signs of leaks under the vehicle?
checkpoint-status |  |  | checkpoint | Doors open and close?
checkpoint-status |  |  | checkpoint | Bonnet and boot open and close?
checkpoint-group |  |  | section | Vehicle Interior
checkpoint-status |  |  | checkpoint | Clean interior?
checkpoint-status |  |  | checkpoint | Floor free of hazards?
checkpoint-status |  |  | checkpoint | Seats able to be adjusted and in good order?
checkpoint-status |  |  | checkpoint | Seat belts not frayed or cracked?
checkpoint-status |  |  | checkpoint | Mirrors adjusted?
checkpoint-status |  |  | checkpoint | Any warning lights on?
checkpoint-status |  |  | checkpoint | Heater and A/C working?
checkpoint-status |  |  | checkpoint | Horn working?
checkpoint-status |  |  | checkpoint | Brakes working?
checkpoint-group |  |  | section | Front - End of Vehicle
checkpoint-status |  |  | checkpoint | Headlights (high/low) operational?
checkpoint-status |  |  | checkpoint | Hazard lights operational?
checkpoint-status |  |  | checkpoint | Turning signals (left & right) operational?
checkpoint-status |  |  | checkpoint | Wiper blades operational and in good condition?
checkpoint-status |  |  | checkpoint | Front grill free of debris?
checkpoint-group |  |  | section | Rear - End of Vehicle
checkpoint-status |  |  | checkpoint | Tail lights operational?
checkpoint-status |  |  | checkpoint | Brake lights operational?
checkpoint-status |  |  | checkpoint | Turning signals (left & right) operational?
checkpoint-status |  |  | checkpoint | Reversing lights operational?
checkpoint-status |  |  | checkpoint | Rear window wipers operational?
checkpoint-group |  |  | section | Safety Equipment
checkpoint-status |  |  | checkpoint | Tyre changing equipment available and in good working order?
checkpoint-status |  |  | checkpoint | First aid kit with adequate supplier?
checkpoint-status |  |  | checkpoint | Fire extinguisher fully charged with updated certificate?
checkpoint-group |  |  | section | Maintenance Check
checkpoint-no-status |  |  | checkpoint | Maintenance Check
text | f4109693-3942-5d78-97e7-c977f88efa62 |  | textbox | Engine oil level:
text | 6a39762b-a4e5-5e04-af69-4d374af34c30 |  | textbox | Engine coolant (check reservoir)
checkpoint-group |  |  | section | WOF
checkpoint-no-status |  |  | checkpoint | WOF
text | 98deed0a-3201-5951-a4f6-19186cf0e6b5 |  | textbox | Current WOF:
checkpoint-group |  |  | section | Rego
checkpoint-no-status |  |  | checkpoint | Rego
text | a0b2077f-9bc2-5861-a78d-a2bee6ebc78b |  | textbox | Current Rego:
checkpoint-group |  |  | section | Road User Miles
checkpoint-status |  |  | checkpoint | Up to date?
text | e7de428e-6290-5e46-8d5a-407f1dbdb105 |  | textbox | Odometer Reading:
holdpoint |  |  | signoff | Signature:
checklist-flat |  |  | checklist | 2 Job handover to Site Manager and Foreman (PM) |  |  |  |  | Yes | 2 Job handover to Site Manager and Foreman (PM) | 58954b04-0ad6-439e-ab64-8b7e02dc6d70
checkpoint-no-status |  |  | checkpoint | Project Details:
text | e49a590f-64ff-564c-b8e2-ad9c32ea66ca |  | textbox | Client:
text | f3e396e7-1600-5acc-a5a0-4ceb32a38cad |  | textbox | Address:
text | c57d80c3-28a1-5661-ac00-9c3e10edbbc2 |  | textbox | Other:
text | 3a8cb1d3-1f68-5a81-acf6-f527588017ce |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Send Foreman Job Question Sheet
checkpoint-status |  |  | checkpoint | Get Foreman to review plans before coming in to see you
checkpoint-status |  |  | checkpoint | Have Master Schedule sent
checkpoint-status |  |  | checkpoint | Have survey serout and plan sent
checkpoint-status |  |  | checkpoint | Make sure Foreman knows if we are working off grids or building lines
checkpoint-status |  |  | checkpoint | Make sure they know heights
text | 1a3f0eb9-2d18-5cfb-902a-a62a084d4823 |  | textbox | Footings height:
text | 10394e0d-513e-5570-b9d9-a99e02bb23bc |  | textbox | Block/wall heights:
text | 1817a008-1e5d-53c3-8933-ed24c4c18929 |  | textbox | Finish floor levels:
text | 01d3202b-9c4e-5ed9-8cc3-6ac60ba7854f |  | textbox | Lift pit levels:
text | 3d9cee35-327b-5fd3-a235-f19aae8c852f |  | textbox | Finish Ground Levels (for footings outside of building lines)
checkpoint-status |  |  | checkpoint | DPM require
checkpoint-status |  |  | checkpoint | Waterproofing areas
checkpoint-status |  |  | checkpoint | Formworks and bracing required and what was quoted
checklist-flat |  |  | checklist | Job Handover to Foreman |  |  |  |  | Yes | Job Handover to Foreman | 59c6abf4-3717-4b12-8208-7ce60ff49289
checkpoint-no-status |  |  | checkpoint | Project Details
text | 101ac9cc-be37-5a1b-b79b-c419bdcc6e4b |  | textbox | Project Details:
text | f07ca227-e88d-5202-99f1-0f057a77eca0 |  | textbox | Client:
text | 271a532f-ad2c-56e0-94ce-41ab2057aa43 |  | textbox | Address:
text | 8286f6d7-67b1-5fd3-83f9-ae8c03c189c3 |  | textbox | Other:
text | ad3c3876-8bcc-5c31-b87f-e567d7552356 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Send Foreman Job Question Sheet
checkpoint-status |  |  | checkpoint | Get Foreman to review plans before coming in to see you
checkpoint-status |  |  | checkpoint | Have Master Schedule sent
checkpoint-status |  |  | checkpoint | Have survey serout and plan sent
checkpoint-status |  |  | checkpoint | Make sure Foreman knows if we are working off grids or building lines
checkpoint-status |  |  | checkpoint | Make sure they know heights
text | bf29547c-8bbb-5bc2-8175-7999f31823c3 |  | textbox | Footings height:
text | 4ca48c85-a947-5f45-87f4-ea8ea65c8d9a |  | textbox | Block/wall heights:
text | a95fce3c-1631-5245-b60a-2f334d5e805c |  | textbox | Finish floor levels:
text | a8bbb6a9-2ce1-59e6-ac51-7027badc07cb |  | textbox | Lift pit levels:
text | 92fd1e3e-ef0f-53c3-bb85-63249ffa9ff7 |  | textbox | Finish Ground Levels (for footings outside of building lines)
checkpoint-status |  |  | checkpoint | DPM require
checkpoint-status |  |  | checkpoint | Waterproofing areas
checkpoint-status |  |  | checkpoint | Formworks and bracing required and what was quoted
checklist-flat |  |  | checklist | 3.2 Footing Pre Pour Quality Assurance |  |  |  |  | Yes | 3.2 Footing Pre Pour Quality Assurance | 6f3547ac-3fae-4946-9eb5-c18fd8dbd9e1
checkpoint-status |  |  | checkpoint | Check all top of footing heights and make sure they are as per plan? Label as footing engineer detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | All footing depths as per plan? Label as per engineer footing detail( Multiple photos required)
checkpoint-status |  |  | checkpoint | All footing widths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Specified DPM used in footings? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All DPM laps taped? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Waterproofing membrane in required parts of footing? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel bottom minimum bottom cover achieved in all places (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel minimum side cover achieved in all places (Boxing or to earth)(Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends all tied? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends as per minimum lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Bottom mat of footing spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Top mat spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect bottom mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continous bent steel to connect top mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | Where footings step up, have Z bends and horizontals been installed as per engineer design. (Multiple photos required)
checkpoint-status |  |  | checkpoint | On step ups, form work set to footing depth and no more? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter Line been profiles and set as per engineer requirements from block / earth face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Starters within 5 mm of engineer plans from block face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter spacings set as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter lap for post concrete pour, set to have minimum steel lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Height pegs or nails installed and sprayed for Lay team (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Footings clear from rubbish and dirt (Multiple photos required)
checkpoint-status |  |  | checkpoint | All waratahs and starters have starter caps on (Multiple photos required)
checkpoint-status |  |  | checkpoint | All excess steel / materials stored neatly and out of lay and blockie teams way? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Access for concrete pump clear
checkpoint-status |  |  | checkpoint | All rubbish in bin or removed from site
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team has been organised
checklist-flat |  |  | checklist | Monday Toolbox Meeting |  |  |  |  | Yes | Monday Toolbox Meeting | 72570c75-072e-436c-a079-1132716d88f4
checkpoint-status |  |  | checkpoint | Details Complete (pass once all relevant details are inputted below)
text | 6f5ecbea-cbf2-5a12-a076-5141e6cea10f |  | textbox | Quick debrief/recap on last week
text | 01bbbdf4-2ab7-5bc7-b92c-51f1256b6019 |  | textbox | Brief on what the plan is for the week
text | 5cd7f664-4330-500f-aaa9-d4e282872223 |  | textbox | Goals/key dates for the week
text | 96364098-99dd-5331-96e3-4e830a39e934 |  | textbox | Today's plan
text | c528ea0b-fa2f-5ce2-b3fb-a251bb36a816 |  | textbox | Individuals task for the day/week.
text | 24e29295-ea89-563e-aac6-41fcc2c2381b |  | textbox | A safe work practice topic to discuss, i.e: grinding with eye protection/hearing protection
select | befc0b39-9b4d-5173-a10c-77c7a38542b4 |  | dropdown | Van's any tool issues/have they been reported to office. | Yes,No
holdpoint |  |  | signoff | Toolbox conducted by:
checklist-flat |  |  | checklist | 3 Site Manager and Foreman job planning prior to meeting PM (SM / F) |  |  |  |  | Yes | 3 Site Manager and Foreman job planning prior to meeting PM (SM / F) | 751adc33-91b7-4c3d-8c7d-3cc5f20ce254
checkpoint-no-status |  |  | checkpoint | Foreman and Site Manager Job planning Prior to meeting PM
text | f7f7c984-5c65-5438-99be-363ccd943632 |  | textbox | Project details:
text | c022aceb-02b3-5225-9e26-e033b370c32f |  | textbox | Client:
text | 53554457-c271-574d-ad0a-b83d648daaa9 |  | textbox | Address:
text | 7ab093c3-ef6c-5326-8f3f-610efa93ebf7 |  | textbox | Other:
text | cfb3bf50-7e66-5df6-9797-37a969510d99 |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review plans, including engineer set and build question sheet
checkpoint-status |  |  | checkpoint | Go over PM's Job schedule
checkpoint-status |  |  | checkpoint | Identify key dates
checkpoint-status |  |  | checkpoint | Deliveries
checkpoint-status |  |  | checkpoint | QA's
checkpoint-status |  |  | checkpoint | Inspections
checkpoint-status |  |  | checkpoint | Pour dates
checkpoint-status |  |  | checkpoint | Identify materials used
checkpoint-status |  |  | checkpoint | DPM
checkpoint-status |  |  | checkpoint | Steel
checkpoint-status |  |  | checkpoint | Mebrane type
checkpoint-status |  |  | checkpoint | Boxing required
checkpoint-status |  |  | checkpoint | Identify survey plan and Heights
checkpoint-status |  |  | checkpoint | Identify waterproofing locations and where DPM ends
checkpoint-status |  |  | checkpoint | If we have footing outside of building lines, top of footings in these loctions need to be at least 200 mm below FFL
checklist-flat |  |  | checklist | 2.2 Footing Methodology |  |  |  |  | Yes | 2.2 Footing Methodology | 80730027-20dd-4128-b514-4812158bdf03
checkpoint-status |  |  | checkpoint | Set profiles to above Footing FFL
checkpoint-status |  |  | checkpoint | Surveyor to install grids on profiles (No builder to set a gridline)
checkpoint-status |  |  | checkpoint | Surveyor to mark Block side of grid line with an X on profile both sides
checkpoint-status |  |  | checkpoint | Install all stringlines
checkpoint-status |  |  | checkpoint | Measure all walls and confirm measurements within tolerance of plan measurements
checkpoint-status |  |  | checkpoint | Check diagonals
checkpoint-status |  |  | checkpoint | Transfer grids to ground and mark out each footing as per engineer dimension
checkpoint-status |  |  | checkpoint | Confirm all top of footing heights and make sure they are as per plan? Label as per footing engineer detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Confirm footing depths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Confirm footing widths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Specified DPM used in footings? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Dig out footings
checkpoint-status |  |  | checkpoint | Confirm all footing depths as per plans and within tolerable deep to begin building footing
checkpoint-status |  |  | checkpoint | Confirm all footing tops as per plans and within tolerable deep to begin building footing
checkpoint-status |  |  | checkpoint | Box footings where required
checkpoint-status |  |  | checkpoint | Insert DPM into footings where required
checkpoint-status |  |  | checkpoint | All DPM laps taped? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Waterproofing membrane in required parts of footing? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel out bottom mat as per singeer plans
checkpoint-status |  |  | checkpoint | Steel bottom minimum bottom cover achieved in all places (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel minimum side cover achieved in all places (Boxing or to earth)(Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends all tied? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends as per minimum lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Bottom mat of footing spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Top mat spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect bottom mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect top mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | Where footings step up, have Z bends and horizontals been installed as per engineer design. (Multiple photos required)
checkpoint-status |  |  | checkpoint | On step ups, form work set to footing depth and no more? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter Line been profiled and set as per engineer requirements from block / earth face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Starters with in 5 mm of engineer plans from block face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter spacings set as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter lap for post concrete pour, set to have minimum steel lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Height pegs or nails installed and sprayed for Lay team (Multiple photos required)
checkpoint-status |  |  | checkpoint | All footings clear from rubbish and dirt (Multiple photos required)
checkpoint-status |  |  | checkpoint | All waratahs and starters have starter caps on (Multiple photos required)
checkpoint-status |  |  | checkpoint | All excess steel / materials stored neatly and out of lay and blockie team way? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Access for concrete pump clears
checkpoint-status |  |  | checkpoint | All rubbish in bin or removed from site
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photos required)
checkpoint-status |  |  | checkpoint | Hand over to lay team been organised
checklist-flat |  |  | checklist | 6 Site Manager and Foreman’s Job planning (SM / F) |  |  |  |  | Yes | 6 Site Manager and Foreman’s Job planning (SM / F) | 80d74678-9999-4ced-a698-2d8287ace7f9
checkpoint-no-status |  |  | checkpoint | Project Details
text | 618c34b8-902c-5d50-b08c-304120c185f4 |  | textbox | Project Details:
text | 9f4ae31d-2207-541f-821e-71b0e674496b |  | textbox | Client:
text | a260687b-f380-532c-b2f4-e280563af58e |  | textbox | Address:
text | 38979c2f-d45a-577c-9389-9bb927949c29 |  | textbox | Other:
text | 86c44e0c-a084-530f-b7c4-386535c90ef8 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Job built from start to finish - Compare with Program
checkpoint-status |  |  | checkpoint | Design issues noted and send to client
checkpoint-status |  |  | checkpoint | Site Specific OTWC requirements - Send to client
checkpoint-status |  |  | checkpoint | Master Program built and send to client
label | 25a55154-bd8a-558b-92d0-268fbdfad4a9 |  | note | To include materials drop offs
label | a2e21c94-6b16-5462-b09f-04f81cae434f |  | note | To include formwork required
label | 9ae429d5-e3b8-503d-8922-77e736ce9033 |  | note | To include concrete bookings
label | 311552b1-3c56-5688-a912-322b247776aa |  | note | To include inspections
checkpoint-status |  |  | checkpoint | Concrete bookings insert into Concrete Schedule
checkpoint-status |  |  | checkpoint | Material bookings into Material Schedule
checkpoint-status |  |  | checkpoint | Site Manager to get a copy of the Job Schedule
checkpoint-status |  |  | checkpoint | Schedule to have Toolbox Meeting
checklist-sectioned |  |  | checklist | Accident & Incident Investigation Report |  |  |  |  | Yes | Accident & Incident Investigation Report | 93f75c10-f769-4a24-9fad-8d48812d8ba6
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Completed
text | 4a85a19d-528a-5905-9bf9-fc7f7f2d5306 |  | textbox | Name of Investigator:
checkpoint-group |  |  | section | Particulars of Incident
checkpoint-status |  |  | checkpoint | Particulars of Incident Details Completed
select | df0a533a-68f7-572f-828d-d74a34f51161 |  | dropdown | Day of Incident: | Monday,Tuesday,Wednesday,Thursday,Friday,Saturday,Sunday
text | b5eeec9f-ccec-54e7-9dec-855efc31aa68 |  | textbox | Time:
text | a4c2d05f-1e74-5706-adb9-6ed1adf0e86c |  | textbox | Project/Site:
date | 69b8d607-827c-52ee-a41b-3032e7bb38b4 |  | date | Date Reported:
checkpoint-group |  |  | section | Injured Person Details
checkpoint-status |  |  | checkpoint | Injured Person Details Completed
text | db03d8b0-e79e-595c-9f93-659e33deac91 |  | textbox | Name:
text | 388def2d-db5b-5058-9c37-915c88acc2f9 |  | textbox | Age:
text | 3c4f1451-7fe9-523b-8738-58d8fafc4ad8 |  | textbox | Phone Number:
text | 6ce41441-0edb-5c27-b5d6-c61d5e9bc6c5 |  | textbox | Address:
text | 23d25a89-960f-517f-baab-865ea7790af1 |  | textbox | Reported date of incident:
text | 7873853a-47eb-5b2b-a3e6-fe5bc1be55a3 |  | textbox | Length of employment:
text | 211480f5-3198-5e49-ab41-a6cc0ff59a6b |  | textbox | Time on job:
checkpoint-status |  |  | checkpoint | Type Of Injury:
boolean | fb727d28-23ef-5435-a3f5-2321c229e068 |  | tickbox | Strain/sprain
boolean | 6fd3f5b7-c464-5f56-b895-bf89f9e0e8f7 |  | tickbox | Fracture
boolean | 6913e030-33e7-5b53-b410-1fb45729533a |  | tickbox | Laceration/cut
boolean | ffc98d29-5a7b-5816-8c0d-6b0cb3ff8f39 |  | tickbox | Bruising
boolean | 7341b721-9506-57ab-bf27-621553af09ef |  | tickbox | Scratch/abrasion
boolean | 1e977339-ffc6-58ec-9d3e-f1ca09953b82 |  | tickbox | Amputation
boolean | d61c2485-190b-5302-bc89-397668a13e93 |  | tickbox | Burn scald
boolean | 50b26c80-414b-5a57-ab15-28c19707fd4a |  | tickbox | Dislocation
boolean | d5e38100-5314-5258-b5fa-ab4f1ad9bfa5 |  | tickbox | Internal
boolean | 1520645f-8685-594d-98d1-dfc22a3e9d09 |  | tickbox | Foreign body
boolean | 43fc06fe-9f63-517d-8fd5-90d2734a6754 |  | tickbox | Chemical reaction
boolean | 7d33a445-0d6b-55e0-9409-3bad8184a9ca |  | tickbox | Other
text | ff0702bd-6b71-5028-9fe1-aacaa52608ff |  | textbox | If other please specify:
text | 8190c8e4-2e60-5e31-b887-7d5616e87e57 |  | textbox | Injured Part of Body:
checkpoint-group |  |  | section | Damaged Property
checkpoint-status |  |  | checkpoint | Damaged Property Details Completed
text | 55ee3d18-353a-5045-aba8-98b1718d7996 |  | textbox | Property/material damaged:
text | 10a41a93-bd62-5c3c-a758-dfc140687430 |  | textbox | Nature of damage:
text | 116c34ce-2deb-5395-b54d-2317d195eb96 |  | textbox | Object/substance inflicting damage:
checkpoint-group |  |  | section | Incident
checkpoint-status |  |  | checkpoint | Incident Details Complete
text | 9ea824ad-0fe5-5424-b3bf-25f50d568bbd |  | textbox | Describe what happened (space overleaf for diagram – essential for all vehicle incidents):
checkpoint-group |  |  | section | Analysis
checkpoint-status |  |  | checkpoint | Analysis Details Completed
text | f0e94530-c8e9-5fd7-a4ae-63408e0b18b8 |  | textbox | What were the causes (root and contributing causes) of the incident?
text | 8a23af3d-b605-5430-bcd0-fb6fa280d0dd |  | textbox | Root causes – safety system failures:
text | a4397a1b-279d-5acb-9f13-5f1335efe3b7 |  | textbox | Contributing causes – unsafe acts and conditions:
checkpoint-group |  |  | section | Prevention
checkpoint-status |  |  | checkpoint | Prevention Details Completed
text | 0607b9bd-f131-5bc9-87e4-e10d350ab4b0 |  | textbox | What action has or will be taken to prevent a recurrence? Tick items already actioned
boolean | edbc8442-dcf6-5bd3-bd82-7e5948c08df7 |  | tickbox | Completed
text | d132e953-8fe4-5fe7-9bb0-b71d5a40178c |  | textbox | By Whom:
text | f39bd154-5d3f-5ae0-90c3-84f709083459 |  | textbox | When:
checkpoint-group |  |  | section | Treatment and Investigation of Incident
checkpoint-status |  |  | checkpoint | Treatment and Investigation of Incident Details Completed
text | cf8721f2-0ea5-54fc-9b53-f39aefaf21cc |  | textbox | Treatment and Investigation of Incident :
text | 2be0743b-5aef-5f66-b1b7-313bc1aeff93 |  | textbox | Name of person giving First Aid:
text | c372b585-0b28-543d-a9b3-7dea34acde5a |  | textbox | Doctor/Hospital:
text | 6f742029-ebf9-55f3-86c7-b69d682ab071 |  | textbox | Incident investigated by:
date | ea336dd1-98c7-59d4-ac78-851b05c88c98 |  | date | Date:
select | f0a56278-2219-5112-bf15-b98b62880586 |  | dropdown | Worksafe NZ advised | Yes,No
date | ded41739-a56f-5bc6-bd65-daf625f8c20b |  | date | Date:
checkpoint-group |  |  | section | Signoff
checkpoint-status |  |  | checkpoint | Required people sent signoff request
holdpoint |  |  | signoff | Signoff
checklist-flat |  |  | checklist | 0 Pricing Pre-Start Meeting |  |  |  |  | Yes | 0 Pricing Pre-Start Meeting | 93fffc90-b896-49c4-8d98-3f49bc5f747f
checkpoint-no-status |  |  | checkpoint | Pricing Pre-Start Meeting
text | 98215756-676c-5c7b-976e-02fcc4f77520 |  | textbox | Project Details:
text | 1f3bcaae-99e9-517c-b5d6-7c2048ea8705 |  | textbox | Client:
text | bc79498f-6f61-5651-9c69-25261ae5fe42 |  | textbox | Address:
text | e519a35f-d84e-5e97-b005-b900be47677b |  | textbox | Other:
text | 3c5f87d6-49e0-5a5c-9626-727508ec2400 |  | textbox | Attendance:
text | 91d9c0bc-02d3-5845-8d62-d4ae0dd9e0ed |  | textbox | Tender Manager:
text | 41680006-7206-57bb-a076-7e44d8c881bb |  | textbox | Tender Status:
text | 76386736-8056-5cbe-84a1-362c28dc78a3 |  | textbox | Tender submission due date:
text | 8b43314b-6559-58a4-ad6b-38e185349cd9 |  | textbox | Job Details/Scope:
checkpoint-status |  |  | checkpoint | Has a Client Programme be provided?
checkpoint-status |  |  | checkpoint | Suppliers & Subcontractors Identified:
checkpoint-status |  |  | checkpoint | Have the documents been uploaded to Sharepoint?
checkpoint-status |  |  | checkpoint | A tasks list & a Project Programme (Project Manager):
checkpoint-status |  |  | checkpoint | Tender Clarifications/RFI's Required:
checkpoint-status |  |  | checkpoint | Risks or Opportunities:
checkpoint-status |  |  | checkpoint | Pre Submission meeting date scheduled:
checkpoint-status |  |  | checkpoint | Is a meeting with the client required? (At this stage)
checklist-flat |  |  | checklist | Foreman Question Sheet |  |  |  |  | Yes | Foreman Question Sheet | 9483b957-f003-4fe3-a35d-158f9c202b2a
checkpoint-status |  |  | checkpoint | Do you understand profile and survey setout or do you require more information?
checkpoint-no-status |  |  | checkpoint | Are your survey marks off grid lines or building lines?
button | 558bb1db-0b2a-54a8-b5ed-e98ecec8a4d5 |  | button |  | Grid lines, Building Lines
checkpoint-no-status |  |  | checkpoint | Item Details
boolean | 71370885-f2f3-5da8-896f-1b5c7c041858 |  | tickbox | Do you understand all heights?
boolean | e5c86ed2-de95-574c-9599-9e817117275a |  | tickbox | Do you have all dimensions?
text | ebeef4b0-2619-58de-aa9d-7484ef34382b |  | textbox | What formwork are you using for each component of the job?
checkpoint-status |  |  | checkpoint | Has the formwork and bracing been organised to be onsite before you require it?
checkpoint-no-status |  |  | checkpoint | Material Details
text | f90d83f5-6f0f-5e8b-bdde-9d7f66c1d5b3 |  | textbox | Where have your materials been ordered from?
date | 991e8fc9-9c1a-532c-aee7-5cd85b2485ad |  | date | What date do you expect your materials to be delivered?
checkpoint-no-status |  |  | checkpoint | Have all materials been ordered to site or do you need to pickup materials? If so, notify your van.
button | dc171e04-e59c-5ac3-b336-c40c63af40c8 |  | button |  | To Site, Pickup
checkpoint-no-status |  |  | checkpoint | Key Dates
text | 899b3681-f7dd-5c53-ac64-9ff2479b42b7 |  | textbox | Identify key dates to make
text | 88ca5ba1-4e8b-561a-9c89-f5230f1e45cf |  | textbox | Identify inspection dates
checkpoint-no-status |  |  | checkpoint | DPM & Waterproofing
text | b0a0cb68-27ed-5955-ba1b-af4e9c9388ba |  | textbox | What DPM and tape required?
boolean | ffa37c92-1e72-5f05-9418-f6d5df178d5c |  | tickbox | Has this been ordered?
text | a451ff23-60d7-56ef-9445-298fd9976704 |  | textbox | Waterproofing - Identify waterproofing location
boolean | a852dd23-3691-5495-9d33-67e2453908ea |  | tickbox | Make sure digout accounts for waterproofers
boolean | 4a4f4c27-838a-597e-9703-baa205bacb5b |  | tickbox | Go over van load out list with your van
boolean | c670b854-6f6b-5960-95a4-7c753047bb46 |  | tickbox | Has your van got everything needed for the job
text | 417b223d-bb18-50cd-a6f7-1b948c0000b3 |  | textbox | Rebates
text | ff14dd08-ac23-5d7a-8aad-a5d1f2c68327 |  | textbox | Profile timber and walls
checklist-sectioned |  |  | checklist | Site Inspection - |  |  |  |  | Yes | Site Inspection - | a003a78d-80ab-429b-b155-7c7f4b017dc0
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete (pass once relevant details are recorded below)
text | f8d2b48b-86c5-57e6-84e1-adb627871003 |  | textbox | Site/Location :
text | 3171f2bf-a5c5-512a-ada9-33f91e00f630 |  | textbox | Name of Inspector :
checkpoint-group |  |  | section | Site Control
checkpoint-status |  |  | checkpoint | Hazard Board and signage up-to-date
select | 7e7158a1-7797-5267-aa1b-ba063674d835 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Environmental plan - issues
select | b8371a80-5257-57e1-9f59-4b54243908ad |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
text | 07ad93e3-e1a1-5ae2-b3b0-3abca1266d75 |  | textbox | Toolbox talk last date:
checkpoint-status |  |  | checkpoint | Safety inductions for all on-site
select | 9550c0f7-10e5-576c-8808-d602b76fd348 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Safety notice board current
select | 317eed64-54ef-5a78-afd2-04c42dfca248 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Site Facilities
checkpoint-status |  |  | checkpoint | Offices clean, adequate & good lighting
select | 764efb0c-4c14-519c-aea6-567bfcb78179 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Smoko sheds - clean, portable water
select | 327159b2-aa84-5514-8ad5-8022c46d91d5 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Toilets - clean, washing water
select | 368c8378-0650-5d07-a51d-33892a7e6480 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Tool /equipment sheds adequate
select | 96b8e50b-dfd7-537b-b600-e7647fcfa46c |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | General Site Tidiness and Access ways
checkpoint-status |  |  | checkpoint | Clear, safe access to work areas
select | f82e0d1f-9820-5e3f-b97c-d5b27faedc21 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Stairways and accessways clear
select | 62c5810c-6138-53db-ae63-e9bb4dd6793f |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Hoardings /fence and gates secure
select | 5479e917-1a21-587b-9840-90274eb8ac89 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Loose materials secure from wind
select | 33a4eade-68f7-518d-b5b8-c161f2638fd9 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | House Keeping
select | 5f0df94c-adc7-5c5e-9d2c-e1d7df61726c |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Personal Safety Equipment
checkpoint-status |  |  | checkpoint | Signage displayed and legible
select | 82732aed-cf51-5d69-a60f-417ceffda52a |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Hardhats and boots being worn
select | 7c4f5797-bebb-5b51-9383-f5dd49897f60 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Glasses /ear muffs /vests /masks used
select | ebac633f-d4f7-570d-a7fe-239cbecea027 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Task specific PPE used
select | 85b7505d-ee9d-5a68-b032-af06462e2467 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | First Aid/Fire Prevention
checkpoint-status |  |  | checkpoint | First Aid Box Available
select | 123b3a1f-c8a0-5c0c-a484-a9b7ad31a8a1 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Accident register
select | b30d37c8-8632-5ca2-849e-dbeacb3faefe |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Fire Extinguishers
boolean | 71c932a3-7e39-5e13-8663-b9a97b34c342 |  | tickbox | Available
boolean | afb4ccfb-1c45-5ffc-a9cd-c76e7a090a43 |  | tickbox | Current (12mth)
boolean | 44209b2f-747b-5870-95a9-940ff3b6b15e |  | tickbox | Sufficient number
select | 64a428d2-5d1f-50e7-87f8-ebf571a86038 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Evacuation
boolean | 827d592e-e0c2-5b06-a9cc-d526a098bd11 |  | tickbox | Procedure current
boolean | 1416f887-f036-599d-a67c-85087d87ea4e |  | tickbox | All emergencies incl
select | ccfc6355-9905-5ee7-a7a9-01c05226b60d |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Cranes/hoist/lifting equipment
checkpoint-status |  |  | checkpoint | Proper lift assessment plan done
select | 295fe2cd-389d-5252-a079-e085ad068ba4 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Crane certification current
select | d11afec8-8a2d-5563-af2e-e04a82f1c4e5 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Slings/chains certified
select | d94c9520-ba1b-5c8c-b338-be084da0e3a0 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Operator procedures in place
select | bfa5bba2-b58c-5d75-af9f-9ca4c80c8129 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Inspections being done
select | bdc8efcf-15b2-55e1-bc8b-f43c6fbca169 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Man cage available
select | cfb7f45c-e4e2-50a5-9210-60a1041e1001 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Emergency plan in place
select | 5c9ece42-49f5-5dd4-899c-b64589535087 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Tools and equipment
checkpoint-status |  |  | checkpoint | In good condition
select | 24907ef0-e34c-517b-8e32-2798dfc01cbb |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Appropriate guards fitted
select | f9777af6-c159-52e6-9425-03ac39d35d90 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Trained user
select | 167e7462-b189-5e08-a8b3-1bf5d076f597 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Excavations
checkpoint-status |  |  | checkpoint | Correctly Shored/Benched/Battered
select | cb7dbc41-46ee-5763-be3e-c0e0e89a17ab |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Access/Egress Installed
select | 8cc4c32d-ceb8-5344-aebc-882e5a6348a8 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Hot Works
checkpoint-status |  |  | checkpoint | Hot work permits being issued
select | fb777bb5-163c-5d21-88f3-5da947036bfc |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Fire extinguishers on hand
select | 82b15a70-91d3-54ba-a381-99993d779c8b |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Operators using PPE
select | d2b97a2f-9410-52cf-98d5-712e5fc16a5c |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Electrical Equipment
checkpoint-status |  |  | checkpoint | Main board lockable /weatherproof
select | a9be2802-653a-5a35-83af-94c5910815cb |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Current tagged and damage-free leads
select | e620a49e-324d-5e98-836d-f03dcd19dbc3 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Current tagged plant
select | a4827712-98f2-53ae-8887-2d22e03ed9d4 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Current tagged lifeguards
select | a63bdcfd-23b3-5f00-8f25-93ab8177f9fa |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Leads safely placed
select | 8b17ea2a-1b04-52be-a4f2-a84700d1aabd |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Equipment in good condition
select | 3ebe7561-9ee1-55bd-8888-ec04fb70f38f |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Appropriate guards on equipment
select | 6081155e-7e5c-5dd1-9813-cd1d71a1991a |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Adequate temporary lighting
select | 04ecefbc-2803-5b54-b618-d2eec141de5c |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Chemicals
checkpoint-status |  |  | checkpoint | Correctly stored
select | 9c411e12-d4de-53d9-a6b7-55e0f6cf4082 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Safety Data Sheet (SDS) available
select | 12cd6f2a-1589-5a3b-9ecf-1e24f6991940 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Operators using PPE
select | 51bf8b7d-4477-5d13-8327-3f3441273f80 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | P.A.T Tools
checkpoint-status |  |  | checkpoint | P.A.T tool WoF current and secure
select | a6e03e8b-5282-5eb5-bae2-4ef0e7652ab2 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Staff trained in tool use (SWPS)
select | 3f283dde-e40e-58f9-8e0b-838e54f4a65b |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | PAT signage on site
select | d8e9a302-614d-509a-83ea-0ac07e2cfb1b |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Ladders
checkpoint-status |  |  | checkpoint | Good condition
select | 2642d37e-d4f9-52d3-a674-1be2e6389399 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Access Ladders secured top and bottom
select | cf8198c7-177c-5b32-9874-57141aa3afab |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Stays and rungs undamaged
select | 98e08d28-615f-57c4-9f0b-43b391268d85 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Working within weight limits
select | db740a40-7657-50ec-9172-cda2fe4b5bb0 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Fall Hazards
checkpoint-status |  |  | checkpoint | Fall Hazards
select | 57cb7c2a-1787-5eda-a01d-a58dda6226d2 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Floor openings
select | 3f88abdf-a3a6-5823-ba2f-5cd3b1a3b3d1 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Lift shafts
select | 930b11fa-5e02-5ef3-b2d0-06da6f9a769c |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Stairs
select | 431c6ae5-80a6-5e4d-8344-1b3e8975a3c1 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | EWP
checkpoint-status |  |  | checkpoint | Clean, Deck Clear
select | b68d0c6d-b8d2-5a6b-af65-6e1824a6e9b7 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Log complete
select | ec191243-3eee-5397-883c-0ef92404b1db |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-status |  |  | checkpoint | Exclusion in place
select | f42b08d5-bacd-5947-8bbe-e14f2412af76 |  | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
checkpoint-group |  |  | section | Signoff
checkpoint-status |  |  | checkpoint | Required people sent signoff request
holdpoint |  |  | signoff | Signoff
checklist-flat |  |  | checklist | Site Inspection Pre Job Starting - Site Manager and Foreman |  |  |  |  | Yes | Site Inspection Pre Job Starting - Site Manager and Foreman | ab6e7c6d-e7a8-4b2d-b603-af8e2e4f3022
checkpoint-no-status |  |  | checkpoint | Site Inspection Pre Job Starting - Site Manager and Foreman
text | e3aac975-cfa6-5499-bc5e-5837ad382d60 |  | textbox | Project Details:
text | ae0472df-bf75-5a90-a4ce-80da5281a471 |  | textbox | Client:
text | 091248a0-d8df-5267-8158-d0bc3ba0529a |  | textbox | Address:
text | 5cc98935-2241-5706-8892-cc69a3c2301e |  | textbox | Other:
text | e7119dfb-1114-5f44-91bc-1a05828414b3 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Traffic management required for our job scope?
checkpoint-status |  |  | checkpoint | If so, has the client been informed and agreed it will be in place for our start date?
checkpoint-status |  |  | checkpoint | Have materials been dropped off?
checkpoint-status |  |  | checkpoint | If not, contact suppliers, let them know where you want materials delivered and what is delivery time and date:
checkpoint-status |  |  | checkpoint | Identify workstations
checkpoint-status |  |  | checkpoint | Pod cutting station outside of slab
checkpoint-status |  |  | checkpoint | Steel bending and cutting station
checkpoint-status |  |  | checkpoint | Timber cutting station
checkpoint-status |  |  | checkpoint | Skip bin onsite?
checkpoint-status |  |  | checkpoint | Portaloo onsite?
checkpoint-status |  |  | checkpoint | Power to site?
checkpoint-status |  |  | checkpoint | Water to site?
checkpoint-status |  |  | checkpoint | Site box and work drawings?
checkpoint-status |  |  | checkpoint | If none of the above are onsite and are needed for us, has client been informed?
checkpoint-status |  |  | checkpoint | Boundary and survey set outs/pegs been done?
checkpoint-status |  |  | checkpoint | Cut heights and locations as OTWC requirements?
checkpoint-status |  |  | checkpoint | If not, has client been informed and start date been changed for the problem to be sorted?
checkpoint-status |  |  | checkpoint | OTWC vehicle parking confirmed with client & the location has been identified?
checkpoint-status |  |  | checkpoint | Any other issues that need to be brought up to client?
checkpoint-status |  |  | checkpoint | If so, has client been informed?
checklist-sectioned |  |  | checklist | Toolbox Meeting - |  |  |  |  | Yes | H&S - Toolbox Meeting Minutes | abb78030-4175-42c9-ad84-0d0b724eb7e6
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete (pass once all relevant details are inputted below)
text | 046a2411-6b41-57e4-bc85-12257b24f1f5 |  | textbox | Office location:
label | ee0f1286-2c9b-5b21-a438-3016ba54875a |  | note | Who is running this meeting
text | 5f2f8321-9b65-58c7-b26e-b3cfbc723969 |  | textbox | Name:
text | d7a1244c-5256-5f84-ad53-62a51ac6d913 |  | textbox | Company:
text | 643e783d-762b-5f86-951b-bd154508e36a |  | textbox | Agenda items:
text | dfcc2ac6-2e1c-535b-8bfb-5199f8564401 |  | textbox | Theme of the week (topic for focus):
checkpoint-group |  |  | section | Health and safety issues
checkpoint-status |  |  | checkpoint | Relevant Issues recorded with appropriate actions and date
text | 83a497b9-10a6-5f52-b2c0-dabd3b410cd9 |  | textbox | Issue raised from site safety inspection:
text | 1664ecd9-fb1b-537b-bd1f-b2504b4c34d4 |  | textbox | Actions:
text | 744b79ae-43d3-5665-ad42-000fd2069a3d |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | Issues outstanding from previous briefings recorded with appropriate actions and date
text | a610561b-d9c4-5a3a-aab1-8b6aefa4b6b0 |  | textbox | Issues outstanding from previous briefings:
text | 6d785e60-7115-5ca8-a3c2-5405ccb268e2 |  | textbox | Actions:
text | c2e5e9bc-436b-57fa-911d-b240481e4a4c |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 3. Employee-raised issues recorded with appropriate actions and date
text | ef6bd9cf-7551-5f17-994c-acf8fb3de4f9 |  | textbox | Employee-raised issues:
text | bd11a521-166e-5f8e-911f-abb0acc1d518 |  | textbox | Actions:
text | 8325226d-1503-590d-8371-54d4b3629a72 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 4. Positive safe-action observations recorded with appropriate actions and date
text | 1273109c-7098-54b5-91fe-4893de9a9c75 |  | textbox | Positive safe-action observations:
text | c9b12c6a-965c-52a7-8ffd-0fd36d6babc4 |  | textbox | Actions:
text | ce627d04-4684-54ba-a01b-b6d04c351bb1 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 5. Incidents or injuries recorded with appropriate actions and date
text | bbee1804-a0d4-57fa-92ec-0241693f2314 |  | textbox | Incidents or injuries:
text | f2c02fd1-51c7-5912-ba19-35ecb9b83e81 |  | textbox | Actions:
text | 4160f944-1ff1-5069-8e5d-65588732fce0 |  | textbox | By who and when:
checkpoint-group |  |  | section | Job plans reviewed
checkpoint-status |  |  | checkpoint | Job/Task plan(s) reviewed & Action(s) recorded below
text | 6cd60c99-3c39-5489-a8f3-94ea51e25655 |  | textbox | 1
text | 21252bec-4a2a-5999-b52b-1666ae489c63 |  | textbox | 2
text | dcaeb69a-e77b-57a1-a8c9-48370d8369da |  | textbox | 3
text | e907eddf-aab6-5552-9c95-30720c2db6e7 |  | textbox | 4
text | 5cd95df3-d036-518a-ba79-eb8c9323bfa2 |  | textbox | 5
text | 923c9575-cf4f-5a28-8873-85019dd4112b |  | textbox | 6
checkpoint-group |  |  | section | Operational issues
checkpoint-status |  |  | checkpoint | Operational Item(s) & Action(s) recorded below
text | f29ed4a9-a29d-5334-9db1-0da6ffc16024 |  | textbox | 1
text | e4b22bc3-6f5f-536a-9133-19ec8e40963b |  | textbox | 2
text | 5fe9a3b6-3a92-572a-ad44-9f3f212337ab |  | textbox | 3
text | b5f29b7e-e9ad-543a-93df-19564b107ec6 |  | textbox | 4
text | eae0f8c1-6b53-53d2-afb7-225eae25eed4 |  | textbox | 5
text | 3d12b04f-8a61-5810-abed-44c56025210d |  | textbox | 6
checkpoint-group |  |  | section | Other business
checkpoint-status |  |  | checkpoint | Other Business Item(s) & Action(s) recorded below
text | 307ce52d-0194-59e1-868f-a0b82847db6b |  | textbox | 1
text | ff1064dd-74f3-59f0-bacb-82d4eca0896e |  | textbox | 2
text | 782d767c-131c-5d81-9468-474b219fcc46 |  | textbox | 3
text | 5a51cdcb-00bc-5b27-a148-22c8eb4b8e6c |  | textbox | 4
checkpoint-group |  |  | section | Attendees
checkpoint-status |  |  | checkpoint | Add name and Photo of attendees (pass once all attendees are recorded)
holdpoint |  |  | signoff | Send signoff request to all attendees
checkpoint-group |  |  | section | Review by management
checkpoint-status |  |  | checkpoint | Send to management to review?
holdpoint |  |  | signoff | Reviewed and signed off by management
checklist-flat |  |  | checklist | Date: |  |  |  |  | Yes | H&S - Daily Prestart | b3a32242-abc3-41f9-91e1-c3e69814f1f2
checkpoint-status |  |  | checkpoint | Person/s in charge of site operations
checkpoint-status |  |  | checkpoint | Weather conditions
select | db7a69c2-537e-5341-8877-c525ee016314 |  | dropdown | Conditions | Sunny, Overcast, Cloudy, Rainy
checkpoint-status |  |  | checkpoint | Wind Conditions
select | 94c30a63-0e13-5001-ade0-ccaf5a4d7d75 |  | dropdown | Conditions | Strong, Medium, Low, None
checkpoint-status |  |  | checkpoint | Meeting minutes
checkpoint-status |  |  | checkpoint | Safety minutes
checkpoint-status |  |  | checkpoint | Main contractor supplied minutes
checkpoint-status |  |  | checkpoint | Signatures of all attendees
holdpoint |  |  | signoff | Send signoff to all attendees
checklist-flat |  |  | checklist | 8 Site inspection Pre-job start Site Manager and Foreman (SM / F) |  |  |  |  | Yes | 8 Site inspection Pre-job start Site Manager and Foreman (SM / F) | bbe866a4-aae1-4ec1-a040-6bec25ca0725
checkpoint-no-status |  |  | checkpoint | Site Inspection Pre Job Starting - Site Manager and Foreman
text | dff58566-4c3d-50e7-bddf-61610550e488 |  | textbox | Project Details:
text | 58ef7ba0-432b-5019-bd4c-cc6e86cba80e |  | textbox | Client:
text | 58184fba-db45-59f7-b9d3-e23e675bd6c3 |  | textbox | Address:
text | 17247fcd-42b6-5dc8-b537-4fecc812f38c |  | textbox | Other:
text | b0b2b6e5-82dd-53cb-91c1-8f1d857a0a91 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Traffic management required for our job scope?
checkpoint-status |  |  | checkpoint | If so, has the client been informed and agreed it will be in place for our start date?
checkpoint-status |  |  | checkpoint | Have materials been dropped off?
checkpoint-status |  |  | checkpoint | If not, contact suppliers, let them know where you want materials delivered and what is delivery time and date:
checkpoint-status |  |  | checkpoint | Identify workstations
checkpoint-status |  |  | checkpoint | Pod cutting station outside of slab
checkpoint-status |  |  | checkpoint | Steel bending and cutting station
checkpoint-status |  |  | checkpoint | Timber cutting station
checkpoint-status |  |  | checkpoint | Skip bin onsite?
checkpoint-status |  |  | checkpoint | Portaloo onsite?
checkpoint-status |  |  | checkpoint | Power to site?
checkpoint-status |  |  | checkpoint | Water to site?
checkpoint-status |  |  | checkpoint | Site box and work drawings?
checkpoint-status |  |  | checkpoint | If none of the above are onsite and are needed for us, has client been informed?
checkpoint-status |  |  | checkpoint | Boundary and survey set outs/pegs been done?
checkpoint-status |  |  | checkpoint | Cut heights and locations as OTWC requirements?
checkpoint-status |  |  | checkpoint | If not, has client been informed and start date been changed for the problem to be sorted?
checkpoint-status |  |  | checkpoint | OTWC vehicle parking confirmed with client & the location has been identified?
checkpoint-status |  |  | checkpoint | Any other issues that need to be brought up to client?
checkpoint-status |  |  | checkpoint | If so, has client been informed?
checklist-flat |  |  | checklist | Variation Contract - |  |  |  |  | Yes | Variation Contract | c91251a9-621c-498e-a59c-a32e7cdac4bc
checkpoint-status |  |  | checkpoint | Job Details
text | b33aaca6-1a12-5cf9-b92b-f91c6c67f2d7 |  | textbox | Details of Work (Inc. Location):
text | c70e5e8a-fd09-5cda-ad63-a7cbe5557e5d |  | textbox | Client:
text | 5f39eb5e-ed74-533d-a2a0-6aee53086163 |  | textbox | Reason for Variation:
text | 80356454-51a3-5cf3-a755-5f763ea88644 |  | textbox | Project:
text | e8476883-9117-51f0-a8c5-0846f1654a64 |  | textbox | Job No:
text | e597aa2d-12ed-5661-bf48-acc08100304a |  | textbox | Hours:
text | b0541525-0163-5f68-84e1-892c652d2210 |  | textbox | Site Instruction No:
text | 0d32fe65-cdc8-54ea-8dbb-9a2573303d79 |  | textbox | Materials Equipment:
text | ad3706b3-7c6e-598b-93db-53296d6d30c7 |  | textbox | Agreed Value:
checkpoint-status |  |  | checkpoint | Work Details:
text | 6d3f6e49-d128-5f97-a6ae-79b95e8135d2 |  | textbox | Details of Work (Inc. Location):
text | 7288d9a2-ddec-5383-a3ab-732dc665044c |  | textbox | Name:
text | 1b94430d-0adc-51c5-bd08-de6946dc5023 |  | textbox | Reason for Variation:
text | d485d5e3-2702-5fa8-954a-0b7dde5d4f3e |  | textbox | Hours:
text | ccb2e85b-00bb-55bf-9248-6599abb00d1d |  | textbox | Materials Equipment:
text | e61892c7-587f-5547-ab12-67ecc9e49221 |  | textbox | Agreed Value:
checkpoint-status |  |  | checkpoint | Foreman Sign Off
text | 095f4a05-ad95-5879-9668-8b4b683cc736 |  | textbox | Name:
text | aab6f7e2-0a9d-56a6-83cc-6cccd39c34e0 |  | textbox | Name:
checkpoint-status |  |  | checkpoint | Project Manager Sign Off
text | 59448d74-f8d8-5831-89c4-838978b7bfc1 |  | textbox | Name:
text | 5e39fd1c-28f4-5094-9692-0fab50602b34 |  | textbox | Name:
checkpoint-status |  |  | checkpoint | Signature of Authorising Officer
text | 91b18675-1c0a-52cf-8ced-a92835d46da9 |  | textbox | Name:
checklist-flat |  |  | checklist | 7 Foreman Job Checklist (F) |  |  |  |  | Yes | 7 Foreman Job Checklist (F) | da20985e-a389-4167-b810-9d3a391a16ea
checkpoint-status |  |  | checkpoint | Job file formed
checkpoint-status |  |  | checkpoint | Plans reviewed and required details printed and laminated?
label | 7f26f76b-3b96-5394-a322-358db254c715 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Survey markout plan printed and laminated?
label | ec349978-f832-5e00-aa34-8d6863600b1d |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All heights printed and kaminated?
label | 7ecc793b-6a1a-5cd6-b363-d0a724ce2f50 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Job Master Schedule printed and laminated? (if schedule changes, throw away old and add new)
label | ba3a0988-7c35-5933-bb0b-ffebea604895 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Amounts
label | 12987662-21ac-50ca-a70e-83161ace3697 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Dockets
label | 245e4b91-df31-55ac-ad12-5e69c31fd523 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Toolboxes
label | d4bc0f10-21da-5f58-8807-587850058da0 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | SSSP
label | e18a739a-6953-5145-9e11-1f61093ba06b |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Waterproofing markout
label | 7ca253b7-5c07-5c26-aa0f-c2605a44b2e5 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | PM - Foreman handover printed
label | d6745fe6-d6a6-5f6a-af2e-8e3bc42f8513 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All Qas printed
label | 1b896b83-8011-52a6-9fe4-81fa82b18015 |  | note | Add to Job File
checklist-flat |  |  | checklist | 4 Site Manager and Foreman Question Sheet (SM / F) |  |  |  |  | Yes | 4 Site Manager and Foreman Question Sheet (SM / F) | da4fe9b8-0b55-4afd-a8df-e5f05abadaa6
checkpoint-status |  |  | checkpoint | Do you understand profile and survey setout or do you require more information?
checkpoint-status |  |  | checkpoint | Are your survey marks off grid lines or building lines?
button | 9159a8ac-1a17-54c7-acc1-3946d7ec5fa4 |  | button |  | Grid lines, Building Lines
checkpoint-status |  |  | checkpoint | Item Details
boolean | bd7d6744-e8d5-5825-a9fb-5a1f2724084a |  | tickbox | Do you understand all heights?
boolean | dd1e6a12-2cff-5ac8-967b-9c3cfb3af147 |  | tickbox | Do you have all dimensions?
text | 69deca45-af58-5807-b4bc-e31738678250 |  | textbox | What formwork are you using for each component of the job?
checkpoint-status |  |  | checkpoint | Has the formwork and bracing been organised to be onsite before you require it?
checkpoint-status |  |  | checkpoint | Material Details
text | b5f8527b-8c92-57d0-a0dd-9a7e3fdc68ec |  | textbox | Where have your materials been ordered from?
date | ef49e44d-f2a9-505b-8963-c75b030a9b6d |  | date | What date do you expect your materials to be delivered?
checkpoint-status |  |  | checkpoint | Have all materials been ordered to site or do you need to pickup materials? If so, notify your van.
button | 08ce5b7e-e400-5e26-9b94-7574ee6ae025 |  | button |  | To Site, Pickup
checkpoint-status |  |  | checkpoint | Key Dates
text | 0e0ac625-66d4-535b-a181-f9b99730d2d4 |  | textbox | Identify key dates to make
text | 67a16086-90e3-5f97-867f-575feb22a795 |  | textbox | Identify inspection dates
checkpoint-status |  |  | checkpoint | DPM & Waterproofing
text | c92fe533-f66b-53e0-b1d7-d517ddde7ae2 |  | textbox | What DPM and tape required?
boolean | 8f9a195e-49e8-56e4-897d-b7a4a884be42 |  | tickbox | Has this been ordered?
text | 0db2e871-68fb-5c3f-b854-458d740cc094 |  | textbox | Waterproofing - Identify waterproofing location
boolean | 93562c87-5888-5f54-a2c6-6ba0a55f6935 |  | tickbox | Make sure digout accounts for waterproofers
boolean | 2fd9bde4-5054-57e4-9fda-00acf8a53a4d |  | tickbox | Go over van load out list with your van
boolean | e08da1c1-2189-54ab-a419-914f5b4bd0d2 |  | tickbox | Has your van got everything needed for the job
text | 1155eebe-8233-5001-b6bb-2dcf4dddff47 |  | textbox | Rebates
text | 12d490c9-7d15-5e62-91b0-687a6c327f95 |  | textbox | Profile timber and walls
checklist-sectioned |  |  | checklist | Foreman Job Checklist (Complicated Residential) |  |  |  |  | Yes | Foreman Job Checklist (Complicated Residential) | dae33d47-35cb-4b1a-a561-4ae41ddb1321
checkpoint-group |  |  | section | Footing Prep (Placemakers):
checkpoint-status |  |  | checkpoint | Polythene/Poly tape
checkpoint-status |  |  | checkpoint | Footing formwork
checkpoint-status |  |  | checkpoint | DPM/DPM Tape (Footings/Slabs)
checkpoint-status |  |  | checkpoint | Profile timber
checkpoint-status |  |  | checkpoint | Starter timbers
checkpoint-status |  |  | checkpoint | Denso tape
checkpoint-status |  |  | checkpoint | Drainage (DPM/Filter cloth/Weed mat pegs/Novacoil/Sock)
checkpoint-status |  |  | checkpoint | Slab polythene and tape to be ordered with footing order
checkpoint-status |  |  | checkpoint | Slab rebate timber
checkpoint-group |  |  | section | Footing and blockwork (Fletchers):
checkpoint-status |  |  | checkpoint | Footing and block steel
checkpoint-status |  |  | checkpoint | Tie wire
checkpoint-status |  |  | checkpoint | Chairs
checkpoint-status |  |  | checkpoint | Control joint bars for blocks
checkpoint-group |  |  | section | Slab Steel (Fletchers):
checkpoint-status |  |  | checkpoint | Footing and block steel
checkpoint-status |  |  | checkpoint | Tie wire
checkpoint-status |  |  | checkpoint | Chairs
checkpoint-status |  |  | checkpoint | Control joint bars for blocks
checkpoint-group |  |  | section | Expol order:
checkpoint-status |  |  | checkpoint | Double spacer
checklist-flat |  |  | checklist | Foreman's Job Planning |  |  |  |  | Yes | Foreman's Job Planning | ddd7a1aa-3ffc-4239-8ba2-9d1db2df0a0b
checkpoint-no-status |  |  | checkpoint | Foreman's Job Planning
text | dd79810e-7537-5a78-bd4b-bac8d6822992 |  | textbox | Project Details:
text | cfc6641a-e658-592f-9dcf-4177c8b55534 |  | textbox | Client:
text | 5d17ed81-f44a-5bed-860f-c6de39cff22a |  | textbox | Address:
text | 89f6cd5e-2b57-5b2e-9df5-9a620344182e |  | textbox | Other:
text | dee635b6-8c91-56af-a0b6-9db3624562f7 |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review Master Schedule
checkpoint-status |  |  | checkpoint | Plan Days / Weeks according to Master schedule; Labour size and tasks to complete
checkpoint-status |  |  | checkpoint | Bring your team in for and go over job with them, explain the job file
checkpoint-status |  |  | checkpoint | Make sure Van is loaded with everything it will need for the job
checkpoint-status |  |  | checkpoint | Team book and load trailer as required, day prior to job starting
checkpoint-status |  |  | checkpoint | Remember Monday morning Toolboxes and Friday debriefs
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details | f084c253-1c31-4816-a11b-06fcc40545fc
checkpoint-status |  |  | checkpoint | Project details entered below
text | 0d25126c-9f1f-57ee-ae25-6585d8c080ef |  | textbox | Job File Number
text | 730d7839-c4a5-5c8b-a45b-e2cc7078a998 |  | textbox | Project Name
text | 57568d34-e8d4-5af4-9b45-40ebb5de4a7f |  | textbox | Site Address
text | 8d9493d3-eb38-5003-aa14-19771c389e82 |  | textbox | Main Contractor
text | 105278ea-79f5-5c99-a136-0db443e3f873 |  | textbox | Main Contractor POC
text | 797784f5-bf1b-54b2-a7e7-da6fc1393edb |  | textbox | Structural Engineer
text | 5faf1886-d756-5712-ae7a-2a42c96c500f |  | textbox | Architect
checklist-flat |  |  | checklist | Job Planning |  |  |  |  | Yes | Job Planning | f266e3dc-6b80-418b-bbe8-f8d207db2137
checkpoint-no-status |  |  | checkpoint | Project Details
text | d7d0e418-1c52-5eea-81e4-6b94dfff2038 |  | textbox | Project Details:
text | fa93299c-e3d9-5e30-b650-98777471c9fb |  | textbox | Client:
text | 86ba68c0-632c-506f-9ff6-9023c356926e |  | textbox | Address:
text | 727db94e-733c-5da5-b0d7-dbe2b0877746 |  | textbox | Other:
text | 6047fc5d-d742-5e48-99c3-e58cbfab2109 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Job built from start to finish - Compare with Program
checkpoint-status |  |  | checkpoint | Design issues noted and send to client
checkpoint-status |  |  | checkpoint | Site Specific OTWC requirements - Send to client
checkpoint-status |  |  | checkpoint | Master Program built and send to client
label | 5e29e31e-6cf1-576c-a128-da2e50ab9d24 |  | note | To include materials drop offs
label | f8f3f7f9-c321-5466-b926-cb77cd1b1d32 |  | note | To include formwork required
label | 1391f6a5-ab87-5abf-ab96-6c4be5073f88 |  | note | To include concrete bookings
label | 5e9b6c9a-c846-54b0-aebf-35e5fdfd1db6 |  | note | To include inspections
checkpoint-status |  |  | checkpoint | Concrete bookings insert into Concrete Schedule
checkpoint-status |  |  | checkpoint | Material bookings into Material Schedule
checkpoint-status |  |  | checkpoint | Site Manager to get a copy of the Job Schedule
checkpoint-status |  |  | checkpoint | Schedule to have Toolbox Meeting
checklist-flat |  |  | checklist | PM - Foreman Job |  |  |  |  | Yes | PM - Foreman Job | f28a3dac-a133-4e5b-aa8f-20fb937ec26d
checkpoint-status |  |  | checkpoint | Have you reviewed Plans/Job Schedule?
checkpoint-status |  |  | checkpoint | Do you understand survey markout grids? Building lines?
checkpoint-status |  |  | checkpoint | Heights:
text | 9a556060-1b1f-51ac-bb3f-ead98a28095a |  | textbox | Footing Depth
text | 2509a464-1897-5e06-9d09-202842ee4f0c |  | textbox | Bottom of footing measurement
text | 27f7eff0-b5f1-5765-9b2a-37efde4fd370 |  | textbox | Top of footing measurement
text | f5b8da2f-4e4b-5683-9a79-8024484b2857 |  | textbox | Finish Floor Line (FFL)
text | 97c6d13a-5b21-5070-a5e4-eada75f23e52 |  | textbox | Block wall heights
text | 00dd7167-8402-5e56-a27c-78e61d7911a7 |  | textbox | Insitu wall heights
checkpoint-status |  |  | checkpoint | Have you got all dimensions?
checkpoint-status |  |  | checkpoint | Show Foreman complicated components of Job and solutions
checkpoint-status |  |  | checkpoint | DPM require/tape
checkpoint-status |  |  | checkpoint | Waterproofing locations, explain importance of larger digout in these locations:
label | e65d3339-6002-52e8-b6c3-6118e18880e3 |  | note | - Go over Engineer Details
label | 6ba6438d-ff72-5314-8154-31cf6eec4a11 |  | note | - Go over Building Methodology
label | c7d0c29b-e457-5960-a67e-2a3d720f2370 |  | note | - Go over Key dates
label | dfd962bd-2807-5516-a227-75a2aa96db8a |  | note | - Go over size of team
label | 41853547-7eea-57ae-afec-af98f7b4a844 |  | note | - Go over rebates
label | b004acba-f7c8-5870-9e26-0e438f1e47bb |  | note | - Go over penetrations
checkpoint-status |  |  | checkpoint | Materials to site
checkpoint-status |  |  | checkpoint | What has been allowed/ and what hasn't
checkpoint-status |  |  | checkpoint | What needs to be taken to site
checkpoint-status |  |  | checkpoint | Any other points/discussion:
checklist-sectioned |  |  | checklist | Vehicle Tool Inventory |  |  |  |  | Yes | Vehicle Tool Inventory | ff5aa8f7-a452-4dae-9a9a-88012d06a7e8
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | d7fbaa73-11fa-50bf-9767-799aac26643c |  | textbox | Equipment:
text | ffdb650e-009e-547a-9ced-8c9b4d300ca7 |  | textbox | Date:
text | db6d78ed-72b2-5da4-88d0-f4cd281de34a |  | textbox | Conducted By:
text | 97dc1547-1d05-5ff8-a388-c805cda16cb8 |  | textbox | Overall Comment:
checkpoint-group |  |  | section | Power Tools
checkpoint-no-status |  |  | checkpoint | Power Tools
text | 63d15d5e-a17b-5634-abd3-7d4c704b5c95 |  | textbox | Power Tool Name:
text | 50d39729-9b02-5fc6-953d-36b27c0b6ba6 |  | textbox | Quantity:
text | d3bf9dca-5469-5bb5-be1b-2c28b8f2562a |  | textbox | Serial Number:
text | 67929a7a-f9d8-50c3-a4d6-9898cb66c512 |  | textbox | Test & Tag Due:
select | f8968a80-4d7b-5ccc-ad38-832982a85c9c |  | dropdown | Further Action Required | Yes,No
text | ed9b9386-f6b0-5d99-a37c-b56c06ae64cb |  | textbox | Power Tool Name:
text | ab1c7826-a4dc-505b-b0f2-d5c128e4dd4e |  | textbox | Quantity:
text | 9cfd1b2d-92ec-5a55-9d5f-c6c1ea806a76 |  | textbox | Serial Number:
text | ecb4ece3-02d6-53e4-b323-7b13d1d2a762 |  | textbox | Test & Tag Due:
select | 8172d21f-750e-50de-af6d-7d5e713cf941 |  | dropdown | Further Action Required | Yes,No
text | a8e588c4-5afc-586d-81b4-339fe1af0074 |  | textbox | Power Tool Name:
text | 9d73d437-a425-5964-99fe-5f5a0c9f8fcd |  | textbox | Quantity:
text | 077fd138-85b3-51c7-9d31-4244c1f15a81 |  | textbox | Serial Number:
text | a0ed10ab-5040-5fc9-96e1-0846311912e7 |  | textbox | Test & Tag Due:
select | 470d0f5b-a3ae-574f-9239-d9eb8dc852ef |  | dropdown | Further Action Required | Yes,No
text | f1fdaaca-1120-561f-bae3-85118d0d3949 |  | textbox | Power Tool Name:
text | 58ebe11b-b445-5908-aa64-54221ee3621e |  | textbox | Quantity:
text | 4138152f-c653-56e6-8e21-903c7887e19e |  | textbox | Serial Number:
text | 0e85bb8c-0a09-59d2-83fb-9d952eef2706 |  | textbox | Test & Tag Due:
select | a7df6a99-d56b-5857-a6cc-463b57e78d72 |  | dropdown | Further Action Required | Yes,No
text | 7082f1f2-c606-59a0-86f1-0f8235a99f05 |  | textbox | Power Tool Name:
text | 8a1990e6-ba4c-5f63-a4d0-8b44a54ac8b7 |  | textbox | Quantity:
text | 95572911-892d-5c39-970e-51802c286dd4 |  | textbox | Serial Number:
text | 82ceff0c-5f7f-54d5-9d37-0e8b77dc1ac1 |  | textbox | Test & Tag Due:
select | 1a5a3021-1046-5d5d-ac64-81a6255db614 |  | dropdown | Further Action Required | Yes,No
checkpoint-group |  |  | section | Hand Tools
checkpoint-status |  |  | checkpoint | Screeds (Please specify)
checkpoint-status |  |  | checkpoint | Trowels (Please specify)
checkpoint-status |  |  | checkpoint | Knee Board x 2
checkpoint-status |  |  | checkpoint | Mag Float x 4
checkpoint-status |  |  | checkpoint | Rakes x 3
checkpoint-status |  |  | checkpoint | Concrete Broom
checkpoint-status |  |  | checkpoint | Broom
checkpoint-status |  |  | checkpoint | Stick Pole
checkpoint-status |  |  | checkpoint | Bull Float
checkpoint-status |  |  | checkpoint | Shovel
checkpoint-status |  |  | checkpoint | Spade
checkpoint-status |  |  | checkpoint | Level 1m
checkpoint-status |  |  | checkpoint | Sledgehammer
checkpoint-status |  |  | checkpoint | Hose 10m
checkpoint-status |  |  | checkpoint | Strop & Ratchet
text | e7ee6a2a-a93f-5d66-86d3-21fdf58c572c |  | textbox | Quantity:
checkpoint-group |  |  | section | Health & Safety
checkpoint-status |  |  | checkpoint | First Aid Kit
checkpoint-status |  |  | checkpoint | Fire Extinguisher
checkpoint-status |  |  | checkpoint | Gloves
checkpoint-status |  |  | checkpoint | Hard Hat
checkpoint-status |  |  | checkpoint | Ear Muffs
checkpoint-status |  |  | checkpoint | Hi Viz
checkpoint-status |  |  | checkpoint | Safety Glasses
checkpoint-group |  |  | section | Consumables
checkpoint-status |  |  | checkpoint | Chalk Line
holdpoint |  |  | signoff | Signature: