## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | 1 Job estimation handover (QS / PM) |  |  |  |  | Yes | 1 Job estimation handover (QS / PM) | 2db93ec9-d577-44c9-85a3-dd5569649720
checkpoint-no-status |  |  | checkpoint | Project Details
text | d99afc70-13e3-56ef-9e08-acd0d6a00382 |  | textbox | Project Details:
text | 1a8bd94d-4f7e-5a01-af8a-cfef03dedb26 |  | textbox | Client:
text | 44d05bd9-a677-5694-a476-5948b6aa4548 |  | textbox | Address:
text | 0d4ac330-d1f7-5a58-acf4-4b54cbe56c08 |  | textbox | Other:
text | dec0fd6e-2c27-53aa-8e5e-e61fe29cb595 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Estimator and Project Team - Discuss quoted job (QS/PM)
checkpoint-status |  |  | checkpoint | Critical tags discussed
checkpoint-status |  |  | checkpoint | Any tender ageement with subcontractors and supplier discussed and documented. (Who are the subcontractors and suppliers)
checkpoint-status |  |  | checkpoint | Tender and risks and opportunities discussed with project team
checkpoint-status |  |  | checkpoint | P&G Allowances
checkpoint-status |  |  | checkpoint | Tender discuss and approved by relevant person/s
checkpoint-status |  |  | checkpoint | Formwork / Propping / Rebates allowed for Job
checkpoint-status |  |  | checkpoint | Program and Labour allowances for each phase of the job
checkpoint-status |  |  | checkpoint | Any other job information that needs to be handed over.
checklist-flat |  |  | checklist | 2 Job handover to Site Manager and Foreman (PM) |  |  |  |  | Yes | 2 Job handover to Site Manager and Foreman (PM) | 3a5df4b6-519e-405d-9b3c-66142cbd226c
checkpoint-no-status |  |  | checkpoint | Project Details:
text | 10d26677-df36-5452-beff-d34e0a29a837 |  | textbox | Client:
text | f1558895-6b02-59f5-bf82-44f15f863d55 |  | textbox | Address:
text | 115569a7-5cd7-5c39-be65-e7dc3b697102 |  | textbox | Other:
text | 059c1890-9625-554c-a7fc-a4e06859b97a |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Send Foreman Job Question Sheet
checkpoint-status |  |  | checkpoint | Get Foreman to review plans before coming in to see you
checkpoint-status |  |  | checkpoint | Have Master Schedule sent
checkpoint-status |  |  | checkpoint | Have survey serout and plan sent
checkpoint-status |  |  | checkpoint | Make sure Foreman knows if we are working off grids or building lines
checkpoint-status |  |  | checkpoint | Make sure they know heights
text | 1fd1b7e5-ce6f-5b2a-89b4-95dc7dbf1289 |  | textbox | Footings height:
text | 4dd93f02-422b-5c9a-b8fd-65ae87134dd2 |  | textbox | Block/wall heights:
text | 779dd5bc-4d73-5cee-9d49-7ddea812b253 |  | textbox | Finish floor levels:
text | b80b97a5-6bf1-5b6c-9e95-7b6788de81da |  | textbox | Lift pit levels:
text | df859786-c3a0-5ad1-8be2-db66e47bff51 |  | textbox | Finish Ground Levels (for footings outside of building lines)
checkpoint-status |  |  | checkpoint | DPM require
checkpoint-status |  |  | checkpoint | Waterproofing areas
checkpoint-status |  |  | checkpoint | Formworks and bracing required and what was quoted
checklist-flat |  |  | checklist | 3.1 Slab Pre pour Quality Assurance |  |  |  |  | Yes | 3.1 Slab Pre pour Quality Assurance | 3b63cb86-bb2a-4a54-a775-bc84d078fab9
checkpoint-no-status |  |  | checkpoint | What is FFL
checkpoint-status |  |  | checkpoint | Edgebeam / Rebates set to FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Edgebeam running down correct gridlines (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Joinery Rebates set to required depths
checkpoint-status |  |  | checkpoint | Garage Rebate set as per client requirements
checkpoint-status |  |  | checkpoint | Inslab rebates in correct slab position (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates set to correct depth from FFL
checkpoint-status |  |  | checkpoint | Formwork Sprayed with form release (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum bottom cover (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from form work (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All bends tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps minimum lap requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from form work and rebates (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minum cover from services (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Stringline run and left up in multiple places to prove cover from FFL to top of Mesh for engineer and council (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Floor checked all over to make sure no steel is above FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Thickening measurement as per plan and same top and bottom (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Pods been cut outside the slab
checkpoint-status |  |  | checkpoint | All DPM taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM up to edgebeam (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Services taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inside pad free from rubbish (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Starter caps on all waratahs or exposed starters (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Rubbish in bins and site cleaned up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess boxing and steel stacked neatly and out of lay teams way, ready for pick up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Nothing around the slab and in way of Lay team (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess pods and pod rubbish been collected or supplier been called to pick up
checkpoint-status |  |  | checkpoint | Site in clean and respectable state (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team has been organised
checklist-flat |  |  | checklist | 3.2 Footing Pre Pour Quality Assurance |  |  |  |  | Yes | 3.2 Footing Pre Pour Quality Assurance | 3d4acf65-e820-4547-8e36-497618f45ffd
checkpoint-status |  |  | checkpoint | Check all top of footing heights and make sure they are as per plan? Label as footing engineer detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | All footing depths as per plan? Label as per engineer footing detail( Multiple photos required)
checkpoint-status |  |  | checkpoint | All footing widths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Specified DPM used in footings? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All DPM laps taped? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Waterproofing membrane in required parts of footing? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel bottom minimum bottom cover achieved in all places (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel minimum side cover achieved in all places (Boxing or to earth)(Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends all tied? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends as per minimum lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Bottom mat of footing spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Top mat spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect bottom mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continous bent steel to connect top mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | Where footings step up, have Z bends and horizontals been installed as per engineer design. (Multiple photos required)
checkpoint-status |  |  | checkpoint | On step ups, form work set to footing depth and no more? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter Line been profiles and set as per engineer requirements from block / earth face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Starters within 5 mm of engineer plans from block face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter spacings set as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter lap for post concrete pour, set to have minimum steel lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Height pegs or nails installed and sprayed for Lay team (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Footings clear from rubbish and dirt (Multiple photos required)
checkpoint-status |  |  | checkpoint | All waratahs and starters have starter caps on (Multiple photos required)
checkpoint-status |  |  | checkpoint | All excess steel / materials stored neatly and out of lay and blockie teams way? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Access for concrete pump clear
checkpoint-status |  |  | checkpoint | All rubbish in bin or removed from site
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team has been organised
checklist-flat |  |  | checklist | 7 Foreman Job Checklist (F) |  |  |  |  | Yes | 7 Foreman Job Checklist (F) | 5255c16d-6172-429a-b9da-7ac188c50aad
checkpoint-status |  |  | checkpoint | Job file formed
checkpoint-status |  |  | checkpoint | Plans reviewed and required details printed and laminated?
label | 9b9e0e34-b89d-50be-a799-083dd9e71bb6 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Survey markout plan printed and laminated?
label | af3523df-a16d-52f9-9607-6a2f3a5a7e4f |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All heights printed and kaminated?
label | 72566b64-dd7e-5111-a65f-65d0d3b63c8f |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Job Master Schedule printed and laminated? (if schedule changes, throw away old and add new)
label | 6718ba89-a672-56ed-90b6-c7b97fb6d799 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Amounts
label | d6771c2a-bb3e-5b34-9408-000bb990fd0a |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Concrete Dockets
label | bae64e9f-3011-500c-ab97-f2aef50cdba4 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Toolboxes
label | 3eafe6f7-c68e-5985-bc0d-324a49e86520 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | SSSP
label | 3f726223-5af1-5c0d-81a6-231c825e074e |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | Waterproofing markout
label | 5a6a23d9-4cbd-54f8-bb81-b9c698ed5747 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | PM - Foreman handover printed
label | a39bb3d7-fc64-51d5-bc3c-d2b13be3ae80 |  | note | Add to Job File
checkpoint-status |  |  | checkpoint | All Qas printed
label | fc8b5fc0-544e-528d-97b1-9254fe6b814d |  | note | Add to Job File
checklist-flat |  |  | checklist | Foreman and Site Manager Job planning Prior to meeting PM |  |  |  |  | Yes | Foreman and Site Manager Job planning Prior to meeting PM | 5c36702f-7923-431a-b2e6-d66343f5adbe
checkpoint-no-status |  |  | checkpoint | Foreman and Site Manager Job planning Prior to meeting PM
text | 30dc9a7d-112e-5731-b0d9-65314f6cd77f |  | textbox | Project details:
text | 6c0b0e93-af96-5422-bf8c-29b8b1fe0280 |  | textbox | Client:
text | 19327e34-5b33-5505-ae35-5c17a0240c59 |  | textbox | Address:
text | 3874c4d8-3533-5b41-87eb-87555e86cbe1 |  | textbox | Other:
text | 6304ed4b-369a-5d2d-9c57-f171afd2857a |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review plans, including engineer set and build question sheet
checkpoint-status |  |  | checkpoint | Go over PM's Job schedule
checkpoint-status |  |  | checkpoint | Identify key dates
checkpoint-status |  |  | checkpoint | Deliveries
checkpoint-status |  |  | checkpoint | QA's
checkpoint-status |  |  | checkpoint | Inspections
checkpoint-status |  |  | checkpoint | Pour dates
checkpoint-status |  |  | checkpoint | Identify materials used
checkpoint-status |  |  | checkpoint | DPM
checkpoint-status |  |  | checkpoint | Steel
checkpoint-status |  |  | checkpoint | Mebrane type
checkpoint-status |  |  | checkpoint | Boxing required
checkpoint-status |  |  | checkpoint | Identify survey plan and Heights
checkpoint-status |  |  | checkpoint | Identify waterproofing locations and where DPM ends
checkpoint-status |  |  | checkpoint | If we have footing outside of building lines, top of footings in these loctions need to be at least 200 mm below FFL
checklist-flat |  |  | checklist | 5 PM handover to Site Manager and Forman (PM / SM / F) |  |  |  |  | Yes | 5 PM handover to Site Manager and Forman (PM / SM / F) | 811de479-e491-4492-b73d-fcaf61a355c8
checkpoint-status |  |  | checkpoint | Have you reviewed Plans/Job Schedule?
checkpoint-status |  |  | checkpoint | Do you understand survey markout grids? Building lines?
checkpoint-status |  |  | checkpoint | Heights:
text | 11be5887-ac6f-5156-adb5-071d5911881b |  | textbox | Footing Depth
text | 4e8cc179-f887-59fe-9196-0aee9e26b5a5 |  | textbox | Bottom of footing measurement
text | 4fd443b0-470c-59b9-af37-774c9fee0de9 |  | textbox | Top of footing measurement
text | 752a1a79-a4bf-5364-893b-1011614687d9 |  | textbox | Finish Floor Line (FFL)
text | a3f3efd4-cb0a-50cb-85c0-d57f9efbee3b |  | textbox | Block wall heights
text | 903c3f63-a894-5ecb-a4f7-e191d1fe4d95 |  | textbox | Insitu wall heights
checkpoint-status |  |  | checkpoint | Have you got all dimensions?
checkpoint-status |  |  | checkpoint | Show Foreman complicated components of Job and solutions
checkpoint-status |  |  | checkpoint | DPM require/tape
checkpoint-status |  |  | checkpoint | Waterproofing locations, explain importance of larger digout in these locations:
label | 11c69784-1d7c-5a39-be25-27f18460b523 |  | note | Go over Engineer Details
label | bd65d741-8569-5b07-94f9-c21317c0e462 |  | note | Go over Building Methodology
label | 67e03482-275a-5a6d-9b61-156e68fce992 |  | note | Go over Key dates
label | e19d1467-a3ee-5e66-8a51-8b67341fd8b3 |  | note | Go over size of team
label | feedf0cb-e74c-51be-896f-6996f9436d5e |  | note | Go over rebates
label | 829997e2-7e27-5b13-a375-0bb955e79062 |  | note | Go over penetrations
checkpoint-status |  |  | checkpoint | Materials to site
checkpoint-status |  |  | checkpoint | What has been allowed/ and what hasn't
checkpoint-status |  |  | checkpoint | What needs to be taken to site
checkpoint-status |  |  | checkpoint | Any other points/discussion:
checklist-flat |  |  | checklist | Foreman's Job Planning |  |  |  |  | Yes | Foreman's Job Planning | a767f994-b9a5-477c-b60b-2f2504a15de8
checkpoint-no-status |  |  | checkpoint | Foreman's Job Planning
text | dd79810e-7537-5a78-bd4b-bac8d6822992 |  | textbox | Project Details:
text | cfc6641a-e658-592f-9dcf-4177c8b55534 |  | textbox | Client:
text | 5d17ed81-f44a-5bed-860f-c6de39cff22a |  | textbox | Address:
text | 89f6cd5e-2b57-5b2e-9df5-9a620344182e |  | textbox | Other:
text | dee635b6-8c91-56af-a0b6-9db3624562f7 |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review Master Schedule
checkpoint-status |  |  | checkpoint | Plan Days / Weeks according to Master schedule; Labour size and tasks to complete
checkpoint-status |  |  | checkpoint | Bring your team in for and go over job with them, explain the job file
checkpoint-status |  |  | checkpoint | Make sure Van is loaded with everything it will need for the job
checkpoint-status |  |  | checkpoint | Team book and load trailer as required, day prior to job starting
checkpoint-status |  |  | checkpoint | Remember Monday morning Toolboxes and Friday debriefs
checklist-flat |  |  | checklist | Site Inspection Pre Job Starting - Site Manager and Foreman |  |  |  |  | Yes | Site Inspection Pre Job Starting - Site Manager and Foreman | ab317970-8a6e-4a2f-8a4f-2e4631e8383b
checkpoint-no-status |  |  | checkpoint | Site Inspection Pre Job Starting - Site Manager and Foreman
text | e3aac975-cfa6-5499-bc5e-5837ad382d60 |  | textbox | Project Details:
text | ae0472df-bf75-5a90-a4ce-80da5281a471 |  | textbox | Client:
text | 091248a0-d8df-5267-8158-d0bc3ba0529a |  | textbox | Address:
text | 5cc98935-2241-5706-8892-cc69a3c2301e |  | textbox | Other:
text | e7119dfb-1114-5f44-91bc-1a05828414b3 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Traffic management required for our job scope?
checkpoint-status |  |  | checkpoint | If so, has the client been informed and agreed it will be in place for our start date?
checkpoint-status |  |  | checkpoint | Have materials been dropped off?
checkpoint-status |  |  | checkpoint | If not, contact suppliers, let them know where you want materials delivered and what is delivery time and date:
checkpoint-status |  |  | checkpoint | Identify workstations
checkpoint-status |  |  | checkpoint | Pod cutting station outside of slab
checkpoint-status |  |  | checkpoint | Steel bending and cutting station
checkpoint-status |  |  | checkpoint | Timber cutting station
checkpoint-status |  |  | checkpoint | Skip bin onsite?
checkpoint-status |  |  | checkpoint | Portaloo onsite?
checkpoint-status |  |  | checkpoint | Power to site?
checkpoint-status |  |  | checkpoint | Water to site?
checkpoint-status |  |  | checkpoint | Site box and work drawings?
checkpoint-status |  |  | checkpoint | If none of the above are onsite and are needed for us, has client been informed?
checkpoint-status |  |  | checkpoint | Boundary and survey set outs/pegs been done?
checkpoint-status |  |  | checkpoint | Cut heights and locations as OTWC requirements?
checkpoint-status |  |  | checkpoint | If not, has client been informed and start date been changed for the problem to be sorted?
checkpoint-status |  |  | checkpoint | OTWC vehicle parking confirmed with client & the location has been identified?
checkpoint-status |  |  | checkpoint | Any other issues that need to be brought up to client?
checkpoint-status |  |  | checkpoint | If so, has client been informed?
checklist-flat |  |  | checklist | 3 Site Manager and Foreman job planning prior to meeting PM (SM / F) |  |  |  |  | Yes | 3 Site Manager and Foreman job planning prior to meeting PM (SM / F) | ae51836f-5dfb-4d34-942f-e63bfc89c22a
checkpoint-no-status |  |  | checkpoint | Foreman and Site Manager Job planning Prior to meeting PM
text | b7ff6381-e629-5e26-b0e8-45e7526cbc55 |  | textbox | Project details:
text | b1800020-c49d-5c27-b564-d94dada99303 |  | textbox | Client:
text | 49e99486-22a3-51b4-8d18-90238774132e |  | textbox | Address:
text | 6a1f071f-3d51-5a6f-99a6-30169db44533 |  | textbox | Other:
text | be457be5-c34d-5faa-895c-7ff8af1f9596 |  | textbox | Attendance:
checkpoint-status |  |  | checkpoint | Review plans, including engineer set and build question sheet
checkpoint-status |  |  | checkpoint | Go over PM's Job schedule
checkpoint-status |  |  | checkpoint | Identify key dates
checkpoint-status |  |  | checkpoint | Deliveries
checkpoint-status |  |  | checkpoint | QA's
checkpoint-status |  |  | checkpoint | Inspections
checkpoint-status |  |  | checkpoint | Pour dates
checkpoint-status |  |  | checkpoint | Identify materials used
checkpoint-status |  |  | checkpoint | DPM
checkpoint-status |  |  | checkpoint | Steel
checkpoint-status |  |  | checkpoint | Mebrane type
checkpoint-status |  |  | checkpoint | Boxing required
checkpoint-status |  |  | checkpoint | Identify survey plan and Heights
checkpoint-status |  |  | checkpoint | Identify waterproofing locations and where DPM ends
checkpoint-status |  |  | checkpoint | If we have footing outside of building lines, top of footings in these loctions need to be at least 200 mm below FFL
checklist-flat |  |  | checklist | 8 Site inspection Pre-job start Site Manager and Foreman (SM / F) |  |  |  |  | Yes | 8 Site inspection Pre-job start Site Manager and Foreman (SM / F) | afc67997-f10a-4e22-a38c-1d75ddbb9c11
checkpoint-no-status |  |  | checkpoint | Site Inspection Pre Job Starting - Site Manager and Foreman
text | 643fdb4e-180e-5c62-b17e-5aa80112b9a1 |  | textbox | Project Details:
text | bd1a67cb-889f-599d-8017-82aac32118a9 |  | textbox | Client:
text | a530b0aa-0af4-59e4-8537-88e5dec5c293 |  | textbox | Address:
text | a475db22-9740-5446-b93b-fef475756f6e |  | textbox | Other:
text | 9e3758fd-2604-5279-aa31-a75cf73b6009 |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Traffic management required for our job scope?
checkpoint-status |  |  | checkpoint | If so, has the client been informed and agreed it will be in place for our start date?
checkpoint-status |  |  | checkpoint | Have materials been dropped off?
checkpoint-status |  |  | checkpoint | If not, contact suppliers, let them know where you want materials delivered and what is delivery time and date:
checkpoint-status |  |  | checkpoint | Identify workstations
checkpoint-status |  |  | checkpoint | Pod cutting station outside of slab
checkpoint-status |  |  | checkpoint | Steel bending and cutting station
checkpoint-status |  |  | checkpoint | Timber cutting station
checkpoint-status |  |  | checkpoint | Skip bin onsite?
checkpoint-status |  |  | checkpoint | Portaloo onsite?
checkpoint-status |  |  | checkpoint | Power to site?
checkpoint-status |  |  | checkpoint | Water to site?
checkpoint-status |  |  | checkpoint | Site box and work drawings?
checkpoint-status |  |  | checkpoint | If none of the above are onsite and are needed for us, has client been informed?
checkpoint-status |  |  | checkpoint | Boundary and survey set outs/pegs been done?
checkpoint-status |  |  | checkpoint | Cut heights and locations as OTWC requirements?
checkpoint-status |  |  | checkpoint | If not, has client been informed and start date been changed for the problem to be sorted?
checkpoint-status |  |  | checkpoint | OTWC vehicle parking confirmed with client & the location has been identified?
checkpoint-status |  |  | checkpoint | Any other issues that need to be brought up to client?
checkpoint-status |  |  | checkpoint | If so, has client been informed?
checklist-flat |  |  | checklist | 2.1 Slab Installation Methodology |  |  |  |  | Yes | 2.1 Slab Installation Methodology | c0ffff02-9fcf-4fe7-a12b-5e6647ad35ae
checkpoint-no-status |  |  | checkpoint | What is FFL
checkpoint-status |  |  | checkpoint | Set Profiles to 30 mm above FFL and stransfer gridlines onto profiles
checkpoint-status |  |  | checkpoint | Set up stringlines, check measurements and diagonals
checkpoint-status |  |  | checkpoint | Clean / wash down all footings and Block wall header blocks
checkpoint-status |  |  | checkpoint | Check all prep heights are within tolerance
checkpoint-status |  |  | checkpoint | Set Edgebeam and Rebates set to FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Set correct Edgebeam face running down correct gridlines (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Joinery Rebates set to required depths (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Garage Rebate set as per client requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All waratahs have starter caps on (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Site Cleaned / Rubbish in bin/ Materials located in centralised locations/ Ready for Plumbers?
checkpoint-status |  |  | checkpoint | Steel and Pod cutting loctions outside of pad established (centralise all rubbish to one location)
checkpoint-status |  |  | checkpoint | Pods have been cut outside the slab
checkpoint-status |  |  | checkpoint | All steel has minimum bottom cover (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from form work (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All bends tied (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All steel laps minimum lap requirements (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from pods (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minimum cover from form work and rebates (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Mesh has minum cover from services (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Stringline run and left up in multiple places to prove cover from FFL to top of Mesh for engineer and council (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates set to correct depth from FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Floor checked all over to make sure no steel is above FFL (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Thickening measurement as per plan and same top and bottom (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | All DPM up to edgebeam (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Services taped (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inside pad free from rubbish (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Starter caps on all waratahs or exposed starters (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Rubbish in bins and site cleaned up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess boxing and steel stacked neatly and out of lay teams way, ready for pick up (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Nothing around the slab and in way of Lay team (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Excess pods and pod rubbish been collected or supplier been called to pick up
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Inslab rebates in correct slab position (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Formwork Sprayed with form release (Multiple photo's required)
checkpoint-status |  |  | checkpoint | Hand over to lay team been organised
checklist-flat |  |  | checklist | 2.2 Footing Methodology |  |  |  |  | Yes | 2.2 Footing Methodology | d873982c-9f80-4041-88df-8e3533f3c8b2
checkpoint-status |  |  | checkpoint | Set profiles to above Footing FFL
checkpoint-status |  |  | checkpoint | Surveyor to install grids on profiles (No builder to set a gridline)
checkpoint-status |  |  | checkpoint | Surveyor to mark Block side of grid line with an X on profile both sides
checkpoint-status |  |  | checkpoint | Install all stringlines
checkpoint-status |  |  | checkpoint | Measure all walls and confirm measurements within tolerance of plan measurements
checkpoint-status |  |  | checkpoint | Check diagonals
checkpoint-status |  |  | checkpoint | Transfer grids to ground and mark out each footing as per engineer dimension
checkpoint-status |  |  | checkpoint | Confirm all top of footing heights and make sure they are as per plan? Label as per footing engineer detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Confirm footing depths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Confirm footing widths as per plan? Label as per engineer footing detail (Multiple photos required)
checkpoint-status |  |  | checkpoint | Specified DPM used in footings? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Dig out footings
checkpoint-status |  |  | checkpoint | Confirm all footing depths as per plans and within tolerable deep to begin building footing
checkpoint-status |  |  | checkpoint | Confirm all footing tops as per plans and within tolerable deep to begin building footing
checkpoint-status |  |  | checkpoint | Box footings where required
checkpoint-status |  |  | checkpoint | Insert DPM into footings where required
checkpoint-status |  |  | checkpoint | All DPM laps taped? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Waterproofing membrane in required parts of footing? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel out bottom mat as per singeer plans
checkpoint-status |  |  | checkpoint | Steel bottom minimum bottom cover achieved in all places (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel minimum side cover achieved in all places (Boxing or to earth)(Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends all tied? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel laps and bends as per minimum lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Bottom mat of footing spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Steel Top mat spacings as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect bottom mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | All corners have continuous bent steel to connect top mats (Multiple photos required)
checkpoint-status |  |  | checkpoint | Where footings step up, have Z bends and horizontals been installed as per engineer design. (Multiple photos required)
checkpoint-status |  |  | checkpoint | On step ups, form work set to footing depth and no more? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter Line been profiled and set as per engineer requirements from block / earth face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | All Starters with in 5 mm of engineer plans from block face? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter spacings set as per engineer plans? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Starter lap for post concrete pour, set to have minimum steel lap cover? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Height pegs or nails installed and sprayed for Lay team (Multiple photos required)
checkpoint-status |  |  | checkpoint | All footings clear from rubbish and dirt (Multiple photos required)
checkpoint-status |  |  | checkpoint | All waratahs and starters have starter caps on (Multiple photos required)
checkpoint-status |  |  | checkpoint | All excess steel / materials stored neatly and out of lay and blockie team way? (Multiple photos required)
checkpoint-status |  |  | checkpoint | Access for concrete pump clears
checkpoint-status |  |  | checkpoint | All rubbish in bin or removed from site
checkpoint-status |  |  | checkpoint | Site in clean and respectable state. (Multiple photos required)
checkpoint-status |  |  | checkpoint | Hand over to lay team been organised
checklist-flat |  |  | checklist | 6 Site Manager and Foreman’s Job planning (SM / F) |  |  |  |  | Yes | 6 Site Manager and Foreman’s Job planning (SM / F) | e0e8288d-65f8-48d6-b4a5-dbe64154c90a
checkpoint-no-status |  |  | checkpoint | Project Details
text | 4c97ecf3-f84d-56dd-8e32-0911b105dce2 |  | textbox | Project Details:
text | 64671e63-a856-551a-830e-548e0d6a7418 |  | textbox | Client:
text | 3e896051-bff9-58f8-935a-4072f4a71752 |  | textbox | Address:
text | d0b0fbe7-da3a-5a0c-b2dd-2260d820b0d1 |  | textbox | Other:
text | 8a2f31d0-72e9-59ff-a122-a1518abc09fd |  | textbox | Attendence:
checkpoint-status |  |  | checkpoint | Job built from start to finish - Compare with Program
checkpoint-status |  |  | checkpoint | Design issues noted and send to client
checkpoint-status |  |  | checkpoint | Site Specific OTWC requirements - Send to client
checkpoint-status |  |  | checkpoint | Master Program built and send to client
label | 61547dd6-fac2-5024-aa63-7472fb9facba |  | note | To include materials drop offs
label | 4bd364d1-5653-5f88-ac90-469b7e17200e |  | note | To include formwork required
label | 002e25f7-8570-5274-8bd0-688ae455df5d |  | note | To include concrete bookings
label | 8eddd09b-4732-520f-848a-28672e770405 |  | note | To include inspections
checkpoint-status |  |  | checkpoint | Concrete bookings insert into Concrete Schedule
checkpoint-status |  |  | checkpoint | Material bookings into Material Schedule
checkpoint-status |  |  | checkpoint | Site Manager to get a copy of the Job Schedule
checkpoint-status |  |  | checkpoint | Schedule to have Toolbox Meeting
checklist-flat |  |  | checklist | 4 Site Manager and Foreman Question Sheet (SM / F) |  |  |  |  | Yes | 4 Site Manager and Foreman Question Sheet (SM / F) | ef6bf04a-249a-477a-b996-53068644142e
checkpoint-status |  |  | checkpoint | Do you understand profile and survey setout or do you require more information?
checkpoint-status |  |  | checkpoint | Are your survey marks off grid lines or building lines?
button | af790c26-5abb-5a1e-89ff-ebad507f52bd |  | button |  | Grid lines, Building Lines
checkpoint-status |  |  | checkpoint | Item Details
boolean | 891b51e4-788a-55d7-9acd-efff468a9fc5 |  | tickbox | Do you understand all heights?
boolean | 9283e211-aa21-518c-8578-cf556becd3f9 |  | tickbox | Do you have all dimensions?
text | 765879a3-b3f8-597d-88d4-2805e2d9cbef |  | textbox | What formwork are you using for each component of the job?
checkpoint-status |  |  | checkpoint | Has the formwork and bracing been organised to be onsite before you require it?
checkpoint-status |  |  | checkpoint | Material Details
text | 5b210ab3-a67f-590b-bb3e-540aec3bb584 |  | textbox | Where have your materials been ordered from?
date | 4db7f4f0-9506-5ff7-a4fa-cd72df21bef7 |  | date | What date do you expect your materials to be delivered?
checkpoint-status |  |  | checkpoint | Have all materials been ordered to site or do you need to pickup materials? If so, notify your van.
button | 6fdd97fe-e4a4-546d-a395-80ea1749c32a |  | button |  | To Site, Pickup
checkpoint-status |  |  | checkpoint | Key Dates
text | c33d2a76-77d8-5281-8d6a-ab8b4430b283 |  | textbox | Identify key dates to make
text | 9f33b17b-bd23-5f03-87f8-77fd25766e16 |  | textbox | Identify inspection dates
checkpoint-status |  |  | checkpoint | DPM & Waterproofing
text | 8da3c7ac-a9af-56d2-a72e-97ffb833c47b |  | textbox | What DPM and tape required?
boolean | 36526945-1202-5f89-ad06-640f33b67ed2 |  | tickbox | Has this been ordered?
text | bab20eb4-0272-5781-806f-9cd312998a81 |  | textbox | Waterproofing - Identify waterproofing location
boolean | c4affd8c-9b09-5834-9b20-79f69bfeeaf6 |  | tickbox | Make sure digout accounts for waterproofers
boolean | 5e6d3be3-9652-5334-b7fc-05850b1b6d6c |  | tickbox | Go over van load out list with your van
boolean | d5f19545-0d69-5a2e-b3f2-e7e046beadf8 |  | tickbox | Has your van got everything needed for the job
text | 20f1ca21-3b74-5fb4-b32b-0a74e4a0636e |  | textbox | Rebates
text | 38b1ce14-dec6-5f71-bfd3-45aef7226d78 |  | textbox | Profile timber and walls
checklist-flat |  |  | checklist | 0 Pricing Pre-Start Meeting |  |  |  |  | Yes | 0 Pricing Pre-Start Meeting | f2ec9633-6d0f-4666-a811-0fdd59b4227f
checkpoint-no-status |  |  | checkpoint | Pricing Pre-Start Meeting
text | 98215756-676c-5c7b-976e-02fcc4f77520 |  | textbox | Project Details:
text | 1f3bcaae-99e9-517c-b5d6-7c2048ea8705 |  | textbox | Client:
text | bc79498f-6f61-5651-9c69-25261ae5fe42 |  | textbox | Address:
text | e519a35f-d84e-5e97-b005-b900be47677b |  | textbox | Other:
text | 3c5f87d6-49e0-5a5c-9626-727508ec2400 |  | textbox | Attendance:
text | 91d9c0bc-02d3-5845-8d62-d4ae0dd9e0ed |  | textbox | Tender Manager:
text | 41680006-7206-57bb-a076-7e44d8c881bb |  | textbox | Tender Status:
text | 76386736-8056-5cbe-84a1-362c28dc78a3 |  | textbox | Tender submission due date:
text | 8b43314b-6559-58a4-ad6b-38e185349cd9 |  | textbox | Job Details/Scope:
checkpoint-status |  |  | checkpoint | Has a Client Programme be provided?
checkpoint-status |  |  | checkpoint | Suppliers & Subcontractors Identified:
checkpoint-status |  |  | checkpoint | Have the documents been uploaded to Sharepoint?
checkpoint-status |  |  | checkpoint | A tasks list & a Project Programme (Project Manager):
checkpoint-status |  |  | checkpoint | Tender Clarifications/RFI's Required:
checkpoint-status |  |  | checkpoint | Risks or Opportunities:
checkpoint-status |  |  | checkpoint | Pre Submission meeting date scheduled:
checkpoint-status |  |  | checkpoint | Is a meeting with the client required? (At this stage)