## ITP Cover Page
Traffic Signals Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 110 - Rev C
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 110
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | TRAFFIC SIGNALS |  |  |  |  | Revision: | 1000 |  | C
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A-2701 to 146000-002AA-2795
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Review | 2024-02-08 |  | Kanav Chhabra |  | First revision for internal review & approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Review | 2024-02-23 |  | Emil Fergusson |  | Ammendements added per request of BBO representative Emil Fergusson via InEight on 23/02/2024 (Reference: DN1205-BBO-GCO-0214). |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | Approved Copy - Minor Corrections | 2024-02-23 |  | Emil Fergusson |  | Minor corrections to titles/contact details (Reference: DN1205-BBO-GCO-0215). |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body (Full) (hidden)
Traffic Signals Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.1 | General
1.1.1 | Drawings | Prior to starting works, ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to work planning and start | M | PE
1.1.2 | Construction Pack | ITP to be submitted to the Engineer and approved prior to works beginning | Downer | In-Eight Document Approval/Acknowledgement | Submit 10 days prior to commencement of works | H | PE
|  | Methodology and associated documents to be prepared, reviewed and approved internally prior to work commencement. | Downer | Construction Pack Sign Off | Prior to Construction & after any major incident | M | PE
1.1.3 | Survey Set-out | Ensure traffic signal pole, access chamber, and controller cabinet locations are set out per IFC drawings/data. | Design Drawings | ITP Sign Off | Prior to Construction & Every Revision of IFC Drgs / Data | M | PE
1.1.4 | Walk-over | HCC Traffic Engineer to walk over and confirm pole locations. 1st Contact: Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport DDI: (07) 838 6638 Mob: 0278086506 Email: Brandon.Harley@HCC.govt.nz Alt Contact: Holly Blackley - Senior Transport Network Operator HCC City Transport DDI: (07) 838 6817 Mob: 0278087593 Email: Holly.Blackley@hcc.govt.nz 2nd Alt Contact: John Kinghorn - HCC City Transport Mobile: Email: John.Kinghorn@hcc.govt.nz | Design Drawings | In-Eight Document Approval/Acknowledgement | Prior to construction | H | PE
1.1.5 | Environmental Protection | Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events | Project ESCP Plans | ITP Sign Off | Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events | M | PE
1.1.6 | Stakeholder | Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners | Project Stakeholder Management Plan | ITP Sign Off | Prior to Construction with continue updates throughout the works | M | PE
1.1.7 | Permits | Ground Disturbance Permit must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. Doner Permit encompasses external provider permit requirements. All known services must be clearly marked on site and briefed to the workforce . | Section 2.2.10 Project Specification | Ground Disturbance Permit DN-ZH-FM043.1 | Prior to Construction Reviewed and Reissued weekly or when site conditions change | H | PE
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2.1 | General
2.1.1 | Pole Producer Statements | PS1 certificate required for all pole types. | Project Specification Apendix E 3.16 | InEight Transmittal / CONQA entry | Prior to pole acquisition | H | PE
2.1.2 | Controller Cabinet | Unless otherwise specified, VC6 ELV controller (compatible with latest SCATS software) fitted with a generator socket matching existing HCC controller cabinet colours. Must be fitted with a sticker indicating the Site ID Number. | Project Specification Apendix E 2.3.5/2.3.6/3.6 | Nil - Visual Check | Each controller/intersection | M | PE
2.1.3 | Site ID Number | HCC to provide Site ID number. | Project Specification Apendix E 3.6 | Written correspondence | Prior to commissioning | M | PE
2.1.4 | CCTV camera | HCC must approve of traffic monitoring camera which should meet requirements. Hardware is required to have a minimum 12 months warranty period. HCC preference is an Axis Q6075-E along with an Axis Q6010-E, using the Axis T91L61 pole mounts. | Project Specification Appendix E 3.19.1 | Written correspondence | Prior to material acquisition | M | PE
2.1.5 | Communications Connection | Engage HCC to apply for these with Lightwire. Provide latitude/longitudes of controller cabinet locations to use in application. | Project Specification Apendix E 3.18 | Written correspondence | 3 months prior to connection | M | PE
2.1.6 | Electrical Connection | Apply for new commercial electrical connection via the WEL Networks website/login for each new signalised intersection (NC1 Form). Traffic signals subontractor to confirm electrical requirements. | Project Specification Appendix E 3.3 | Approval document/NC1 Form with ICP number | 3 months prior to connection | M | PE
SECTION 3 – CONSTRUCTION ACTIVITY
3.1 | Software
3.1.1 | Software/personality files and CIS | HCC to provide to contractor (Downer or TSL). Contact (s): John Kinghorn - HCC City Transport Mobile: Email: John.Kinghorn@hcc.govt.nz Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport DDI: (07) 838 6638 Mob: 0278086506 Email: Brandon.Harley@HCC.govt.nz | Project Specification Appendix E 3.15.3 | In-Eight Documents/Mail | Requested at least 6 weeks prior to bench testing date. | H | HCC / WTOC
3.1.2 | Bench Test | Traffic signals contractor to bench test files. | NZTA P43 3.15.4 | PDF Document | Once per intersection, at least 1 week prior to comissioning | H | PE / TSL
3.2 | Civil (Pole / Cabinet / Access Chamber) Installations
3.2.1 | Soil Bearing Strength | Report results. Check this meets poles deisgn (i.e. >= 50kPa). | Drawings/PS1/NZTA P43 2.5.1.3 | Shear Vane | One pole per intersection corner (i.e. north-west, north-east etc) | H | PE / TSL
3.2.2 | Pole Base Photograph | Photographic evidence of each pole base to be submitted as part of PS3 | Project Specification Appendix E 3.16 | Photographs | Each pole base prior to foundation pour. | M | TSL
3.2.3 | Pole Concrete Footings (poles in berm, not concrete) | Where a pole is not surrounded by concrete, the pole must have 500mm2 of concrete surrounding it with a depth of 150mm (20MPa as below). | NZTA P43 3.9 | Nil - Visual Check | Each footing not within concrete or asphalt. | M | PE
3.2.4 | Pole Concrete Footing Strength | Confirmation footing concrete strength (where required - i.e. delivery dockets) is min 20MPa at 28days, or as specified in foudation design. | NZTA P43 3.9 | Concrete dockets | At least once per pour | M | PE / TSL
3.2.2 | Pole Installation | Plumbed vertical Tolerance: +/- 10mm per 5.0m length |  | Nil - Visual Check | Each pole | M | TSL
3.2.5 | Identification Numbers | Ensure poles are fitted with/displaying the correct number and match the CIS sheets (pole numbers match program and diagram numbers). |  | Nil - Visual Check | Each pole | M | PE
|  | Controller cabinet fitted with Site ID Number sticker. | Project Specification Apendix E 3.6 | Nil - Visual Check | Each controller cabinet/intersection | M | PE
3.2.6 | Mow Strip / Concrete Surrounds | Access chambers installed in the berm surrounded by 300mm wide concrete apron to 100mm deep. 25MPa 28-day compressive strength concrete. | NZTA P43 4.4.2 | Nil - Visual Check | Each access chamber in the berm | M | PE / TSL
|  | KSJB to have 150mm wide concrete surround to a depth of 150mm. | NZTA P43 4.7 | Nil - Visual Check | Each KSJB in the berm | M | PE
|  | Controller cabinet to be surrounded by 300mm wide concrete apron around the base of the controller, widened to 900mm on the side adjacent to the door. 100mm thick, with slight fall away from conroller. | NZTA P43 3.6 | Nil - Visual Check | Each controller cabinet | M | PE
3.3 | Cabling and Electrical Testing
3.3.1 | Loop Cutting | Rubberised bitument adhesive sealant applied to all saw cuts in the roadway | Project Specification Appendix E 3.11 | Nil - Visual Check | All saw cuts | M | PE
|  | Saw cuts made through kerb and channel to be sealed with epoxy resin motar. | Project Specification Appendix E 4.7 | Nil - Visual Check | All saw cuts | M | PE
3.3.2 | Loop Electrical Testing | 500V test from the isolated conductors down to earth. Results: Result ≥ 10 megaohms. Q ≥ 15 when measured in the kerbside junction box (KJB). Submit results signed by technician who conducted the testing and in a report. | NZTA P43 3.11.1 | Test Results/Certificate | Each loop | M | TSL
3.3.3 | Cable Slack | - minimum 2.0m cable slack in controller left at the controller base - minimum 1m slack left in access chambers on all cable runs. | NZTA P43 4.4.3 | Nil - Visual Check | Each intersection | M | TSL
3.3.4 | Electrical Certification | Completed and signed certificate of electrical compliance. | NZTA P43 3.16 | Certificate | 1 per intersection prior to commissioning. | H | TSL
3.3.5 | CCTV Installation | - All traffic lanes visible at intersection limit line. - Required viewing distance down each leg achieved. - Viewing Optimised for legs with adjacent signalised intersections | Project Specification Appendix E 3.19.2 | Nil |  | M | TSL
|  | Site assessment plan showing location and visibility of the proposed camera to be proved to HCC. | Project Specification Appendix E 3.19.2 | Plan |  | H | TSL
|  | HCC to approve of final camera location prior to instllation. | Project Specification Appendix E 3.19.2 | Written correspondence |  | H | HCC / WTOC
3.3.6 | Communications Connection | Initial site coverage testing and scoping complete. | Project Specification Appendix E 3.18 | Written correspondence |  | H | HCC / WTOC
|  | Power supply to the radio and CAT6 shielded outdoor grade cable running from the controller to the radio mount location. | Project Specification Appendix E 3.18 | Nil |  | M | TSL
3.4 | Site Acceptance and Commissioning
3.4.1 | SCATS Connection | Signals contractor to notify City Transportation Unit (CTU) Operations Room at least 1 week before SCATS commnications will be available from the controller. | Project Specification Appendix E 3.15.4 | Email Record | 1 week prior to SCATS communication being available from controller | M | PE / TSL
|  | SCATS comminication achieved for a minimum of 48hours prior to comissioning. | Project Specification Appendix E 3.15.4 | In-Eight record of maintained HCC/CTU SCATS contact. | Min 48hrs prior to comissioning | H | PE / HCC / TSL
3.4.2 | Documents | Cable termination chart, CIS and logbook placed in document pocket inside controller cabinet. | NZTA P43 3.16 | Nil - Visual Check | Within 2 weeks of commissioning | H | PE
3.4.3 | Approval to Commission | RCA traffic signals representative (City Transportation) approval to switch on. | Project Specification Appendix E 3.15.4 | In-Eight Approval/Acknowledgement | Once per intersection | H | PE
3.4.4 | Site Acceptance Chart | Site Acceptance Test Chart to be filled out and signed. | Project Specification E 3.15.4 | SAT Form | Once per intersection | H | TSL
SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
4.1 | General
4.1.1 | Producer Statements | PS1 Design Producer Statement from Chartered Professional Engineer | Project Specification Appendix E 3.16 | Producer Statement 1 | Each Pole Post-Installation | H
|  | PS3 Certificate to be accompanied by photographic evidence of each pole (see requirement above). | Project Specification Appendix E 3.16 | Producer Statement 3 | Each Pole Post-Installation | H
4.1.2 | Site Handover/Acceptance | Approval from Hamilton City Council and the signals maintenance contractor. | Project Specification Appendix E 2.2.2 | In-Eight Documented Approval/Acknowledgement | Post Works Completion | H
4.1.3 | Survey As-Builts | Asbuilts reviewed and submitted showing final location of all poles, access chambers, KSJB, loops and cabinets. | Project Specification | Survey Data As Built Drawings Photographs Red Pen As-Builts including Undercuts | Post Works Completion | H
Note on C63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Required for Prac Completion

## ITP Master Body (Edited)
Traffic Signals Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.1 | General
1.1.1 | Drawings | Prior to starting works, ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to work planning and start | M | PE
1.1.2 | Construction Pack | ITP to be submitted to the Engineer and approved prior to works beginning | Downer | In-Eight Document Approval/Acknowledgement | Submit 10 days prior to commencement of works | H | PE
|  | Methodology and associated documents to be prepared, reviewed and approved internally prior to work commencement. | Downer | Construction Pack Sign Off | Prior to Construction & after any major incident | M | PE
1.1.3 | Survey Set-out | Ensure traffic signal pole, access chamber, and controller cabinet locations are set out per IFC drawings/data. | Design Drawings | ITP Sign Off | Prior to Construction & Every Revision of IFC Drgs / Data | M | PE
1.1.4 | Walk-over | HCC Traffic Engineer, BBO Designer and MSQA rep to walk over and confirm pole locations. HCC 1st Contact: Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport DDI: (07) 838 6638 Mob: 0278086506 Email: Brandon.Harley@HCC.govt.nz HCC Alt Contact: Holly Blackley - Senior Transport Network Operator HCC City Transport DDI: (07) 838 6817 Mob: 0278087593 Email: Holly.Blackley@hcc.govt.nz HCC 2nd Alt Contact: John Kinghorn - HCC City Transport Mobile: Email: John.Kinghorn@hcc.govt.nz BBO MSQA Contact: Emil Karlsson - Intermediate Site Engineer Mobile: 0273371065 Email: ekarlsson@bbo.co.nz BBO MSQA Alt Contact: Ryan Fergusson - Senior Site Engineer Mobile: 0274060378 Email: rfergusson@bbo.co.nz BBO MSQA 2nd Alt Contact: Zion Nordstrom - Email: znordstrom@bbo.co.nz BBO Designer: TBC - MSQA to contact/bring with. | Design Drawings | Written correspondence / Photographs | Prior to construction | H | PE
|  | BBO/HCC written confirmation of any changes made to pole positions. | BBO Requirement | Written Correspondence (InEight preferred) | Post walkover, and prior to installation | H | BBO / HCC / WTOC
1.1.5 | Environmental Protection | Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events | Project ESCP Plans | ITP Sign Off | Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events | M | PE
1.1.6 | Stakeholder | Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners | Project Stakeholder Management Plan | ITP Sign Off | Prior to Construction with continue updates throughout the works | M | PE
1.1.7 | Permits | Ground Disturbance Permit must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. Doner Permit encompasses external provider permit requirements. All known services must be clearly marked on site and briefed to the workforce . | Section 2.2.10 Project Specification | Ground Disturbance Permit DN-ZH-FM043.1 | Prior to Construction Reviewed and Reissued weekly or when site conditions change | H | PE
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2.1 | General
2.1.1 | Pole Producer Statements | PS1 certificate required for all pole types. | Project Specification Apendix E 3.16 | PS1 Certificates | Prior to pole acquisition | H | PE
2.1.2 | Controller Cabinet | Unless otherwise specified, VC6 ELV controller (compatible with latest SCATS software) fitted with a generator socket matching existing HCC controller cabinet colours. Must be fitted with a sticker indicating the Site ID Number. | Project Specification Apendix E 2.3.5/2.3.6/3.6 | Nil - Visual Check | Each controller/intersection | M | PE/TSL
2.1.3 | Site ID Number | HCC to provide Site ID number. | Project Specification Apendix E 3.6 | Written correspondence | Prior to commissioning | M | PE / HCC/WTOC
2.1.4 | CCTV camera | HCC must approve of traffic monitoring camera which should meet requirements. Hardware is required to have a minimum 12 months warranty period. HCC preference is an Axis Q6075-E along with an Axis Q6010-E, using the Axis T91L61 pole mounts. | Project Specification Appendix E 3.19.1 | Written correspondence | Prior to material acquisition | M | PE/TSL
2.1.5 | Communications Connection | Engage HCC to engage Lightwire. Project team to coordinate with for on-site installation. | Project Specification Apendix E 3.18 | Written correspondence | 3 months prior to connection | M | PE
2.1.6 | Electrical Connection | Apply for new commercial electrical connection via the WEL Networks website/login for each new signalised intersection (NC1 Form). Traffic signals subontractor to confirm electrical requirements. | Project Specification Appendix E 3.3 | Approval document/NC1 Form with ICP number | 3 months prior to connection | M | PE
SECTION 3 – CONSTRUCTION ACTIVITY
3.1 | Software
3.1.1 | Software/personality files and CIS | HCC to provide to contractor (Downer or TSL). Contact (s): John Kinghorn - HCC City Transport Mobile: Email: John.Kinghorn@hcc.govt.nz Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport DDI: (07) 838 6638 Mob: 0278086506 Email: Brandon.Harley@HCC.govt.nz | Project Specification Appendix E 3.15.3 | In-Eight Documents/Mail | Requested at least 6 weeks prior to bench testing date. | H | HCC / WTOC
3.1.2 | Bench Test | Traffic signals contractor to bench test files. | NZTA P43 3.15.4 | PDF Document | Once per intersection, at least 1 week prior to comissioning | H | PE / TSL
3.2 | Civil (Pole / Cabinet / Access Chamber) Installations
3.2.1 | Soil Bearing Strength | Report results. Check this meets poles deisgn (i.e. >= 50kPa). | Drawings/PS1/NZTA P43 2.5.1.3 | Shear Vane | One pole per intersection corner (i.e. north-west, north-east etc) | M | PE / TSL
3.2.2 | Pole Base Photograph | Photographic evidence of each pole base to be submitted as part of PS3 | Project Specification Appendix E 3.16 | Photographs | Each pole base prior to foundation pour. | M | TSL
3.2.5 | Identification Numbers | Ensure poles are fitted with/displaying the correct number and match the CIS sheets (pole numbers match program and diagram numbers). |  | Nil - Visual Check | Each pole | M | PE
|  | Controller cabinet fitted with Site ID Number sticker. | Project Specification Apendix E 3.6 | Nil - Visual Check | Each controller cabinet/intersection | M | PE
3.2.6 | Mow Strip / Concrete Surrounds | Access chambers installed in the berm surrounded by 300mm wide concrete apron to 100mm deep. 25MPa 28-day compressive strength concrete. | NZTA P43 4.4.2 | Nil - Visual Check | Each access chamber in the berm | M | PE / TSL
|  | KSJB to have 150mm wide concrete surround to a depth of 150mm. | NZTA P43 4.7 | Nil - Visual Check | Each KSJB in the berm | M | PE
|  | Controller cabinet to be surrounded by 300mm wide concrete apron around the base of the controller, widened to 900mm on the side adjacent to the door. 100mm thick, with slight fall away from conroller. | NZTA P43 3.6 | Nil - Visual Check | Each controller cabinet | M | PE
3.3 | Cabling and Electrical Testing
3.3.1 | Loop Cutting | Rubberised bitument adhesive sealant applied to all saw cuts in the roadway | Project Specification Appendix E 3.11 | Nil - Visual Check | All saw cuts | M | PE
|  | Saw cuts made through kerb and channel to be sealed with epoxy resin motar. | Project Specification Appendix E 4.7 | Nil - Visual Check | All saw cuts | M | PE
3.3.2 | Electrical Certification (COC)/ Record of Inspection (ROI) | Completed and signed certificate of electrical compliance. | NZTA P43 3.16 | Certificate | 1 per intersection prior to commissioning. | H | TSL
3.4 | Site Acceptance and Commissioning
3.4.1 | SCATS Connection | Signals contractor to notify City Transportation Unit (CTU) Operations Room at least 1 week before SCATS commnications will be available from the controller. | Project Specification Appendix E 3.15.4 | Written correspondence | 1 week prior to SCATS communication being available from controller | M | PE / TSL
|  | SCATS comminication achieved for a minimum of 48hours prior to comissioning. | Project Specification Appendix E 3.15.4 | Written correspondence | Min 48hrs prior to comissioning | M | PE / HCC / TSL
3.4.2 | Documents | Cable termination chart, CIS and logbook placed in document pocket inside controller cabinet. | NZTA P43 3.16 | Nil - Visual Check | Within 2 weeks of commissioning | H | PE
3.4.3 | Approval to Commission | RCA traffic signals representative (City Transportation) approval to switch on. | Project Specification Appendix E 3.15.4 | Written correspondence | Once per intersection | H | PE
3.4.4 | Site Acceptance Chart | Site Acceptance Test Chart to be filled out and signed. | Project Specification E 3.15.4 | SAT Form | Once per intersection | H | TSL
SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
4.1 | General
4.1.1 | Producer Statements | PS1 Design Producer Statement from Chartered Professional Engineer | Project Specification Appendix E 3.16 | Producer Statement 1 | Each Pole Type | H
|  | PS3 Certificate to be accompanied by photographic evidence of each pole (see requirement above). | Project Specification Appendix E 3.16 | Producer Statement 3 | Each Pole Post-Installation | H
4.1.2 | Site Handover/Acceptance | Approval from Hamilton City Council and the signals maintenance contractor. | Project Specification Appendix E 2.2.2 | Written Correspondence | Post Signal Works Completion | H
4.1.3 | Survey As-Builts | Asbuilts reviewed and submitted showing final location of all poles, access chambers, KSJB, loops and cabinets. | Project Specification | Survey Data As Built Drawings Photographs Red Pen As-Builts including Undercuts | Post-installation | H