## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Traffic Signals - Rev B | itp |  |  |  |  | ITP - Traffic Signals - Rev B
section | 1.1 - General
checkpoint | 1.1.1 - Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to work planning and start
label | Activity - M
label | By - PE
checkpoint | 1.1.2 - Construction Pack (1)
label | Acceptance / Conformance Criteria - ITP to be submitted to the Engineer and approved prior to works beginning
label | Standard / Specification - Downer
label | Verifying Document - In-Eight Document Approval/Acknowledgement
label | Frequency - Submit 10 days prior to commencement of works
label | Activity - H
label | By - PE
checkpoint | 1.1.2 - Construction Pack (2)
label | Acceptance / Conformance Criteria - Methodology and associated documents to be prepared, reviewed and approved internally prior to work commencement.
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack Sign Off
label | Frequency - Prior to Construction & after any major incident
label | Activity - M
label | By - PE
checkpoint | 1.1.3 - Survey Set-out
label | Acceptance / Conformance Criteria - Ensure traffic signal pole, access chamber, and controller cabinet locations are set out per IFC drawings/data.
label | Standard / Specification - Design Drawings
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
label | Activity - M
label | By - PE
checkpoint | 1.1.4 - Walk-over (1)
label | Acceptance / Conformance Criteria - HCC Traffic Engineer, BBO Designer and MSQA rep to walk over and confirm pole locations.
label | – – – – – – – – – – – – – – –
label | HCC 1st Contact:
label | ○ Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport
label | ○ DDI: (07) 838 6638
label | ○ Mob: 0278086506
label | ○ Email: Brandon.Harley@HCC.govt.nz
label | – – – – – – – – – – – – – – –
label | HCC Alt Contact:
label | ○ Holly Blackley - Senior Transport Network Operator HCC City Transport
label | ○ DDI: (07) 838 6817
label | ○ Mob: 0278087593
label | ○ Email: Holly.Blackley@hcc.govt.nz
label | – – – – – – – – – – – – – – –
label | HCC 2nd Alt Contact:
label | ○ John Kinghorn - HCC City Transport
label | ○ Mobile:
label | ○ Email: John.Kinghorn@hcc.govt.nz
label | – – – – – – – – – – – – – – –
label | BBO MSQA Contact:
label | ○ Emil Karlsson - Intermediate Site Engineer
label | ○ Mobile: 0273371065
label | ○ Email: ekarlsson@bbo.co.nz
label | – – – – – – – – – – – – – – –
label | BBO MSQA Alt Contact:
label | ○ Ryan Fergusson - Senior Site Engineer
label | ○ Mobile: 0274060378
label | ○ Email: rfergusson@bbo.co.nz
label | – – – – – – – – – – – – – – –
label | BBO MSQA 2nd Alt Contact:
label | ○ Zion Nordstrom -
label | ○ Email: znordstrom@bbo.co.nz
label | – – – – – – – – – – – – – – –
label | BBO Designer:
label | ○ TBC - MSQA to contact/bring with.
label | – – – – – – – – – – – – – – –
label | Standard / Specification - Design Drawings
label | Verifying Document - Written correspondence / Photographs
label | Frequency - Prior to construction
label | Activity - H
label | By - PE
checkpoint | 1.1.4 - Walk-over (2)
label | Acceptance / Conformance Criteria - BBO/HCC written confirmation of any changes made to pole positions.
label | Standard / Specification - BBO Requirement
label | Verifying Document - Written Correspondence (InEight preferred)
label | Frequency - Post walkover, and prior to installation
label | Activity - H
label | By - BBO / HCC / WTOC
checkpoint | 1.1.5 - Environmental Protection
label | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans. Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events.
label | Standard / Specification - Project ESCP Plans
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to Construction. Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events.
label | Activity - M
label | By - PE
checkpoint | 1.1.6 - Stakeholder
label | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works. Agree plans for maintaining access to properties during construction with landowners.
label | Standard / Specification - Project Stakeholder Management Plan
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to Construction with continue updates throughout the works
label | Activity - M
label | By - PE
checkpoint | 1.1.7 - Permits
label | Acceptance / Conformance Criteria - Ground Disturbance Permit must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip.
label | ○ Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. Doner Permit encompasses external provider permit requirements.
label | ○ All known services must be clearly marked on site and briefed to the workforce .
label | Standard / Specification - Section 2.2.10 Project Specification
label | Verifying Document - Ground Disturbance Permit, DN-ZH-FM043.1
label | Frequency - Prior to Construction. Reviewed and Reissued weekly or when site conditions change.
label | Activity - H
label | By - PE
section | 2.1 - General
checkpoint | 2.1.1 - Pole Producer Statements
label | Acceptance / Conformance Criteria - PS1 certificate required for all pole types.
label | Standard / Specification - Project Specification Apendix E 3.16
label | Verifying Document - PS1 Certificates
label | Frequency - Prior to pole acquisition
label | Activity - H
label | By - PE
checkpoint | 2.1.2 - Controller Cabinet
label | Acceptance / Conformance Criteria - Unless otherwise specified, VC6 ELV controller (compatible with latest SCATS software) fitted with a generator socket matching existing HCC controller cabinet colours.
label | ○ Must be fitted with a sticker indicating the Site ID Number.
label | Standard / Specification - Project Specification Apendix E 2.3.5/2.3.6/3.6
label | Verifying Document - Nil - Visual Check
label | Frequency - Each controller/intersection
label | Activity - M
label | By - PE/TSL
checkpoint | 2.1.3 - Site ID Number
label | Acceptance / Conformance Criteria - HCC to provide Site ID number.
label | Standard / Specification - Project Specification Apendix E 3.6
label | Verifying Document - Written correspondence
label | Frequency - Prior to commissioning
label | Activity - M
label | By - PE / HCC/WTOC
checkpoint | 2.1.4 - CCTV camera
label | Acceptance / Conformance Criteria - HCC must approve of traffic monitoring camera which should meet requirements. Hardware is required to have a minimum 12 months warranty period.
label | ○ HCC preference is an Axis Q6075-E along with an Axis Q6010-E, using the Axis T91L61 pole mounts.
label | Standard / Specification - Project Specification Appendix E 3.19.1
label | Verifying Document - Written correspondence
label | Frequency - Prior to material acquisition
label | Activity - M
label | By - PE/TSL
checkpoint | 2.1.5 - Communications Connection
label | Acceptance / Conformance Criteria - Engage HCC to engage Lightwire. Project team to coordinate with for on-site installation.
label | Standard / Specification - Project Specification Apendix E 3.18
label | Verifying Document - Written correspondence
label | Frequency - 3 months prior to connection
label | Activity - M
label | By - PE
checkpoint | 2.1.6 - Electrical Connection
label | Acceptance / Conformance Criteria - Apply for new commercial electrical connection via the WEL Networks website/login for each new signalised intersection (NC1 Form).
label | ○ Traffic signals subontractor to confirm electrical requirements.
label | Standard / Specification - Project Specification Appendix E 3.3
label | Verifying Document - Approval document/NC1 Form with ICP number
label | Frequency - 3 months prior to connection
label | Activity - M
label | By - PE
section | 3.1 - Software
checkpoint | 3.1.1 - Software/personality files and CIS
label | Acceptance / Conformance Criteria - HCC to provide to contractor (Downer or TSL).
label | Contact (s):
label | – – – – – – – – – – – – – – –
label | John Kinghorn - HCC City Transport
label | ○ Mobile:
label | ○ Email: John.Kinghorn@hcc.govt.nz
label | – – – – – – – – – – – – – – –
label | Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport
label | ○ DDI: (07) 838 6638
label | ○ Mob: 0278086506
label | ○ Email: Brandon.Harley@HCC.govt.nz
label | – – – – – – – – – – – – – – –
label | Standard / Specification - Project Specification Appendix E 3.15.3
label | Verifying Document - In-Eight Documents/Mail
label | Frequency - Requested at least 6 weeks prior to bench testing date.
label | Activity - H
label | By - HCC / WTOC
checkpoint | 3.1.2 - Bench Test
label | Acceptance / Conformance Criteria - Traffic signals contractor to bench test files.
label | Standard / Specification - NZTA P43 3.15.4
label | Verifying Document - PDF Document
label | Frequency - Once per intersection, at least 1 week prior to comissioning
label | Activity - H
label | By - PE / TSL
section | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
checkpoint | 3.2.1 - Soil Bearing Strength
label | Acceptance / Conformance Criteria - Report results. Check this meets poles deisgn (i.e. >= 50kPa).
label | Standard / Specification - Drawings/PS1/NZTA P43 2.5.1.3
label | Verifying Document - Shear Vane
label | Frequency - One pole per intersection corner (i.e. north-west, north-east etc)
label | Activity - M
label | By - PE / TSL
checkpoint | 3.2.2 - Pole Base Photograph
label | Acceptance / Conformance Criteria - Photographic evidence of each pole base to be submitted as part of PS3
label | Standard / Specification - Project Specification Appendix E 3.16
label | Verifying Document - Photographs
label | Frequency - Each pole base prior to foundation pour.
label | Activity - M
label | By - TSL
checkpoint | 3.2.5 - Identification Numbers (1)
label | Acceptance / Conformance Criteria - Ensure poles are fitted with/displaying the correct number and match the CIS sheets (pole numbers match program and diagram numbers).
label | Verifying Document - Nil - Visual Check
label | Frequency - Each pole
label | Activity - M
label | By - PE
checkpoint | 3.2.5 - Identification Numbers (2)
label | Acceptance / Conformance Criteria - Controller cabinet fitted with Site ID Number sticker.
label | Standard / Specification - Project Specification Apendix E 3.6
label | Verifying Document - Nil - Visual Check
label | Frequency - Each controller cabinet/intersection
label | Activity - M
label | By - PE
checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (1)
label | Acceptance / Conformance Criteria - Access chambers installed in the berm surrounded by 300mm wide concrete apron to 100mm deep. 25MPa 28-day compressive strength concrete.
label | Standard / Specification - NZTA P43 4.4.2
label | Verifying Document - Nil - Visual Check
label | Frequency - Each access chamber in the berm
label | Activity - M
label | By - PE / TSL
checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (2)
label | Acceptance / Conformance Criteria - KSJB to have 150mm wide concrete surround to a depth of 150mm.
label | Standard / Specification - NZTA P43 4.7
label | Verifying Document - Nil - Visual Check
label | Frequency - Each KSJB in the berm
label | Activity - M
label | By - PE
checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (3)
label | Acceptance / Conformance Criteria - Controller cabinet to be surrounded by 300mm wide concrete apron around the base of the controller, widened to 900mm on the side adjacent to the door. 100mm thick, with slight fall away from conroller.
label | Standard / Specification - NZTA P43 3.6
label | Verifying Document - Nil - Visual Check
label | Frequency - Each controller cabinet
label | Activity - M
label | By - PE
section | 3.3 - Cabling and Electrical Testing
checkpoint | 3.3.1 - Loop Cutting (1)
label | Acceptance / Conformance Criteria - Rubberised bitument adhesive sealant applied to all saw cuts in the roadway
label | Standard / Specification - Project Specification Appendix E 3.11
label | Verifying Document - Nil - Visual Check
label | Frequency - All saw cuts
label | Activity - M
label | By - PE
checkpoint | 3.3.1 - Loop Cutting (2)
label | Acceptance / Conformance Criteria - Saw cuts made through kerb and channel to be sealed with epoxy resin motar.
label | Standard / Specification - Project Specification Appendix E 4.7
label | Verifying Document - Nil - Visual Check
label | Frequency - All saw cuts
label | Activity - M
label | By - PE
checkpoint | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
label | Acceptance / Conformance Criteria - Completed and signed certificate of electrical compliance.
label | Standard / Specification - NZTA P43 3.16
label | Verifying Document - Certificate
label | Frequency - 1 per intersection prior to commissioning.
label | Activity - H
label | By - TSL
section | 3.4 - Site Acceptance and Commissioning
checkpoint | 3.4.1 - SCATS Connection (1)
label | Acceptance / Conformance Criteria - Signals contractor to notify City Transportation Unit (CTU) Operations Room at least 1 week before SCATS commnications will be available from the controller.
label | Standard / Specification - Project Specification Appendix E 3.15.4
label | Verifying Document - Written correspondence
label | Frequency - 1 week prior to SCATS communication being available from controller
label | Activity - M
label | By - PE / TSL
checkpoint | 3.4.1 - SCATS Connection (2)
label | Acceptance / Conformance Criteria - SCATS comminication achieved for a minimum of 48hours prior to comissioning.
label | Standard / Specification - Project Specification Appendix E 3.15.4
label | Verifying Document - Written correspondence
label | Frequency - Min 48hrs prior to comissioning
label | Activity - M
label | By - PE / HCC / TSL
checkpoint | 3.4.2 - Documents
label | Acceptance / Conformance Criteria - Cable termination chart, CIS and logbook placed in document pocket inside controller cabinet.
label | Standard / Specification - NZTA P43 3.16
label | Verifying Document - Nil - Visual Check
label | Frequency - Within 2 weeks of commissioning
label | Activity - H
label | By - PE
checkpoint | 3.4.3 - Approval to Commission
label | Acceptance / Conformance Criteria - RCA traffic signals representative (City Transportation) approval to switch on.
label | Standard / Specification - Project Specification Appendix E 3.15.4
label | Verifying Document - Written correspondence
label | Frequency - Once per intersection
label | Activity - H
label | By - PE
checkpoint | 3.4.4 - Site Acceptance Chart
label | Acceptance / Conformance Criteria - Site Acceptance Test Chart to be filled out and signed.
label | Standard / Specification - Project Specification E 3.15.4
label | Verifying Document - SAT Form
label | Frequency - Once per intersection
label | Activity - H
label | By - TSL
section | 4.1 - General
checkpoint | 4.1.1 - Producer Statements (1)
label | Acceptance / Conformance Criteria - PS1 Design Producer Statement from Chartered Professional Engineer
label | Standard / Specification - Project Specification Appendix E 3.16
label | Verifying Document - Producer Statement 1
label | Frequency - Each Pole Type
label | Activity - H
checkpoint | 4.1.1 - Producer Statements (2)
label | Acceptance / Conformance Criteria - PS3 Certificate to be accompanied by photographic evidence of each pole (see requirement above).
label | Standard / Specification - Project Specification Appendix E 3.16
label | Verifying Document - Producer Statement 3
label | Frequency - Each Pole Post-Installation
label | Activity - H
checkpoint | 4.1.2 - Site Handover/Acceptance
label | Acceptance / Conformance Criteria - Approval from Hamilton City Council and the signals maintenance contractor.
label | Standard / Specification - Project Specification Appendix E 2.2.2
label | Verifying Document - Written Correspondence
label | Frequency - Post Signal Works Completion
label | Activity - H
checkpoint | 4.1.3 - Survey As-Builts
label | Acceptance / Conformance Criteria - Asbuilts reviewed and submitted showing final location of all poles, access chambers, KSJB, loops and cabinets.
label | Standard / Specification - Project Specification
label | Verifying Document - Survey Data, As Built Drawings, Photographs, Red Pen As-Builts including Undercuts
label | Frequency - Post-installation
label | Activity - H