## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-006 - Subgrade Preparation | itp |  |  |  | Yes | ITP-006 - Subgrade Preparation | 16449355-1a7c-47ef-8edc-6ddd3694e88e
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | 893bf6e7-4a37-5e97-8daf-b37da26c3297 |  | note | FREQUENCY: Prior to Commencing
label | 0c7b93f6-7db2-540c-aecd-1477392e27b9 |  | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | def5be00-4967-5b88-8c2b-a6df254f60c1 |  | note | REFERENCE DOCUMENTS: Inductions Register
label | 3a30e32e-a8c9-5e49-aa53-1a8a0d00ac04 |  | note | INSPECTION/TEST METHOD: Document review
label | 532e37f1-bd01-53d9-8143-0a171a5acce9 |  | note | RECORD OF CONFORMITY: Site induction signed.
label | c98742b8-a127-5d7b-a54e-08751eee13b5 |  | note | AP
label | 60611175-0076-5591-9912-a3a9dff10e9c |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | a3fa2af0-f757-5488-9282-40f1f6eceaa9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Check that current revision drawings are being used
label | bdc056ee-04cb-505f-af82-c5b9961b5595 |  | note | FREQUENCY: Prior to Commencing
label | a36f5aa4-3c66-5cc7-984e-bd3bf0ced9ed |  | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | 4e6c9278-864f-58bd-976f-a5afe1b5d886 |  | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | a026163f-b2b8-5f8f-a5bc-0b21a59126ea |  | note | INSPECTION/TEST METHOD: Document review
label | 3a83636a-fec1-5969-9816-5a578c42a1fe |  | note | RECORD OF CONFORMITY: Latest Revision Drawings
label | 09e1e12d-e74e-55b8-a946-e0ec050fa34e |  | note | AP
label | d958188a-c80f-5753-b263-2bfb4b8854a1 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | b958c8ab-a6ce-5dc1-8a75-4b0352f75276 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | e7017621-0cfc-55c5-9f17-b0345534be26 |  | note | FREQUENCY: Prior to Commencing
label | 1d3bbcfb-f7d6-5426-b2f2-2eb34c3cdf3f |  | note | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
label | 1e8b288b-998d-5c0c-9c4a-118fe68ebca4 |  | note | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | 417d22b2-574f-522e-bfa0-246aff7e2bda |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | cb959529-3a6d-5053-a2ab-1801d0ff13b3 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 672cd9bb-ce54-599d-a893-4473b395ecfe |  | note | IP
label | ccc3ae67-eb44-52cd-aa25-396f3f848492 |  | note | RESPONSIBILITY: Site Engineer
date | 35114ee1-361c-557f-980b-4226f236600a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | 9d513e59-9c51-5725-a309-f6b1181245ee |  | note | FREQUENCY: Prior to commencing
label | 36ac7f83-0777-5641-9e38-dbf938e0b89a |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | cfbb40de-f0d3-5351-a29a-a8bf23ed03fd |  | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS
label | d5c32734-b0ae-5178-9b07-cacd5d2abaa4 |  | note | INSPECTION/TEST METHOD: Document Review
label | ab92b676-8e11-5292-8a26-1c08d8b2bc6a |  | note | RECORD OF CONFORMITY: SWMS(s) signed
label | a744c05b-aa74-54df-aa28-220a5fe60400 |  | note | IP
label | dfdc9882-0853-5695-a42c-f8645f3a5891 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | 5d14e63d-ffc1-5990-9edf-eef6154950ab |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Excavation Permit issued
label | dd87bc67-d17a-5ad2-89fc-188c63f96e98 |  | note | FREQUENCY: Prior to commencing
label | 53e72493-b72f-548c-acbd-808a6bc33efe |  | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | 9c804df4-319e-549b-aece-02d596be7942 |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | ba2701e1-9103-5996-a918-0cd167979603 |  | note | INSPECTION/TEST METHOD: Document Review
label | 6365ccc2-d64e-52b7-8f76-682003a16a1f |  | note | RECORD OF CONFORMITY: Excavation Permit No.
label | cf7c0e91-9975-5aa9-8999-72e2e8a5c819 |  | note | IP
label | 51745aa2-24bd-5eb0-b0d6-5b41ba90897b |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | 5c20de5f-6b8a-5cf7-8fc2-3301518f28ec |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Survey set-out
label | 66fde403-149c-5687-9492-7c28e1cff864 |  | note | FREQUENCY: Prior to Commencing
label | 0bbdcc30-957b-55fe-aea4-1d785eb7d8a1 |  | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
label | bd82983e-e687-5cd6-8cae-84bcf3ef5c7a |  | note | REFERENCE DOCUMENTS: Project Spec.Cl.1190.07 Latest IFC Drawings
label | 5ec26b93-4d9f-5b33-a638-90a4dfaff128 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 613a91f0-01e3-5806-9eff-bac8cb7bc70b |  | note | RECORD OF CONFORMITY: Compliance with latest IFC drawings, Survey records & pegs on the ground
label | efe42d6d-afbb-5752-9e8b-68cf8bb4ec04 |  | note | SCP
label | ab70864f-7102-5c3e-8315-3883d629a041 |  | note | RESPONSIBILITY: Site Engineer & Surveyor
date | 1445b69f-ec4c-51fa-abd7-60a7e9ea032f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Unsuitable Material
label | d5d17da1-21d2-590e-8024-1b6cbacf876d |  | note | FREQUENCY: During Excavation
label | 7fd2b6f2-5cec-5800-a897-c12bc6f90b6d |  | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
label | 209bea5a-c683-5b9e-bd77-9641b9eb974d |  | note | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
label | 7811d46b-b29f-5bb9-91f8-ed3cbd64b17a |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | 4679e61f-7512-5f80-9906-fc4df0a3b6b9 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 85312a1f-c544-5a69-9f2c-a1c578fef775 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | e3641447-0898-52c2-be74-4dc29731e9f8 |  | note | IP
label | 74712886-2198-5ee6-8295-1a69b389829a |  | note | RESPONSIBILITY: Project Engineer
date | 7b7bae2a-ddf3-5648-9d9c-e13054c46a1a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Material Category
label | 317e53c1-5eaa-559b-a639-400ec63f06ba |  | note | FREQUENCY: Prior to Commencing
label | 1165c866-219f-53b5-a477-c76c5f51daaa |  | note | ACCEPTANCE CRITERIA: Prior excavation, Superintendent and Fulton Hogan responsible shall inspect each type of material encountered and, subject to verification by laboratory testing, agree on category of material in accordance with VicRoads Spec Section 204.04
label | f1d21ef8-fc9d-5072-b499-3f3017c7840c |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04, Cl. 204.06(c)
label | d6ae6b51-4cf7-5595-90dc-a0cbf13a3f14 |  | note | INSPECTION/TEST METHOD: Document Review
label | 1ffc463b-1c56-5ec2-a7b7-d1efd5ea830d |  | note | RECORD OF CONFORMITY: Superintendent agreement, Signed ITP
label | 96c8ba78-10c6-5cb7-a7f7-d5a346f1c412 |  | note | HP
label | e6a306d9-6668-5b75-a725-bb602059461b |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | e0f6c0c5-480c-58c4-8117-d3e2b8dc5988 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Trimming and level conformity
label | df14cb0d-c992-50b2-9725-2808c9bd183c |  | note | FREQUENCY: Each Lot (one day's production) prior to Commencing
label | f5bc2bac-b331-5e16-b739-5152f4a0f335 |  | note | ACCEPTANCE CRITERIA: Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping not differ by more than 5 mm above or 15 mm below the specified level.
label | ee3a679b-bcc8-5018-83e4-9368030baa00 |  | note | ○ Level at any point of sugbrade shall not lie more than 20mm below a 3m straightedge in any direction excepting crowns.
label | 15df3915-88e2-55cb-b1cd-d16f26a4d400 |  | note | ○ Water shall not pond at any point.
label | 79c5e3b1-a9d1-5a99-bd9d-d29e974d996f |  | note | ○ The mean and standard deviation of the departures from the theoretical surface level within each lot shall meet the requirements of Table 204.031.
label | 35e6a1c1-c278-5dce-9118-0f936e48c964 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.03(f), Cl. 204.03(g) Table 204.031
label | 8eb8f17d-95a9-52a8-8fad-c350578bbb16 |  | note | INSPECTION/TEST METHOD: Survey Report
label | 7a282bb2-edfd-58fd-8573-9a0659819bbe |  | note | RECORD OF CONFORMITY: Survey Record
label | ab04b6ea-7547-5fd7-92b4-b96d823f163a |  | note | SCP
label | 0db7a13e-cc3e-591f-ad6b-a48303a8e7f7 |  | note | RESPONSIBILITY: Site Engineer & Surveyor
date | d51e30a1-c527-595e-b5c3-8506450f966c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Acceptance of Rock Subgrade (when applicable)
label | a7a5d32a-c678-50f8-a5e9-34559483936f |  | note | FREQUENCY: Prior construction of the regulating layer
label | c46c1830-0f78-5815-96ff-c32ee106b251 |  | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | 0b87a394-2a75-5ab3-a136-f9364ba24ad4 |  | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | 6b243f3b-5ddb-5e2b-8d61-51d6879d9851 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | 80f208e1-1153-5aee-a642-688a25c6e122 |  | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | 7d09a166-7d76-5a0a-994e-81097615f54f |  | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | 7eaad319-592a-51a1-ba38-fb365941dfd5 |  | note | HP
label | 08d2ab3f-625d-59d7-b769-427a8666e567 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | f1ae0d60-7a47-58cc-989b-328d43c88ed6 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Cut to Fill Zones
label | 1829d5de-ffc0-5296-ad22-e09a5388f261 |  | note | FREQUENCY: Each Lot (one day's production) prior to Commencing
label | a6b19c65-046b-529f-8cd7-b81b1317e265 |  | note | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type B material.
label | 8933b6aa-ae1c-5ce7-9c7e-d274a418109f |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(g)
label | 3c91cb08-0a92-5a0c-9f97-29b3580fafe1 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 1f35f6bd-a001-5347-86a9-362e2d2f6c49 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 1141d029-2992-58db-85fd-d5114c9791c5 |  | note | IP
label | 459210f4-cca1-5c2b-aac3-ec6522a6e5fe |  | note | RESPONSIBILITY: Site Engineer
date | d035bd15-365e-50ca-86c5-92088877ed11 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Testing for Compaction and Material Properties
checkpoint-status |  |  | checkpoint | 3.1 - Proof Rolling
label | 1a08cbe4-77b3-5b3f-8b1e-673f7934c4b9 |  | note | FREQUENCY: Each Lot (one day's production), prior to Commencing Fill
label | 32eaf26c-eab2-5737-be2a-dee224b0257e |  | note | ACCEPTANCE CRITERIA: Test rolling of all fill layers and subgrade shall be in accordance with Section 173 and 204 of the VicRoads Standard Specification.
label | 1de56b7a-3d8f-5eac-9401-24f4883f1da5 |  | note | ○ Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | e08aae0b-d975-5b52-a677-21613898ba81 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173.03, Cl. 204.12
label | 08a5300d-4d3d-56e1-a0eb-c1a8e7f97409 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 694b5358-8f3b-59e7-b9b0-e5ae26f10725 |  | note | RECORD OF CONFORMITY: Proof Rolling Register signed.
label | 7c6f024b-9a02-5f5d-bdff-41376bd2fe58 |  | note | WP
label | 0e71dd3d-60fd-5818-9bd1-dfeef87f86c6 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | e08aea09-2e17-5999-a08d-b68ad72568cf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Testing for Compaction and Material Properties
label | 6abd3ba6-831b-571b-a58e-d0c319b5a498 |  | note | FREQUENCY: Testing as per table 204.141 of VicRoads Spec. for Roadworks and Bridgeworks
label | ab446358-f4a7-5e6d-b12d-a6e6320df7cf |  | note | ACCEPTANCE CRITERIA: Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level= minimum compaction 99% MDD.
label | 68e16984-f3d1-5a29-8dc6-4c70b29d044e |  | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of cuts= minimum compaction 97% MDD.
label | 2aa73bb9-4d65-5946-bc70-e471f9b61489 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173.04, Cl. 204.13, Cl. 204.14, Table 204.131, Table 204.141
label | 994c3f13-24ff-59bf-b9b2-b7aa912b0d00 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | c6ed5b5b-db9b-5fe5-b826-9c58ef7545cf |  | note | RECORD OF CONFORMITY: Test Results
label | a6139014-bb8a-5a3d-af1a-2e7057f58aba |  | note | TP
label | 87e87941-1b13-5e0e-b7f7-fa1e118b3ce8 |  | note | RESPONSIBILITY: Site Engineer
date | bff6fa2f-cad0-5fad-ad3a-ad36db13951c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 8d27fe0a-83da-5b0e-b1ff-b5ad389e3b04 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 8233d13b-e993-55b7-83e3-8640af7419d7 |  | textbox | Print Name:
text | e5963cae-38f9-54aa-8a1a-a8c4a8f50bff |  | textbox | Position:
date | ee963eee-6223-5d7f-b8f0-1c13b264df79 |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-008 - Cement Treated Subbase | itp |  |  |  | Yes | ITP-008 - Cement Treated Subbase | 3465c8a8-0b58-4953-95a2-a9cdf922ab6a
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 0be0203e-47eb-5dd7-89eb-75ad79e6030c |  | note | FREQUENCY: Prior to commencing any activity
label | 4e3ce692-6cfa-56f3-9d83-bcee3f6c8e18 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 467cba02-9f2a-5b4d-a298-a949a7f02993 |  | note | – using the correct and complete set of drawings
label | adcf2f08-ec14-51e6-bf81-4d783ebf4fcf |  | note | – all drawings are the latest revision
label | bbdff5ae-59d6-5461-a094-a078bfc53c26 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 878ae8f7-785f-57e2-bc3a-81cec965cf52 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 16db5af4-7479-5e2b-a208-309d6814c504 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 22d505af-59e6-5a0f-983e-d54020f95e3b |  | note | HP*
label | 0abec465-e998-5232-aeef-cf28a21933ef |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | 55a23325-a79f-5546-a1f1-572eb96e97b3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Material Mix Design
label | ef238f5f-777c-577b-91a3-00ed86832709 |  | note | FREQUENCY: Prior to commencing any activity
label | d2d13b60-02c6-5f91-bc67-117286dcfb1d |  | note | ACCEPTANCE CRITERIA: Material proposed for import as Class 3 sub-base material meets the requirements of VR Section 812 or 820. Obtain material compliance data from the supplier and submit to VRs for approval
label | 3ee2469c-b306-5e52-b2a9-db89b96cfdea |  | note | REFERENCE DOCUMENTS: Cl 812.04, Section 820.04 to 820.09, RC 500.02
label | a91c05ba-3fb9-5928-81b0-7118ccead9bd |  | note | INSPECTION/TEST METHOD: Document Review
label | 88197d11-e0f6-5aef-a515-fb5673d6fa2b |  | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | 08e7fcd7-bde4-5445-a9c1-5047d393432a |  | note | HP*
label | 72671c90-99f9-54d8-800f-e1798de69bfe |  | note | RESPONSIBILITY: Project Engineer
date | 69b15ad4-364a-59b1-844f-bb9bbc1225e6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Implementation of all measures and controls
label | 1ef47389-1cbf-5282-b1e9-7820f4f63b6d |  | note | FREQUENCY: Prior to commencing any activity
label | efa2aaa6-1631-596f-9d26-203fb08c7b84 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | ce982ac4-4c5c-5871-a540-980ad3f1ed51 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 76ff9a45-7a62-56cd-af38-98f41cff59d8 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | ae99657a-54cb-571d-b7d7-a20b43d82e23 |  | note | RECORD OF CONFORMITY: This ITP signed
label | cda8e0e3-8010-5296-b20f-adb0c92e65f8 |  | note | HP*
label | a1df4a5c-ec25-5d91-a28f-89861700437c |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | 7b9940ca-7161-51f4-91e2-97c06b7845a4 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Materials
label | 51a0d852-9393-515e-9ef5-9d9df76af7b8 |  | note | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
label | 8c7669ad-267e-5eba-8da6-43edc471e023 |  | note | REFERENCE DOCUMENTS: Cl 306.04
label | e217871d-dc07-54b7-ae97-f65fb9ecd0fe |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d598cb1c-836a-51f3-b144-48436b22c577 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 406b1135-0215-5927-bcda-207aa1c7ee59 |  | note | IP
label | ffa0fcb0-318c-57f0-b492-eb440c597146 |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | 460861c9-efb8-5d1f-8f40-04e2593026c3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Moisture Content
label | 8fd17a15-5ad4-5971-92c1-da4ba20430aa |  | note | ACCEPTANCE CRITERIA: The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modified optimum moisture content.
label | fecd514f-0d85-59d8-92f1-de6814e769c8 |  | note | REFERENCE DOCUMENTS: Cl 306.05
label | bd4dbcc0-08ef-5fd3-9450-18eeaf758314 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f02a88c1-e9b6-52c9-8860-6e6eed5134c8 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a41771ed-34c0-53c4-bd5d-fc3072e41dad |  | note | IP
label | 2ae289bd-b986-52a1-a8f3-20809b4b2763 |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | a42f3e7d-cc7b-5efa-824c-49ebabe6c74b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Jointing
label | 2628ce2a-c95d-585c-b771-e89f080bd958 |  | note | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements unless otherwise approved by the Superintendent:
label | c9070e6e-6ab1-575a-a84e-3770035dc34d |  | note | (a) material shall be spread in such a manner as to minimise the number of joints;
label | b097b81d-149e-562f-89c4-b6a7746f8d3d |  | note | (b) in any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | bcb8b0c2-e256-5216-997a-a6d5f489ccf3 |  | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | 2dd8a3a3-c025-5bd2-8132-80306be8de6e |  | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | 7564dfbe-9675-5879-afa6-7be0b8fd2457 |  | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lane lines or within 300 mm of the centre of a traffic lane.
label | 6d743680-26b7-5e86-a6fa-80d750050cca |  | note | REFERENCE DOCUMENTS: Cl 306.08
label | 939b860f-f7c6-50a7-8c46-45b1df3d9e1f |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 0267afd3-76b0-5d2d-8985-b3a7729c250d |  | note | RECORD OF CONFORMITY: Signed ITP
label | 64aa1ab3-5c21-571c-88a2-9c5d0988b20e |  | note | IP
label | 1dc08698-4d78-52a2-8574-919f5cbd40d1 |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | e1d2e3ae-b72b-56ee-b431-b2925fa65876 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Testing Requirements
checkpoint-status |  |  | checkpoint | 3.1 - Test Rolling
label | 162e2e68-bf94-5292-b574-5d02abcc3c6e |  | note | FREQUENCY: Each lot
label | ab9d670e-f683-5a4b-a190-08306f8a30b0 |  | note | ACCEPTANCE CRITERIA: Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
label | 739a0c1a-79e8-57b9-bc02-9d9ad359272e |  | note | REFERENCE DOCUMENTS: CL 306.09
label | d7d86419-6df7-569b-81d5-66fb058a52f8 |  | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | a4dbc400-7371-5197-b09b-fa831c42afe7 |  | note | TP
label | d4e658fd-e15b-505e-8f9d-392fafd1f4ec |  | note | RESPONSIBILITY: Superintendent / foreman
date | 696e1171-aca8-56bf-88ac-64330a4f080b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Compaction
label | 53bc7d92-611d-5faa-b4f9-8ab4712dedbb |  | note | FREQUENCY: Each lot
label | 9e1c02c6-b65b-5a56-9fc4-169a84299d98 |  | note | ACCEPTANCE CRITERIA: Testing and Acceptance of Compaction
label | 9f50fde1-306a-5671-b56d-64e832667ec2 |  | note | ○ The work represented by the lot will be accepted as far as compaction is concerned if the mean density ratio for the lot is not less than 96.0%.
label | a734d4b6-86c2-5e8b-b4c6-f69db534aefa |  | note | ○ If the mean of the individual density ratio test values for the lot is less than 96.0%, but greater than or equal to 92% the work represented by the lot may be accepted but the method of rectification and/or redesign of the pavement shall be approved by the Superintendent. Alternatively, the Superintendent may accept the work at a reduced rate calculated using the formula:
label | f2b2d988-70bc-5c86-9da2-a709b11d39c5 |  | note | REFERENCE DOCUMENTS: CL 306.09
label | 5daca48e-36ca-58b9-bd4c-9555d3fccea0 |  | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | b9bf2cb9-a16d-5995-8433-faf9594d8e7d |  | note | TP
label | 9d082f4f-a346-5ad8-99be-a4b5d82644c7 |  | note | RESPONSIBILITY: Project Engineer
date | 24bf7bee-f338-540d-ba06-5099805735af |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Survey Conformance
label | 9c5e709f-2b02-5aa5-a917-3c7646fe365f |  | note | FREQUENCY: Each lot
label | 4d8220fc-42d7-564d-b2ce-ac064612a063 |  | note | ACCEPTANCE CRITERIA: Pavement subbase shall be finished to a smooth and uniform surface and shall, after compaction, conform within the following limits to the levels, lines, grades, thicknesses and cross sections as specified or shown on the drawings.
label | f513db30-9cfe-5e5a-bf6d-87742687d3fa |  | note | (a) Width and Alignment
label | 5aa24e84-e6d9-572c-af16-9f5bcaefa410 |  | note | – The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
label | c72d8b20-0220-568c-bc82-a4ad71ab6011 |  | note | (b) Surface Level of Subgrade and Pavement
label | b1083f6b-b381-50d2-986d-ac2ed1a28908 |  | note | – The surface level of the subgrade and pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet requirements as specified in Clause 306.12.
label | ec40d2a7-e9a5-52c1-83a4-6a921c38361e |  | note | Surface level tolerances:
label | 9c6a69c5-b886-5026-a414-f8b15d8bff47 |  | note | ○ Range x = +6, -12mm
label | 9598fb8e-21ac-5ae5-80c1-65859c997cec |  | note | REFERENCE DOCUMENTS: Cl 306
label | c125cbce-da86-5851-ac76-657c093d76e9 |  | note | INSPECTION/TEST METHOD: Survey
label | 760663d9-2160-5e77-ba38-a236e74f82bc |  | note | RECORD OF CONFORMITY: Cl 306.12.
label | 0b35ca66-890f-57eb-a340-1ce41a877a45 |  | note | SCP
label | 7239b210-fe44-585a-a4ae-0e26697fd1bb |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | e33bfdfa-1e0d-567e-9974-63645387a551 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Curing
label | e0afe05b-a518-5413-8632-13abfc4af3af |  | note | FREQUENCY: Each lot
label | 4b808943-5366-5fab-bd67-6c660fcc2aca |  | note | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified
label | 5b2ca045-6b48-5908-81fa-e397285371c8 |  | note | ○ The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
label | 473e30d3-d376-5ea9-9309-f3ddaf41cee0 |  | note | ○ Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
label | 05c62783-a890-5a3d-845b-44e5b518153f |  | note | ○ The subbase shall be kept in good order and condition and free from contamination.
label | 5efe5039-1da3-5cd9-ab5f-edd49f1034c0 |  | note | REFERENCE DOCUMENTS: Cl 306.11
label | 7e7dcb91-426d-5f0f-bd1f-72c663954c34 |  | note | INSPECTION/TEST METHOD: Survey
label | e511c89a-2209-5472-8acc-692960385b6c |  | note | RECORD OF CONFORMITY: This ITP signed off;
label | eafa8cb7-fa7d-5cfe-b187-c134e661cad4 |  | note | IP
label | 8d1b74d9-98d6-5f05-bbc8-f480db095956 |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | d9659804-31ef-5ce1-bbaa-f055df7ec917 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 36778b60-4847-5a2e-9ea8-8231a3ac3d89 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | b5773c08-732a-516b-b363-ac531cef8c70 |  | textbox | Print Name:
text | d22a349f-b8e4-5e3e-be2b-e37eafdc375b |  | textbox | Position:
date | b3f1c338-0760-5411-9f7c-bd8ddd397b3d |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-002 - Construction of Underground Stormwater Drainage | itp |  |  |  | Yes | ITP-002 - Construction of Underground Stormwater Drainage | 40353ab1-b634-41be-aca0-f5b956ec3169
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | e90ad774-8067-526f-b015-c97cd30d3473 |  | note | FREQUENCY: Prior to commencing any activity
label | e629852d-1521-500c-ae45-9efc94f34e2e |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 908bb0c1-f95e-5f80-bc99-bcddb2fbd641 |  | note | – using the correct and complete set of drawings
label | 04c35bd8-d43b-5a89-9068-49bb9976c9b9 |  | note | – all drawings are the latest revision
label | ded3ca70-dd14-5851-ac24-2d98c8fbdd43 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 47ec6295-7209-5373-b464-da39511bb14c |  | note | INSPECTION/TEST METHOD: Visual inspection
label | c13a19f7-3007-54cc-93bb-c5ffbe7a9626 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 1c188d46-a1d0-58f8-af4f-f11c27059601 |  | note | HP*
label | 626757fb-9c77-5411-ba63-5b14d6347ea8 |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | 8e819a2c-daa6-5136-bd0f-5be6414c5240 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | f5deb7c8-5b26-5c21-b6f4-ee856096577b |  | note | FREQUENCY: Prior to commencing any activity
label | f46720e7-475d-5de6-b359-39535afe07a9 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
label | 448c7398-60a8-58c7-a53f-ae59ad905e2c |  | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | 3b2755a6-b1d3-5755-96b0-60994f2ae0c7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e8089db1-bddb-5c1b-b860-9166cb2715d9 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 057a81cd-645d-5286-8196-7b34e2cc1120 |  | note | HP*
label | 2041988f-16f5-51a9-a02d-63769915d63e |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | 8c08b989-25d3-58b0-aa52-46d3274a4d41 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Precast Materials Inspection
label | 59735fcf-489c-5e51-829d-d8bf9c90519c |  | note | FREQUENCY: Each Delivery
label | 6c8ab821-413a-5ea9-bc3d-9f4ed9791c45 |  | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
label | 7d6bbbc7-dc6f-5dd7-b893-caea8830fdb1 |  | note | REFERENCE DOCUMENTS: 701.04b
label | 326b5ca1-b8c2-5556-b706-10f1ac23fcce |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d6f22f94-e955-52a1-bd1e-46ff6a57b6e2 |  | note | RECORD OF CONFORMITY: This ITP signed, Receival and Inspection Checklist
label | 7a4757a1-962c-5540-9d68-b5dcbc58477b |  | note | IP
label | ad655d04-6e85-5291-846e-57b513386177 |  | note | RESPONSIBILITY: Project Engineer
date | d917b6f0-d312-55b2-80b2-77dd9a6fd923 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Precast Pipe Compliance
label | 90aad275-0041-5599-92ef-2cd14b2674c3 |  | note | FREQUENCY: Prior to Commencing
label | 7053f72c-0dbc-5159-9d8b-15edee42506d |  | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058. Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
label | 06ede95c-1c59-5112-9c58-13ba5ecf6d21 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04(a), Cl. 701.04(b)(i), Cl. 705.04(d), Cl. 705.11 AS4058, AS4680
label | cbd89a1d-3341-5efe-91e1-297d330795cc |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | 0875dc37-f8ad-565b-83a1-b8d1188cdc96 |  | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | e35df0e6-8104-5fac-9b07-b38876bb81fe |  | note | IP
label | 957fef52-4ff9-5919-8ce4-929ef013ad84 |  | note | RESPONSIBILITY: Project Engineer
date | 96db5984-6bbb-5f9f-a805-97b65e3dc958 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Bedding material classification
label | b6c41726-9adb-5340-8dca-357ace0fb738 |  | note | FREQUENCY: Prior to start
label | b7940f4d-83d8-5582-aa8b-c1af549fcdd0 |  | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | 6ae4e8d7-777d-5856-92e2-7f96a8970961 |  | note | ○ 100% passing 19mm sieve.
label | feda79df-51e3-5d88-9bfe-12378b731a89 |  | note | ○ 5%-40% passing 0.075mm.
label | 0ea059a7-5811-502f-91f0-ceca876e383a |  | note | ○ PI = 20 max.
label | bdcbcaa4-2369-5cd8-b399-ca3908206ee0 |  | note | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
label | 41d383cc-f600-5ec7-a6c8-ef2d2ca8745c |  | note | INSPECTION/TEST METHOD: Verify
label | c925c39b-8a11-52ee-94ed-ddf6f8f26c43 |  | note | RECORD OF CONFORMITY: Test Reports from supplier
label | 781dcb0e-da23-5bf6-a90e-bc7ab4bd31b0 |  | note | TP
label | 96f91276-2038-5d1c-9f27-0235f7204273 |  | note | RESPONSIBILITY: Project Engineer
date | c9ca0322-4f43-5d55-9456-d7e87ecaa44a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - Backfill material Classification
label | 9e5f83af-706f-5071-b88f-3da27b39e3a0 |  | note | FREQUENCY: Prior to start
label | 88f536bf-4c47-53e7-9637-b454c5c90869 |  | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | daf0e340-3d7b-51de-8f69-c1c18f502114 |  | note | ○ 100% passing 37.5mm sieve.
label | 8112c4ad-1f08-5c69-bac9-d9a9dbef499b |  | note | ○ 5%-40% passing 0.075mm sieve.
label | 95309e88-576d-5bdc-868b-811ecac6ff5e |  | note | ○ PI = 20 max.
label | f4d46a9e-234a-5832-92e2-c8661cb5a7e3 |  | note | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
label | 73af99ca-31c2-53f7-82f7-4e41a138dfe4 |  | note | INSPECTION/TEST METHOD: Verify
label | 8e1afcf6-fb42-5b7a-981e-3ff39060a79e |  | note | RECORD OF CONFORMITY: Test Reports from supplier
label | 528560fd-7bfd-53c9-96ef-92d5628cd9a8 |  | note | TP
label | 1336512d-0160-543c-8458-50510ada7a44 |  | note | RESPONSIBILITY: Project Engineer
date | e18d3307-d301-55b7-a559-877d0b87ea54 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.7 - Mortar material classification
label | 74518bf4-dc51-5a33-a771-a8f603f8e2e4 |  | note | FREQUENCY: Prior to start
label | ca030fc0-e017-5c90-bdc4-f170b3d97122 |  | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | 9d114ad1-a2bf-5850-9f2d-cccc39872705 |  | note | REFERENCE DOCUMENTS: 610.33
label | a8598eed-747c-59a7-89ec-475613434f8a |  | note | INSPECTION/TEST METHOD: Verify
label | a293fb09-3758-5c09-a998-6178c6a79f22 |  | note | RECORD OF CONFORMITY: Test Reports from supplier
label | 8434a35a-c829-5f03-929d-ef55f6e09cab |  | note | TP
label | 45bb203c-ab56-5a5e-86a6-31094eeab2af |  | note | RESPONSIBILITY: Project Engineer
date | a503e713-9497-5230-97ff-cb5cdf0e609a |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Excavation Permit
label | 78d6c320-452b-5348-bdfd-d3161678cd68 |  | note | FREQUENCY: Each lot
label | e9ba4a1e-8dbe-5f02-983b-d2527d4a182b |  | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | 18422e1f-cc16-59fa-9d2c-9fab80ea3430 |  | note | ○ Plant and equipment shall be appropriate for the task.
label | d0b4d19e-741f-587c-8e64-05312b073af9 |  | note | ○ Excavation operations shall not disturb areas outside the limit of excavation.
label | fe4c73f9-f2c8-5f54-b945-13b830977e75 |  | note | REFERENCE DOCUMENTS: Excavation permit
label | 240f074c-4c38-5efb-9273-d7d53c0c59a9 |  | note | INSPECTION/TEST METHOD: Verify
label | 7dcb331f-a490-55f7-9689-04d8994c3abb |  | note | RECORD OF CONFORMITY: ITP Signed
label | 0ed8dfd4-fc22-5d2d-8b2d-b63f2ee0590c |  | note | HP*
label | fe652354-9ebd-5d47-b6b3-a83d012c1acf |  | note | RESPONSIBILITY: Project Engineer
date | 2379eb09-7978-52bd-8330-e7d66faca878 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Set out drainage
label | 9a2f48d0-9b6e-5d48-bb3a-6188716fc819 |  | note | FREQUENCY: Prior to excavation
label | 54ccc313-353d-5d59-aefd-9437bc2f1039 |  | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | 01d70df2-291d-5bce-957b-db4d4fdad56c |  | note | REFERENCE DOCUMENTS: Drawings 701.10
label | dd346676-f8b4-59a4-a41f-803a4b125730 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 02b9f7f6-553e-5c47-83d2-c2894c524c0a |  | note | RECORD OF CONFORMITY: ITP Signed
label | bc1a0929-1e99-532b-8b02-a3cea6a874cc |  | note | HP
label | 027fc626-4cdd-5a11-8343-934c581e6168 |  | note | RESPONSIBILITY: Engineer / Forman & Superintendent
date | e45d4f01-a7a7-570e-b37a-2eecc70e0b91 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Excavation (pipes)
label | b4c546cf-a892-5514-8f9c-2688ea02464a |  | note | FREQUENCY: Each Trench
label | 60e969dc-c82b-5de9-947e-0909d8c042bb |  | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
label | 14b2f7ee-4574-5738-ba2b-288b9a8ce64f |  | note | Depth of trench:
label | a4ad4e10-1fc6-5a33-8505-771e5ee97c98 |  | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
label | 833edc50-e00f-5e77-9f80-a90b9fca81c5 |  | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
label | 2aa8a1a5-eacf-578a-a396-14031cb277eb |  | note | REFERENCE DOCUMENTS: 701.15 Table 701.151
label | 91dd1f1a-9208-5170-b796-a39875fe170e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 94e077cc-feaf-5f2a-96de-a056e56b931e |  | note | RECORD OF CONFORMITY: ITP Signed
label | 86bc8841-ec9c-585f-8e83-b21ff5830da1 |  | note | IP
label | f19ec6fc-50e6-538e-a0b8-ae534ee19b98 |  | note | RESPONSIBILITY: Site Foreman
date | 8ac1794b-1203-522b-80cc-e57d217eccc0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Compact base of trench
label | 53c01bec-6621-5a1c-8eef-0ad7170acf55 |  | note | FREQUENCY: Each Trench
label | 5be35c49-bd49-5741-ac24-02f9da2da730 |  | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | 1e5587d1-ce79-53a9-bc40-5ae05ded7875 |  | note | REFERENCE DOCUMENTS: 701.1
label | a22f496e-4121-5d5d-818c-3a545d29b0fc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d20b674f-ec65-5600-a79f-8766a604c215 |  | note | RECORD OF CONFORMITY: ITP Signed
label | ea45cad8-555e-56e2-af3a-04b8d9d391ec |  | note | IP
label | 8d1c9ea2-0c3a-5a6e-b916-2e6d4b6e80e5 |  | note | RESPONSIBILITY: Project Engineer
date | d53b6798-86c8-50fa-97c1-e44d39e595dc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Place bedding material & compact
label | 2f5be8a8-3be6-5ef2-baf0-96bfd8162673 |  | note | FREQUENCY: Each Trench
label | ad2240ba-3b91-566d-b974-df2750ccf9ea |  | note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
label | ae8c1334-78ba-507c-ba77-d62e2814258c |  | note | ○ 100mm under pipes.
label | 2fe48f8b-a4ee-5fbd-936c-adaf7cf7c615 |  | note | ○ 80mm (earth foundation)
label | b6ecd94b-aac3-5066-8926-7d5b61050f3c |  | note | ○ 150mm (rock foundation)
label | 4b67934f-63a9-550d-86f6-9c259e99acb7 |  | note | REFERENCE DOCUMENTS: 701.19
label | 921f9441-65d1-58b8-9026-137864b5a500 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f5d76ad2-6ffa-5654-bf46-726196da4461 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 7e1a115b-a4f8-55fa-8856-d54b14918129 |  | note | IP
label | fadb55b6-e55e-5a9d-8e18-a616c6361cfd |  | note | RESPONSIBILITY: Project Engineer
date | 0d3e5586-77df-5773-bd8a-911acbf143e4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Place pipes
label | 34486e83-564a-5804-8c84-9ff6da0e3279 |  | note | FREQUENCY: Each Line/Pit
label | 2b97ef0b-89c7-57d6-8b51-d47fd8e09b06 |  | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | edbfd7b5-95cd-5955-9193-ef6317b18b58 |  | note | REFERENCE DOCUMENTS: Drawings 701.17
label | 9a07b595-efce-58f1-9d50-48c7517db61a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | cf97e9bb-5c02-57bc-acf4-9434f5145847 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 8669d2fb-8502-55cb-aa86-fc60cbe9ebf4 |  | note | IP
label | bec27780-7be4-5e71-bbf3-8b6de6a64565 |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | 59bf3cb7-826f-5a66-a30c-b5b705a48924 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Jointing pipe sections
label | e25cc93f-7c3d-5e53-aa91-e33a1d583379 |  | note | FREQUENCY: Each Line
label | ab94745c-77fd-55c1-b389-8bff2457319e |  | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
label | ca152b3b-f858-5df9-a09d-9e90a5ed1d5f |  | note | REFERENCE DOCUMENTS: 701.18
label | 72aef72f-2c06-55a9-9960-be7eab9f3c29 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 32e4936e-2056-5f4c-b0ef-3bfe3e3a4064 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 59af6eac-beec-5860-a9e4-46d602c12ba2 |  | note | IP
label | 0db5e5b8-f5b3-596a-8e4d-ffecd48e45b0 |  | note | RESPONSIBILITY: Project Engineer / Site Foreman
date | 4b5ed609-0378-59a6-8f42-4eaae27f70dc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Place & compact backfill material over pipes
label | 6b8ae07e-1b3c-5534-9212-fbac154bd277 |  | note | FREQUENCY: each lot
label | 8de0f5c9-f98f-5290-af96-e6b54bd81d8f |  | note | ACCEPTANCE CRITERIA:
label | b3d87cf2-e061-5e99-a7d2-00608f96b470 |  | note | ○ Backfill under paved area: fill trench with selected back fill material to subgrade level
label | c0d700e3-2959-5659-8826-ec245de7e838 |  | note | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | 3fba2b5a-dd54-52f4-8f43-c82e0ab88027 |  | note | ○ Loose layer thickness <= 150mm.
label | b8b25c78-d700-56ec-82b6-2e5195a2cee3 |  | note | ○ 1 lot = 150mm layer
label | 60df1c62-cc0c-5c68-944a-8c976f0789f5 |  | note | REFERENCE DOCUMENTS: 701.14, 701.15
label | f097eca0-8a91-5713-95ad-4bf4879b1170 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | dd3be8d4-808a-5102-81cd-184bfd3181b0 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 50b6a224-a8e8-5d8c-8c6f-598d001c4da1 |  | note | IP
label | 1d45d5d6-f3b1-5388-aaff-64a98c1a99a5 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | d130d5dc-e154-5d2e-982b-7fc67e4c0da2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Repairs to damaged pipes
label | b9727118-4cdb-52a6-a75c-4c93b0f2939a |  | note | FREQUENCY: Each damaged pipe
label | 1df2a305-ae83-5ef4-a6dd-72d7eebe1620 |  | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures. All repair procedures undertaken in accordance with Cl 701.25.
label | 9d36c136-934c-5591-9f09-68edd7b813e3 |  | note | REFERENCE DOCUMENTS: 701.31
label | 23d33d72-7763-53a2-84d2-c3e405efc8dc |  | note | INSPECTION/TEST METHOD: Verify
label | 2325e34e-2b57-5246-b5de-621d59530df4 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 788228e0-d9f3-5d5a-b8d1-59fb1925d699 |  | note | HP
label | 47a7361c-d814-5f06-9ca8-863176c0bfad |  | note | RESPONSIBILITY: Engineer / Forman & Superintendent
date | 77189d04-1474-5a54-9553-13b87f998a48 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Testing & Completion
checkpoint-status |  |  | checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
label | 3d32cf26-a56a-5a41-a3db-a436d58ceb6c |  | note | FREQUENCY: as required/requested
label | 58fb6f7d-4f48-5051-acc4-4b2e46961b56 |  | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort. Bedding material shall be compacted using a compaction plated to refusal.
label | a81f5b29-10ef-54f5-94f4-875541ee9390 |  | note | REFERENCE DOCUMENTS: 701.2
label | ac12dc3a-2657-5082-b03c-937d7d15a9df |  | note | INSPECTION/TEST METHOD: Verify
label | ca6d88ad-046f-548c-b7ae-c78243900d43 |  | note | RECORD OF CONFORMITY: Test Reports
label | 31a236eb-fc7e-5188-b6a8-c342e76bb152 |  | note | TP
label | ca594d5e-d3ea-5ba4-962d-a63610526e83 |  | note | RESPONSIBILITY: Project Engineer
date | 8e2ab8e8-2f94-5ede-8405-9e23b2ed40dc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0a46a105-2a24-53e9-ad1e-4b690c525f9d |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 6a445c72-7bea-5c82-9e92-b2bacdef549c |  | textbox | Print Name:
text | b1b69e27-e3b9-53d3-a987-c38d9278a726 |  | textbox | Position:
date | ddced495-cf7f-529a-b95a-968c774d8bea |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-009 - Subsoil Drainage | itp |  |  |  | Yes | ITP-009 - Subsoil Drainage | 44d0c79e-7060-41b0-89c8-027c939ec08d
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | e3a6dc7c-7132-5852-b57c-0857f5f3b9c6 |  | note | FREQUENCY: Prior to Commencing
label | fa3d2719-d62b-57dd-8ae4-c8514a63dbae |  | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | a19f5a26-710b-5bc2-b6df-6073edf0ebf4 |  | note | REFERENCE DOCUMENTS: Inductions Register
label | f0af2664-2f20-5e78-96ec-00ceab8bbd31 |  | note | INSPECTION/TEST METHOD: Document review
label | 02c917d1-28cd-5d91-a8af-14655d34ef46 |  | note | RECORD OF CONFORMITY: Site induction signed.
label | e0eee77a-642c-5069-b754-b429d8fab3e5 |  | note | AP
label | 2454fc85-fac9-56e4-9d9f-989b68b7e5aa |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 578bd6d0-ac3b-5940-bcaa-c648708e633b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | 7c3d96eb-02c3-5668-9e0f-032b762a7647 |  | note | FREQUENCY: Prior to commencing
label | 934df31e-adf7-5a38-8030-7b820df281b2 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | 2205428f-b728-5785-a980-f3b8be08b269 |  | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | 62780aa4-4224-5546-bb02-dc6587fb5e17 |  | note | INSPECTION/TEST METHOD: Document Review
label | 7bd8f8dd-159c-5e2f-8ba3-072abc4053b8 |  | note | RECORD OF CONFORMITY: SWMS(s) signed
label | 261c9d81-60b5-540f-ab70-bd86cfa006e4 |  | note | HP
label | 9017ebb0-503a-54ab-a844-e7538ff3af1a |  | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | 436ca3df-1656-526e-9c84-145790a91017 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Check that current revision drawings are being used
label | cf8abb83-1e05-5e8c-ac6d-cc4d4e895c93 |  | note | FREQUENCY: Prior to Commencing
label | 7240c17b-b58c-52ba-b501-e0cf420da569 |  | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | 6bdf03a1-66ae-5e2e-8c3f-c661e0d7db47 |  | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | 53b1156f-9881-5893-afd3-70d1d0fd785b |  | note | INSPECTION/TEST METHOD: Document review
label | 3c236c3a-6b03-5ef9-bc65-7a62b571f6de |  | note | RECORD OF CONFORMITY: Latest Revision Drawings
label | 83f29ff3-f539-5719-ab62-4e45aedf78a8 |  | note | AP
label | c245b190-7400-566a-8dd0-f9c4255627c7 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | dc060389-0989-5a3d-b8a7-1b616578eb3b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | 04acf72a-0ee6-50ea-ac2f-65fccbcd9d75 |  | note | FREQUENCY: Prior to Commencing
label | b36bbb3f-78cd-5327-b88a-d575938b2d95 |  | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | 617d6cbb-5c2a-5421-aeca-80645477ca3f |  | note | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | 33c9957a-0fed-5311-90fa-b5c26b978cd8 |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | 61b43ff5-e2c6-57db-b448-4da83dbf7b2d |  | note | RECORD OF CONFORMITY: Signed ITP
label | d89337c9-4c3b-5894-84d0-273db90cbb9e |  | note | IP
label | b1360a9d-896b-507b-9529-1be25d9119e7 |  | note | RESPONSIBILITY: Site Engineer
date | 14ee022a-a94d-5e3f-bab4-e5e3801b8cc8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Excavation Permit issued
label | e9961dcd-c67a-5fe6-a121-79cdedcd29a5 |  | note | FREQUENCY: Prior to Commencing
label | 9c548af1-d310-53fa-b689-772700e65708 |  | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | a6d74b4f-25c2-567b-8ae5-99691348e977 |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | 950a73fc-f244-5aec-917a-7bc92eba4825 |  | note | INSPECTION/TEST METHOD: Document review
label | 4da3d5af-7b21-58db-a77b-457f83998612 |  | note | RECORD OF CONFORMITY: Excavation Permit #
label | 41dacc22-f344-5682-98e3-216300a443be |  | note | IP
label | 13a6cf65-79a5-5cc2-8da3-e784e6d5c426 |  | note | RESPONSIBILITY: Site Engineer
date | c0dcec94-8342-5726-88be-63d784b0137d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - Materials
label | baf2751a-9892-5b04-abe4-945a248d8394 |  | note | FREQUENCY: Prior to Commencing
label | 80f4a153-74ea-5199-b794-cea5213d536a |  | note | ACCEPTANCE CRITERIA: All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2
label | 322d1561-5893-5498-8fc8-67911728a199 |  | note | REFERENCE DOCUMENTS: Project Spec. Cl.3030.05(a)
label | 6a4c64a4-c37f-5367-a735-d860ed7cfe43 |  | note | INSPECTION/TEST METHOD: Document review
label | 9d8eab08-ec7f-5025-a6db-802e6d46194a |  | note | RECORD OF CONFORMITY: Signed ITP
label | fc7b84e8-87ee-5f87-b674-56cd5702bbb2 |  | note | IP
label | bf9c1683-1daa-5f36-8a41-5679698f207d |  | note | RESPONSIBILITY: Site Engineer
date | 043f6528-63ea-50a9-b815-a3093a93c854 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Drainage Works
checkpoint-status |  |  | checkpoint | 2.1 - Excavation of Trench
label | 0b11dd3a-7b24-56f9-b5a7-82aa90bc2013 |  | note | FREQUENCY: When placing drainage
label | 1062a955-3ee2-5ac0-a439-0f7935e9b2a1 |  | note | ACCEPTANCE CRITERIA: The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed.
label | bf045e1f-59eb-577b-8a6a-f6df8e870002 |  | note | ○ Perforated Pipe Crown level to be minimum 200mm below subgrade level.
label | b744e90d-b0df-5d89-b45c-d96ab48189ea |  | note | ○ Grade of trench to be not flatter than 1 in 250.
label | 5d76a705-e629-530d-9e47-d54a305365d5 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08, VicRoads Spec. Cl.702.09(a)(b)
label | c5a9b4bf-e081-5f6b-b900-8b4e28da3367 |  | note | INSPECTION/TEST METHOD: Site inspection
label | 394b7883-1581-57bc-9a4b-430dcda10329 |  | note | RECORD OF CONFORMITY: Signed ITP
label | a586c5e9-46a2-5a66-bef9-f551fbdf6243 |  | note | HP
label | a03d1b1d-17b1-5224-bc7a-6db6454db50a |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 738a602f-d4a2-5ead-b416-48149e893d70 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Use of Geotextile
label | 2d419021-2c3a-5b62-80ab-6b94d6120c31 |  | note | FREQUENCY: When placing drainage
label | 63603317-54a8-5e4f-9334-24f912e44af1 |  | note | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
label | b7b74ff1-1cde-5085-943c-a5857478a1a0 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08
label | d0f866c8-b0f4-506a-a905-4c0b4d5c2dfe |  | note | INSPECTION/TEST METHOD: Site inspection
label | fdbaf7ee-db55-52bd-9e94-4def3c72fefb |  | note | RECORD OF CONFORMITY: Signed ITP
label | 0140c413-bab4-525b-bba7-ba1936c14ba4 |  | note | IP
label | 37b3c677-8571-571f-867d-ea9c7ea3b745 |  | note | RESPONSIBILITY: Site Engineer
date | 6c2c5537-0ba1-5055-8a79-017340cc0828 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Installation of Subsoil Drainage
label | 18dcb1a6-fa57-5f20-aa49-5f53a2046965 |  | note | FREQUENCY: When placing drainage
label | d784c621-fec1-532c-a579-53653b03b759 |  | note | ACCEPTANCE CRITERIA: Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level. Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe
label | 12c619c4-7ce3-5512-821b-9d4ab9ad8ca2 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(d)
label | ee36ea52-8829-544f-9fe0-c69de9257ce5 |  | note | INSPECTION/TEST METHOD: Site inspection
label | 06c9566a-bec8-5441-8014-d271e970cab3 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 0aef2317-5c43-5979-8851-f4f9db4c16f9 |  | note | IP
label | db81c908-ca40-5c82-a889-751e4a81f698 |  | note | RESPONSIBILITY: Site Engineer
date | 03588f74-1afd-554d-b2b1-d992f8e699e5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Placing of Granular Filter Material
label | 365b9f52-d150-59b3-95ec-415d15f6edba |  | note | FREQUENCY: When placing drainage
label | 1604cb23-6aad-5136-b8b9-f56d5025ad7d |  | note | ACCEPTANCE CRITERIA: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
label | 21bbf8ad-97c0-5d6b-ad2f-9655dda58611 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(g)
label | 2b12b933-eb6f-535b-be62-1e646e4d6fd9 |  | note | INSPECTION/TEST METHOD: Document Review
label | 8087c28f-7dfc-5365-b317-54bd721023e5 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 80cb3278-7506-54c6-a671-ad7d45c6cd75 |  | note | HP
label | 687eff9d-1cc4-56fc-80a4-443b512b7ba5 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | eabc5b63-a1a4-58d3-a61f-df88b158552c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Flushing Test
label | 41d9cb29-a815-5b1d-a0a1-6ba2068a9a50 |  | note | FREQUENCY: After drainage is placed
label | bc7fe5cf-281b-528e-88c4-7a99e3c055df |  | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction
label | 53b56f0a-fd8a-5834-95fc-5be4747abb70 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(h)
label | 3443a409-d176-5691-89b6-45360438a76a |  | note | INSPECTION/TEST METHOD: Site inspection
label | 6146f3cd-b27c-5bea-b8b9-a6baa13db78a |  | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | 8a2784eb-8560-5c9e-81fd-48c626a332f3 |  | note | WP
label | e9cfe12f-8aef-5a9a-9bd4-e741b3916221 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 7e67b891-3818-52aa-9de2-39daccee59b1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - CCTV
label | e8b7b7ee-1b07-516f-b492-1bf095b53101 |  | note | FREQUENCY: After drainage is placed
label | bb962872-d74a-5966-a760-a172aadd8db2 |  | note | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | a0b7c558-1f0f-5e76-9596-9761643e619d |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(i)
label | 0968cf82-d230-5a70-ab0f-afe896926360 |  | note | INSPECTION/TEST METHOD: Site inspection
label | 23fefb7e-78e0-55f7-a7b9-de1e1a9e87b7 |  | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | d3d9d1ed-3c06-5e78-b96f-16025223e49c |  | note | HP
label | ec7c908a-bb42-5296-8c42-3b3930f33aaa |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | efc9221f-b735-505f-810b-f8b941a7dbd0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | de2667f3-fc3e-5683-bfe5-825fa78ffd12 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 69c560cf-2135-589d-badf-aeb02b9852e3 |  | textbox | Print Name:
text | 918a7ae7-fc66-5e6f-aec8-e16f360e9863 |  | textbox | Position:
date | 94a73e59-d0b6-5dae-9ef7-994775967eab |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-003 - Earthworks Foundation | itp |  |  |  | Yes | ITP-003 - Earthworks Foundation | 7a5bbcdb-40ec-4d22-81af-32033eb70b7f
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | edaad290-99fb-5a12-b80d-d770f506f8f0 |  | note | FREQUENCY: Prior to Commencing Work
label | 8a4628aa-ef1f-5599-971d-33896ef8bdb1 |  | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | 649bf7e5-26c6-5711-86dc-171916490dc1 |  | note | REFERENCE DOCUMENTS: Induction Register
label | 8d3bf4fe-8bde-5106-b4a2-c97d3b411d0a |  | note | INSPECTION/TEST METHOD: Document Review
label | e2f57374-9d99-5a41-87dd-924290b16872 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 742fc542-3fc1-55e5-9012-cd78ce520017 |  | note | HP*
label | f8c1da7f-699f-513f-905c-44f100cd71e1 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 16ce5877-8965-50dd-a0e9-77408328c48c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | d5f0af96-c667-5940-b038-cc8a9d9afa6c |  | note | FREQUENCY: Prior to commencing any activity
label | 9537afc2-b3f3-576f-877a-07f39e1b6889 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | 5b34a70f-47d1-5291-ad94-03d249ec829d |  | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS
label | ff77609a-d23c-5cab-b120-0423902568d1 |  | note | INSPECTION/TEST METHOD: Document Review
label | aa989325-46d8-588f-9f8a-ebcf2e2282b1 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 5771e19b-8323-5d74-b220-6c56156ea34b |  | note | HP*
label | 32bf2a6d-d3c2-5b1b-a443-cfdb8c2209af |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 8cd88dfd-7669-5715-8cdc-ccbd7ac376e3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Excavation Permit issued
label | 7e51cecc-b244-5b21-8d53-cbceca2314d7 |  | note | FREQUENCY: Prior to commencing
label | 7cc47136-ec50-5181-b744-a104f71da412 |  | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | 0928539e-ed1e-5b4d-850a-ced45f89e113 |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | 412034fd-c57d-5d4c-8031-d508ebf7cbff |  | note | INSPECTION/TEST METHOD: Document Review
label | ca2cb02b-8492-5dcf-b6e1-ba99461f5c3c |  | note | RECORD OF CONFORMITY: Excavation Permit No.
label | 254be4b2-1b05-5a90-b66d-1e27e459939e |  | note | IP
label | f4ddcf0d-43d9-5f16-a49e-dc6e3dac8e26 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | a7da59b2-b044-55ba-bf60-b2f974bc0cec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Check that current revision drawings are being used
label | b5525b5c-8138-56f6-85c4-0b2e739a5d6e |  | note | FREQUENCY: Prior to Commencing Work
label | fef59d24-4402-5849-a8e5-44e30d2a8afa |  | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | 33c49608-4fac-5bb3-8800-21605ae17385 |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | 00df43d2-ca8d-50ce-a2c2-24f75085a476 |  | note | INSPECTION/TEST METHOD: Document Review
label | 1bb38b1c-11ff-5b24-aa3d-0b7e20ae09e5 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 931d4769-8392-598c-8eb2-00186e14c99e |  | note | IP
label | 03cc229a-72ae-506c-853b-37b4c0580acb |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 41587f5c-716d-5d77-9925-7d19e795c9dd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | 9ff1ae31-6668-549d-8073-82723d89f0a6 |  | note | FREQUENCY: Prior to Commencing Work
label | 5e057d0a-229b-5956-80f4-568c91217d64 |  | note | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
label | 5c8dbb95-a68c-5e6f-97b9-709001c140bc |  | note | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | f6e789b0-9ff5-59ec-9a82-57a6a275d2cb |  | note | INSPECTION/TEST METHOD: Document Review
label | 5a816ad1-5dfe-551d-8b54-9b88fe36ddee |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 948806fa-ca6a-56fa-86e5-9e48a7a01907 |  | note | IP
label | caf70b1f-ff6c-5ce2-ab0e-31e2e3a0756f |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | d5889967-37fb-5a35-809b-5e941ced2a2d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - Verification of Site Clearing
label | a7ad42ec-e00b-5b00-b571-388176faa054 |  | note | FREQUENCY: Prior to Commencing
label | e605e107-d12e-5386-ba52-ecde698b196a |  | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
label | c0d2031a-a4eb-541b-96f9-32b09fd72edf |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05 ITP-001
label | 0e28792c-bb50-5a9c-b230-3ed502496ce0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | b06de4c2-73d7-5306-84b2-abfefb813bd2 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 05adbc36-37e3-5706-9978-5ef788945a13 |  | note | IP
label | 0910ac73-f25d-5f7b-8954-fdf549660fec |  | note | RESPONSIBILITY: Project Engineer
date | 43d970ff-ed0d-509f-b063-79b76a337778 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.7 - Material Category
label | bced17f2-1417-5afa-80e1-3a180c8bdc30 |  | note | FREQUENCY: Prior and During Excavation
label | 79dd2b0d-ce00-56c9-8b7a-0db5de8e4766 |  | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of material in accordance with Clause 204.04
label | 9e2ee3b0-3935-55b5-8ad9-a9271e94e0c6 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.04, Cl.204.06(c)
label | 889bc8f1-6b60-5b9e-8551-648a9dc17034 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 49161b1d-a84a-56e1-9b7a-ad57251e1e79 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 2d6020db-7f6d-5eb7-8304-7820430d749a |  | note | IP
label | 3bde901b-4016-5760-a9b6-7e2d063eed3e |  | note | RESPONSIBILITY: Project Engineer
date | d741f227-e16a-5304-bf35-8bbac705f946 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.8 - Placing Fill
label | e0e2cf12-7672-5b18-b948-f7f69280246c |  | note | FREQUENCY: Prior to Commencing Fill
label | e54d6a8e-d5a1-5a02-b430-75f49ab8906b |  | note | ACCEPTANCE CRITERIA: Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent
label | cd7439ff-0585-5947-bc0b-547270efa500 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
label | 57ddebc5-e1a8-5fc3-a33d-8a63e1c1918b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9d42acd5-2bda-56c3-b592-e229ea2d1835 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 5071ce57-f432-5976-9b86-d89a8993cc4e |  | note | IP
label | 588084c2-05b3-5196-844e-c9e3babfc68e |  | note | RESPONSIBILITY: Project Engineer
date | 61e8da0e-9114-50ab-96d2-b32d87cf6926 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.9 - Rock Subgrade
label | c6338775-1879-581b-8997-3ce00ed037d6 |  | note | FREQUENCY: During Excavation
label | 6d3af2f5-ffea-5228-bca1-d17ca01fedfd |  | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Details of any necessary amendments to the sub surface drainage design including trasverse subsurface drainage at the interfaces shall be submitted to the Superintendent for review.
label | 49f9695e-b394-596f-ab5b-1dccbbc8e4be |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | 95354de5-8bc1-5b8c-833c-5411f3bd79dd |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | b4b8dc83-0793-5064-9f36-1f1de419b1b3 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 7571587c-8fbb-5bca-9ebb-b0adc3a51813 |  | note | IP
label | 6e23c880-1785-55b8-a8c2-0ceaedbe9edd |  | note | RESPONSIBILITY: Project Engineer
date | 5afcc883-bef3-51de-a3b4-3054c6e99ea9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.10 - Ground Water
label | 20fdc082-04ed-575d-a448-3eb74055e3e4 |  | note | FREQUENCY: During Excavation
label | f87a416b-2a1d-561e-9737-a5e68ebfde40 |  | note | ACCEPTANCE CRITERIA: The Superintendent shall be notified where groundwater or seepage is encountered and the proposed action to be taken, shall be submitted for review. Any necessary approvals from relevant authorities for treatment and disposal of this groundwater shall also be submitted .
label | 6ea770e9-7e2e-5262-910d-04c17a0b46c8 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(h)
label | 666c811c-0ff6-5994-a93f-ae03e3acede0 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 69b3be80-f64d-5576-870e-2c8efb5dbb6f |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 27f460f4-a134-5944-bfd8-a2b258397331 |  | note | IP
label | 537de900-4afc-5648-97fb-c42f84c2c8ed |  | note | RESPONSIBILITY: Project Engineer
date | 620a1707-dc03-5948-88b0-a89def8f8de1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.11 - Unsuitable Material
label | 49640fa6-2c47-565c-9589-9f7cbb1870c3 |  | note | FREQUENCY: During Excavation
label | 171baf58-b3c3-5131-947e-ac20705db73d |  | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
label | 377fd432-edff-5fc6-be4f-2de61a404394 |  | note | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
label | 4c60eb2d-ba64-53b9-85a9-4af4a2ecaa62 |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | 2c5c3f27-36e0-56d4-8e48-febf74675d4a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4764f003-5d9a-556d-97d4-7bd8a2048997 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 9991fdc1-061e-5b87-b97f-762451ddf681 |  | note | IP
label | 9da06eba-dc83-5de3-b6c5-1bd2c3a2be62 |  | note | RESPONSIBILITY: Project Engineer
date | 1f1bc54b-60f9-5594-9815-8ba323c091a6 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Survey set-out
label | b9d576ac-0ed9-58a9-8e1d-87cb77e2b64d |  | note | FREQUENCY: Prior to Commencing
label | b4528c97-25d4-5ed2-99eb-b5ca787760a0 |  | note | ACCEPTANCE CRITERIA: The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings.
label | 0b3e22ee-a348-58c0-8372-ddd8d705871a |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | ab7e8b53-0855-50a5-b639-1fb3bc150245 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 407651c0-72ae-53b9-ab39-aae2b41e5b5a |  | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | c350416f-b471-52e1-adcb-f26f5ae77a26 |  | note | SCP
label | f8f89aab-92bc-539e-ad9f-66876239c9c6 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
date | bdc84168-7636-5670-b577-408683ed41a4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Surface Preparation
label | f2fab04c-6df0-5f65-9705-e751072f4f75 |  | note | FREQUENCY: During Excavation
label | ea8f722d-5f77-5dbf-8239-2777fede8c3c |  | note | ACCEPTANCE CRITERIA: For areas where the subgrade height is less than one metre above cut height, the cut should be scarified to 150mm and recompacted with Type B material
label | 66827fb3-93ea-55e8-810f-3c21db25b2cb |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04, Cl. 204.06
label | 6d12ef4c-0d91-51d6-8865-401045dd7423 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | c7124731-cd50-52a9-88a8-d45c6811852e |  | note | RECORD OF CONFORMITY: Signed ITP
label | 31f30d33-9edd-5d48-a00a-159c928e39e8 |  | note | HP
label | 9df71fd5-cb7c-59d6-9f64-c20c51ef5b3c |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
date | 82594eb8-5a82-5170-8e26-4599820a41d3 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Foundation Treatment (if required)
label | e29acf8c-0996-52ab-9949-34302129aade |  | note | FREQUENCY: Prior to Treatment (if required)
label | 958c7ef4-51e4-53d6-9a48-6dcaba64e586 |  | note | ACCEPTANCE CRITERIA: Proposed method reviewed, refer relevant ITP
label | e5cff7c9-e99a-5437-9a38-ff6a059b6bdc |  | note | REFERENCE DOCUMENTS: Relevant ITP
label | 53e4a2d4-5d36-51e4-9eea-41e8d087a805 |  | note | INSPECTION/TEST METHOD: Document review
label | 18901245-d0ba-524e-b1ca-39c9ec34752d |  | note | RECORD OF CONFORMITY: Signed ITP
label | 571f3d9e-7479-5e8d-b199-fea99287c0e8 |  | note | IP
label | f73a8212-776f-5522-9069-ce3c9186baaf |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 8387bacb-6239-5e4b-bf1f-fb741185e6e7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 31047000-c4d4-5506-ace0-b58e7c989ced |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | c0b414bb-4f52-5a5c-85df-117b6146d21d |  | textbox | Print Name:
text | c120a63b-acad-5556-9fe5-ff03488527d8 |  | textbox | Position:
date | c3c13472-7b49-5bb0-9311-8f516b60911a |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-001 - Clearing and Grubbing | itp |  |  |  | Yes | ITP-001 - Clearing and Grubbing | a28d384b-8e0e-4554-9faa-7e235a7d0263
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check current drawings are used on site for works
label | d54b772b-9340-5317-97cb-f8570ca37cac |  | note | FREQUENCY: Prior to commencing any activity
label | ed048f0e-abef-5248-b01b-0cf621b1446d |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | a011703f-be23-50a9-ac4f-6f38502a5390 |  | note | – using the correct and complete set of drawings
label | a4f39929-112f-5683-849b-2880ed5d1323 |  | note | – all drawings are the latest revision
label | 8f54946f-e843-5fa1-8ed3-2e6a239f2781 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 20a7686e-9475-591c-948e-d24087febbe8 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | a35e8098-0d44-51da-93d2-5b2a6db9c3eb |  | note | RECORD OF CONFORMITY: This ITP signed
label | 7cf9099b-ed5c-5cf1-b251-12f6ae573ac4 |  | note | HP*
label | af21373d-0f0e-57f1-a54f-a538e6581b42 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 14359aae-2c5c-52a4-9857-5ca6c6596fb2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 9ba77c7a-82f7-56a8-8c85-2a0f112ece18 |  | note | FREQUENCY: Prior to commencing any activity
label | 65d79c17-df35-5e25-ab73-83c2c5ad9349 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS & WP
label | 048e1623-9a25-5604-90f8-dccbe8c6d4e3 |  | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
label | 612fdb2f-a559-5b72-ae0b-8e5d6d9afffd |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3b016252-63c4-57f0-95cb-f87fe7f24f7c |  | note | RECORD OF CONFORMITY: This ITP signed
label | 56f4b655-1b9f-5fcd-a11a-83871fd769d9 |  | note | HP*
label | b84e853e-692a-5d89-be57-73c96fb014c8 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | ae6dcdad-ab03-5c02-9fb6-1e84fa4953f1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Excavation Permit issued
label | 11c670bb-894d-53ea-a1ba-e66128b0e45d |  | note | FREQUENCY: Prior to Commencing
label | 17b5a985-f253-5ba6-9c3f-721b8d357e29 |  | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | 16b76cd8-e90c-59d2-9096-fa494b346b3b |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | 76ffff1d-6ac2-55aa-a283-43718369ed62 |  | note | INSPECTION/TEST METHOD: Document review
label | 11fb770d-415d-593a-be3a-a6abbff9452b |  | note | RECORD OF CONFORMITY: Excavation Permit #
label | f638d41d-4dba-5ec8-b8ee-dc7ae6d54174 |  | note | IP
label | dad0f177-b841-55e0-900d-94e89b04ee22 |  | note | RESPONSIBILITY: Site Engineer
date | a15f5c21-d20d-5d34-aa50-d11a7140bf2c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Flora & Fauna
label | 3c3e39fa-8198-5a0c-8179-c9d82ca6bad2 |  | note | FREQUENCY: Prior to commencing clearing
label | 0972a8fd-3ee4-55f3-8856-53d405e79976 |  | note | ACCEPTANCE CRITERIA: A qualified Ecologist is or trained wildlife handler to be present during removal of native vegetation; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
label | 760d74f8-9420-52fb-ae4a-bc9effb967f4 |  | note | REFERENCE DOCUMENTS: Construction Environmental Management Plan Appendix 2
label | e72ff817-9e84-507f-acd1-c05e23288648 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8c4b4c66-98d8-5555-8f1e-bd55ce2cee1a |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 62a740dc-3dad-559a-bede-47ab74aac9c7 |  | note | IP
label | f6a0b910-4548-5d3d-9e83-7b63fb6ef555 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 9566e05d-510b-5a60-89f7-2de75708faa4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Permit to distrurb flora & fauna
label | 8f4185fb-5bfb-5e50-a01f-01ecfe3e6e72 |  | note | FREQUENCY: Prior to commencing clearing
label | 0fd52308-5264-5f63-a65a-46d04aefe2e0 |  | note | ACCEPTANCE CRITERIA: VicRoads has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
label | 81e56efb-f10d-556c-bcdd-e7d4c95144bb |  | note | REFERENCE DOCUMENTS: Condition Plans endorsement
label | 9587e1f0-23b5-5e78-90f9-ef69c53663ab |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1945d92e-78fb-5b66-a593-cf69cab7bf6d |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 42c6ad30-326b-55af-af62-a3fb4b5932a0 |  | note | IP
label | 82ba6827-5a01-5cfd-b093-a2306d34ca2f |  | note | RESPONSIBILITY: Project Engineer
date | 0498fef4-6985-51cb-a279-ff3b8dbd44f7 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Clear & Grub
checkpoint-status |  |  | checkpoint | 2.1 - Define work area
label | c448e293-2815-562d-a900-356f3b709909 |  | note | FREQUENCY: Prior to commencing clearing
label | c9fde084-bcc5-5c63-aeef-a99927e1c02c |  | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
label | 8846c4f6-af11-52a1-b57c-bc7b5114e328 |  | note | REFERENCE DOCUMENTS: 201.1
label | 829930ca-1e6f-5533-9a57-69eeda4d57aa |  | note | INSPECTION/TEST METHOD: Inspect
label | 4cf9e97d-3bef-5834-9762-ded23cf723ce |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 761ec413-d36d-5a4a-aece-c5a1d699a6c2 |  | note | HP
label | ed529de3-4919-58ad-b784-dc67c989d173 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
date | ce58706e-403d-5f2c-ad18-78187701dd11 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Cultural Heritage and Areas of Significance
label | 36e3d179-403b-5c99-8441-c3dfb94b539f |  | note | FREQUENCY: Prior to commencing clearing
label | 37b1cb08-675a-5fda-95d5-bb1d7e5f9517 |  | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | 6986cd80-bf46-5dd4-9f51-a1f29ee3b875 |  | note | ○ Works are to be suspended immediately and Cultural Heritage representatives (BLCAC) are to be notified, if any items of significance are discovered or identified during construction.
label | 5aa90c57-4af7-5482-bf05-e0aa62e96460 |  | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | ec0ddfea-a16d-5b62-9cca-e8a736291cd6 |  | note | REFERENCE DOCUMENTS: CHMP
label | 3574060d-e032-56d6-b1fd-5da7c0d58603 |  | note | INSPECTION/TEST METHOD: Inspect
label | b541994c-ee3c-51d0-bf7a-de99acc2dc11 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 7df6b37a-30c4-52f6-a502-20a0fb45156d |  | note | HP
label | 91432a8a-8161-5cf5-8a4b-d5d3080dec77 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
date | 6fead208-2a76-5f80-8263-9413db53f712 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Joint Inspection to Mark vegetation or habitat to be removed
label | 9c46ca26-f02c-5e72-8bf6-09e7918cf16f |  | note | FREQUENCY: Prior to commencing clearing
label | c35dd909-34e8-5d46-88ad-d1bff89fdd87 |  | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the project Arborist and project Ecologist
label | f3f5d89b-1fb1-5b37-9feb-d29db0b28128 |  | note | REFERENCE DOCUMENTS: Drawings CEMP Tree Management Plan 176.I1
label | e7adae1d-0720-53a1-adc7-2e0154779a68 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | a3b4ffac-ccb2-50d2-bcea-13538404f93e |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | f5d37595-eef1-58a1-a159-70c38828553c |  | note | HP
label | f1d3ecc7-b9c4-51ac-8e32-1206ced83e87 |  | note | RESPONSIBILITY: Project Engineer/ Superintendent
date | 6b983b7f-cafc-5ff1-a4aa-ed26422ae907 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Felling of Trees
label | 75aeb063-9c39-5056-82a9-4c21f464f865 |  | note | FREQUENCY: Prior to commencing clearing
label | 5379cd54-1f41-5ec1-af94-f155ffcd9648 |  | note | ACCEPTANCE CRITERIA: Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared
label | b8c64516-9274-5c0e-98af-b8291fe599fe |  | note | REFERENCE DOCUMENTS: 201.04
label | 5e3bc26c-1141-5bb9-936e-6b7167cbef81 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8676cde9-c2f4-5636-b259-d9e5f4fb35dd |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 7d3ffcc2-8d03-5e10-bf25-d672bc001474 |  | note | IP
label | 8072312b-1873-566e-ad54-669b6dc6fb49 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 24e2965f-9ce8-55b4-91c3-80e6a0f0a8d4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Backfill holes
label | 57265ff3-d6c5-5a7b-a9ed-e3a1005ae156 |  | note | FREQUENCY: After clearing
label | f767e980-e05d-54e3-8ed4-9a638e9b553f |  | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted
label | 82a46572-fc19-5936-adcb-d7847338143a |  | note | REFERENCE DOCUMENTS: 201.05
label | 47e4c47a-eeac-5d21-bbbe-f19d04c48916 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1c7bda55-05bf-57d5-a00e-3b072ece7392 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 59f11bf1-4b0b-532b-9508-a0b7dbdf4e74 |  | note | IP
label | c31a6fa7-926e-5a6a-a2c4-0dcf8a414200 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 5e632389-2e6e-519f-991a-2d4d22b6add6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Dispose of Trees and vegetation
label | 2fcbaa07-cd82-57f2-8202-23f8874698a9 |  | note | FREQUENCY: After clearing
label | 99365dde-7045-5582-8da4-e1f7ac028911 |  | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works. Noxious weeds shall not be mulched.
label | a4753333-ab65-5f25-9a04-ac9892c9ea7f |  | note | REFERENCE DOCUMENTS: 201.07
label | a138e591-2edb-5234-adda-a7e4364eb3bb |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d8e09ebb-ba6e-5a97-9b87-a1466bad796c |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 55ee83f5-15a3-58ff-a49f-5d6ba88cd7b0 |  | note | IP
label | 268e52c3-9fdc-5baf-90a4-b5125f1d2324 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 348277a0-86b1-58f1-9888-087e3e72a410 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Dispose of concrete, bituminous and other recyclable materials.
label | 242cbc65-6230-5840-ae99-858c3a3c1531 |  | note | FREQUENCY: After clearing
label | ea2a5a33-bbaa-5804-bf5d-c079636a3cb2 |  | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
label | b7467c1c-c77a-5ba7-8a3e-ccb065efa255 |  | note | REFERENCE DOCUMENTS: 201.07
label | 5f32fd65-b5b9-5dc0-8b65-4b3941b91713 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7e0fd933-a2ef-5aa6-9cfb-525c705bd801 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 68e76d66-3b1e-5751-95a9-4ac44e9017f5 |  | note | IP
label | a02dc693-1cb8-5e46-9014-9a834f8900a7 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 2b9b80ed-5605-55e7-bced-ee74b5e08630 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Stripping of topsoil
label | 50795f9d-d5ab-5470-9b46-d1c9b4e5ce68 |  | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | 442aed30-1237-5c04-8bd7-6f9c2f64a28b |  | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | 98edf6ea-de58-59b7-afa8-6e7f1dced2fe |  | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
label | a111c9f4-8da6-5dae-a308-2f7f847faffd |  | note | ○ Topsoil shall be re-spread as soon as practicable.
label | ed3071f5-242b-5035-83fd-acd62726d8c4 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.05
label | 78464dc6-0f5a-5477-ae40-82f1629f9a67 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 5aa5c4ce-a52b-5422-9534-0110c29fafff |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 33ff405f-ad55-5f1a-a68f-3c495c30a0d1 |  | note | IP
label | d439fd28-accc-5a1e-ac45-4a69531facca |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 8f2a3c62-530d-5822-bf5a-d41b7d6fc958 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Removal of abandoned services
label | 18ab4cbe-b400-5002-9112-55fb1d7b9314 |  | note | FREQUENCY: Prior to commencing works
label | ee0ac0a3-1b1a-5614-a110-f65b749a11e1 |  | note | ACCEPTANCE CRITERIA: Pits which are no longer required shall be removed or broken back to a depth not less than 0.3 m below the finished surface of the subgrade.
label | ffce6f93-fb7a-5e49-8c1f-47820b9f4a41 |  | note | ○ Remaining pipe openings shall be sealed with concrete.
label | ad670959-48bc-5353-9b57-8ec98b82b5fc |  | note | ○ Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%.
label | 801b9a8f-03ad-55c7-91ba-7c17095cc956 |  | note | ○ The calculation of density ratio shall be based on Standard compactive effort.
label | 5d9cd510-fdff-563f-8123-aa368d32b344 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05
label | 0e4bf340-9f78-5c6c-8c15-39a485afe4e4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | abcaf34c-c2e1-5a31-96ee-bb4aa3d5b963 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | b7addacd-4316-5855-882f-0c6a880a4a8e |  | note | IP
label | 557cff7d-aedf-50ab-a34a-bfdb454e9e46 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 93e68b43-e034-59ba-991b-4822479de03d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.10 - Clearing of Trees and Vegetation
label | c68dc168-d8b3-50e2-9960-873caaa7bb32 |  | note | FREQUENCY: During clearin works
label | c9a608ae-1a03-5b93-917f-8a37f3eebde9 |  | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work. Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | 5c07469a-a957-53cd-aede-47e3b2b68c89 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
label | f611d39d-5339-5c2e-b91e-550e047086ac |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7c1c90da-0b7d-5550-aaf1-fc2f8a628a09 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | c882ce65-0aa4-5dab-b13f-198186966e7a |  | note | IP
label | b45c0262-0b29-514e-beab-8884723896b4 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 8c4ef3a1-6661-50de-997a-42959f1a6dfa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11 - Grubbing of vegetation
label | b0847b6e-811d-5039-83d2-7bf0b0baea46 |  | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | a548f53e-d03b-5c4a-b835-7a225d0d0abd |  | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
label | fc6747fa-69ac-526c-87b4-c3f1958a6176 |  | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
label | e31cc5b6-fbba-5d49-a8a3-88c9486bd58b |  | note | REFERENCE DOCUMENTS: CEMP VicRoads Spec. Cl.201.05
label | d9d11eb5-b744-539b-ad76-2c8c0b833bac |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 46a95eb2-b94a-53b8-ba86-8ce4c36da648 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 939a9f41-fbda-565a-8af7-2a4964e108b0 |  | note | IP
label | 0f0436b4-3ac7-534a-b18a-c93482fa84b9 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 6a3ed5d7-a398-5468-a589-a83b589171ee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b4a6982f-17f2-58ae-a535-f46a920a0fe5 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 2e98d35b-53a0-580c-82a3-c5ec3e8c74b1 |  | textbox | Print Name:
text | cf2fe074-4de3-5888-835c-3d6b3fe7d213 |  | textbox | Position:
date | 91027d33-fb14-575f-a5d8-b24d87fb7760 |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-007 - Guardrail Installation | itp |  |  |  | Yes | ITP-007 - Guardrail Installation | baaa6697-e56b-4282-9a45-a821848718a2
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | be4dc4ab-21b4-5129-81e1-72a44651edac |  | note | FREQUENCY: Prior to Commencing
label | cd723c98-fec6-5193-aa38-f6664d250db4 |  | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | 7c2aec00-0479-5e8a-8051-1134daf94f6d |  | note | REFERENCE DOCUMENTS: Inductions Register
label | 54389754-02d9-50bd-895f-2d0a6756be2c |  | note | INSPECTION/TEST METHOD: Document review
label | 43961286-fdb7-5c7e-80d4-1c05b007db98 |  | note | RECORD OF CONFORMITY: Site induction signed.
label | 856de7ea-e224-50a3-a723-32977e8ac103 |  | note | AP
label | c70673e9-1c6c-5782-8036-ed74a6dc182c |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 83ea25bb-ccc8-5b67-be87-560b0e4a18d5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | dc981f82-f893-5b9e-998c-9c11862d0db3 |  | note | FREQUENCY: Prior to commencing
label | 97f72f0d-222d-5b64-ac79-89ebb9d1e56c |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | 01e125a9-5525-5559-97fa-3c6f0f1bdaf1 |  | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | 89a5c260-7c62-56f2-b232-ffad73d7ec57 |  | note | INSPECTION/TEST METHOD: Document Review
label | 26a26055-4d37-5b1b-9e75-c9a82e849a3f |  | note | RECORD OF CONFORMITY: SWMS(s) signed
label | a55c22d9-df4f-52d4-91dd-58beeb20698a |  | note | IP
label | a9147eaa-2222-5b67-950a-f6794eba812d |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 6ee68f92-8ac0-54e9-bb80-c39d7c0b416e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Check that current revision drawings are being used
label | 167fa765-2b37-5ca7-b85c-d84ad5e78f5b |  | note | FREQUENCY: Prior to Commencing
label | 81e72349-190f-5196-b593-90b7a112f006 |  | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | e78db1a7-bccc-5ad4-8d02-6b7eaa7f1dee |  | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | a6ded079-7295-5d84-96f8-4ea07e7eacb4 |  | note | INSPECTION/TEST METHOD: Document review
label | 57807ba5-a46a-5f7d-882c-c1215df0074c |  | note | RECORD OF CONFORMITY: Latest Revision Drawings
label | be08e2e7-727a-53c4-9f41-bbe287bb2480 |  | note | AP
label | 3729177d-c8a1-5239-a796-bace0b230e34 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 031b14a9-20a8-5bb5-9194-d24f8598d874 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | 9ed7571c-49df-523b-ac82-a3bce1fdfe8f |  | note | FREQUENCY: Prior to Commencing
label | 586eb517-17e2-5545-8d81-bd65d3e81833 |  | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | e31d42da-847f-5dac-8600-76f789754748 |  | note | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | 62c0bee3-ab6f-5dd1-810f-1e110efcfa4b |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | c7a3d3d5-9132-568c-94b9-6c32293eb82a |  | note | RECORD OF CONFORMITY: Signed ITP
label | ea38d716-f0d5-5c0c-a5f7-f8f6ef2513f0 |  | note | IP
label | 6afdd84f-c849-52fd-a079-203ddadacc95 |  | note | RESPONSIBILITY: Site Engineer
date | 4e460abc-e6c0-5401-b839-ac260fce149c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Excavation Permit issued
label | 45408ad9-9f02-500d-af5d-f90cda119cc7 |  | note | FREQUENCY: Prior to Commencing
label | 0e38d4b5-03a4-59aa-a3e3-749f82a75fbe |  | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | 46b4b5b5-9e5d-5c7b-b1a0-ff70eeb0430b |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | 922d2433-5f41-59d1-993b-0d59cb336057 |  | note | INSPECTION/TEST METHOD: Document review
label | 8cf62360-3c4e-53c8-b5cc-3a72834dc2e4 |  | note | RECORD OF CONFORMITY: Excavation Permit #
label | 31ad375f-c28c-5ed9-827a-7c8f794891c1 |  | note | IP
label | 7d3c588c-1e37-5f08-b373-c739d152a168 |  | note | RESPONSIBILITY: Site Engineer
date | 8f400b71-1920-5521-ad77-8c02551fe5e0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - Approval of Guardrail System
label | 6a722cf4-3acf-5867-845f-31fa3f74722f |  | note | FREQUENCY: Prior to Commencing
label | bd79f3ac-e184-550b-8526-e7350fbcf772 |  | note | ACCEPTANCE CRITERIA: Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
label | 28112a4c-24ee-5955-8dc2-8ee7984643fd |  | note | REFERENCE DOCUMENTS: RDN 06-04
label | 0bb45a00-7866-5f90-846c-05ee12da8670 |  | note | INSPECTION/TEST METHOD: Document review
label | 2ed4ba1e-9171-52e8-8246-5ba2b1428365 |  | note | RECORD OF CONFORMITY: Signed ITP/Email
label | 832cb765-4b93-553e-8ac2-b0d0d4df2c2e |  | note | HP
label | b9f2b8e6-47f2-5e17-9b1f-7026d9d47b69 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 93872eef-c91b-526b-af5d-cf8dc079d66d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Material Approvals
checkpoint-status |  |  | checkpoint | 2.1 - Approved steel supply
label | da6ac946-4db9-5d5f-a892-c0c7e84da07a |  | note | FREQUENCY: Prior to Commencing
label | f817ee67-0511-5d5b-a675-b3a045e80293 |  | note | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
label | ce69d024-7904-5b74-8338-9c6e0e7cc60c |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(b)
label | 447c6d98-bb4f-5490-bc8c-cb1bdb990929 |  | note | INSPECTION/TEST METHOD: Document review
label | a1a58109-317e-5cb1-b8b1-e22a1505eb69 |  | note | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved), Material Test Certificates
label | 336c2607-60ca-53bd-9b2a-06267b6b0e11 |  | note | HP
label | f9f6b8f3-2800-50cf-a759-db90f6f781c2 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | db53cec6-59c2-5c30-9d12-8354d5ce9238 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Approved Galvanisation records
label | 8b71dc08-049e-5c51-b443-dc223650b93c |  | note | FREQUENCY: Prior to Commencing
label | e555c4db-6215-53e8-ac31-289c8b97d510 |  | note | ACCEPTANCE CRITERIA: Surface preparation in accordance with AS1627 parts 1 & 4. Zinc coating mass of galvanised components to be in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform
label | edec69eb-f935-5de6-8a7d-23df4f8eeb1c |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(d)
label | 756d1a93-5f5d-57d3-8984-76dd0e5773e4 |  | note | INSPECTION/TEST METHOD: Document review
label | 327acfdd-eaf5-58db-850b-8fd492da946b |  | note | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved) Manufacturer's certificate of compliance, Test Certificates
label | 4e8f5fd7-b86e-596f-8a3b-a6ef0c8b5837 |  | note | HP
label | 658b6b21-9db4-514f-9c6f-7f6c6ab96751 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 58332d7e-e939-58dc-817c-10a48043255e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Installation of Guardrail & Maintenance strip
checkpoint-status |  |  | checkpoint | 3.1 - Survey set-out
label | 2b8a5d85-c794-5afa-bd50-a25725e9285e |  | note | FREQUENCY: Prior to Commencing
label | 344e16b4-6b37-5af7-8957-2bbfee4d9532 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.. IFC and latest available revision used
label | 696a57fc-5009-57ff-b4d0-dd385127201d |  | note | REFERENCE DOCUMENTS: Latest IFC Drawings
label | 8129e8c6-b51d-58f4-bc57-8bab46fb3ecb |  | note | INSPECTION/TEST METHOD: Site inspection
label | f823a782-dabc-5b84-a1fa-2fb3f234acd3 |  | note | RECORD OF CONFORMITY: Signed ITP
label | bb2a6a57-433b-5a16-a518-113610a527b3 |  | note | SCP
label | c3747377-b028-57fd-ada9-20d9fea84b82 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 70cd9745-2fbd-55c2-8cc6-51420d85f465 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Service Location
label | 97a3592e-3ee8-504b-99fd-57825563037f |  | note | FREQUENCY: Prior to Commencing
label | 14885d08-7da1-51ae-b02d-83e288832604 |  | note | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
label | 8107567b-9c84-57c3-8768-b9ce3bc7e554 |  | note | REFERENCE DOCUMENTS: Services file & Current DBYD notifications
label | 19d2f3a3-d112-5557-971f-c614fcbaace6 |  | note | INSPECTION/TEST METHOD: Site inspection
label | af909bc6-4915-5aad-ba2f-e6580ab9e5b8 |  | note | RECORD OF CONFORMITY: Services marked on the ground
label | 6e30d708-b5d2-5908-b887-cf4704ede541 |  | note | IP
label | bcf3f459-ea3a-530f-b3d3-6feca6a8b108 |  | note | RESPONSIBILITY: Site Engineer
date | 07d51ee7-0e07-595b-b42e-bae7061108cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Approval of location and length
label | 9443bbfc-2986-5a0a-868e-901898a022e4 |  | note | FREQUENCY: Prior to Installation
label | 27c2d7e7-e70a-5812-9653-a725e03e033c |  | note | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the superintendent the required location and length of all guard fence.
label | 7343c0d6-6707-5a78-b8d7-2317526b4751 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08
label | c2647948-09e7-538b-9892-05136df5e0d9 |  | note | INSPECTION/TEST METHOD: Site inspection
label | 3ba1c032-35e7-57d3-a30b-de2390dff54e |  | note | RECORD OF CONFORMITY: Signed ITP
label | 8e4d4884-b4a8-55dc-89d8-7b8757418abd |  | note | HP
label | 9e9cc9c8-197c-5197-bbfe-75fb46a36859 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 2d90c74a-5208-5370-8a24-b2fe376909c1 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Install posts, rails and terminations
label | 29c5f95b-0701-5d9c-9b4b-f03f1a913e6c |  | note | FREQUENCY: During construction.
label | a9a5adb9-00b6-597c-b477-96a790fe2ba9 |  | note | ACCEPTANCE CRITERIA: Tolerances
label | 199692d0-24b2-59ad-8919-9929489ca22d |  | note | W-beam guard fence shall be erected to the following tolerances:
label | ba7ec263-01e4-5f3c-affb-e1eacb8edb51 |  | note | (i) Variation from true plan position of posts ±20 mm
label | c7485838-cd4a-5ae9-987e-f91c4b7631d0 |  | note | (ii) Variation of line of w-beams from specified vertical profile ±10 mm
label | a75b9dce-a4a2-505f-aa12-0bc41178e03a |  | note | (iii) Variation of w-beams from specified horizontal alignment ±20 mm
label | 4ded78f2-6de0-582d-a8e8-f54fdeddfb57 |  | note | (iv) Variation of posts from vertical (measured at top of the post) ±15 mm
label | ed44769b-c840-577f-abdc-19a9ad47c793 |  | note | (v) Orientation of block and/or post to w-beam +0 mm, -15 mm (measured at the point of greatest offset between the block or post to the w-beam)
label | 02e36965-5d91-5189-8124-44e7b5237577 |  | note | (vi) Dimension of holes -0 mm, +50 mm
label | 1b92f751-29f9-5498-b78c-11113940ae8b |  | note | (vii) Top of bolt head relative to w-beam -0 mm, +5 mm
label | 9e57e363-8962-5cfa-a016-52d28574f09c |  | note | ○ After installation the top of the rail shall be within 25 mm of the specified level and 50 mm of the specified line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length
label | 5ca9b88a-1319-581b-9b1d-6b688a9fb435 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08(d)
label | ce4e4624-e6de-5d16-ba3d-b528690018bf |  | note | INSPECTION/TEST METHOD: Document Review
label | f8257c32-b515-5d22-b4f6-21cb7c0a03d3 |  | note | RECORD OF CONFORMITY: Signed ITP
label | d4787aa6-7c6d-5205-b288-c47823bd2af5 |  | note | IP
label | 67ad8c39-e083-5f56-9ea3-e5c763c4f9bb |  | note | RESPONSIBILITY: Site Engineer
date | b868395f-2741-5382-865e-8789113cbe66 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Construct crushed rock base for maintenance strip
label | df2d0eef-80cf-5baa-938a-604486d97852 |  | note | FREQUENCY: During construction.
label | 9308fe42-a8af-54c0-a783-feecdd1d09b5 |  | note | ACCEPTANCE CRITERIA: Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
label | 57f3e066-a6a3-5ecd-b6e8-a780805c4b12 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
label | 04d19d07-dffd-50d1-8308-8985acea44a6 |  | note | INSPECTION/TEST METHOD: Site inspection
label | 4413e2b6-a58b-5c6a-8474-abcc48bb98d2 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 67959d24-af48-549e-9390-865615eb9f14 |  | note | WP
label | 73458645-718a-5696-af05-a2ae663121a6 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 902c8735-16b1-5c9d-b102-362046a9dfdc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Construct concrete maintenance strip
label | 28e81bd8-506e-5c26-9a69-99ffd06362c1 |  | note | FREQUENCY: During construction.
label | 58f8acc4-072a-53bd-860a-4af32f285545 |  | note | ACCEPTANCE CRITERIA: Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam.
label | bad334f3-5fe4-5579-a908-fac46efebed4 |  | note | ○ Separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative), full depth expansion joints 200mm either side of posts.
label | 5608c259-87c0-5385-a207-f74686d3ffcd |  | note | ○ Fresh concrete to be protected from rain or other damage until hard set.
label | 6a1f42e1-a634-554a-b405-51ee967e80d8 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
label | 2e5e987c-4564-5c64-b269-e2be792b1e4e |  | note | INSPECTION/TEST METHOD: Site inspection
label | e4b0f71a-5b32-5ffd-9948-4bd22478cd6f |  | note | RECORD OF CONFORMITY: Concrete dockets/Signed ITP
label | d721eb46-5312-5e75-96cd-b110b6266ffe |  | note | WP
label | 682e3558-17d5-5bfe-8993-8a1d527dc14c |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 0fabaadf-f2b0-5efc-ace3-7fa6e0da29a1 |  | date | Date Completed:
checkpoint-group |  |  | section | 4 - Testing
checkpoint-status |  |  | checkpoint | 4.1 - Compliance Audit of Barrier System Installation
label | eb823780-26fa-5bd8-a7af-e7c7dc239ddc |  | note | FREQUENCY: Prior the issue of the Certificate of Practical Completion
label | 4600c58c-be25-5a32-b837-e1df7e49adc0 |  | note | ACCEPTANCE CRITERIA: Prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract and the Contractor shall complete and submit to the superintendent a signed copy of the Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual.
label | b898774a-22b1-5b3b-a059-49119cbf097d |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.10
label | 0bb20b7c-8225-5788-8b9a-d85551fc7547 |  | note | INSPECTION/TEST METHOD: Document Review
label | d0f5fdd0-8846-5bd5-b3ed-2a5d0ccba6c0 |  | note | RECORD OF CONFORMITY: Safety barrier compliance audit, Manufacturer compliance certificate
label | 8793d852-5d8e-5055-94b5-a76472c7ece6 |  | note | HP
label | 27dd7cda-3fd0-5306-984c-eafb20d5fb14 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 9f49d8ab-479a-5722-9b66-b3f7f3c6c9e5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Completion
checkpoint-status |  |  | checkpoint | 5.1 - Delineators
label | eada0e96-5cdf-5844-b260-7c7a423c3d38 |  | note | FREQUENCY: Once installation of assets is completed
label | 64a7998f-30be-56cf-99a6-0570ab6a11bf |  | note | ACCEPTANCE CRITERIA: The Contractor shall arrange delineators so that vehicles approaching from either direction at night will only see:
label | 7754ed28-8a2a-5f8e-aa03-b6e4a9bea9c7 |  | note | ○ red delineators on the left side of one-way and two-way roadways;
label | 46038b0d-7aa5-561e-aa8f-c6b7956d90a4 |  | note | ○ white delineators on the right side of two-way roadways; and
label | adf4ec81-a079-5f4e-b199-dfa693dbbdaf |  | note | ○ yellow delineators on the right side of one-way roadways.
label | 52bc24fe-1d53-5a1b-80e1-193fc536c0a7 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.11
label | 23de2298-13bf-55b6-9ccf-dd2a4fc19373 |  | note | INSPECTION/TEST METHOD: Site inspection
label | d494e01d-4b2b-5b1b-9df4-5d46349ee1ce |  | note | RECORD OF CONFORMITY: Site Photos/Signed ITP
label | eb8adfca-c704-54c6-9bfe-d70889acf4ba |  | note | IP
label | 76b90dca-d632-5535-bf84-a5ea6d29b959 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | bd58b129-d7bc-5137-99a0-7124fae65261 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Survey data captured for As-Builts
label | 2fcf3c38-9850-5f77-8f48-ea5d936e690a |  | note | FREQUENCY: Completion of Works
label | abf9f39f-042e-5538-acfe-31e39a9223e9 |  | note | ACCEPTANCE CRITERIA: As-Built drawings to be submitted to client
label | 56e7c936-605e-5ae7-9d1e-34fd4a3d5d2a |  | note | REFERENCE DOCUMENTS: VicRoads Spec. 708
label | 1297c9c7-3201-5b47-b3e5-5d268f8fc2ea |  | note | INSPECTION/TEST METHOD: Document Review
label | f0a4c992-0f74-59e6-b009-9df8d2693b37 |  | note | RECORD OF CONFORMITY: As-Builts, Survey reports
label | ef6f3d56-4568-5997-8b07-34c3e23e1de3 |  | note | IP
label | c910a748-5977-5c5f-a280-7ea88440cb83 |  | note | RESPONSIBILITY: Superintendent / Site Engineer
date | 0e585cf5-fcd7-5d04-83df-e453b38459b2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3fc20486-af35-5db8-8eff-8d40d9529de4 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 83557ac3-2c18-59ae-8928-e3c90f996063 |  | textbox | Print Name:
text | 45a325db-bca8-5275-bc4a-d5f06ddb55c7 |  | textbox | Position:
date | 9d07b925-3d15-577f-8d17-5d03160b445f |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-005 - Crushed Rock Class 4 | itp |  |  |  | Yes | ITP-005 - Crushed Rock Class 4 | c887f370-03ee-45b2-8d0b-d292a7cd503a
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | 3428f0c5-5e62-5f67-b721-f4f57c1d9abe |  | note | FREQUENCY: Prior to Commencing
label | 9c31448e-0f78-5216-a950-4c8d00ef959f |  | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | 26952e95-a15b-55e1-872b-2128c113b84e |  | note | REFERENCE DOCUMENTS: Inductions Register
label | 3cfbfa34-7b33-5299-b49e-bfe6f553eb30 |  | note | INSPECTION/TEST METHOD: Document review
label | 721a3577-bf0f-57a3-bd78-a26248fdad64 |  | note | RECORD OF CONFORMITY: Site induction signed.
label | 904643d2-0cc2-5cb5-94b6-5a28357aceb5 |  | note | AP
label | d8331b42-82e6-5a54-91e9-1f0076c595a1 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 131e89ca-f297-540f-94be-644cb41c9aae |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | 805b8012-b680-552f-ac40-29fc4a04cbb3 |  | note | FREQUENCY: Prior to commencing
label | b8e00c7d-8d45-57c8-9327-e5b4e065c384 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | 17e00ba4-1ba9-539d-b371-1fb18bb06527 |  | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | 1435d9ba-6208-5ffc-839f-e76d03245b7c |  | note | INSPECTION/TEST METHOD: Document Review
label | 7918f3c4-4083-59be-b0ea-a0e91df619a6 |  | note | RECORD OF CONFORMITY: SWMS(s) signed
label | b7f6dce2-aac1-54a6-9a64-da3095e8e640 |  | note | HP
label | 4f34f2fe-b410-549a-91c7-b3bc37c8adfd |  | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | 52c18f5b-b859-529e-b93f-9fb66b74022a |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Check that current revision drawings are being used
label | e5f4d122-0409-5bc7-b000-99c24264c0d0 |  | note | FREQUENCY: Prior to Commencing
label | 3600edee-670d-5aa1-90a4-fb104a468887 |  | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | 46746115-048e-54a1-8174-9aecba93d06f |  | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | 8ef79192-affb-530f-b17c-b2d78edb7f21 |  | note | INSPECTION/TEST METHOD: Document review
label | ca1b81f4-6ff5-5bcd-a37d-f0172bcf8111 |  | note | RECORD OF CONFORMITY: Latest Revision Drawings
label | 989e5190-7aed-52e2-b004-6c0094438ece |  | note | AP
label | 60fa016b-bbc6-51e0-9bc9-17b104d89aee |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 116d30b2-3ff7-5fb2-a11e-cb01a7ea688f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | 54e959e4-9da9-54e3-b2f4-72e6a2401571 |  | note | FREQUENCY: Prior to Commencing
label | 327451e0-30f2-574c-b814-b629a3d7a173 |  | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | f15ca456-a42d-54ae-a97a-3368a4d88900 |  | note | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | f1b072c2-2cd4-5677-8b4f-2e30c4b39596 |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | e0f56fd0-f67c-560d-a83b-c87bda282f31 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 17f9e9dc-0092-55ee-8766-7f6295a4c4bd |  | note | IP
label | ed233a08-f073-578d-a47c-290c556e29e7 |  | note | RESPONSIBILITY: Site Engineer
date | 82714dcc-8a58-54e8-8e0a-d9c5e1fdd38d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Excavation Permit issued
label | 63d62324-65ac-59a8-b325-816f881e4914 |  | note | FREQUENCY: Prior to Commencing
label | 73d25f42-49ba-5a43-b27d-d60785a9abf3 |  | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | cf829e0d-6c39-5919-85ae-b72268e7885d |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | d053d6b2-0534-5049-ba8f-e5d92f7f915c |  | note | INSPECTION/TEST METHOD: Document review
label | f4544952-3296-5c04-8c05-435a7eba19fb |  | note | RECORD OF CONFORMITY: Excavation Permit #
label | dccb6ff0-e0de-5da0-9751-8214b1c3e4e0 |  | note | IP
label | 521b7f2d-c1fc-5c30-a43f-2a838f4bfd7f |  | note | RESPONSIBILITY: Site Engineer
date | 28cd077a-0fb4-59a1-8bc1-3eda4a640e94 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - Crushed Rock Mix design
label | e8e0ae57-35b2-5094-b632-4d1c58090362 |  | note | FREQUENCY: Prior to Commencing Work
label | 5f0c2707-8e49-51d9-997c-847ff5ccb352 |  | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | 4357c2d7-9a26-5cf5-a97a-c7b852a2dbca |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
label | 66b09f4d-3cac-5b47-89f3-1e7656d1a418 |  | note | INSPECTION/TEST METHOD: Document Review
label | a64ccf94-c17e-5ed5-9155-c305b3650159 |  | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | 40d9b0ac-4d51-53a7-95e4-571af5d97408 |  | note | HP*
label | ccfd1043-f9df-582c-838b-f0d2839b3dd4 |  | note | RESPONSIBILITY: Site Engineer
date | ebdd0b5c-3333-5ed2-a484-a37158c43576 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Placing Fill
checkpoint-status |  |  | checkpoint | 2.1 - Transverse Joints
label | 8fcc5857-beb7-5c06-94e8-54cdaaa6477a |  | note | FREQUENCY: Check prior to placing material
label | d17df259-f4c8-599b-a8a5-800376b5097b |  | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
label | 47788171-018d-5800-9735-c001491383f1 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
label | 73ceaa80-fc6c-5720-8a3b-34c92408f0a0 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 0eacf812-fa6c-59aa-9f4a-142ec39b8cb0 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 5dd3a3c0-7c70-50cc-94d0-03dabdee915c |  | note | IP
label | d863a7bc-ba6a-5cba-8d1c-ba8c011a3689 |  | note | RESPONSIBILITY: Site Engineer
date | fdd4449a-621a-5b1c-b691-569427d4c62a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Longitudinal Joints
label | fbd1fb4e-6508-54f8-8fb2-d31e48ac4f63 |  | note | FREQUENCY: Check prior to placing material
label | 2d1de656-7ed3-56ba-8053-980bf70eca47 |  | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | 9730dce1-fa4c-54a2-ab11-03d40b4b69c0 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
label | 04734a2c-b05c-5685-90c5-2513e6c00da3 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 6ca18937-2273-5cd1-8f45-4a0deceea38f |  | note | RECORD OF CONFORMITY: Signed ITP
label | a88b6e4d-2735-53fc-80d2-bbef75befdcf |  | note | IP
label | 91af7bcb-51a8-5cfd-933b-984cd8b637bc |  | note | RESPONSIBILITY: Site Engineer
date | 3cd7cae0-1996-57ea-afdd-3cf9ae0979fc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Lot Size
label | 5d3249cb-b18f-531b-a001-0c4389386384 |  | note | FREQUENCY: Check prior to placing material
label | d28e64d7-d5b0-57e0-a1a6-09c25c9f9319 |  | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | 23eadce1-6056-5c2a-b818-c05a6de52607 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii) Table 304.111
label | ba4574c8-e8ab-5db1-a063-b21e2b312c6a |  | note | INSPECTION/TEST METHOD: Site Inspection
label | f656d372-ce24-558e-8dda-663bae31e79a |  | note | RECORD OF CONFORMITY: Signed ITP
label | cc551ba2-e428-536b-bacd-3cd86ffa70e5 |  | note | IP
label | a1344bfb-a47d-56af-93a1-d7895d7ddbbd |  | note | RESPONSIBILITY: Site Engineer
date | 13f54267-cbca-57d1-854b-a49c742efc08 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Proof Roll
label | d96f7994-5421-5f1d-b0e5-757f429c84a9 |  | note | FREQUENCY: After placing material
label | 88f5836d-2db1-5ea5-807c-79aa077503c6 |  | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
label | 056710d4-5a17-5c7f-9fbf-f396147f4330 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv) Cl. 173
label | 636a51cd-35be-5991-b0d6-4f48bcbc2fe0 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | d0a48c61-0c45-5162-8d34-d8cb45ec7f43 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 9fec03ba-3f32-58e0-b310-1bff788168d3 |  | note | WP
label | d239576b-91cd-5366-95e0-8f5736ccf77c |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | 553894ba-89f4-5626-b070-22214cba1694 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Testing Requirements
checkpoint-status |  |  | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | 28f6e809-aee4-58a2-805b-bb9792e9f18d |  | note | FREQUENCY: Prior to Testing
label | ad67cb1a-4bd9-5f6d-bdc6-50ce30f86338 |  | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
label | 96a80933-632d-5fb0-8f29-27b2fd6c3aee |  | note | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | 3075e039-922c-59af-b51e-08392f1d5d97 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161, VicRoads Spec. Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i) Table 304.111
label | 29a74f3b-f2a8-5c8f-91a6-e61e84342746 |  | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | 237c065f-7d82-5f66-923a-5a8146842dda |  | note | RECORD OF CONFORMITY: Signed ITP
label | 5f7317fa-df29-5b8c-8d96-4ef5977f4bc8 |  | note | IP
label | e9061ac3-4455-5ce2-906b-65a03815f3a6 |  | note | RESPONSIBILITY: Site Engineer
date | f808e633-0701-54b9-84d3-0685ab7d4ae3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Modified Compactive Effort
label | 877022a0-f9cb-543c-b94d-f3605a7b8886 |  | note | FREQUENCY: As per 3.1
label | dfa6b41c-139e-5636-8e45-e2f84f612cc3 |  | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 98.0% (Scale A) 6 lot test
text | 3efda218-f635-54e2-b123-b1b44ce7d979 |  | textbox | Initial Frequency Test No. |  |  | - > 97.0%
label | b5db0d83-d546-51b6-98ac-bb167c9940af |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
label | df0597af-cddf-5d2b-b244-957eed8dc199 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | fdd0041c-3fd4-5e03-8738-4d82a346c29e |  | note | RECORD OF CONFORMITY: Test Records
label | 1ac74541-cfeb-5821-92ab-b0b609a0e715 |  | note | TP
label | 05019bb4-35b9-579c-a550-029b443010c6 |  | note | RESPONSIBILITY: Site Engineer
date | 2dbbf3cd-40a4-5cf6-a3f4-63d2a4c41055 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Permeability Testing
label | 5f312d5c-9d0c-5fc3-b016-07bed7d0cde2 |  | note | FREQUENCY: As per 3.1
label | b7f2b42f-7744-5786-a116-c871d6d17b0b |  | note | ACCEPTANCE CRITERIA: Class 4 Crushed rock max 5x10^-9 m/sec.
label | ffa15fd0-46f4-5995-a666-f3cb50c97896 |  | note | ○ Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051 and allows FH to use 9x10-9 m/s Max permeability
label | ec6f5530-3d4e-5a9b-b86a-fcd4875d0aea |  | note | REFERENCE DOCUMENTS: Project Spec. Cl.3040.05(a) Table 3040.051, RFI-0085.01
label | bf2d7a1e-8464-5e0d-9625-f49291f524c2 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 8d6bbf50-e691-5257-8d18-310fbc5b07f6 |  | note | RECORD OF CONFORMITY: Test Records from Supplier
label | 41cc7da0-dd28-54e9-882e-2645de1f75cb |  | note | TP
label | 77c2f5e9-3362-50df-885b-7f5f5404dcd3 |  | note | RESPONSIBILITY: Site Engineer
date | 3a5e40fa-19ed-5b3c-b78d-49e475669aff |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Survey Level
label | eb2b0b39-68ab-5205-a360-f7a4f0780ffd |  | note | FREQUENCY: At completion
label | fe67a9c8-be16-51d4-9361-b36b4ac88714 |  | note | ACCEPTANCE CRITERIA: Scale A:
label | 1f2acfbd-a8a6-599e-b35a-8892fa23b98d |  | note | – Minimum number of measurements per lot: 80 For Upper
label | ba82308d-c90d-5828-ab5c-6ca41793b00b |  | note | – Upper Subbase: Mean + 4mm to - 8mm with a maximum Standard Deviation of 8mm
label | 09b07546-7fbd-573a-9d76-08cbec927138 |  | note | – Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm.
label | b9ee9a65-7f3d-5a5e-a876-e3304e8b00bd |  | note | – Base: Mean ± 5 with a maximum Standard Deviation of 8mm.
label | 5fe2fea6-5f8b-5879-9cf7-21233b05751e |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
label | bc3ee358-4e62-5ec5-aeeb-901430e2c2f9 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | dfb882a4-3da1-58bb-89bf-026da69b7806 |  | note | RECORD OF CONFORMITY: Test Records
label | 5f1c45b4-a736-504f-881c-675953edab04 |  | note | TP
label | ad0d942b-f18a-5f40-85b8-e63b162bc8e5 |  | note | RESPONSIBILITY: Site Engineer
date | b2ff1b10-72d7-56ed-a350-92a235416390 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 6fe35c57-d995-5d7e-960e-4293b637c7b9 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 0be128c3-c91e-5011-88c3-d08dc5d37f3a |  | textbox | Print Name:
text | c4980dcf-bd02-5274-9466-0663710686ec |  | textbox | Position:
date | 182b078f-1516-585a-b155-95d2936bd676 |  | date | Date:
checklist-sectioned |  |  | checklist | ITP-004 - Fill with Material Type B | itp |  |  |  | Yes | ITP-004 - Fill with Material Type B | f19f11fe-09ba-47fa-a6d5-cabd0b40e335
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | f2bc9b76-ea0d-5182-b18b-918aae7234c4 |  | note | FREQUENCY: Prior to Commencing
label | 961304b7-a8de-574a-ad34-b0b526206366 |  | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | a290fb59-bb87-5516-b5df-a79b3c5ce880 |  | note | REFERENCE DOCUMENTS: Inductions Register
label | f0293525-fd63-5f4b-a29d-2ab1855f0d23 |  | note | INSPECTION/TEST METHOD: Document review
label | 5a5576bb-ad13-54ce-8c66-b88a2945ab6c |  | note | RECORD OF CONFORMITY: Site induction signed.
label | 97d0d01a-7298-57b8-bc79-d1815349b593 |  | note | AP
label | c202b273-4e4a-52b0-9c20-f11182946858 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | 1601a3e9-57f2-50bb-9ec4-8eb7e0a9b1c5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | 0683b36e-4e31-5051-80f1-c1af4759a20a |  | note | FREQUENCY: Prior to commencing
label | cab95ae2-8a95-585f-b4a2-144f1b86fad6 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | 16718fc0-6a86-519b-b59a-9ddc5551226c |  | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | beeb01b3-9ed6-56fb-9bbe-a5dd0585fea9 |  | note | INSPECTION/TEST METHOD: Document Review
label | 50deb0c7-7f09-5401-935e-60c831bc3d12 |  | note | RECORD OF CONFORMITY: SWMS(s) signed
label | 224f8df9-f66b-5339-95bf-47c91eda4381 |  | note | HP
label | e3e8931b-9e66-57a7-9ea0-e36e6a23d870 |  | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | 354d7e1a-9f0a-5169-aef1-ed764b61c3d4 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Check that current revision drawings are being used
label | 9e038d58-118e-5d3b-a363-5f6789d97d17 |  | note | FREQUENCY: Prior to Commencing
label | 15f488aa-c6e9-5173-b8de-610259a14474 |  | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | 33bf7360-3771-51c5-af6f-09a1dc3b17a5 |  | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | d2fb0248-a670-5b23-9f7e-a81d9eb0b8ec |  | note | INSPECTION/TEST METHOD: Document review
label | 8cbb14bd-723f-5210-972a-bae5a1e9e0a3 |  | note | RECORD OF CONFORMITY: Latest Revision Drawings
label | 1374a8d1-851f-5bc2-ba0c-47e6d2506b20 |  | note | AP
label | bb8a5cc4-00c1-569a-85a9-56936a683871 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
date | e7598689-e4df-5b96-a0ab-f2d62832b212 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | d9388216-f142-5211-90a2-4f8556ec0546 |  | note | FREQUENCY: Prior to Commencing
label | 0b21811e-aa87-5227-9361-c78dfe976796 |  | note | ACCEPTANCE CRITERIA: Prior to Commencing
label | cdd73204-dd5c-5b81-84df-a83e904cdd66 |  | note | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | 6d7f614e-c0db-59fa-9609-613a2ae6f8ec |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | 6a03c8ee-6cc2-5575-8e2d-dbe2e51ba3b2 |  | note | RECORD OF CONFORMITY: Signed ITP
label | d5183b13-f2bd-5bda-a0c0-1e1f1621ffa7 |  | note | IP
label | c269c371-e74d-5699-a169-1aebc92bd294 |  | note | RESPONSIBILITY: Site Engineer
date | 9eff2e20-b452-52de-a6d2-aeb588c96745 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Excavation Permit issued
label | ef2d6710-3b0b-50e8-9146-4911f92efd97 |  | note | FREQUENCY: Prior to Commencing
label | 91731030-a9a7-59a6-a050-2316871f9514 |  | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | bdcdb5c9-70ed-5111-b85a-a6d0e14db7c9 |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | e2079e11-c4bb-535b-8270-297d3c5fb809 |  | note | INSPECTION/TEST METHOD: Document review
label | 57ef0641-b745-5c3b-a29c-44bb01d1860c |  | note | RECORD OF CONFORMITY: Excavation Permit #
label | 6fd1bf50-91b7-5bc9-b7d8-885e69cc985c |  | note | IP
label | 6053c28e-95bf-5ce7-8bf6-112f41d01389 |  | note | RESPONSIBILITY: Site Engineer
date | 73b2215a-1a5b-56e4-ad41-0098be9aefe5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 - Verify Material
label | 8c2afd9c-150e-5937-8996-b2c0b1d1e56a |  | note | FREQUENCY: Prior to Commencing
label | 839d50e6-acdb-5805-a899-7f678ee5011a |  | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and FH shall inspect each type of material encountered and subject to verification by appropriate laboratory testing and agree on the category of the material.
label | d4918b6e-6c1f-5af3-983f-c685d380f944 |  | note | ○ Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel or steel by-products.
label | 066ee219-525e-5bd9-a1a8-65879e78ec99 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(c), Cl.204.04(c)
label | 33d71533-4fd4-5fad-8082-8d3674a59a19 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 65257d20-2e46-5f49-9ba9-2101a24443f0 |  | note | RECORD OF CONFORMITY: Test Results, Material Ctegory agreed with Superintendent
label | ce1e721c-b15d-5b51-903d-1c0c4cf48da4 |  | note | HP
label | a1b26550-c4e3-5e25-a746-d246e6376ec4 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | 319e6670-e444-5d4b-a111-f3c8e1d3f2c4 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Placing Type B Material
checkpoint-status |  |  | checkpoint | 2.1 - Survey set-out
label | 9385bace-9853-5275-8ed2-8e8b9afe4ea8 |  | note | FREQUENCY: Prior to Commencing Excavation
label | 50eef63c-3ea4-5c44-a3b4-3199ad2327c2 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
label | 4f3a0466-1eb2-5510-97ff-d9f06ba55458 |  | note | REFERENCE DOCUMENTS: Latest IFC Drawings
label | 4d69dba9-34a5-5f24-b511-647a7e99a85c |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 81baf421-4cb8-551a-a99b-42225400cb2a |  | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | d780485b-3218-55f5-b291-cb3c57b90449 |  | note | SCP
label | 15bbc913-71de-5e34-8268-c79b873e6942 |  | note | RESPONSIBILITY: Site Engineer & Surveyor
date | e04ee5bb-355b-5270-bb17-aa249b71ad5f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Fill Construction
label | fd9607ad-3092-5df1-b433-87b74fca1d47 |  | note | FREQUENCY: Prior to Commencing Excavation
label | bd8a69f7-c0ae-52e3-a5b1-fdf53137ec72 |  | note | ACCEPTANCE CRITERIA: No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent
label | 600a4b2b-9797-51f6-8d36-d0fa67e059c1 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
label | 18ee002f-e1b3-568c-a563-d9f214640d82 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 073ca142-216d-57c9-95e9-0ce8adeb4994 |  | note | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
label | 57a6d35a-26da-542e-b7e6-164bd18e16bb |  | note | HP
label | 0168b4a1-63c4-54b7-b66a-314625adc585 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | 0280a7df-a1ec-5c72-bf9e-cdb8dbf97976 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Keyed fill layers
label | 356bfb83-3a49-5335-b6b9-70af2a6a8186 |  | note | FREQUENCY: During Excavation
label | 4f82483f-a8b9-5aa6-a520-ca5de1894953 |  | note | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
label | e0c142ec-5b53-563a-8eb3-af1d90487f26 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
label | 7e882c6f-be3c-5fd6-a42e-f695a8449890 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 471c1083-0eec-5086-b7a1-a26bafdba353 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 1fc3b167-a319-5643-a61f-1e15f233e0a3 |  | note | IP
label | bd36de3e-1af9-54ce-a68a-9da86d8938be |  | note | RESPONSIBILITY: Site Engineer
date | 1cd61122-0ae5-58ef-ba17-a290766c501b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Layer thickness
label | 572ff152-5038-59c4-a368-a33c25db6b7c |  | note | FREQUENCY: During Excavation
label | 473e4149-2b40-5cb4-a945-8f320785a7aa |  | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
label | 27b2049f-22e1-5ade-b489-e5ee9fac98de |  | note | ○ A procedure shall be established to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
label | f3dd62a9-2466-584e-a726-2ac0eeb2b052 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
label | 637ad7c3-3d74-53d6-83f8-2adbb6856c57 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 305e9233-1f24-59b2-8ffb-48a3cf2bf33b |  | note | RECORD OF CONFORMITY: Signed ITP
label | 4bc2397b-b2ec-58a9-aaf4-30d9b3509569 |  | note | IP
label | 170c029d-5fea-5115-b855-a0d8ca242754 |  | note | RESPONSIBILITY: Site Engineer
date | 96bdcdc8-71d6-5740-8427-6cdfdc92f9c5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Proof Roll
label | d1506450-ba0d-5ae2-9ece-978031cc46a6 |  | note | FREQUENCY: Each Lot (one day's production or 5,000m2, whichever is lesser)
label | 4b604a4b-306a-5971-ba9f-e205bfd9f716 |  | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
label | c9f08b31-ba14-5f25-8a06-64661f785d42 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12, Cl.173.03
label | 37b30c69-010e-5d3f-8ed5-077453a0e87a |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 2896c878-6728-594f-9527-4528c0bd1332 |  | note | RECORD OF CONFORMITY: Proof Roll Form completed & signed.
label | 198e9587-60d9-5bbc-ab4d-a4f6c7592647 |  | note | WP
label | 2e9c3812-568e-51a8-b6ee-7722a982f874 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
date | 51e51282-1ba0-54e7-a042-e683c3cc0c5c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Preparation of final surface
label | cc633459-d4c5-5d9e-9f7b-edc3aa32d2fd |  | note | FREQUENCY: Prior to construction of subgrade layer
label | 46ffd3ed-2251-553d-be26-908e0ba147ee |  | note | ACCEPTANCE CRITERIA: The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | 92086274-0b98-5725-a9fa-59ee31bcc692 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.15, Cl. 204.03(g)
label | 147fdf4c-b559-5acd-8289-d64e6f647a3b |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 77683725-8fdc-5ce6-b6af-474d1282bc61 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 6d77062b-cff4-5336-bbb4-1766e62c5025 |  | note | IP
label | bbcaa5fd-d4a0-51bf-b996-02179c26184b |  | note | RESPONSIBILITY: Site Engineer
date | f162f88c-e15f-5d08-8b76-5848b629dfb1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Conformity with Drawings
label | ef3d0dc1-dc1f-5b5b-ba50-6e6959dc4da1 |  | note | FREQUENCY: Prior to construction of subgrade layer
label | c0ee9d20-f63f-589b-aa10-b8a4b63c621a |  | note | ACCEPTANCE CRITERIA: Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water. Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings
label | a373c4ee-651c-55f8-a23b-412f94c26f32 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.03(f)
label | fa9569cc-91c7-58ae-aa3f-6cc727558bb4 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | f88926fd-6c52-5cbd-bba2-655af5332e98 |  | note | RECORD OF CONFORMITY: Signed ITP
label | 6ff5a5c5-7225-5e10-90a1-008c4434e0de |  | note | IP
label | 9acf64db-68b5-5834-bb97-657b88dfd7f4 |  | note | RESPONSIBILITY: Site Engineer
date | 1f5b8501-3e02-5869-919b-7baaa27190c7 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Testing
checkpoint-status |  |  | checkpoint | 3.1 - Compaction Testing
label | 7de3481e-3e40-5740-9f25-85f6c1e553f3 |  | note | FREQUENCY: Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142 of VicRoads must be agreed with Superintendent.
label | c2b75495-2fbe-5c0c-98f3-11a8060789f4 |  | note | ACCEPTANCE CRITERIA: Type B Material placed more than 400 mm below top of Type B Material should be compacted to 97% of MDD. Type B Material placed within 400 mm of top of Type B Material should be compacted to 99% MDD.
label | dc8623db-c021-5810-a32b-fcd9288ced02 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.13(a), Cl.204.13(b) Table 204.131, Table 204.142
label | 9b3ff602-4f17-5863-aea7-2265843f2f15 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | f8c87d4a-1fcf-58de-9446-b6a889c1fc63 |  | note | RECORD OF CONFORMITY: Compaction Test Records
label | d1cf57fa-4eba-569a-9bdd-d6b2d02bf571 |  | note | TP
label | df7ba0b6-193e-5291-a593-2a1cccaf5617 |  | note | RESPONSIBILITY: Site Engineer
date | fa44d513-c9e3-5cc2-b404-cd5aced20dbd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Maximum Particle Size
label | 72f3f8b2-fea8-59d2-8c7e-aa865103088a |  | note | FREQUENCY: Test every lot (one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements.
label | 331d9c7c-73e3-54ee-869f-1049a34f9fe8 |  | note | ACCEPTANCE CRITERIA: Maximum particle size should be 150mm when soil is within 400mm of the top of Type B soil, and 400 mm at depths greater than 400 mm below the top of Type B material.
label | f96a34c7-8684-5e76-8ba1-f779b2fec7ab |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c), Cl.204.14(a)
label | b4046081-979b-5caa-9fda-088f3d65afe3 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 5b378ee0-12ed-537a-ace2-4748693c2388 |  | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
label | 1dcf40a2-7724-5fcd-9ae6-e7369f168b37 |  | note | TP
label | dd7ff0a5-82ef-534a-9b84-4178a22c35b0 |  | note | RESPONSIBILITY: Site Engineer
date | dc09a2b1-33d7-5370-8058-83ec7c690abf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - CBR/Swell
label | 1ff41f80-94fd-5821-9b00-e863a8685ced |  | note | FREQUENCY: The initial lot (one day's production or 10,000m2, whichever is lesser). Reduced testing frecuency (every 8 lots) for future lots shall be agreed with the Superintendent
label | ebca310a-9989-52dd-b1b3-cc6ad54ff70b |  | note | ACCEPTANCE CRITERIA: CBR: ≥ 2%, Swell: < 2.5% swells greater than or equal to 2.5% shall be classified as expansive and approved by the Superintendent).
label | 6647c7e4-6db2-5738-bc54-3b1ad48412c9 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14, Cl. 204.04(c) Table 204.141
label | 80196089-bcfb-5066-8eeb-f65a1f2ab999 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 5f54aaff-fa8f-5d22-afa1-a12c99a690f9 |  | note | RECORD OF CONFORMITY: CBR/Swell Test Records
label | d99d1124-8245-5d93-9fd9-7bc527566083 |  | note | TP
label | eda5e1e7-cb06-5643-bb4e-4eb96e6cc82f |  | note | RESPONSIBILITY: Site Engineer
date | fad40942-2109-5834-8079-932a80f43758 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Atterberg Limit Tests
label | 2d30f4ae-7962-5b0e-aee4-8602ede4b235 |  | note | FREQUENCY: 1 Test per 2 lots (each lot is one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements. Reduced testing frecuency (1 test per every 4 lots) for future lots shall be agreed with the Superintendent
label | 1478dfbc-dd91-5969-844d-6e6c874cda94 |  | note | ACCEPTANCE CRITERIA: Ensure that soil post-compaction is not classified as silt
label | bdaadeb0-3a74-5111-9a90-82c52169a3d0 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14 Table 204.141
label | 5cfdf5a5-6c2d-5d3b-a244-f7fc9517f9b5 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | a63a6ebe-256f-503c-a5d1-3a624c182e06 |  | note | RECORD OF CONFORMITY: PI Test Records
label | 8ea917bd-41d1-5a33-ae19-372b1ffa7090 |  | note | TP
label | 197c386f-d901-5216-afa0-15998ec0c83c |  | note | RESPONSIBILITY: Site Engineer
date | 9ea7dcf1-461a-58d1-a5d4-453e3e094e4b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | aefea1b7-262d-58d1-96e7-6f6c85134605 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 1a177e84-1701-5b17-a87c-5ae2cf8300da |  | textbox | Print Name:
text | ef147254-2730-5896-aa07-3409c4167775 |  | textbox | Position:
date | 76bd8f8b-fa50-523e-9c81-a3dfc94e0f36 |  | date | Date: