## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-014
Revision :
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Ballarto Road |  | Preparation of Subgrade |  | Name: | Ruby Lewis | Name: | Nikhil Patil |  | Name: | Nikhil Patil
Contract No: |  | DOT28757 |  | Specifications: VicRoads Standard Specification Section 204
|  |  |  | Structure / Component: Pavement |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : | 2024-02-15 | Date : | 2024-02-15 |  | Date : | 2024-02-15
Lot No: |  |  | Lot Details: | Subgrade |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP | QMP, TMP, JSEA, SWMS, ITP | Visual Inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | N/A |  | N/A
2 | Construction Works
2.1 | Survey Set-Out |  | Prior to commencement of excavation | Area has been set out in accordance with the drawings | Work Procedure | Verify | This ITP signed | IP | Engineer/ Surveyor | N/A |  | N/A
2.2 | Excavation Permit |  | Lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | This ITP Signed Off | HP* | Project Engineer | N/A |  | N/A
2.3 | Material classified as silt |  | Prior to Commencing | Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent | VicRoads Spec. Cl. 204.04(c) | Document Review | Superintendent satisfied with Stabilisation Signed ITP/ records | HP | Engineer or Forman / Superintendent |  |  | N/A
2.4 | Acceptance of Rock Subgrade (when applicable) |  | Prior construction of the regulating layer | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review. | VicRoads Spec. Cl. 204.06(f) | Site Inspection/ Document Review | Superintendent acceptance Signed ITP | HP | Engineer or Forman / Superintendent |  |  | N/A
2.5 | Unsuitable Material |  | Each Lot | Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review. | 204.07(d) | Visual Inspection | This ITP Signed Off | HP | Engineer or Forman / Superintendent |  |  | N/A
2.6 | Groundwater |  | Each Lot | Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater | 204.06 (h) | Visual inspection | This ITP signed off | HP | Engineer or Forman / Superintendent |  |  | N/A
3 | Testing
3.1 | Proof Rolling |  | Each Lot | Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification | Cl 204.12 Section 173 | Visual Inspection | This ITP signed off | HP* WP | Engineer or Forman / Superintendent |  |  | N/A
3.2 | Compaction Testing |  | Each Lot | Ripped and re-compacted material below Cut Floor Level = minimum compaction 99% MDD. Type B Material placed within 400 mm of top of Type B Material = minimum compaction 99% MDD. Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 97% MDD. | Table 204.131 | Test Point | Test Records Lot Register | TP | Project Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.