## MFU-FH-ITP-0029
|  |  | Inspection and Test Plan - Control and Supervision of the Works Construction of Kerb & Channel | [7 empty] | Document # ITP-019
[11 empty] | Revision : 01 | Date :15/05/23
Client: | DTP |  | Construction Process: | Construction of Kerb & Channel |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Ballarto Road |  |  |  |  | Name: | Ruby Lewis | Name: | Nikhil Patil |  | Name: | Nikhil Patil
Contract No: | DOT28757 |  | Specifications: | Vicroads Sections 703 AS 2876 |  | Site Engineer |  | Quality Manager |  |  | Construction Manager
Structure / Component:
Date: |  |  | Location: |  |  | Date : | 2024-02-15 | Date : | 2024-02-15 |  | 2024-02-15
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing Work | All personnel on site have been inducted to Fulton Hogan site | Inductions Register | Document review | Site induction signed | AP | Site Engineer / Site Foreman | N/A
1.2 | Safety measures are in place, SWMS undertaken |  | Prior to commencing | A Safe Work Method Statement for identified hazards shall be signed onto by the contractors on site. Where a SWMS is amended, a copy of all relevant documentation and details shall be immediately submitted. | Fulton Hogan OH&S | Document Review | SWMS(s) signed | HP | Site Engineer, Site Foreman & Superintendent
1.3 | Check that current revision drawings are being used |  | Prior to Commencing Work | Issued For Construction (IFC) and latest available revision used | IFC Project Drawings/ Drawing Register | Document review | Latest revision IFC drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing Work | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | EMP, induction register | Document review & Site inspection | Site induction signed This ITP signed | IP | Site Engineer | N/A
1.5 | Excavation Permit issued |  | Prior to Commencing Work | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review & Site inspection | Excavation Permit # | HP* | Site Engineer | N/A |  | N/A
1.6 | Traffic Management (When required) |  | Prior to Commencing | Approved TMP and MOA | TMP Relevant to work zone | Document review & Site inspection | Approved TMP & MOA | IP | Project Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Setting Out |  | Prior to Commencing Work | Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional properties as shown on the drawings. | VicRoads Spec Cl.703.17 | Site inspection | Survey records & pegs on the ground This ITP Signed off | HP | Project Engineer, Superintendent & Surveyor |  |  | N/A
2.2 | Service Location |  | Prior to Commencing | Current DBYD documents received and works executed by qualified service locator. | DBYD | Site Inspection | Services marked on current IFC drawings and on the ground. | HP* | Site Engineer | N/A
2.3 | Temporary Drainage Provisions |  | Prior to Commencing | If obstructing waterways, culverts or channels, temporary diversion of discharge and stormwater to be in place. The safe discharge of drainage and stormwater is to be maintained at all times during construction, with prior written approval sought from the relevant waterway authority. | VicRoads Spec Cl.703.18 | Site Inspection | Writen approval from relevant waterway authority This ITP to be signed | AP | Supervisor / Site Engineer | N/A |  | N/A
2.4 | Bedding |  | Each lot | All bedding material used for cast in place concrete paving works shall be compacted size 20mm Class 3 or 4 Crushed Rock or Class 3 or 4 Crushed Concrete, manufactured and supplied in accordance with sections 812 or 820 respectively. Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface. | VicRoads Spec Cl.703.21 | Site Inspection | This ITP to be signed. Visual proof record and Crushed Rock Certificate. | IP | Site Engineer | N/A
2.5 | Pre-concrete check |  | Each lot | Concrete shall not be placed when the air temperature measured at the point of placement is >35 C or < 5 C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10 C or greater than 32 C. Unless otherwise specified concrete shall be N32 standard strength. Approved VR mix used. Concrete extrusion machines have minimum cement content of 320 kg/m3. | VicRoads Spec Cl.703.09 Cl.610.17 (a)(b) (c)(d) | Site Inspection/ Temp Verification | This ITP to be signed | IP | Supervisor / Site Engineer | N/A
2.6 | Machine Extrusion |  | Each lot | Concrete shall be fed to the machine at a uniform rate. The machine shall be operated to produce a satisfactorily compacted, dense mass of concrete free of any faulty or honeycombed patches. Surfaces shall be substantially free from surface pitting larger than 5mm diameter. | VicRoads Spec Cl 703.23 | Site Inspection | This ITP to be signed | IP | Site Engineer | N/A
2.7 | Tolerances |  | Each lot | Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm. Deviation of finished work shall not exceed; 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas. Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm. | VicRoads Spec. Cl 703.15 | Site Inspection | This ITP to be signed | IP | Site Engineer | N/A
2.8 | Finish Surfaces |  | Each lot | Egdings: Rendering shall be applied witihin 30 minutes of placing or extruding concrete. Rendered to a thickness not exceeding 3mm and steel trowel finished. Footpaths and Surfacing: Use a wooden float for a lightly textured non-skid finish. Concrete to have a neat appearance and uniform colour | VicRoads Spec. Cl 703.25 | Site Inspection/ Temp Verification | This ITP to be signed | IP | Supervisor/Site Engineer | N/A
2.9 | Joints |  | Each joint | Transverse joints: constructed at right angles to the back of edgings and the edge of surfacing at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section). | VicRoads Spec. Cl 703.26 | Site Inspection / Verification | This ITP to be signed | IP | Supervisor / Site Engineer | N/A
2.1 | Backfilling |  | Frequency | Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging, unless otherwise specified. | VicRoads Spec. Cl 703.29 | Site Inspection / Verification | This ITP to be signed | IP | Supervisor | N/A
3 | Completion
3.1 | Survey data captured for as-built purposes |  | Completion of each lot | Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings. | IFC Drawings / survey records | Document review | As-built survey records | SCP | Project Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent