## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-016 - Topsoil Placement | itp |  |  |  |  | ITP-016 - Topsoil Placement
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Ensure correct materials are being used
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Topsoil placed on formations and disturbed areas shall be capable of supporting healthy, full cover of grass growth, and contain organic material
label | ○ Topsoil material shall be free from subsoil, tree roots, clay balls, stones, rocks, rubbish, contaminants, weeds, pathogens and toxic levels of any element with a pH in the range of 5 to 8.
label | ○ Imported topsoil shall conform to the material properties outlined in Table 720.042
label | REFERENCE DOCUMENTS: 204.04a
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed, Material Test Report (Import Only)
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Stripping Topsoil
checkpoint | 2.1 - Survey Set Out
label | FREQUENCY: Prior to commencing stripping
label | ACCEPTANCE CRITERIA: Area has been pegged out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Surveyor
date | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Designation of stock pile area or disposal site
label | FREQUENCY: Prior to commencing stripping
label | ACCEPTANCE CRITERIA: An area for stockpiling has been designated or a disposal site identified
label | REFERENCE DOCUMENTS: 204.05c
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Weed treatment
label | FREQUENCY: Prior to commencing stripping
label | ACCEPTANCE CRITERIA: Site has been inspected for noxious weeds and weed treated if present
label | REFERENCE DOCUMENTS: 204.05c
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.5 - Maintenance of stockpiles
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Stockpiles maintained neatly and away from stormwater drains
label | ○ Erosion controls in place
label | ○ Stockpile treated to minimise spread of weeds and pathogens
label | REFERENCE DOCUMENTS: 204.05c
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
section | 3 - Placing Topsoil
checkpoint | 3.1 - Topsoil Placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Confirm underlying cut/fill areas comply with Cl204.03 before placing topsoil. All disturbed areas not paved or landscaped topsoiled to the following depths:
label | ○ batter slopes > 2:1 = 50mm min
label | ○ planting beds = 100mm min
label | ○ verge - 50mm outer edge to 20mm within 100mm of seal
label | ○ all other areas – 75mm min
label | REFERENCE DOCUMENTS: Cl 204.17
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 3.2 - Surface level
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Area topsoiled spread, levelled, but not compacted (except verge area).
label | REFERENCE DOCUMENTS: Cl 204.17
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: