## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-019 - Construction of Kerb & Channel (Rev 01) | itp |  |  |  |  | ITP-019 - Construction of Kerb & Channel (Rev 01)
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to Fulton Hogan site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: A Safe Work Method Statement for identified hazards shall be signed onto by the contractors on site.
label | ○ Where a SWMS is amended, a copy of all relevant documentation and details shall be immediately submitted.
label | REFERENCE DOCUMENTS: Fulton Hogan OH&S
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP
label | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: IFC Project Drawings/ Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest revision IFC drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP, induction register
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Site induction signed, This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Excavation Permit #
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Traffic Management (When required)
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Approved TMP and MOA
label | REFERENCE DOCUMENTS: TMP Relevant to work zone
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Approved TMP & MOA
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.
label | ○ The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
label | ○ The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional properties as shown on the drawings.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.17
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground, This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer, Superintendent & Surveyor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Service Location
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current DBYD documents received and works executed by qualified service locator.
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Services marked on current IFC drawings and on the ground.
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Temporary Drainage Provisions
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge and stormwater to be in place.
label | ○ The safe discharge of drainage and stormwater is to be maintained at all times during construction, with prior written approval sought from the relevant waterway authority.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.18
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Writen approval from relevant waterway authority, This ITP to be signed
label | AP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.4 - Bedding
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All bedding material used for cast in place concrete paving works shall be compacted size 20mm Class 3 or 4 Crushed Rock or Class 3 or 4 Crushed Concrete, manufactured and supplied in accordance with sections 812 or 820 respectively.
label | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.21
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP to be signed. Visual proof record and Crushed Rock Certificate.
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Pre-concrete check
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature measured at the point of placement is >35 C or < 5 C.
label | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10 C or greater than 32 C.
label | ○ Unless otherwise specified concrete shall be N32 standard strength. Approved VR mix used. Concrete extrusion machines have minimum cement content of 320 kg/m3.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl 703.23
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.6 - Machine Extrusion
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete shall be fed to the machine at a uniform rate.
label | ○ The machine shall be operated to produce a satisfactorily compacted, dense mass of concrete free of any faulty or honeycombed patches.
label | ○ Surfaces shall be substantially free from surface pitting larger than 5mm diameter.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl 703.23
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Tolerances
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm.
label | ○ Deviation of finished work shall not exceed; 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas.
label | ○ Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.15
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.8 - Finish Surfaces
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Egdings: Rendering shall be applied witihin 30 minutes of placing or extruding concrete.
label | ○ Rendered to a thickness not exceeding 3mm and steel trowel finished. Footpaths and Surfacing: Use a wooden float for a lightly textured non-skid finish.
label | ○ Concrete to have a neat appearance and uniform colour
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.25
label | INSPECTION/TEST METHOD: Site Inspection/ Temp Verification
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Supervisor/Site Engineer
date | Date Completed:
checkpoint | 2.9 - Joints
label | FREQUENCY: Each joint
label | ACCEPTANCE CRITERIA: Transverse joints: constructed at right angles to the back of edgings and the edge of surfacing at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.26
label | INSPECTION/TEST METHOD: Site Inspection / Verification
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.10 - Backfilling
label | FREQUENCY: Frequency
label | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay.
label | ○ Topsoil compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging, unless otherwise specified.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.29
label | INSPECTION/TEST METHOD: Site Inspection / Verification
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Supervisor
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Survey data captured for as-built purposes
label | FREQUENCY: Completion of each lot
label | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements.
label | ○ Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
label | ○ As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | REFERENCE DOCUMENTS: IFC Drawings / survey records
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: As-built survey records
label | SCP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: