## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-010 - Insitu Pit Construction | itp |  |  |  |  | ITP-010 - Insitu Pit Construction
section | 1 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | 1.3 - Use of approved mix design
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Concrete mixes used will be inline with Table 705.041 - VR330/32 for drainage pits
label | REFERENCE DOCUMENTS: Cl 705.04
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation.
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Excavation and erection of falsework/formwork
checkpoint | 2.1 - Excavation
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
label | REFERENCE DOCUMENTS: Cl 705.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | 2.2 - Construction Methodology
label | FREQUENCY: Prior to erection
label | ACCEPTANCE CRITERIA: Formwork shall be used in such a manner that it can be removed without damage to the concrete.
label | ○ Formwork shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to to confine freshly placed concrete and maintain position and shape during construction.
label | REFERENCE DOCUMENTS: Cl 703.12
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
section | 3 - Steel reinforcing
checkpoint | 3.1 - Placement methodology
label | FREQUENCY: At all times
label | ACCEPTANCE CRITERIA: All steel reinforcement to be securely held during placing and compacting of concrete.
label | ○ Supports shall be of a material durable to impose loads without movement of the reinforcement.
label | ○ The placement method shall not allow the reinforcement to become contaminated by contact with other steel.
label | REFERENCE DOCUMENTS: Cl 703.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | 3.2 - Minimum Cover
label | FREQUENCY: At all times
label | ACCEPTANCE CRITERIA: The specified minimum cover must be maintained at all tire wire positions. A tolerance of 0 to +5mm is allowed.
label | REFERENCE DOCUMENTS: Cl 703.13
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
section | 4 - Pre-pour Planning and Inspection
checkpoint | 4.1 - Pre-pour inspection
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement and embedments comply with the project drawings and specifications. Hold Point released by the Superintendent.
label | REFERENCE DOCUMENTS: CL 705.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Placing Concrete
checkpoint | 5.1 - Carry out sampling of concrete
label | FREQUENCY: 0-50m3 - 1 sample
label | ACCEPTANCE CRITERIA: No. of Samples: 0 to 50m3 - 1 No.
label | REFERENCE DOCUMENTS: Cl 703.11
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: CLB, CLC
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 5.2 - Compressive testing
label | FREQUENCY: 0-50m3 - 1 sample
label | ACCEPTANCE CRITERIA: A minimum of one cylinder shall be tested at 7 days and a minimum of 2 cylinders at 28 days.
label | ○ The average compressive strength at 28 days shall not be lower than the specified minimum compressive strength.
label | ○ Additioinally, the compressive strength of each individual cylinder shall be no less than 90% of that at 28 days.
label | REFERENCE DOCUMENTS: Cl 703.11
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Concrete test records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 5.3 - Placement methodology
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials.
label | ○ Concrete shall not be freely dropped from height >2m
label | ○ Concrete shall not be moved horizontally by vibrators
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | 5.4 - Compaction
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Vibration shall be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer.
label | ○ Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly.
label | ○ Concrete shall not be vibrated to the point where segregation of the ingredients occurs.
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: