## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Metro Laying Hotmix Asphalt ITP | itp |  |  |  |  | Metro Laying Hotmix Asphalt ITP
section | 1 - Preliminary Works
checkpoint | 1.1 - Mix Design approval
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Mix design to be used has been approved by project superintendent, prior to use
label | REFERENCE DOCUMENTS: 407.09 Mix Design Registration
label | INSPECTION/TEST METHOD: Approval Correspondance
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Project Engineer/ Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Supervisor
date | Date Completed:
checkpoint | 1.3 - Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs and Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | – Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan"
label | REFERENCE DOCUMENTS: 407.17
label | INSPECTION/TEST METHOD: Infrared Thermometer
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Supervisor
date | Date Completed:
checkpoint | 1.4 - Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints for the final Wearing Course are located on lane lines
label | ○ Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines
label | REFERENCE DOCUMENTS: 407.21
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Project engineer FHC
date | Date Completed:
checkpoint | 1.5 - Tack Coat
label | FREQUENCY: Prior to Commencing paving
label | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.25-0.50 L/m2 of CRS60. This rate is to be doubled on joints and chases. Tack coat must be allowed to fully cure.
label | ○ NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces
label | ○ Photographical evidence must be obtained (with an identifiable landmark)
label | *from 1st July 2022, "trackless Tack Coat" must be used
label | REFERENCE DOCUMENTS: 407.19 AS2150 11
label | INSPECTION/TEST METHOD: Spray area and inspect
label | RECORD OF CONFORMITY: Completed ITP, Photograph
label | IP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Foreman
date | Date Completed:
checkpoint | 1.6 - Water Resistant Bituminous Bond Coat (Open Graded Asphalt)
label | FREQUENCY: Prior to Commencing paving
label | ACCEPTANCE CRITERIA: A water resistant bond coat shall be applied to the existing surface consisting of cationic rapid setting bitumen emulsion (60% bitumen content) applied at a rate of application of not less than 0.5 l/m2 using a calibrated sprayer to uniformly spray the emulsion.
label | REFERENCE DOCUMENTS: 417.09
label | INSPECTION/TEST METHOD: Spray area and inspect
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Foreman
date | Date Completed:
section | 2 - Asphalt Placement Works
checkpoint | 2.1 - Commencement of Placing
label | FREQUENCY: Prior to Commencing paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority.
label | REFERENCE DOCUMENTS: 407.23
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Delivery of Mix
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Check correct mix design has been supplied, as per pavement design.
label | REFERENCE DOCUMENTS: Pavement Design Details 407.20
label | INSPECTION/TEST METHOD: Check asphalt delivery docket
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Foreman
date | Date Completed:
checkpoint | 2.3 - Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: 407.11 Table 407.111
label | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Foreman
date | Date Completed:
checkpoint | 2.4 - Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Measure and Record on Daily Lot Record
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Fulton Hogan Foreman/ Engineer
date | Date Completed:
checkpoint | 2.5 - Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: Pavement Design Details 407.25(a),(b)
label | INSPECTION/TEST METHOD: Dips using ruler or dip stick
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Foreman
date | Date Completed:
checkpoint | 2.6 - Paver Stoppages
label | FREQUENCY: If paver stops
label | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | REFERENCE DOCUMENTS: 407.25 (c)
label | INSPECTION/TEST METHOD: Thermometer
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Foreman
date | Date Completed:
checkpoint | 2.7 - Surface Finish of Wearing Course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: 407.25 (c)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Foreman
date | Date Completed:
checkpoint | 2.8 - Kerb and Channel
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | REFERENCE DOCUMENTS: 407.29 (a)(ii)
label | INSPECTION/TEST METHOD: Visual Inspection & Measurement
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Foreman
date | Date Completed:
checkpoint | 2.9 - Trafficking pavement after placment
label | FREQUENCY: After final roll
label | ACCEPTANCE CRITERIA: Trafficking or placement of asphalt over type SF asphalt is not permitted unless the majority of the SF asphalt has a surface temperature of 50°C or less and Falling.
label | ○ Where trafficking of SF aspahlt results in deformation, further trafficking shall cease until such time that the type SF aspahlt has adequately cooled to allow works to continue without further damage. For Stone Mastic Asphalt, this must be 40°C.
label | REFERENCE DOCUMENTS: 407.28, 404.14
label | INSPECTION/TEST METHOD: Visual Inspection & Thermometert
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Asphalt Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing
checkpoint | 3.1 - Compaction Testing (Open Graded Apshalt)
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Accpetance of compaction shall be on a procedural basis
label | REFERENCE DOCUMENTS: 417.12,
label | INSPECTION/TEST METHOD: OGA/SMA Compaction Procedure
label | RECORD OF CONFORMITY: Completed ITP
label | TP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Fulton Hogan Laboratory Technician
date | Date Completed:
checkpoint | 3.2 - Compaction Testing (Stone Mastic Apshalt)
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Per lot, the Characteristic Density Ratio must meet the minimum limit of 96.0%
label | ○ For layers thinner than 25mm, acceptance may be on a procedural basis.
label | REFERENCE DOCUMENTS: 404.15, 404.14 OGA/SMA Compaction Procedure
label | INSPECTION/TEST METHOD: Nuclear Density Test, OGA/SMA Compaction Procedure
label | RECORD OF CONFORMITY: Completed ITP, Compaction rerports
label | TP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
date | Date Completed:
checkpoint | 3.3 - Compaction Testing (Dense Graded Apshalt)
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits:
label | ○ >50mm layer depth = 96.0%
label | ○ <50mm layer depth = 95.0%
label | – Additional Test must be undertaken on the longitudinal joints for wearing courses
label | ○ Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0%
label | ○ Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis
label | ○ Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis
label | REFERENCE DOCUMENTS: Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure
label | INSPECTION/TEST METHOD: Nuclear Density Test, DGA Compaction Procedure
label | RECORD OF CONFORMITY: Completed ITP, Compaction rerports
label | TP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
date | Date Completed:
checkpoint | 3.4 - Level Conformance
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b)
label | REFERENCE DOCUMENTS: 407.30, 407.29
label | INSPECTION/TEST METHOD: Survey Results
label | RECORD OF CONFORMITY: Completed ITP, Survey Conformance Results
label | WP
label | PROJECT ENGINEER/SITE ENGINEER/SUPERINTENDENT/SURVEYOR/FOREMAN: Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: