## Suspended Slabs Checklist
Notes | Parent Visi Title | Visi Title | Visi Description | Visi Type | Assignee | Reviewer | Required Field (#1) | Field Type (#1) | Required Field (#2) | Field Type (#2) | Required Field (#3) | Field Type (#3)
|  | Suspended Slabs Checklist |  | Inspection | I&D Group
| Suspended Slabs Checklist | Pre-Pour |  | Inspection | I&D Group
| Pre-Pour | Soffit Finish Check: Attached RCP has been referenced to identify soffit finish. |  | Task | I&D Group |  | Attach RCP. | Attachment
| Pre-Pour | Formwork Checks: Drawing Number |  | Task | I&D Group |  | Confirm Architectural concrete profile drawing no. & revision. | Attachment
| Pre-Pour | Formwork Checks: Set Down | Check all in-situ slab set down/shower bases/hobs have been installed in the correct location | Task | I&D Group
| Pre-Pour | Formwork Checks: Beam and Slab Depths | Check all beam and slab depths are correct as per IFC structural drawings | Task | I&D Group |  | Confirm Stuctural General arrangement drawing no. & revision | Attachment
| Pre-Pour | Formwork Checks: Cast-ins | Check installation of cast-ins (facade unistruts, crane and hoist ties) | Task | I&D Group
| Pre-Pour | Formwork Checks: Penetrations | Check all penetrations have been installed in accordance to the architectural concrete profile plan | Task | I&D Group
| Pre-Pour | Formwork Checks: Engineer's Inspection | Verify that formwork (frames, bases, tables, pans) have been inspected by formwork engineer | Task | I&D Group |  | Verify items have been rectified, and signed off by a formwork engineer prior to any suspended slab pour | Checkbox | Upload formwork engineer's inspection report | Attachment
| Pre-Pour | Reinforcement Checks: Drawing number | All reinforcement to be placed in accordance with the IFC structural drawings | Task | I&D Group |  | Confirm reinforcement drawings are attached in the inspection report | Checkbox
| Pre-Pour | Reinforcement Checks: Engineer's Inspection | Verify Engineers reinforcement inspection report received and all items are closed out | Task | I&D Group |  | Verify inspection report items have been closed out | Checkbox
| Pre-Pour | Reinforcement Checks: Additional reo required outside base engineer, eg Crane tie, alimak, etc | Check for correct bar diameter | Task | I&D Group
| Pre-Pour | Post Tensioning: Drawing Number | All post tensioning to be placed in accordance with the IFC structural drawings. | Task | I&D Group |  | Confirm Post tensioning drawings are attached in the inspection report | Checkbox
| Pre-Pour | Post Tensioning: Ducts, Strands, Anti Burst & Trimmer Bars | Check P.T. ducts, strands, anti burst & trimmer bars are installed and securely fixed in place | Task | I&D Group
| Pre-Pour | Post Tensioning: Engineer's Inspection | Verify Engineers P.T. inspection report received and items closed out | Task | I&D Group |  | Verify inspection report items have been closed out | Checkbox | Upload engineer's P.T. inspection report | Attachment
| Pre-Pour | Preparation for Pour: Area Cleaned | Check pour area cleaned before pour to ensure suspended slab is free of standing water, debris, oils, objectionable coatings & fragments | Task | I&D Group
| Pre-Pour | Preparation for Pour: Temperature Checks | Ensure temperatures when pouring are within acceptable criteria Tester ordered - (1, 4, 7 and 28 day samples) 0 - 50m3 - 1 batch of tests or thereof 50-100m3 - 2 batch of tests or thereof >100m3 - add 1 batch of tests for every 50m3 | Task | I&D Group
| Pre-Pour | Preparation for Pour: Placement Method |  | Task | I&D Group |  | Confirm method used for placing concrete (Kibble or Pump) | Short Answer
| Pre-Pour | Placement of Concrete: Concrete Vibration Length | Check vibrators are long enough to ensure full compaction. A minimum of one of vibrator must be used at all times while the pump is in operation | Task | I&D Group
| Suspended Slabs Checklist | Post Pour |  | Inspection | I&D Group
| Post Pour | Concrete Placement: Total Poured |  | Task | I&D Group |  | Total Poured (m3) | Short Answer | Please attach first and last concrete Docket | Attachment
| Post Pour | Placement of Concrete: Post Pour and post strip (where applicable) As Built Survey | Verify slab level as built has been completed and provided to client | Task | I&D Group |  | Upload as-built survey | Attachment
| Post Pour | Concrete Test Result | Verify concrete has reached the specified strength | Task | I&D Group |  | Test Result | Attachment
| Post Pour | PT Stressing Sign Off |  | Task | I&D Group |  | Verify all works have been completed | Checkbox

## Insitu Columns Checklist
Parent Visi Title | Visi Title | Visi Description | Visi Type | Assignee | Reviewer | Required Field (#1) | Field Type (#1) | Required Field (#2) | Field Type (#2) | Required Field (#3) | Field Type (#3)
| Insitu Columns Checklist |  | Inspection | I&D Group
Insitu Columns Checklist | Pre-Pour |  | Inspection | I&D Group
Pre-Pour | Set Out Checks: Columns | Check setting out for set-out of all columns | Task | I&D Group |  | Attach markup of columns poured | Attachment
Pre-Pour | Existing Slab Conditions: Column Transition | Confirm column transition at the top of the column is correct | Task | I&D Group
Pre-Pour | Formwork Checks: Penetrations | Check all penetrations and cast-in items are installed and in the correct location | Task | I&D Group
Pre-Pour | Reinforcement Checks: Placement | All reinforcement to be placed in accordance with the IFC structural drawings | Task | I&D Group
Pre-Pour | Reinforcement Checks: Column Reinforcment details | Check column reo matches IFC shop drawing and structrual engineers details. | Task | I&D Group
Pre-Pour | Preparation for Pour: Area Cleaned | Pour area cleaned before pour to ensure column is free of standing water, debris, oils, objectionable coatings & fragments | Task | I&D Group
Pre-Pour | Preparation for Pour: Temperature Checks | Ensure temperatures when pouring are within acceptable criteria Tester ordered - (7 & 28 day samples) 1 batch of tests or thereof for every 50m3 placed or one test sample per day each day | Task | I&D Group
Pre-Pour | Preparation for Pour: Placement Method |  | Task | I&D Group |  | Confirm method used for placing of concrete (Chute, Kibble or Pump) | Short Answer
Pre-Pour | Preparation for Pour: Placement Method | Check to ensure pour rate/pour height is as per engineers/manufacturers recommendation (if more than a single pour please specify) | Task | I&D Group
Insitu Columns Checklist | Post Pour |  | Inspection | I&D Group
Post Pour | Concrete Placement: Total Poured |  | Task | I&D Group |  | Total Poured (m3) | Short Answer | Please attach first and last concrete Docket | Attachment
Post Pour | Concrete Test Result | Verify concrete has reached the specified strength | Task | I&D Group |  | Test Result | Attachment

## Core Walls Checklist
Parent Visi Title | Visi Title | Visi Description | Visi Type | Assignee | Reviewer | Required Field (#1) | Field Type (#1) | Required Field (#2) | Field Type (#2) | Required Field (#3) | Field Type (#3)
Core Walls Checklist | Pre-Pour |  | Inspection | I&D Group
Pre-Pour | Set Out Checks: RL Top of Wall | RL may vary depending on location of work | Task | I&D Group |  | Check setting out for RL (top of wall) | Short Answer
Pre-Pour | Formwork Checks: Services Installed | All in-situ wall services have been installed and are in the correct location | Task | I&D Group
Pre-Pour | Formwork Checks: Penetrations & Cast-ins | All penetrations and are installed and in the correct location and are the correct size. | Task | I&D Group |  | Attach wall elevations with highlighted penetrations | Attachment
Pre-Pour | Formwork Checks: Engineer's Inspection | Formwork/Jumpform has been inspected/signed off by a competent person/engineer. | Task | I&D Group |  | Verify items have been rectified, and signed off by an engineer/ competant person. | Checkbox
Pre-Pour | Reinforcement Checks: Core Reinforcment details | Check Core reo matches IFC shop drawing and structrual engineers details. | Task | I&D Group |  | Confirm reinforcement drawings/ Elevations are attached in the inspection report | Checkbox
Pre-Pour | Reinforcement Checks: Key Boxes/Inserts Installed | Check key boxes/inserts are installed as per approved supplier shop drawings | Task | I&D Group
Pre-Pour | Reinforcement Checks: Engineer's Inspection | Verify Engineers reinforcement inspection report received and all items are closed out | Task | I&D Group |  | Verify inspection report items have been closed out.Attach relevant closeout photos and drawings. | Attachment
Pre-Pour | Reinforcement Checks: Engineer's Inspection | Lift cast items are installed and in the correct location and are the correct size. | Task | I&D Group |  | Verify cast in details have been followed and installed. | Checkbox
Pre-Pour | Preparation for Pour: Temperature Checks | Ensure temperatures when pouring are within acceptable criteria Tester ordered - (7 & 28 day samples) 1 batch of tests or thereof for every 50m3 placed or one test sample per day each day | Task | I&D Group
Pre-Pour | Preparation for Pour: Placement Method |  | Task | I&D Group |  | Confirm method used for placing of concrete (Kibble or Pump) | Short Answer
Pre-Pour | Preparation for Pour: Concrete Vibration | Ensure concrete vibration is completed with use of vibrator motor (minimum requirement of 300rpm) | Task | I&D Group
Core Walls Checklist | Post Pour |  | Inspection | I&D Group
Post Pour | Concrete Placement: Total Poured |  | Task | I&D Group |  | Total Poured (m3) | Short Answer | Please attach first and last concrete Docket | Attachment
Post-Pour | Stripping of Formwork: Defect Check | Visual check on walls once stripped to ensure honeycombing has occurred. | Task | I&D Group
Post-Pour | Stripping of Formwork: Defect Patching | Ensure patching to walls has been undertaken for any defect areas that are visible | Task | I&D Group
Post Pour | Concrete Test Result | Verify concrete has reached the specified strength | Task | I&D Group |  | Test Result | Attachment
Note on C6: Pat O'Donoghue: can we link one inpsction to all checklists per job.

## Stairform Stairs Checklist
Parent Visi Title | Visi Title | Visi Description | Visi Type | Assignee | Reviewer | Required Field (#1) | Field Type (#1) | Required Field (#2) | Field Type (#2) | Required Field (#3) | Field Type (#3)
| Stairform Stairs Checklist |  | Inspection | I&D Group
Stairform Stairs Checklist | Pre-Pour |  | Inspection | I&D Group
Pre-Pour | Set Out Checks: Penetrations | Ensure stairs are in correct position and all penetrations are in and correct(set-out & location) | Task | I&D Group |  | Attach Architectural, stair shop drawings and elevations. | Attachment
Pre-Pour | Formwork Checks: Dimensions & Spacings | Ensure spacings between flights are as per the IFC architectural drawings (allowing speed panel to fit between where aplicable). | Task | I&D Group
Pre-Pour | Formwork Checks: Risers | Ensure the correct number of risers are installed as per the IFC architectural and stair shop drawings | Task | I&D Group
Pre-Pour | Formwork Checks: Handrails | Check handrails are installed correctly (including clearance) as per approved shop-drawing | Task | I&D Group
Pre-Pour | Reinforcement Checks: Reinforcment is installed as per IFC documents. | Upload approved reinforcement drawings used for install and check for compliance. | Task | I&D Group |  | Verify all reinforcement has been placed in accordance with the IFC structural drawings and approved Stairform Shop-drawings | Attachment
Pre-Pour | Preparation for Pour: Area Cleaned | Pour area cleaned before pour to ensure column is free of standing water, debris, oils, objectionable coatings & fragments | Task | I&D Group
Pre-Pour | Preparation for Pour: Temperature Checks | Ensure temperatures when pouring are within acceptable criteria Tester ordered - (7 & 28 day samples) 1 batch of tests or thereof for every 50m3 placed or one test sample per day each day | Task | I&D Group
Pre-Pour | Preparation for Pour: Placement Method |  | Task | I&D Group |  | Confirm method used for placing of concrete (Chute, Kibble, Tremie Funel or Pump) | Short Answer
Pre-Pour | Preparation for Pour: Concrete Vibration | Ensure concrete vibration is completed with use of vibrator motor (minimum requirement of 300rpm) | Task | I&D Group
Pre-Pour | Placement of Concrete: Concrete Trends | Check concrete treads (nosing grove) finished in accordance with architectural specifications (if applicable) | Task | I&D Group
Stairform Stairs Checklist | Post Pour |  | Inspection | I&D Group
Post Pour | Concrete Placement: Total Poured |  | Task | I&D Group |  | Total Poured (m3) | Short Answer | Please attach first and last concrete Docket | Attachment
Post Pour | Concrete Test Result | Verify concrete has reached the specified strength | Task | I&D Group |  | Test Result | Attachment
[5 empty] | N20 | 5.98
N28

## Precast Panel Column Installat
Parent Visi Title | Visi Title | Visi Description | Visi Type | Assignee | Reviewer | Required Field (#1) | Field Type (#1) | Required Field (#2) | Field Type (#2) | Required Field (#3) | Field Type (#3)
| Precast Panel / Column Installation |  | Inspection | I&D Group
Precast Panel / Column Installation | IFC Marking Plan and Shop drawings |  | Task | I&D Group |  | Drawing & Revision Number | Attachment
Precast Panel / Column Installation | Precast Panel Pre-Instalation Checklist Received from Rigger |  | Task |  |  |  | Attachment
Precast Panel / Column Installation | Certification/Documentation: Propping Design | Precast panel / column propping design has been approved by a qualified independent engineer | Task | I&D Group |  |  | Attachment
Precast Panel / Column Installation | Certification/Documentation: Grouting Procedure / Product | Grouting procedure / product has been approved by engineer | Task | I&D Group |  |  | Attachment
Precast Panel / Column Installation | Installation Checks: 4.6 Fasteners | 4.6 Fasteners have been used and torqued to the manufacturer's specifications. Please attach Torque register | Task | I&D Group |  |  | Attachment
Precast Panel / Column Installation | Post Installation Checks: Caulking | Caulking has been carried out in accordance with approved caulking products. | Task | I&D Group
Precast Panel / Column Installation | Post Installation Checks: Stitch Plates Welded | Stitch plates have been welded in accordance with IFC structural drawings and weld inspections have been carried out. | Task | I&D Group
Precast Panel / Column Installation | Post Installation Checks: Patching of Stitch Plates | Patching of stitch plates has been completed. | Task | I&D Group
Precast Panel / Column Installation | Post Installation Checks: Prop Removal & Grout Strength | Prop bracing removed in consultation with temporary works engineer. | Task | I&D Group
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is always the same. Can we link all Precast checklists to one drawing