## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Suspended Slabs Checklist | [5 empty] | Suspended Slabs Checklist
section | Pre-Pour
checkpoint | Formwork Checks: Drawing Number
label | Confirm Architectural concrete profile drawing no. & revision.
checkpoint | Formwork Checks: Set Down
label | Check all in-situ slab set down/shower bases/hobs have been installed in the correct location
checkpoint | Formwork Checks: Beam and Slab Depths
label | Check all beam and slab depths are correct as per IFC structural drawings
label | Confirm Stuctural General arrangement drawing no. & revision
checkpoint | Formwork Checks: Cast-ins
label | Check installation of cast-ins (facade unistruts, crane and hoist ties)
checkpoint | Formwork Checks: Penetrations
label | Check all penetrations have been installed in accordance to the architectural concrete profile plan
checkpoint | Formwork Checks: Engineer's Inspection
label | Verify that formwork (frames, bases, tables, pans) have been inspected by formwork engineer
bool | Verify items have been rectified, and signed off by a formwork engineer prior to any suspended slab pour
label | Upload formwork engineer's inspection report
checkpoint | Reinforcement Checks: Drawing number
label | All reinforcement to be placed in accordance with the IFC structural drawings
bool | Confirm reinforcement drawings are attached in the inspection report
checkpoint | Reinforcement Checks: Engineer's Inspection
label | Verify Engineers reinforcement inspection report received and all items are closed out
bool | Verify inspection report items have been closed out
checkpoint | Reinforcement Checks: Additional reo required outside base engineer, eg Crane tie, alimak, etc
label | Check for correct bar diameter
checkpoint | Post Tensioning: Drawing Number
label | All post tensioning to be placed in accordance with the IFC structural drawings.
bool | Confirm Post tensioning drawings are attached in the inspection report
checkpoint | Post Tensioning: Ducts, Strands, Anti Burst & Trimmer Bars
label | Check P.T. ducts, strands, anti burst & trimmer bars are installed and securely fixed in place
checkpoint | Post Tensioning: Engineer's Inspection
label | Verify Engineers P.T. inspection report received and items closed out
bool | Verify inspection report items have been closed out
label | Upload engineer's P.T. inspection report
checkpoint | Preparation for Pour: Area Cleaned
label | Check pour area cleaned before pour to ensure suspended slab is free of standing water, debris, oils, objectionable coatings & fragments
checkpoint | Preparation for Pour: Temperature Checks
label | Ensure temperatures when pouring are within acceptable criteria
label | Tester ordered - (1, 4, 7 and 28 day samples)
label | 0 - 50m3 - 1 batch of tests or thereof
label | 50-100m3 - 2 batch of tests or thereof
label | >100m3 - add 1 batch of tests for every 50m3
checkpoint | Preparation for Pour: Placement Method
textbox | Confirm method used for placing concrete |  | (Kibble or Pump)
checkpoint | Placement of Concrete: Concrete Vibration Length
label | Check vibrators are long enough to ensure full compaction. A minimum of one of vibrator must be used at all times while the pump is in operation
section | Post Pour
checkpoint | Concrete Placement: Total Poured
textbox | Total Poured (m3)
label | Please attach first and last concrete Docket
checkpoint | Placement of Concrete: Post Pour and post strip (where applicable) As Built Survey
label | Verify slab level as built has been completed and provided to client
label | Upload as-built survey
checkpoint | Concrete Test Result
label | Verify concrete has reached the specified strength
label | Test Result
checkpoint | PT Stressing Sign Off
bool | Verify all works have been completed
checklist | Insitu Columns Checklist | [5 empty] | Insitu Columns Checklist
section | Pre-Pour
checkpoint | Set Out Checks: Columns
label | Check setting out for set-out of all columns
label | Attach markup of columns poured
checkpoint | Existing Slab Conditions: Column Transition
label | Confirm column transition at the top of the column is correct
checkpoint | Formwork Checks: Penetrations
label | Check all penetrations and cast-in items are installed and in the correct location
checkpoint | Reinforcement Checks: Placement
label | All reinforcement to be placed in accordance with the IFC structural drawings
checkpoint | Reinforcement Checks: Column Reinforcment details
label | Check column reo matches IFC shop drawing and structrual engineers details.
checkpoint | Preparation for Pour: Area Cleaned
label | Pour area cleaned before pour to ensure column is free of standing water, debris, oils, objectionable coatings & fragments
checkpoint | Preparation for Pour: Temperature Checks
label | Ensure temperatures when pouring are within acceptable criteria
label | Tester ordered - (7 & 28 day samples)
label | 1 batch of tests or thereof for every 50m3 placed or one test sample per day each day
checkpoint | Preparation for Pour: Placement Method (1)
textbox | Confirm method used for placing of concrete |  | (Chute, Kibble or Pump)
checkpoint | Preparation for Pour: Placement Method (2)
label | Check to ensure pour rate/pour height is as per engineers/manufacturers recommendation (if more than a single pour please specify)
section | Post Pour
checkpoint | Concrete Placement: Total Poured
textbox | Total Poured (m3)
label | Please attach first and last concrete Docket
checkpoint | Concrete Test Result
label | Verify concrete has reached the specified strength
label | Test Result
checklist | Core Walls Checklist | [5 empty] | Core Walls Checklist
section | Pre-Pour
checkpoint | Set Out Checks: RL Top of Wall
label | RL may vary depending on location of work
textbox | Check setting out for RL (top of wall)
checkpoint | Formwork Checks: Services Installed
label | All in-situ wall services have been installed and are in the correct location
checkpoint | Formwork Checks: Penetrations & Cast-ins
label | All penetrations and are installed and in the correct location and are the correct size.
label | Attach wall elevations with highlighted penetrations
checkpoint | Formwork Checks: Engineer's Inspection
label | Formwork/Jumpform has been inspected/signed off by a competent person/engineer.
bool | Verify items have been rectified, and signed off by an engineer/ competant person.
checkpoint | Reinforcement Checks: Core Reinforcment details
label | Check Core reo matches IFC shop drawing and structrual engineers details.
bool | Confirm reinforcement drawings/ Elevations are attached in the inspection report
checkpoint | Reinforcement Checks: Key Boxes/Inserts Installed
label | Check key boxes/inserts are installed as per approved supplier shop drawings
checkpoint | Reinforcement Checks: Engineer's Inspection
label | Verify Engineers reinforcement inspection report received and all items are closed out
label | Verify inspection report items have been closed out.Attach relevant closeout photos and drawings.
checkpoint | Reinforcement Checks: Engineer's Inspection
label | Lift cast items are installed and in the correct location and are the correct size.
bool | Verify cast in details have been followed and installed.
checkpoint | Preparation for Pour: Temperature Checks
label | Ensure temperatures when pouring are within acceptable criteria
label | Tester ordered - (7 & 28 day samples)
label | 1 batch of tests or thereof for every 50m3 placed or one test sample per day each day
checkpoint | Preparation for Pour: Placement Method
textbox | Confirm method used for placing of concrete |  | (Kibble or Pump)
checkpoint | Preparation for Pour: Concrete Vibration
label | Ensure concrete vibration is completed with use of vibrator motor (minimum requirement of 300rpm)
section | Post Pour
checkpoint | Concrete Placement: Total Poured
textbox | Total Poured (m3)
label | Please attach first and last concrete Docket
checkpoint | Stripping of Formwork: Defect Check
label | Visual check on walls once stripped to ensure honeycombing has occurred.
checkpoint | Stripping of Formwork: Defect Patching
label | Ensure patching to walls has been undertaken for any defect areas that are visible
checkpoint | Concrete Test Result
label | Verify concrete has reached the specified strength
label | Test Result
checklist | Stairform Stairs Checklist | [5 empty] | Stairform Stairs Checklist
section | Pre-Pour
checkpoint | Set Out Checks: Penetrations
label | Ensure stairs are in correct position and all penetrations are in and correct(set-out & location)
label | Attach Architectural, stair shop drawings and elevations.
checkpoint | Formwork Checks: Dimensions & Spacings
label | Ensure spacings between flights are as per the IFC architectural drawings (allowing speed panel to fit between where aplicable).
checkpoint | Formwork Checks: Risers
label | Ensure the correct number of risers are installed as per the IFC architectural and stair shop drawings
checkpoint | Formwork Checks: Handrails
label | Check handrails are installed correctly (including clearance) as per approved shop-drawing
checkpoint | Reinforcement Checks: Reinforcment is installed as per IFC documents.
label | Upload approved reinforcement drawings used for install and check for compliance.
label | Verify all reinforcement has been placed in accordance with the IFC structural drawings and approved Stairform Shop-drawings
checkpoint | Preparation for Pour: Area Cleaned
label | Pour area cleaned before pour to ensure column is free of standing water, debris, oils, objectionable coatings & fragments
checkpoint | Preparation for Pour: Temperature Checks
label | Ensure temperatures when pouring are within acceptable criteria
label | Tester ordered - (7 & 28 day samples)
label | 1 batch of tests or thereof for every 50m3 placed or one test sample per day each day
checkpoint | Preparation for Pour: Placement Method
textbox | Confirm method used for placing of concrete |  | (Chute, Kibble, Tremie Funel or Pump)
checkpoint | Preparation for Pour: Concrete Vibration
label | Ensure concrete vibration is completed with use of vibrator motor (minimum requirement of 300rpm)
checkpoint | Placement of Concrete: Concrete Trends
label | Check concrete treads (nosing grove) finished in accordance with architectural specifications (if applicable)
section | Post Pour
checkpoint | Concrete Placement: Total Poured
textbox | Total Poured (m3)
label | Please attach first and last concrete Docket
checkpoint | Concrete Test Result
label | Verify concrete has reached the specified strength
label | Test Result
checklist-flat | Precast Panel / Column Installation | [5 empty] | Precast Panel / Column Installation
checkpoint | IFC Marking Plan and Shop drawings
label | Drawing & Revision Number
checkpoint | Precast Panel Pre-Instalation Checklist Received from Rigger
label | Drawing & Revision Number
checkpoint | Certification/Documentation: Propping Design
label | Precast panel / column propping design has been approved by a qualified independent engineer
label | Drawing & Revision Number
checkpoint | Certification/Documentation: Grouting Procedure / Product
label | Grouting procedure / product has been approved by engineer
label | Drawing & Revision Number
checkpoint | Installation Checks: 4.6 Fasteners
label | 4.6 Fasteners have been used and torqued to the manufacturer's specifications. Please attach Torque register
label | Drawing & Revision Number
checkpoint | Post Installation Checks: Caulking
label | Caulking has been carried out in accordance with approved caulking products.
checkpoint | Post Installation Checks: Stitch Plates Welded
label | Stitch plates have been welded in accordance with IFC structural drawings and weld inspections have been carried out.
checkpoint | Post Installation Checks: Patching of Stitch Plates
label | Patching of stitch plates has been completed.
checkpoint | Post Installation Checks: Prop Removal & Grout Strength
label | Prop bracing removed in consultation with temporary works engineer.