## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CHK-002-CIV-CAMMS-Stormwater Drainage Pit Installation Rev 1 | itp |  |  |  | Yes | CHK-002-CIV-CAMMS-Stormwater Drainage Pit Installation Rev 1 | 1cd84ae7-48dd-4ca8-b587-550af6137787
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: CHK-CIV-CAMMS-Stormwater Drainage Pipes Installation
label | ITP Description: CAMMS-Stormwater Drainage Pipes Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 1
label | Revision Date: 7/08/2023
label | ITP created by: Victor Mira
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 Non Dependent
label | Reference: VR 701
label | 1.2 Main ITP
label | Reference: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
label | Acceptance Criteria: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
textbox | Enter: Main ITP Lot Number
section | Preliminaries - Materials
checkpoint | 2.1 Bedding
note | REFERENCE: VR 701
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Material Delivery Docket
textbox | Date Completed:
checkpoint | 2.2 Backfill Material
note | REFERENCE: VR 701
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Material Delivery Docket
textbox | Date Completed:
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Subcontractor QA Submissions and ITP
note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
note | ATTACH: Subcontractor Signed ITP
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
section | Construction Activities
checkpoint | 3.1 Survey Set Out
note | REFERENCE: VR 701.10
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.2 Pit Excavation
note | REFERENCE: VR 705.05
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.3 Excavation Foundation
note | REFERENCE: VR 705.05
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
note | > 80mm for clay foundations
note | > 150mm for rock foundations
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.7 Placement of Pit-Conformity with drawings
note | REFERENCE: VR 701.10
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
note | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
note | (c) invert level of pipes at pits ±50 mm
note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
note | ATTACH: Survey Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Survey Report
textbox | Date Completed:
checkpoint | 3.4 Jointing
note | REFERENCE: VR 705.11
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.5 Shaping of Floor
note | REFERENCE: VR 705.13
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.6 Step Irons
note | REFERENCE: VR 705.12
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.7 Fitting of Covers
note | REFERENCE: VR 705.17
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
note | ○ Height shall be within 10mm of the design level
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.9 Backfilling Around Drainage Pits
note | REFERENCE: VR 705.18
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual inspection
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Compaction and Moisture content tests
note | REFERENCE: VR 701.20
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
note | ATTACH: Compaction and Moisture content test results:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Test Results
textbox | Date Completed:
checkpoint | 6.2 CCTV Inspection
note | REFERENCE: VR 701.30
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
note | ATTACH: CCTV Report (PDF):
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: CCTV Reports
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP