## ITP Cover Page
Footpath Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 114 - Rev C
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 114
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Approved
ITP Description: |  |  | Footpath Construction |  |  |  |  | Revision: | 1000 |  | C
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A-3100-3124
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification, Appendices & RITS
Quality Specified: |  |  | RITS
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Approved | 2023-10-12 |  | Emil Karlsson | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Approved | 2023-12-05 |  | Emil Karlsson | [5 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | Approved | 2024-04-24 |  | Emil Karlsson |  | Addition of Concrete Reinforcing |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Footpath Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements | [6 empty] | Draft for Review
3.01.01 | Construction Pack | Methodology and ITP to be submitted to the Engineer and approved prior to works beginning | Downer | Construction Pack | Submit 10 days prior to commencement of works | HP | ENG
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.07 | Previous Completed Work Packs | Review previously completed workpacks to ensure work completed meets the contract requirements | Downer | CONQA | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | SUB ACTIVITY
4.01.01 | Bedding Sand | Record material type used and source testing of that material | BBO | Source Test/Site Notes | 1 source test per material type | R | SE
4.01.02 | Undercut Backfill | Record material type used and source testing of that material | BBO | Source Test/Site Notes | 1 source test per material type | R | SE
4.01.03 | Uniaxial, Biaxial and Triaxial Geogrid | All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval. | GWS 4.2 | Datasheet | At least two weeks prior to works. | HP | ENG
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | Footpath Construction
5.01.1 | Footpath | After set-out and prior to installation of footpaths | PS - 2.2.16 | Hold Point Release | Min 48h Notice | HP | SE
5.01.2 | Subgrade Preparation | The exposed subgrade (excavated to trial subgrade level or pavement depth) shall be tested by using a Scala Penetrometer for compliance with a CBR value >10 (4 blows per 100mm). For subgrade of CBR value <10 (4 blows per 100mm), refer to 5.01.3. | RITS - 3.4.9.4 | Scala Results | Every 15m | I | SE
5.01.3 | Subgrade Undercut and Subgrade Backfill | Subgrade CBR <10 but > 7 (3 blows per 100mm) 75mm GAP20, CBR <7 (2 blows per 100mm) 100mm undercut & 175mm GAP20, CBR < 3 100mm Undercut, grid (standard biaxial or triaxial equivalent) & 175mm GAP20. | RITS - D3.3.5 BBO | Hold Point Release | Every 15m | HP | ENG
5.01.4 | Undercut Geogrid Placement | Geogrid to be placed flat on subgrade. For areas that require lapping, lapping to be 500mm. | GWS 4.1 | Records | Each undercut | V | SE
5.01.5 | Subgrade Backfill Fill Compaction Testing - Aggregate Subgrade | Aggregate Subgrade Fill shall be compacted to Clegg Impact Value (CIV) 10 for footpaths upto 3m wide, and CIV20 for footpath greater than 3m wide. | RITS - 3.4.6.5 | Clegg Results | Every 15m | I | SE
5.01.6 | Bedding Sand | (For CBR > 10% or 4 blows per 100mm) - Bedding Sand to be replaced at a consistent thickness of 75mm free of foreign materials, bedding surface must be level and free of any peaks or troughs | RITS - 3.8.3.3 | Site Notes / Photos | Every 15m | I | SE
5.01.7 | Concrete Reinforcing | In instances where rain gardens are to be installed, adjacent footpaths consist of a reinforced footing and a mesh section (Pavement Type 4). 2 x D12 Longitudinal bars with a min lap length of 384mm & R10 Stirrups @ 600 CRS. Pavement Type 4 found in DWG3152 - 150mm Concrete with 665 Mesh on 100mm GAP20. Minimum cover of 50mm. | RITS - 3.4.5.4 | Site Notes / Photos | Min 24h Notice | I | SE
5.01.8 | Concrete Pre-Pour | The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from Council. | RITS - 3.4.5.3 | Hold Point Release, Pre-Pour Check | Min 48h Notice | HP | ENG
5.01.9 | Ground Preparation | Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed.Any foreign or organic material hall be cleaned out. | RITS - 3.4.5.3 | Pre-Pour Check | Each Pour | H | SE
5.01.10 | Frozen Ground & Unfavourable Conditions | Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall) | RITS - 3.4.5.3 | Pre-Pour Check | Each Pour | I | SE
5.01.11 | Curing Of Concrete | Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used. | RITS - 3.4.5.5 | Post Pour Check | Each Pour | I | SE
5.01.12 | Concrete Compressive Strength | Concrete to meet a placed 28-day compressive strength of 20-Mpa | RITS - D3.3.5 | Concrete Dockets | Each pour | R | SE
5.01.13 | Finished Work | Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work. | RITS - 3.4.5.7 | Post Pour | Each Pour | I | SE
5.01.14 | Contraction/Expansion Joints | Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and setout via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the footpath shall be removed and re-cast. For reinforced Concrete, Cuts to be 30mm depth to avoid contact with steel reinforcing. | RITS - 3.4.5.8 | Post Pour | Each Pour | I | SE
5.01.15 | Backfilling against Concrete Work | Backfilling against the poured footpath shall take place as soon as practicable after the concrete has reached sufficient strength, with particular emphasis at curves, corners, intersections and pedestrian kerb crossings but not prior to 36 hours after pouring. | RITS - 3.4.5.9 | Site Notes | Not prior to 36 hours after pouring | I | SE
5.01.16 | Finished Concrete (Surface Finish & Final Levels) | All final path and vehicle crossing surfaces shall be true to the lines and levels Specified and ‘broom’ finished. Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water. | RITS - 3.4.5.10 | Post Pour Check | Each Pour | I | SE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
7.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
7.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | H | SV
7.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth. | Downer | Redlines | Post construction | H | PE
7.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE