## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 114 - Footpath Construction Rev C | itp |  |  |  |  | ITP - 114 - Footpath Construction Rev C
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 10 days prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.07 - Previous Completed Work Packs
label | Acceptance / Conformance Criteria - Review previously completed workpacks to ensure work completed meets the contract requirements
label | Standard / Specification - Downer
label | Verifying Document - CONQA
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Bedding Sand
label | Acceptance / Conformance Criteria - Record material type used and source testing of that material
label | Standard / Specification - BBO
label | Verifying Document - Source Test/Site Notes
label | Frequency - 1 source test per material type
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.01.02 - Undercut Backfill
label | Acceptance / Conformance Criteria - Record material type used and source testing of that material
label | Standard / Specification - BBO
label | Verifying Document - Source Test/Site Notes
label | Frequency - 1 source test per material type
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.01.03 - Uniaxial, Biaxial and Triaxial Geogrid
label | Acceptance / Conformance Criteria - All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval.
label | Standard / Specification - GWS 4.2
label | Verifying Document - Datasheet
label | Frequency - At least two weeks prior to works.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.1 - Footpath
label | Acceptance / Conformance Criteria - After set-out and prior to installation of footpaths
label | Standard / Specification - PS - 2.2.16
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.2 - Subgrade Preparation
label | Acceptance / Conformance Criteria - The exposed subgrade (excavated to trial subgrade level or pavement depth) shall be tested by using a Scala Penetrometer for compliance with a CBR value >10 (4 blows per 100mm). For subgrade of CBR value <10 (4 blows per 100mm), refer to 5.01.3.
label | Standard / Specification - RITS - 3.4.9.4
label | Verifying Document - Scala Results
label | Frequency - Every 15m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.3 - Subgrade Undercut and Subgrade Backfill
label | Acceptance / Conformance Criteria - Subgrade CBR <10 but > 7 (3 blows per 100mm) 75mm GAP20, CBR <7 (2 blows per 100mm) 100mm undercut & 175mm GAP20, CBR < 3 100mm Undercut, grid (standard biaxial or triaxial equivalent) & 175mm GAP20.
label | Standard / Specification - RITS - D3.3.5 BBO
label | Verifying Document - Hold Point Release
label | Frequency - Every 15m
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.4 - Undercut Geogrid Placement
label | Acceptance / Conformance Criteria - Geogrid to be placed flat on subgrade. For areas that require lapping, lapping to be 500mm.
label | Standard / Specification - GWS 4.1
label | Verifying Document - Records
label | Frequency - Each undercut
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 5.01.5 - Subgrade Backfill Fill Compaction Testing - Aggregate Subgrade
label | Acceptance / Conformance Criteria - Aggregate Subgrade Fill shall be compacted to Clegg Impact Value (CIV) 10 for footpaths upto 3m wide, and CIV20 for footpath greater than 3m wide.
label | Standard / Specification - RITS - 3.4.6.5
label | Verifying Document - Clegg Results
label | Frequency - Every 15m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.6 - Bedding Sand
label | Acceptance / Conformance Criteria - (For CBR > 10% or 4 blows per 100mm) - Bedding Sand to be replaced at a consistent thickness of 75mm free of foreign materials, bedding surface must be level and free of any peaks or troughs
label | Standard / Specification - RITS - 3.8.3.3
label | Verifying Document - Site Notes / Photos
label | Frequency - Every 15m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.7 - Concrete Reinforcing
label | Acceptance / Conformance Criteria - In instances where rain gardens are to be installed, adjacent footpaths consist of a reinforced footing and a mesh section (Pavement Type 4). 2 x D12 Longitudinal bars with a min lap length of 384mm & R10 Stirrups @ 600 CRS. Pavement Type 4 found in DWG3152 - 150mm Concrete with 665 Mesh on 100mm GAP20. Minimum cover of 50mm.
label | Standard / Specification - RITS - 3.4.5.4
label | Verifying Document - Site Notes / Photos
label | Frequency - Min 24h Notice
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.8 - Concrete Pre-Pour
label | Acceptance / Conformance Criteria - The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from Council.
label | Standard / Specification - RITS - 3.4.5.3
label | Verifying Document - Hold Point Release, Pre-Pour Check
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.9 - Ground Preparation
label | Acceptance / Conformance Criteria - Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed.Any foreign or organic material hall be cleaned out.
label | Standard / Specification - RITS - 3.4.5.3
label | Verifying Document - Pre-Pour Check
label | Frequency - Each Pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.10 - Frozen Ground & Unfavourable Conditions
label | Acceptance / Conformance Criteria - Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall)
label | Standard / Specification - RITS - 3.4.5.3
label | Verifying Document - Pre-Pour Check
label | Frequency - Each Pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.11 - Curing Of Concrete
label | Acceptance / Conformance Criteria - Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used.
label | Standard / Specification - RITS - 3.4.5.5
label | Verifying Document - Post Pour Check
label | Frequency - Each Pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.12 - Concrete Compressive Strength
label | Acceptance / Conformance Criteria - Concrete to meet a placed 28-day compressive strength of 20-Mpa
label | Standard / Specification - RITS - D3.3.5
label | Verifying Document - Concrete Dockets
label | Frequency - Each pour
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 5.01.13 - Finished Work
label | Acceptance / Conformance Criteria - Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work.
label | Standard / Specification - RITS - 3.4.5.7
label | Verifying Document - Post Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.14 - Contraction/Expansion Joints
label | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and setout via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the footpath shall be removed and re-cast. For reinforced Concrete, Cuts to be 30mm depth to avoid contact with steel reinforcing.
label | Standard / Specification - RITS - 3.4.5.8
label | Verifying Document - Post Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.15 - Backfilling against Concrete Work
label | Acceptance / Conformance Criteria - Backfilling against the poured footpath shall take place as soon as practicable after the concrete has reached sufficient strength, with particular emphasis at curves, corners, intersections and pedestrian kerb crossings but not prior to 36 hours after pouring.
label | Standard / Specification - RITS - 3.4.5.9
label | Verifying Document - Site Notes
label | Frequency - Not prior to 36 hours after pouring
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.16 - Finished Concrete (Surface Finish & Final Levels)
label | Acceptance / Conformance Criteria - All final path and vehicle crossing surfaces shall be true to the lines and levels. Specified and ‘broom’ finished. Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water.
label | Standard / Specification - RITS - 3.4.5.10
label | Verifying Document - Post Pour Check
label | Frequency - Each Pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 7.01.01 - Construction Record Compilation
label | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 7.01.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 7.01.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 7.01.04 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | Standard / Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE