## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP031 - AGL Luminaires Installation | itp |  |  |  |  | ITP031 - AGL Luminaires Installation
section | 1.0 Preliminary Works
checkpoint | 1.1 - Check for correct documentation
note | Frequency: Prior to commencing any activity
note | Acceptance Criteria:
note | • Ensure that all employees and subcontractors are using the latest and complete set of drawings
note | Reference Documents:
note | • IFC Drawings
note | • Appendix K- AGL Specification
note | Inspection/ Test Method: Verify
note | Record of conformity: Drawings
note | IP
note | Responsibility: Subcontractor Representative
textbox | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
note | Frequency: Prior to commencing any activities
note | Acceptance Criteria:
note | • All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
note | Reference Documents:
note | • PSP
note | • EMP
note | • TMP
note | • JSEA
note | • SWMS
note | • WP
note | Inspection/ Test Method: Verify
note | Record of conformity: Site and Office Inspection
note | HP*
note | Responsibility: Site Engineer / Site Supervisor
textbox | Date Completed:
checkpoint | 1.3 - Material/Equipment Approvals and Certification
note | Frequency: Prior to Start
note | Acceptance Criteria:
note | • All materials shall be proven to meet contractual requirements prior to acceptance.
note | Reference Documents:
note | • Appendix K- AGL Specification Section 2.3.3
note | Inspection/ Test Method: Verify
note | Record of conformity: Datasheet / Material Submission
note | HP*
note | Responsibility: Site Engineer
textbox | Date Completed:
section | 2.0 Installation of Light
checkpoint | 2.1 - Setting out of Airfield Luminaires
note | Frequency: Each Lot
note | Acceptance Criteria:
note | • Surveyor to confirm location with IFC drawings. Alignment of luminaire positions, shallow seating pots to be checked.
note | Reference Documents:
note | • IFC Drawings
note | • 12554937-E031 to 12554937-E037
note | Inspection/ Test Method: Verify
note | Record of conformity: SCP
note | IP
note | Responsibility: Site Engineer / Surveyor
textbox | Date Completed:
checkpoint | 2.2 - Coring
note | Frequency: Each Light
note | Acceptance Criteria:
note | • As required, Core asphalt to depth as per subcontractor ITC for relevant Method. Remove blanking plate and clean void.
note | Reference Documents:
note | • IFC Drawings
note | • 12554937-E031 to 12554937-E037
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed & Sub-contractor ITC
note | IP
note | Responsibility: Site Engineer / Site Supervisor
textbox | Date Completed:
checkpoint | 2.3 - Saw Cutting
note | Frequency: Each Light
note | Acceptance Criteria:
note | • Saw cut pavement to accommodate new light base. Protect edges as required.
note | Reference Documents:
note | • IFC Drawings
note | • 12554937-E031 to 12554937-E037
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed & Sub-contractor ITC
note | IP
note | Responsibility: Site Engineer / Site Supervisor
textbox | Date Completed:
checkpoint | 2.4 - Installation of Inset light
note | Frequency: Each light
note | Acceptance Criteria:
note | • Ensure correct light is installed in correct position as per the IFC drawings, this ITP and ITC
note | Reference Documents:
note | • IFC Drawings
note | • 12554937-E031 to 12554937-E037
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed & Sub-contractor ITC
note | IP
note | Responsibility: Site Engineer / Site Supervisor
textbox | Date Completed:
checkpoint | 2.5 - Light spacing
note | Frequency: Each Light
note | Acceptance Criteria:
note | • Ensure gap between new light base and pavement not less than 7mm and not more than 15mm.
note | Reference Documents:
note | • IFC Drawings
note | • 12554937-E031 to 12554937-E037
note | Inspection/ Test Method: Verify
note | Record of conformity: This ITP Signed & Sub-contractor ITC
note | IP
note | Responsibility: Site Engineer / Site Supervisor
textbox | Date Completed:
checkpoint | 2.6 - Recess Sealing
note | Frequency: Each light
note | Acceptance Criteria:
note | • Seal top of recess around light base with Dowsil 888 in concrete. Sealant in asphalt as detailed in IFC Drawing.
note | Reference Documents:
note | • IFC Drawings
note | • 12554937-E033
note | Inspection/ Test Method: Verify
note | Record of conformity: This Signed ITP / ITC/As-Built Documentation
note | IP
note | Responsibility: Site Engineer / Site Supervisor
textbox | Date Completed:
checkpoint | 2.7 - Installation of secondary and Earthing Cable
note | Frequency: Each Light
note | Acceptance Criteria:
note | • Each fitting shall have earthing cable provided
note | – Earthing to be 6mm2 single core green/yellow PVC cable.
note | – Twin secondary cable to be 4mm2 each.
note | Reference Documents: -
note | Inspection/ Test Method: Verify
note | Record of conformity: This Signed ITP & Sub-contractor ITC
note | IP
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 2.8 - Series Isolation transformer
note | Frequency: Each Light
note | Acceptance Criteria:
note | • Each luminaire / fitting shall be connected to a series isolation transformer in closest SIT duct pit/ junction can.
note | Reference Documents:
note | • IFC Drawings
note | • 12554937-E031 to 12554937-E037
note | Inspection/ Test Method: Verify
note | Record of conformity: This Signed ITP & Sub-contractor ITC
note | IP
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 2.9 - Luminaire Circuit
note | Frequency: Each Light
note | Acceptance Criteria:
note | • Each luminaire fitting shall be installed on the appropriate circuit as specified in the construction drawings.
note | Reference Documents:
note | • IFC Drawings
note | • 12554937-E031 to 12554937-E037
note | Inspection/ Test Method: Verify
note | Record of conformity: This Signed ITP / As-Built Documentation
note | IP
note | Responsibility: Site Engineer
textbox | Date Completed:
section | 3.0 Post Construction
checkpoint | 3.1 - Redundant equipment
note | Frequency: Each Light
note | Acceptance Criteria:
note | • All existing AGL bases shall be raised, abandoned, removed or replaced as per specification
note | Reference Documents:
note | • Appendix K- AGL Specification Section 3.5.2
note | Inspection/ Test Method: Verify
note | Record of conformity: This Signed ITP & Sub-contractor ITC
note | IP
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 3.2 - Equipment Survey
note | Frequency: Each Light
note | Acceptance Criteria:
note | • Accurately survey the location of airfield lighting equipment.
note | • The survey plan, endorsed by a registered surveyor, must identify the location of all installed equipment in relation to permanent site features and other underground Services.
note | • The survey must also capture all installation details such as the orientation and rotation of visual aids, colour pattern, constructed foundations, etc.
note | Reference Documents:
note | • Appendix K- AGL Specification Section 3.4
note | Inspection/ Test Method: Verify
note | Record of conformity: This Signed ITP & Sub-contractor ITC
note | IP
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | 3.3 - As-Built
note | Frequency: Each Light
note | Acceptance Criteria:
note | • Submission of surveyed luminaire position to superintendent prior to practical completion
note | Reference Documents: -
note | Inspection/ Test Method: Verify
note | Record of conformity: SCP
note | IP
note | Responsibility: Site Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: