## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | FC - R - Down Pipes |  |  |  |  | Yes | FC - R - Down Pipes | 0d5fb9a6-49e0-4334-86e8-7e978b1829d0
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Downpipe installation completed and acceptable
checklist-flat |  |  | checklist | FC - S - Roofing Iron/Flashings |  |  |  |  | Yes | FC - S - Roofing Iron/Flashings | 7509da6c-307d-4eb7-97d9-2efa381e5c74
checkpoint-status |  |  | checkpoint | Correct drawing revision checked, referenced and attached
text | 4faa5954-69c4-5d91-bbed-8c62c8882a89 |  | textbox | Drawing number(s) & Revisions
checkpoint-status |  |  | checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
checkpoint-status |  |  | checkpoint | Roof underlay checked and accurate
checkpoint-status |  |  | checkpoint | Roofing Material fixed correctly/checked and accurate (2-3 photos attached)
checkpoint-status |  |  | checkpoint | Flashing/capping checked and accurate (2-3 Photos attached)
checkpoint-status |  |  | checkpoint | Area left clean and tidy (Photos attached)
label | 56d3db02-fb5e-596e-8767-9ceae35fa0d8 |  | note | Roof and gutters/surrounding area clean and rubbish/fillings removed
checkpoint-status |  |  | checkpoint | All Roof works completed, reviewed and approved (Photos attached)
holdpoint |  |  | signoff | Request sign off
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | FC - S - Roofing |  |  |  |  | Yes | FC - S - Roofing | b7663c47-3127-445e-b3db-459064475a36
checkpoint-group |  |  | section | Pre-installation checks
checkpoint-status |  |  | checkpoint | Scaffolding in place and tagged
checkpoint-status |  |  | checkpoint | Edge protection and safety nets installed
checkpoint-status |  |  | checkpoint | Correct Purlin / Steelwork heights
checkpoint-status |  |  | checkpoint | Correct Precast wall heights
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Plywood Gutter Substrate
checkpoint-status |  |  | checkpoint | Plywood laid a minimum 0.5 degrees
checkpoint-status |  |  | checkpoint | Plywood surface smooth finish CD minimum 1.75mm H3 no knots
checkpoint-status |  |  | checkpoint | Plywood laid with 2mm gaps
checkpoint-status |  |  | checkpoint | Plywood fastened with stainless steel screws recessed 2mm
checkpoint-status |  |  | checkpoint | Outlets installed correctly 73-75mm above plywood
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Steel Tray Substrate
checkpoint-status |  |  | checkpoint | Metal profile installed upside down with fastenings spaced correctly
checkpoint-status |  |  | checkpoint | Flashings installed on hips and valleys
checkpoint-status |  |  | checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint-status |  |  | checkpoint | Outlets framed and plywood routed out
checkpoint-status |  |  | checkpoint | Unused Roofing Iron Secured
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Insulation panels
checkpoint-status |  |  | checkpoint | Sheets installed in brick-bond pattern
checkpoint-status |  |  | checkpoint | No gaps between sheets
checkpoint-status |  |  | checkpoint | Adhesive applied evenly and at correct amount
checkpoint-status |  |  | checkpoint | Sheets held down for correct length of time
checkpoint-status |  |  | checkpoint | Roof is confirmed uniform and flat
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Insulation panels are acceptable level of cleanliness
checkpoint-status |  |  | checkpoint | Membrane colour and thickness confirmed correct
checkpoint-status |  |  | checkpoint | Membrane penetrations have been sealed and are watertight
checkpoint-status |  |  | checkpoint | All welded seams and proprietary items to be seam probed
checkpoint-status |  |  | checkpoint | Observations
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | FC - S - Fascia/Gutter |  |  |  |  | Yes | FC - S - Fascia/Gutter | ed1f93ea-5c96-420b-b0ec-23e364ebd997
checkpoint-status |  |  | checkpoint | Size checked and accurate
checkpoint-status |  |  | checkpoint | Fixings installed (2-4 photos attached)
checkpoint-status |  |  | checkpoint | Rainwater heads checked and accurate (2-4 photos attached)
checkpoint-status |  |  | checkpoint | Paint - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Fascia installation completed (2-4 photos attached)
holdpoint |  |  | signoff | Request sign off
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS