## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | aaa9d88d-d42c-49ee-bf74-6d5374669b63 |  | checklist | Second Fix - Electrical |  |  |  |  | Yes | POST - S - Second Fix - Electrical | 6e720d35-d00e-46bf-831a-7523c4e7e124
checkpoint-status | ff818f7c-e09d-4cfc-8fad-02f195a4066e |  | checkpoint | All cover plates in place & fitted correctly and straight
checkpoint-status | ef629d6a-d9cf-4651-9d88-a3843020d90a |  | checkpoint | All light fittings tight & secure and acceptable
checkpoint-status | 9f3fdafe-db1d-4759-94f2-7bddc8bfafa2 |  | checkpoint | All cables are tied up
checkpoint-status | ca0b6b22-29a5-451f-892d-cde1b00b4ca8 |  | checkpoint | Switch board fit off is completed and acceptable
checkpoint-status | e24674db-7f2d-4ea6-8671-0781af6f80cd |  | checkpoint | Test sheet for insulation Resistance are completed and acceptable
checkpoint-status | 90a2ad4e-84bd-4036-aadf-b6b71c33601a |  | checkpoint | Fixtures level & in place and acceptable
checklist-flat | 827dd6b3-1059-465a-b75f-dc4f502ffb0b |  | checklist | First Fix - Electrical |  |  |  |  | Yes | PRE - S - First Fix - Electrical | abb55629-1161-4f95-9803-2591a3bbe42c
checkpoint-status | fb0cbc60-3286-4a6b-90c2-95ddc4f8804d |  | checkpoint | Check all drawings, plan symbols are identified and wired for, raise any anomalies
checkpoint-status | 65ce2260-3dab-4553-a44f-e0aebe03adbd |  | checkpoint | Check wall and ceiling outlets and fitting positions against Architectural/ Electrical drawings and acceptable
checkpoint-status | 87d1fd0f-f5f5-47d5-839b-7f27a68adb5c |  | checkpoint | Check for any purchaser variations/ client extras
checkpoint-status | cc1cd02a-0130-4bdd-af0d-8484988c48e8 |  | checkpoint | Check all power & light feeds present and acceptable
checkpoint-status | f802f417-3b64-40c2-b20e-612a0026737c |  | checkpoint | Check loop wires installed and acceptable
checkpoint-status | ab544830-7d69-496f-9cad-5f433b68be5d |  | checkpoint | All joinery plans are followed and correct position of outlets installed and acceptable
checkpoint-status | 3403b1a9-459a-4e45-8caa-49a6d8e0fd40 |  | checkpoint | Flush boxes straight and level and acceptable
checkpoint-status | 1121c08b-e603-4f24-982d-575d923cc185 |  | checkpoint | Fire rated flush boxes where required + fire pads installed and acceptable
checkpoint-status | 3afed07f-e93f-4be0-8738-f7d89d5a7af2 |  | checkpoint | Lights are marked out on plans or floor ready for cut out
checkpoint-status | 07f5d25f-7b69-4846-8259-698f6d8f9ac1 |  | checkpoint | Electrical First Fix completed and acceptable and area clean and tidy for next trade
checkpoint-status | 82540cd5-3a72-491e-8a70-d2b3e41abe48 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | c9802fd0-0124-404c-944f-224d96d8ed45 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | cb81d23f-e540-443d-a40c-4f3abdc4457b |  | checklist | Underfloor heating |  |  |  |  | Yes | POST - S - Underfloor heating | e96091e4-1049-4528-b317-d9276729a865
checkpoint-status | c1a1a883-0c72-4367-bb85-4e46d76205a2 |  | checkpoint | Wiring on the floor completed correctly
checkpoint-status | 21d01d4d-5387-4799-8da0-05d24b74bafc |  | checkpoint | Self levelling coverage completed and acceptable
checkpoint-status | 787b4bbc-2965-4d49-bb3e-dd0fe991dfd6 |  | checkpoint | Underfloor heating completed - specified level of finish achieved
checkpoint-status | 1bc48274-e881-4489-bbc9-fe492cd9dcbb |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | e1e6d262-d678-4748-b932-324bddd2f61e |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 1a124289-f48b-4c54-871a-a4820f051c98 |  | checklist | Underground services |  |  |  |  | Yes | F - S - Underground services | f6fc965e-6643-4013-88d8-7a8e3f0a46ad
checkpoint-status | 7b33cd0d-e893-4b95-b5c1-9c895f90dec3 |  | checkpoint | Electrical services/conduits installed at correct location
checkpoint-status | 7049c860-68a6-4140-ba89-4f59cc76f0fa |  | checkpoint | Hydraulic services installed at correct location
checkpoint-status | 52bfbf90-2770-4410-97be-d7b33c2b5ac9 |  | checkpoint | Telecommunications installed at correct location
checkpoint-status | 796a1a6d-1981-4749-988e-0b8e9f0982a5 |  | checkpoint | Any other relevant services installed in correct location
checkpoint-status | 828685fc-2451-4585-b720-a5b9324fa385 |  | checkpoint | All Subfloor services correctly installed to respective area
checkpoint-status | 2fbe36ac-e764-4b91-899e-1cab2d530aee |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 732fe232-29aa-4ddb-a85a-f9304826640b |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS