## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | F - S - Waterproofing |  |  |  |  | Yes | F - S - Waterproofing | 482c3d2b-f57a-4ad2-ac38-44a3d5f281d6
checkpoint-status |  |  | checkpoint | Lap distance for sheet membrane complies with manufacturers specification
checkpoint-status |  |  | checkpoint | Upstand/ perimeter detail installed as specified
checkpoint-status |  |  | checkpoint | Adhesives fully applied as specified and acceptable
checkpoint-status |  |  | checkpoint | Check for air pockets, wrinkles, holes, tears & note and remediated if required
checkpoint-status |  |  | checkpoint | Checked for penetrations/ pipework/ upstands sealed to specified detail
checkpoint-status |  |  | checkpoint | Checked membrane detail at expansion/ construction joints and acceptable
checkpoint-status |  |  | checkpoint | Flood test conducted and no leaks found
checkpoint-status |  |  | checkpoint | Waterproofing membrane installed and correct and any remedial works completed
boolean | 8e1215c5-c31a-5ac8-88e3-c62abdb4addd |  | tickbox | Specified membrane protection is in place
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | FC - S - Roofing |  |  |  |  | Yes | FC - S - Roofing | 5c8e8b53-79f5-4082-a248-40282942b6e5
checkpoint-group |  |  | section | Pre-installation checks
checkpoint-status |  |  | checkpoint | Scaffolding in place and tagged
checkpoint-status |  |  | checkpoint | Edge protection and safety nets installed
checkpoint-status |  |  | checkpoint | Correct Purlin / Steelwork heights
checkpoint-status |  |  | checkpoint | Correct Precast wall heights
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Plywood Gutter Substrate
checkpoint-status |  |  | checkpoint | Plywood laid a minimum 0.5 degrees
checkpoint-status |  |  | checkpoint | Plywood surface smooth finish CD minimum 1.75mm H3 no knots
checkpoint-status |  |  | checkpoint | Plywood laid with 2mm gaps
checkpoint-status |  |  | checkpoint | Plywood fastened with stainless steel screws recessed 2mm
checkpoint-status |  |  | checkpoint | Outlets installed correctly 73-75mm above plywood
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Steel Tray Substrate
checkpoint-status |  |  | checkpoint | Metal profile installed upside down with fastenings spaced correctly
checkpoint-status |  |  | checkpoint | Flashings installed on hips and valleys
checkpoint-status |  |  | checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint-status |  |  | checkpoint | Outlets framed and plywood routed out
checkpoint-status |  |  | checkpoint | Unused Roofing Iron Secured
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Insulation panels
checkpoint-status |  |  | checkpoint | Sheets installed in brick-bond pattern
checkpoint-status |  |  | checkpoint | No gaps between sheets
checkpoint-status |  |  | checkpoint | Adhesive applied evenly and at correct amount
checkpoint-status |  |  | checkpoint | Sheets held down for correct length of time
checkpoint-status |  |  | checkpoint | Roof is confirmed uniform and flat
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Insulation panels are acceptable level of cleanliness
checkpoint-status |  |  | checkpoint | Membrane colour and thickness confirmed correct
checkpoint-status |  |  | checkpoint | Membrane penetrations have been sealed and are watertight
checkpoint-status |  |  | checkpoint | All welded seams and proprietary items to be seam probed
checkpoint-status |  |  | checkpoint | Observations
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS