## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CHK-001-CIV-Stormwater Drainage Pipes Installation | itp |  |  |  |  | CHK-001-CIV-Stormwater Drainage Pipes Installation
section | 1. Referenced Documentation
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-001-CIV-Stormwater Drainage Pipes Installation
label | ITP Description: Stormwater Drainage Pipes Installation Checklist
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 20/06/2023
label | ITP created by: Kamel Alshobaki
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VR Section 701
checkpoint | 1.2 - Non Dependent
label | Reference - VR Section 705
checkpoint | 1.3 - Main ITP
label | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
label | Acceptance Criteria - This Checklist should be used in conjunction with ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
textbox | Enter: Main ITP Lot Number
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Bedding
note | Reference - VR Section 701
note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
note | • ATTACH: Bedding Material Delivery Docket
note | Method - Document Review
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
note | • Material Delivery Docket
checkpoint | 2.2 - Backfill Material
note | Reference - VR Section 701
note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
note | • ATTACH: Backfill Material Delivery Docket
note | Method - Document Review
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
note | • Material Delivery Docket
checkpoint | 2.3 - Stabilized Sand
note | Reference - VR Section 701
note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
note | • ATTACH: Selected Backfill Material Delivery Docket
note | Method - Document Review
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
note | • Material Delivery Docket
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Subcontractor QA Submissions and Approved ITP
note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
note | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
note | • ATTACH: Subcontractor Signed ITP
note | Method - Document Review
note | Frequency - Each Lot (in case undertaken by subcontractor)
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - ConQA Hold Point Release
section | 4. Pre-construction Activities
checkpoint | 4.1 - Survey Set-Out
note | Reference - VR Section 701.10
note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
note | • The culverts constructed shall be constructed true to line and level.
note | • MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
note | Method - Survey, Measure
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
note | • Attach Main Lot Map
section | 5. Construction Activities
checkpoint | 5.1 - Trench Excavation
note | Reference - VR Section 701.15
note | Acceptance Criteria - For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
note | • Horizontal Clearance to wall of trench
note | ○ Pipe Culverts:
note | • 300mm<Horizontal clearance for corrugated metal culverts<1000mm
note | • 300mm<Horizontal clearance for other Pipe culverts<600mm
note | ○ Box Culverts:
note | • 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
note | Method - Visual Inspection, Measure
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.2 - Trench Base
note | Reference - VR Section 701.15
note | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant.
note | Method - Visual
note | Frequency - Each Lot
note | Category - SP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.3 - Bedding-Placement and compaction
note | Reference - VR Section 701.16, VR Section 701.20 (a)
note | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
note | – 100 mm where D < 1500 mm
note | – 200 mm where D ≥ 1500 mm
note | • Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
note | Method - Visual, Measure
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.4 - Laying pipes-Bedding conformity
note | Reference - VR Section 701.17
note | Acceptance Criteria - Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
note | • Laying of pipes or box culverts shall commence from the downstream end.
note | Method - Visual
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.5 - Pipe Laying
note | Reference - VR Section 701.16, VR Section 701.17
note | Acceptance Criteria - Laying of pipes or box culverts shall commence from the downstream end.
note | – Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
note | – The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
note | – The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
note | – When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
note | Method - Visual
note | Frequency - Each Pipe
note | Category - SP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.6 - Pipe Joints and rotation
note | Reference - VR Section 701.18
note | Acceptance Criteria - All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
note | – Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
note | Method - Visual
note | Frequency - Each Pipe
note | Category - SP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.7 - Conformity with drawings
note | Reference - VR Section 701.10
note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
note | • Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
note | (c) invert level of pipes at pits ±50 mm
note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
note | • ATTACH: Survey Report
note | Method - Measure
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
note | • Survey Report
checkpoint | 5.8 - Backfill-Under area to be paved
note | Reference - VR Section 701.19 (a) i
note | Acceptance Criteria - Culvert under area to be paved
note | – Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
note | – Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
note | Method - Visual
note | Frequency - Each Lot
note | Category - SP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.9 - Backfill-Under area not to be paved
note | Reference - VR Section 701.19 (a) ii
note | Acceptance Criteria - The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
note | Method - Visual
note | Frequency - Each Lot
note | Category - SP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.10 - Backfilling with cement stabilised sand
note | Reference - VR Section 701.19 (c)
note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height.
note | Method - Visual
note | Frequency - Each Lot
note | Category - SP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.11 - Backfill Placement
note | Reference - VR Section 701.20
note | Acceptance Criteria - backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
note | Method - Visual
note | Frequency - Each Lot
note | Category - SP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.12 - Backfill Compaction
note | Reference - VR Section 701.20 (b)
note | Acceptance Criteria - 20% of all bedding/Backfill layers for each culvert shall be tested.
note | – Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
note | – Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
note | Method - Test
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - PE
note | Verifying Documents - This Checklist Signed-Off
section | 6. Post-construction Activities
checkpoint | 6.1 - Compaction and Moisture content tests
note | Reference - VR Section 701.20
note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
note | • ATTACH: Compaction and Moisture content test results:
note | Method - Document Review
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE/PE
note | Verifying Documents - This Checklist Signed-Off
note | • Attach Test Results
checkpoint | 6.2 - CCTV Inspection
note | Reference - VR Section 701.30
note | Acceptance Criteria - All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
note | • ATTACH: CCTV Report (PDF)
note | Method - Document Review
note | Frequency - Each Lot
note | Category - HP
note | Responsible person - Nominated Authority
note | Verifying Documents - ConQA HP Release
note | • Attach CCTV Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsible person - PE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP