## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CHK-002-CIV-Stormwater Drainage Pits Installation | itp |  |  |  |  | CHK-002-CIV-Stormwater Drainage Pits Installation
section | 1. Referenced Documentation
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-002-CIV-Stormwater Drainage Pits Installation
label | ITP Description: Stormwater Drainage Pits Installation Checklist
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 20/06/2023
label | ITP created by: Kamel Alshobaki
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VR Section 701
checkpoint | 1.2 - Non Dependent
label | Reference - VR Section 705
checkpoint | 1.3 - Main ITP
label | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
label | Acceptance Criteria - This Checklist should be used in conjunction with ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
textbox | Enter: Main ITP Lot Number
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Bedding
note | Reference - VR Section 701
note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
note | • ATTACH: Bedding Material Delivery Docket
note | Method - Document Review
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
note | • Material Delivery Docket
checkpoint | 2.2 - Backfill Material
note | Reference - VR Section 701
note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
note | • ATTACH: Backfill Material Delivery Docket
note | Method - Document Review
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
note | • Material Delivery Docket
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Subcontractor QA Submissions and Approved ITP
note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
note | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
note | • ATTACH: Subcontractor Signed ITP
note | Method - Document Review
note | Frequency - Each Lot (in case undertaken by subcontractor)
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - ConQA Hold Point Release
section | 4. Pre-construction Activities
checkpoint | 4.1 - Survey Set-Out-
note | Reference - VR Section 710.10
note | Acceptance Criteria - Prior to commencement of excavation the Contractor shall confirm the position of pits with the Superintendent.
note | • PROVIDE MARK-UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
note | Method - Survey, Measure
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
note | • Attach Main Lot Map
section | 5. Construction Activities
checkpoint | 5.1 - Survey Set Out
note | Reference - VR Section 701.10
note | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
note | Method - Visual inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.2 - Pit Excavation
note | Reference - VR Section 705.05
note | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
note | Method - Visual inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.3 - Excavation of Foundation
note | Reference - VR Section 705.05
note | Acceptance Criteria - Bedding conforming to to 710.09 shall be supplied, placed and compacted to a thickness:
note | • > 80mm for clay foundations
note | • > 150mm for rock foundations
note | Method - Visual inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.4 - Placement of Pit - Conformity with drawings
note | Reference - VR Section 701.10
note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
note | • Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
note | (c) invert level of pipes at pits ±50 mm
note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
note | • ATTACH: Survey Report / Data
note | Method - Measure
note | Frequency - Each Lot
note | Category - HP*
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
note | • Attach Survey Report
checkpoint | 5.5 - Jointing
note | Reference - VR Section 705.11
note | Acceptance Criteria - All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
note | • Exposed reinforcement shall be coated with an approved epoxy treatment
note | Method - Visual inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.6 - Shaping of Floor
note | Reference - VR Section 705.13
note | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
note | Method - Visual inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.7 - Step Irons
note | Reference - VR Section 705.12
note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
note | Method - Visual inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.8 - Fitting of Covers
note | Reference - VR Section 705.17
note | Acceptance Criteria - Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
note | • Height shall be within 10mm of the design level.
note | Method - Visual inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | 5.9 - Backfilling Around Drainage Pits
note | Reference - VR Section 705.18
note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal.
note | Method - Visual inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE
note | Verifying Documents - This Checklist Signed-Off
section | 6. Post-construction Activities
checkpoint | 6.1 - Compaction and Moisture content tests
note | Reference - VR Section 701.20
note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
note | • ATTACH: Compaction and Moisture content test results:
note | Method - Document Review
note | Frequency - Each Lot
note | Category - IP
note | Responsible person - SE/PE
note | Verifying Documents - This Checklist Signed-Off
note | • Attach Test Results
checkpoint | 6.2 - CCTV Inspection
note | Reference - VR Section 701.30
note | Acceptance Criteria - All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
note | • ATTACH: CCTV Report (PDF)
note | Method - Document Review
note | Frequency - Each Lot
note | Category - HP
note | Responsible person - Nominated Authority
note | Verifying Documents - ConQA HP Release
note | • Attach CCTV Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsible person - PE
note | Verifying Documents - This Checklist Signed-Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP