## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | itp |  |  |  |  | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | ff9eef7c-b76e-4ebb-adde-76ac9eb4fd12
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | ITP Description: Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 20/06/2023
label | ITP created by: Kamel Alshobaki
label | ITP approved for use by: Jon De Castro
checkpoint | 1 - Materials - Fabrication
note | Reference / ITP Reference - IFC Drawings
note | • Section 620
note | • Section 701
note | • Section 705
note | Acceptance Criteria - (1) Precast items manufactured in accordnace with IFC Drawings
textbox | Drawing Ref No.
note | Method - Visual Inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - Material Delivery Docket
checkpoint | 2 - Materials - Delivery
note | Reference / ITP Reference - IFC Drawings
note | • Section 620
note | • Section 701
note | • Section 705
note | Acceptance Criteria - (1) Purchase Order and Material Description and Qtys matches
note | (2) Ensure precast concrete elements are as per IFC Drawings with no damages upon delivery
note | (3) Lifting and Manufacture compliance certification provided
textbox | Purchase Order No.
note | Method - Visual Inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - Material Delivery Docket
note | • Purchase Order
checkpoint | 3 - Materials - Manufacture's Certificate of Compliance
note | Reference / ITP Reference - IFC Drawings
note | • Section 620
note | • Section 701
note | • Section 705
note | Acceptance Criteria - (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting.
note | Method - Visual Inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - Material Delivery Docket
note | • Compliance Certificate
checkpoint | 4 - Materials - Delivery to site & Storage
note | Reference / ITP Reference - IFC Drawings
note | • Section 620
note | • Section 701
note | • Section 705
note | Acceptance Criteria - (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element.
note | (2) Precast elements are unloaded and stored properly on site as per manufacturer's recommendations.
note | Method - Visual Inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - Material Delivery Docket
checkpoint | 5 - Materials - Others
note | Reference / ITP Reference - IFC Drawings
note | • Section 620
note | • Section 701
note | • Section 705
textbox | Acceptance Criteria - Enter: Additional Comments
note | Method - Visual Inspection
note | Frequency - Each Lot
note | Category - IP
note | Responsibility - SE
note | Verifying Documents - Material Delivery Docket