## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Cable Containment
| Scope |  |  | Cable Containment
Rows
|  | DUCTING - EXTERNAL | dynamic | Cable Containment | DUCTING - EXTERNAL
|  | DUCTING - UNDERSLAB | dynamic | Cable Containment | DUCTING - UNDERSLAB
|  | CABLE TRAY, LADDER & BASKET - L-00 | dynamic | Cable Containment | CABLE TRAY, LADDER & BASKET | L-00
|  | CABLE TRAY, LADDER & BASKET - L-01 | dynamic | Cable Containment | CABLE TRAY, LADDER & BASKET | L-01
|  | CABLE TRAY, LADDER & BASKET - L-02 | dynamic | Cable Containment | CABLE TRAY, LADDER & BASKET | L-02
|  | CABLE TRAY, LADDER & BASKET - L-03 | dynamic | Cable Containment | CABLE TRAY, LADDER & BASKET | L-03
|  | CABLE TRAY, LADDER & BASKET - L-04 | dynamic | Cable Containment | CABLE TRAY, LADDER & BASKET | L-04
|  | WRICON CONNECTIONS - EXTERNAL | dynamic | Cable Containment | WRICON CONNECTIONS - EXTERNAL
Columns
|  | Ducts cut flush with level 0 slab for passive fire treatment |  | Ducts cut flush with level 0 slab for passive fire treatment as per C2100.2.3.
|  | Ducts: All Duct joints face the same direction |  | Ducts: All Duct joints face the same direction
|  | Ducts: All ducts >/= minimum required depth |  | Ducts: All ducts >/= minimum required depth
|  | Ducts: All ducts are sitting on a 50mm bed of crusher dust |  | Ducts: All ducts are sitting on a 50mm bed of crusher dust.
|  | Ducts: All ducts bends are >/= minimum radius |  | Ducts: All ducts bends are >/= minimum radius
|  | Ducts: All ducts laid flat or as required |  | Ducts: All ducts laid flat or as required
|  | Ducts: All ducts of the correct rating |  | Ducts: All ducts of the correct rating
|  | Ducts: All ducts sitting naturally IE, no strained joints |  | Ducts: All ducts sitting naturally IE, no strained joints
|  | Ducts: All installed ducts have end caps fitted |  | Ducts: All installed ducts have end caps fitted
|  | Ducts: Back filled to correct depth for Danger Tape installation Compacted |  | Ducts: Back filled to correct depth for Danger Tape installation Compacted
|  | Ducts: Back filled to correct depth for Mag Slab installation Compacted |  | Ducts: Back filled to correct depth for Mag Slab installation Compacted
|  | Ducts: Complete backfill & compact with appropriate material |  | Ducts: Complete backfill and compact with appropriate material.
|  | Ducts: Dangertape installed covering entire duct route |  | Ducts: Dangertape installed covering entire duct route
|  | Ducts: Excavations complete |  | Ducts: Excavations complete
|  | Ducts: Inspect trench correct depth/profile clear of sharp obstructions |  | Ducts: Inspect trench correct depth/profile clear of sharp obstructions etc
|  | Ducts: Maglab installed covering entire duct route |  | Ducts: Maglab installed covering entire duct route
|  | Ducts: Verify that drawings are latest revision |  | Ducts: Verify that drawings are latest revision
|  | Finalisation: Mark up "As built" drawings |  | Finalisation: Mark up "As built" drawings
|  | Hold Point: Backfilling completed by others |  | Hold Point: Backfilling completed by others, requirements listed under C2115.4.
|  | Hold Point: Notice issued to BECA for inspection prior to backfilling |  | Hold Point: Notice has been issued to BECA for inspection prior to backfilling as per C2115.1.
|  | Hold Point: Trenching completed by others |  | Hold Point: Trenching completed by others, requirements listed under C2115.2.
|  | Installation: All sharp edges removed, cut ends/cut-outs neat & square & protected against corrosion |  | Installation: All sharp edges have been removed, cut ends/cut-outs are neat and square and protected against corrosion as per C2112.3.
|  | Installation: Cable support systems assembled |  | Installation: Cable support systems have been assembled so that sharp edges, screws or other fixing materials do not penetrate the cable corridor as per C2112.3.
|  | Installation: Category of installation selected per spec. & installed |  | Installation: Category of installation selected per specification and installed as per AS/NZS 3000:2007 3.11.3.
|  | Installation: Colour coding of Tray, Ladder & Basket installed |  | Installation: Colour coding of Tray, Ladder and Basket has been installed as per C2112.9.
|  | Installation: Correct embedment (145mm) of HST3 seismic anchors |  | Installation: Correct embedment (145mm) of HST3 seismic anchors has been achieved in accordance with Hilti installation instructions.
|  | Installation: Correct torque setting (60nM) of HST3 seismic anchors |  | Installation: Correct torque setting (60nM) of HST3 seismic anchors has been achieved in accordance with Hilti installation instructions.
|  | Installation: Duct joints glued to prevent water ingress |  | Installation: Duct joints glued to prevent water ingress as per C2115.3.3.
|  | Installation: Duct penetrations to subfloor maintained as continuous |  | Installation: Duct penetrations to subfloor maintained as continuous as per C2100.2.3.
|  | Installation: Duct proved & draw wire installed |  | Installation: Duct proved and draw wire installed as per C2115.3.3.
|  | Installation: Ducts cleaned of rocks/debris |  | Installation: Ducts cleaned of rocks/debris as per C2115.3.3.
|  | Installation: Ducts provided with suitable sized end caps to prevent the ingress of soil |  | Installation: Ducts provided with suitable sized end caps to prevent the ingress of soil as per C2115.3.3.
|  | Installation: Fixings & fastenings are of material appropriate parts being fixed & loads imposed & approved Gravity Support methods |  | Installation: Fixings and fastenings are of material appropriate to the parts being fixed and the loads imposed as per C2112.3 and approved Gravity Support methods.
|  | Installation: Fixings & fastenings are of material appropriate parts being fixed & loads imposed & approved Seismic Support methods |  | Installation: Fixings and fastenings are of material appropriate to the parts being fixed and the loads imposed as per C2112.3 and approved Seismic Support methods.
|  | Installation: HST3 M12 x 145 seismic anchors are used/installed as per the WSP seismic design |  | Installation: HST3 M12 x 145 seismic anchors are used/installed as per the WSP seismic design
|  | Installation: Identification of underground wiring provided |  | Installation: Identification of underground wiring provided as per AS/NZ 3000:2007 3.11.4.5.
|  | Installation: Joints & accessories fit closely & are correctly matched |  | Installation: Joints and accessories fit closely and are correctly matched as per C2112.3.
|  | Installation: Long radius sweeps or bends used for all changes in direction (elbows not acceptable) |  | Installation: Long radius sweeps or bends used for all changes in direction (elbows not acceptable) as per C2115.3.3.
|  | Installation: Mechanical protection selected & installed in accordance with category of underground wiring system |  | Installation: Mechanical protection selected and installed in accordance with category of underground wiring system.
|  | Installation: Non-continuous runs of Tray, Ladder & Basket provided with additional earth continuity straps bolted between sections |  | Installation: Non-continuous runs of Tray, Ladder and Basket have been provided with additional earth continuity straps bolted between sections as per C2112.8.
|  | Installation: Solar shields, covers & guards installed |  | Installation: Solar shields, covers and guards have been installed as per C2112.12.
|  | Installation: Tray, Ladder & Basket installed per agreed technical submission reqs. |  | Installation: Tray, Ladder and Basket has been installed per agreed technical submission requirements and as per C2112.10, 11 & 13.
|  | Installation: Wricon welded securely to reo by a third party qualified Welder |  | Installation: Wricon has been welded securely to reo by a third party qualified Welder
|  | Preinstallation: All staff briefed on safety requirements & installation procedure |  | Preinstallation: All staff briefed on safety requirements and installation procedure
|  | Setting Out: Bedding material selected & installed |  | Setting Out: Bedding material selected and installed as per AS/NZS 3000:2007 3.11.4.2.
|  | Setting Out: Clearance from other services maintained |  | Setting Out: Clearance from other services maintained as per AS/NZS 3000:2007 3.9.8.4.
|  | Setting Out: Tray, Ladder & Basket run level, straight & parallel with the building lines |  | Setting Out: Tray, Ladder and Basket has been run level, straight and parallel with the building lines as per C2112.3.
|  | Setting Out: Wricon slab penetrations coordinated & marked out |  | Setting Out: Wricon slab penetrations have been coordinated and accurately marked out.
|  | Sign-Off: All changes to the current construction drawings documented & issued to James Eymael for action |  | Sign-Off: All changes to the current construction drawings have been documented and issued to James Eymael for action.
|  | Sign-Off: Any comments below |  | Sign-Off: Any comments below.
|  | Sign-Off: Underground wiring system minimum depth of cover achieved |  | Sign-Off: Underground wiring system minimum depth of cover achieved as per AS/NZS 3000:2007 table 3.6.
Pre-Pour Floors
| Scope |  |  | Pre-Pour Floors
Rows
|  | WRICON CONNECTIONS - L-00 - ZONE 04 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-00 | ZONE 04
|  | WRICON CONNECTIONS - L-00 - ZONE 05 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-00 | ZONE 05
|  | WRICON CONNECTIONS - L-00 - ZONE 06 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-00 | ZONE 06
|  | WRICON CONNECTIONS - L-00 - ZONE 09 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-00 | ZONE 09
|  | WRICON CONNECTIONS - L-00 - ZONE 10 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-00 | ZONE 10
|  | WRICON CONNECTIONS - L-00 - ZONE 11 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-00 | ZONE 11
|  | WRICON CONNECTIONS - L-01 - ZONE 04 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-01 | ZONE 04
|  | WRICON CONNECTIONS - L-01 - ZONE 05 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-01 | ZONE 05
|  | WRICON CONNECTIONS - L-01 - ZONE 06 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-01 | ZONE 06
|  | WRICON CONNECTIONS - L-01 - ZONE 09 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-01 | ZONE 09
|  | WRICON CONNECTIONS - L-01 - ZONE 10 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-01 | ZONE 10
|  | WRICON CONNECTIONS - L-02 - ZONE 04 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-02 | ZONE 04
|  | WRICON CONNECTIONS - L-02 - ZONE 05 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-02 | ZONE 05
|  | WRICON CONNECTIONS - L-02 - ZONE 06 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-02 | ZONE 06
|  | WRICON CONNECTIONS - L-02 - ZONE 09 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-02 | ZONE 09
|  | WRICON CONNECTIONS - L-02 - ZONE 10 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-02 | ZONE 10
|  | WRICON CONNECTIONS - L-03 - ZONE 04 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-03 | ZONE 04
|  | WRICON CONNECTIONS - L-03 - ZONE 05 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-03 | ZONE 05
|  | WRICON CONNECTIONS - L-03 - ZONE 06 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-03 | ZONE 06
|  | WRICON CONNECTIONS - L-03 - ZONE 09 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-03 | ZONE 09
|  | WRICON CONNECTIONS - L-03 - ZONE 10 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-03 | ZONE 10
|  | WRICON CONNECTIONS - L-04 - ZONE 01 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-04 | ZONE 01
|  | WRICON CONNECTIONS - L-04 - ZONE 02 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-04 | ZONE 02
|  | WRICON CONNECTIONS - L-04 - ZONE 03 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-04 | ZONE 03
|  | WRICON CONNECTIONS - L-04 - ZONE 04 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-04 | ZONE 04
|  | WRICON CONNECTIONS - L-04 - ZONE 05 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-04 | ZONE 05
|  | WRICON CONNECTIONS - L-04 - ZONE 06 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-04 | ZONE 06
|  | WRICON CONNECTIONS - L-04 - ZONE 08 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-04 | ZONE 08
|  | WRICON CONNECTIONS - L-04 - ZONE 09 | dynamic | Pre-Pour Floors | WRICON CONNECTIONS | L-04 | ZONE 09
|  | FLOOR PENETRATIONS - L-00 | dynamic | Pre-Pour Floors | FLOOR PENETRATIONS | L-00
|  | FLOOR PENETRATIONS - L-01 | dynamic | Pre-Pour Floors | FLOOR PENETRATIONS | L-01
|  | FLOOR PENETRATIONS - L-02 | dynamic | Pre-Pour Floors | FLOOR PENETRATIONS | L-02
|  | FLOOR PENETRATIONS - L-03 | dynamic | Pre-Pour Floors | FLOOR PENETRATIONS | L-03
|  | FLOOR PENETRATIONS - L-04 | dynamic | Pre-Pour Floors | FLOOR PENETRATIONS | L-04
Columns
|  | Setting Out: Floor penetrations coordinated & accurately marked out |  | Setting Out: Floor penetrations have been coordinated and accurately marked out.
|  | Setting Out: Wricon slab penetrations coordinated & accurately marked out |  | Setting Out: Wricon slab penetrations have been coordinated and accurately marked out.
|  | Installation: Wricon welded securely to reo by third party qualified Welder |  | Installation: Wricon has been welded securely to reo by a third party qualified Welder
|  | Sign-Off: All changes to current construction drawings documented & issued to James Eymael for action |  | Sign-Off: All changes to the current construction drawings have been documented and issued to James Eymael for action.
|  | Sign-Off: Any comments below |  | Sign-Off: Any comments below.
First Fix - Submains and Feeds
| Scope |  |  | First Fix - Submains and Feeds
Rows
|  | SUBMAIN CABLE SCHEDULE (Awaiting Checklist) | dynamic | First Fix - Submains and Feeds | SUBMAIN CABLE SCHEDULE (Awaiting Checklist)
|  | DB CABLE SCHEDULE - L-00 | dynamic | First Fix - Submains and Feeds | DB CABLE SCHEDULE | L-00
|  | DB CABLE SCHEDULE - L-01 | dynamic | First Fix - Submains and Feeds | DB CABLE SCHEDULE | L-01
|  | DB CABLE SCHEDULE - L-02 | dynamic | First Fix - Submains and Feeds | DB CABLE SCHEDULE | L-02
|  | DB CABLE SCHEDULE - L-03 | dynamic | First Fix - Submains and Feeds | DB CABLE SCHEDULE | L-03
|  | DB CABLE SCHEDULE - L-04 | dynamic | First Fix - Submains and Feeds | DB CABLE SCHEDULE | L-04
Columns
|  | Cable Supports: Catenary Wires are galvanised steel type with a maximum of 5 cables |  | Cable Supports: Catenary Wires are galvanised steel type with a maximum of 5 cables as per C2102.6 and appropriately sized and secured as per C2112.19.
|  | Cable Supports: Cables are adequately supported at all points (max 500mm intervals) |  | Cable Supports: Cables are adequately supported at all points (max 500mm intervals) and are neatly fixed with clips, saddles or ties as per C2111.5.
|  | Cable Supports: Cable ties are appropriated selected & sized |  | Cable Supports: Cable ties are appropriated selected and sized e.g. black cable = black tie, white cable = white tie, fire resistant cable = stainless steel tie.
|  | Cable Supports: Single core cables forming part of a 3-phase system rigidly held in trefoil formation |  | Cable Supports: Single core cables forming part of a 3-phase system are rigidly held in trefoil formation by approved clamps as per C2111.5.
|  | Cable Supports: Cables passing through large draw pits supported on pit walls/with central supports |  | Cable Supports: Cables passing through large draw pits have been supported on pit walls or with central supports to prevent sag as per C2115.3.
|  | Setting Out: All flush boxes are of required type & rating for the partition/wall type & are secured with a minimum of 2 screws |  | Setting Out: All flush boxes are of the required type and rating for the partition/wall type and are secured with a minimum of 2 screws as per C2141.3.
|  | Setting Out: All flush boxes, electrical termination points & lighting points marked out as per current Architectural drawings |  | Setting Out: All flush boxes, electrical termination points and lighting points have been marked out as per the current Architectural drawings and sufficient blockings/dwangs have been provided by the Building Trade.
|  | First Fix: All subcircuit cabling is concealed within walls, ceilings or floor spaces |  | First Fix: All subcircuit cabling is concealed within walls, ceilings or floor spaces as per C2102.6. Alternatively, cables are laid within continuous ducts as per C2115.3.
|  | First Fix: No subcircuit cable bunches exist & overheating considered |  | First Fix: No subcircuit cable bunches exist and overheating has been considered as per C2102.6.
|  | First Fix: All bends & cables under tension have been reviewed & are within manufacturer's recs. |  | First Fix: All bends and cables under tension have been reviewed and are within manufacturer's recommendations as per C2102.6 and C2115.3.
|  | First Fix: Cables neatly arranged on trays/in trunking & no twists/crossovers exist |  | First Fix: Cables are neatly arranged on trays or in trunking and no twists or crossovers exist. Cables are stacked no more than 6 high with 1 cable width spacing to the next bunch as per C2111.5.
|  | First Fix: All cables protected where they pass through any openings, gaps, holes |  | First Fix: All cables are protected where they pass through any openings, gaps, holes by ensuring the surrounding surfaces are smooth as per C2111.5.
|  | First Fix: ELV, LV & HV circuits are appropriately segregated |  | First Fix: ELV, LV and HV circuits are appropriately segregated as per C2111.5.
|  | First Fix: Any cable joints have been documented (as-built) & approved in writing |  | First Fix: Any cable joints have been documented (as-built) and approved in writing by the Engineer as per C2111.5.
|  | First Fix: All cables where changing direction or containment method |  | First Fix: All cables where changing direction or containment method e.g. duct to draw pit or cable tray to catenary wire, or passing through a penetration have been installed with sufficient seismic slack and no sharp changes in direction exist.
|  | First Fix: All installed cables have been labelled with permanent marker multiple times at each end |  | First Fix: All installed cables have been labelled with permanent marker multiple times at each end with neat handwriting as per Aotea agreed sequence of works.
|  | First Fix (Ducting): Cable lubricant used during cable installation |  | First Fix (Ducting): Cable lubricant used during cable installation as per C2115.3.3.
|  | First Fix (Ducting): Conduits/ducts passing through sub-floor void limited to a maximum of one power cable/two lighting cables |  | First Fix (Ducting): Conduits/ducts passing through sub-floor void are limited to a maximum of one power cable or two lighting cables as per C2100.2.3
|  | First Fix (Ducting): Combined cabling installed via ducting system does not exceed 750mm² |  | First Fix (Ducting): Combined cabling installed via ducting system does not exceed 750mm² as per C2100.2.3.
|  | Sign-Off: All cables installed & inspected as per project DB schedules & current construction drawings & pre-line inspections can proceed |  | Sign-Off: All cables have been installed and inspected as per the project DB schedules and current construction drawings and pre-line inspections can proceed.
|  | Sign-Off: All changes to current construction drawings documented & issued to James Eymael for action |  | Sign-Off: All changes to the current construction drawings have been documented and issued to James Eymael for action.
|  | Sign-Off: Any comments below |  | Sign-Off: Any comments below.
Second Fix
| Scope |  |  | Second Fix
Rows
|  | L-00 - ZONE 01 | dynamic | Second Fix | L-00 | ZONE 01
|  | L-00 - ZONE 02 | dynamic | Second Fix | L-00 | ZONE 02
|  | L-00 - ZONE 03 | dynamic | Second Fix | L-00 | ZONE 03
|  | L-00 - ZONE 04 | dynamic | Second Fix | L-00 | ZONE 04
|  | L-00 - ZONE 05 | dynamic | Second Fix | L-00 | ZONE 05
|  | L-00 - ZONE 06 | dynamic | Second Fix | L-00 | ZONE 06
|  | L-00 - ZONE 07 | dynamic | Second Fix | L-00 | ZONE 07
|  | L-00 - ZONE 08 | dynamic | Second Fix | L-00 | ZONE 08
|  | L-00 - ZONE 09 | dynamic | Second Fix | L-00 | ZONE 09
|  | L-00 - ZONE 10 | dynamic | Second Fix | L-00 | ZONE 10
|  | L-00 - ZONE 11 | dynamic | Second Fix | L-00 | ZONE 11
|  | L-01 - ZONE 01 | dynamic | Second Fix | L-01 | ZONE 01
|  | L-01 - ZONE 02 | dynamic | Second Fix | L-01 | ZONE 02
|  | L-01 - ZONE 03 | dynamic | Second Fix | L-01 | ZONE 03
|  | L-01 - ZONE 04 | dynamic | Second Fix | L-01 | ZONE 04
|  | L-01 - ZONE 05 | dynamic | Second Fix | L-01 | ZONE 05
|  | L-01 - ZONE 06 | dynamic | Second Fix | L-01 | ZONE 06
|  | L-01 - ZONE 07 | dynamic | Second Fix | L-01 | ZONE 07
|  | L-01 - ZONE 08 | dynamic | Second Fix | L-01 | ZONE 08
|  | L-01 - ZONE 09 | dynamic | Second Fix | L-01 | ZONE 09
|  | L-01 - ZONE 10 | dynamic | Second Fix | L-01 | ZONE 10
|  | L-02 - ZONE 01 | dynamic | Second Fix | L-02 | ZONE 01
|  | L-02 - ZONE 02 | dynamic | Second Fix | L-02 | ZONE 02
|  | L-02 - ZONE 03 | dynamic | Second Fix | L-02 | ZONE 03
|  | L-02 - ZONE 04 | dynamic | Second Fix | L-02 | ZONE 04
|  | L-02 - ZONE 05 | dynamic | Second Fix | L-02 | ZONE 05
|  | L-02 - ZONE 06 | dynamic | Second Fix | L-02 | ZONE 06
|  | L-02 - ZONE 07 | dynamic | Second Fix | L-02 | ZONE 07
|  | L-02 - ZONE 08 | dynamic | Second Fix | L-02 | ZONE 08
|  | L-02 - ZONE 09 | dynamic | Second Fix | L-02 | ZONE 09
|  | L-02 - ZONE 10 | dynamic | Second Fix | L-02 | ZONE 10
|  | L-03 - ZONE 01 | dynamic | Second Fix | L-03 | ZONE 01
|  | L-03 - ZONE 02 | dynamic | Second Fix | L-03 | ZONE 02
|  | L-03 - ZONE 03 | dynamic | Second Fix | L-03 | ZONE 03
|  | L-03 - ZONE 04 | dynamic | Second Fix | L-03 | ZONE 04
|  | L-03 - ZONE 05 | dynamic | Second Fix | L-03 | ZONE 05
|  | L-03 - ZONE 06 | dynamic | Second Fix | L-03 | ZONE 06
|  | L-03 - ZONE 07 | dynamic | Second Fix | L-03 | ZONE 07
|  | L-03 - ZONE 08 | dynamic | Second Fix | L-03 | ZONE 08
|  | L-03 - ZONE 09 | dynamic | Second Fix | L-03 | ZONE 09
|  | L-03 - ZONE 10 | dynamic | Second Fix | L-03 | ZONE 10
|  | L-04 - ZONE 01 | dynamic | Second Fix | L-04 | ZONE 01
|  | L-04 - ZONE 02 | dynamic | Second Fix | L-04 | ZONE 02
|  | L-04 - ZONE 03 | dynamic | Second Fix | L-04 | ZONE 03
|  | L-04 - ZONE 04 | dynamic | Second Fix | L-04 | ZONE 04
|  | L-04 - ZONE 05 | dynamic | Second Fix | L-04 | ZONE 05
|  | L-04 - ZONE 06 | dynamic | Second Fix | L-04 | ZONE 06
|  | L-04 - ZONE 07 | dynamic | Second Fix | L-04 | ZONE 07
|  | L-04 - ZONE 08 | dynamic | Second Fix | L-04 | ZONE 08
|  | L-04 - ZONE 09 | dynamic | Second Fix | L-04 | ZONE 09
|  | L-04 - ZONE 10 | dynamic | Second Fix | L-04 | ZONE 10
Columns
|  | General Lighting: All luminaires installed with required brackets & fixings |  | General Lighting: All luminaires have been installed with required brackets and fixings as per C2100.2, or suspended as per C2102.7 and C2130.4.
|  | General Lighting: All luminaires installed with necessary componants, control devices & accessories |  | General Lighting: All luminaires have been installed with all necessary componants, control devices and accessories as per C2100.2.
|  | General Lighting: When installed within suspended ceilings, all luminaires installed with installation couplers |  | General Lighting: When installed within suspended ceilings, all luminaires have been installed with installation couplers as per C2100.2.
|  | General Lighting: When installed within Isolation Spaces, all luminaires sealed to prevent air leaks |  | General Lighting: When installed within Isolation Spaces, all luminaires have been sealed to prevent air leaks as per C2100.2.
|  | General Lighting: When installed within MRI rooms, all luminaire drivers located externally to room |  | General Lighting: When installed within MRI rooms, all luminaire drivers have been located externally to the room as per C2100.2.
|  | General Lighting: No manufacturer's name or trademark visible on an installed internal luminaire |  | General Lighting: No manufacturer's name or trade mark is visible on an installed internal luminaire as per C2130.2.
|  | General Lighting: When luminaires recessed they are installed with appropriate hold down fixings |  | General Lighting: When luminaires are recessed they are installed with appropriate hold down fixings that facilitate easy removal as per C2130.2.
|  | General Lighting: All luminaires are installed to manufacturer's specs. |  | General Lighting: All luminaires are installed to manufacturer's specifications as per C2130.4.
|  | General Lighting: Terminations suitably supported & not carrying weight of cable |  | General Lighting: Terminations are suitably supported and are not carrying the weight of the cable as per C2111.5.
|  | General Lighting: Following final installation & practical completion, all luminaires cleaned |  | General Lighting: Following final installation and practical completion, all luminaires have been cleaned as per C2130.4.
|  | Sign-Off: All luminaires installed as per current construction drawings & commissioning can proceed |  | Sign-Off: All luminaires been installed as per the current construction drawings and commissioning can proceed.
|  | Emergency Lighting: All emergency luminaires provided with a contrasting colour unique ID label |  | Emergency Lighting: All emergency luminaires have been provided with a contrasting colour unique ID label as per AS/NZS 2293 2.5
|  | Emergency Lighting: All emergency luminaires installed in correct orientation & LED light directed at required area |  | Emergency Lighting: All emergency luminaires have been installed in the correct orientation and the LED light is directed at the required area e.g. egress pathways, change in level
|  | Sign-Off: All emergency luminaires been installed as per current construction drawings & commissioning can proceed |  | Sign-Off: All emergency luminaires been installed as per the current construction drawings and commissioning can proceed.
|  | LV Power: Socket outlets in patient areas are red coloured, or beige for cleaners or blue for UPS |  | LV Power: Socket outlets in patient areas are red coloured, or beige for cleaners or blue for UPS as per C2100.2.
|  | LV Power: Socket outlets in non-patient areas are white coloured as per subcontractor quote clarifications item 3.08 |  | LV Power: Socket outlets in non-patient areas are white coloured as per subcontractor quote clarifications item 3.08, except 13 outlets in the Main Entrance.
|  | LV Power: Cabling to motors/mechanical plant terminated with slack/loops to allow for vibration & movement |  | LV Power: Cabling to motors or mechanical plant has been terminated with slack/loops to allow for vibration and movement as per C2111.5.
|  | LV Power: Where wall voids are not present outlets installed on mounting blocks |  | LV Power: Where wall voids are not present outlets have been installed on mounting blocks as per C2141.2.
|  | LV Power: Outlets are labelled as per AS/NZS 3003, to identify the RCD & with power available indication |  | LV Power: Outlets are labelled as per AS/NZS 3003, to identify the RCD and with power available indication.
|  | LV Power: All cable terminations made using correctly sized crimp or compression lugs |  | LV Power: All cable terminations have been made using correctly sized crimp or compression lugs as per C2111.5. Alternatively, cable terminations have
|  | LV Power: Outlets installed clean & level |  | LV Power: Outlets have been installed clean and level.
|  | LV Power: Outlets provided with suitable labelling |  | LV Power: Outlets have been provided with suitable labelling.
|  | Sign-Off: All outlets installed as per current construction drawings & commissioning can proceed |  | Sign-Off: All outlets have been installed as per the current construction drawings and commissioning can proceed.
|  | Earthing: Main equipotential earth bars installed 500mm AFFL with 120mm² 1C connection & 20% spare space |  | Earthing: Main equipotential earth bars have been installed 500mm AFFL with a 120mm² 1C connection and 20% spare space as per C2160.1
|  | Earthing: Earth bars installed in MDF room & Aurora substation with a 70mm² connection |  | Earthing: Earth bars have been installed in the MDF room and Aurora substation with a 70mm² connection as per C2160.1
|  | Earthing: Earthing connections installed to all communication racks & frames |  | Earthing: Earthing connections have been installed to all communication racks and frames as per C2160.1
|  | Earthing: Earthing connections (EPJ) installed as per AS/NZS 3003 for both Body & Cardiac Protected Areas |  | Earthing: Earthing connections (EPJ) have been installed as per AS/NZS 3003 for both Body and Cardiac Protected Areas as per C2160.1
|  | Earthing: Supplementary earthing connections installed |  | Earthing: Supplementary earthing connections have been installed as per AS/NZS 3003 for all metallic equipment within both Body and Cardiac Protected Areas as per C2160.1
|  | Sign-Off: Lighting: All changes to current construction drawings documented & issued to James Eymael for action |  | Sign-Off: Lighting: All changes to the current construction drawings have been documented and issued to James Eymael for action.
|  | Sign-Off: Any comments below |  | Sign-Off: Any comments below.