## Sheet1
2.1 | Check for correct documentation | Drawings and Drawing Register | Ensure that all employees and subcontractors are using: -The correct and complete set of drawings -All drawings are the latest revision | Document Review | Prior to Commencing works | N/A | SE | This ITP | 2.1 - Check for correct documentation | Reference - Drawings and Drawing Register | Acceptance Criteria - Ensure that all employees and subcontractors are using: -The correct and complete set of drawings -All drawings are the latest revision | Method - Document Review | Frequency - Prior to Commencing works | Category - N/A | Responsibility - SE | Verifying Documents - This ITP | Date Completed: | 2.1 - Check for correct documentation
2.2 | Submission and records | VicRoads Spec. - Cl.720.03 | Inspections, Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery. Following information shall be provided to the superintendent: Inspections of plant stock for all plant species Records: -Evidence of origin of indigenous provenance plant material -Analysis certificates for grass seed -Details of suppliers -Copies/Photos of fertiliser labels | Document Review | Prior to Commencing works | HP | SE,Superintendent | This ITP Attach Records to TeamBinder Approval Form | 2.2 - Submission and records | Reference - VicRoads Spec. - Cl.720.03 | Acceptance Criteria - Inspections, Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery. Following information shall be provided to the superintendent: Inspections of plant stock for all plant species Records: -Evidence of origin of indigenous provenance plant material -Analysis certificates for grass seed -Details of suppliers -Copies/Photos of fertiliser labels | Method - Document Review | Frequency - Prior to Commencing works | Category - HP | Responsibility - SE,Superintendent | Verifying Documents - This ITP Attach Records to TeamBinder Approval Form | Date Completed: | Reference - Drawings and Drawing Register
2.3 | Supply of Plant Stock | VicRoads Spec. - Cl.720.04 - Table 720.041 | All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans. - Plants are to conform to the supply properties specified in Table 720.041 | Verify | Prior to Commencing works | N/A | SE | This ITP | 2.3 - Supply of Plant Stock | Reference - VicRoads Spec. - Cl.720.04 - Table 720.041 | Acceptance Criteria - All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans. - Plants are to conform to the supply properties specified in Table 720.041 | Method - Verify | Frequency - Prior to Commencing works | Category - N/A | Responsibility - SE | Verifying Documents - This ITP | Date Completed: | Acceptance Criteria - Ensure that all employees and subcontractors are using: -The correct and complete set of drawings -All drawings are the latest revision
2.4 | Supply of indigenous plant stock | VicRoads Spec. - Cl.720.04 | A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750). - The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot: - species name - storage code - collection locality - Latitude/longitude or AMG - approximate number of parent plants sampled - approximate number of plants in that local population | Verify | Prior to Commencing works | N/A | SE | This ITP | 2.4 - Supply of indigenous plant stock | Reference - VicRoads Spec. - Cl.720.04 | Acceptance Criteria - A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750). - The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot: - species name - storage code - collection locality - Latitude/longitude or AMG - approximate number of parent plants sampled - approximate number of plants in that local population | Method - Verify | Frequency - Prior to Commencing works | Category - N/A | Responsibility - SE | Verifying Documents - This ITP | Date Completed: | Method - Document Review
2.5 | Supply of grass seed | VicRoads Spec. - Cl.720.04 - Table 720.045 | Grass seed shall comply with Table 720.045 | Verify | Prior to Commencing works | N/A | SE | This ITP | 2.5 - Supply of grass seed | Reference - VicRoads Spec. - Cl.720.04 - Table 720.045 | Acceptance Criteria - Grass seed shall comply with Table 720.045 | Method - Verify | Frequency - Prior to Commencing works | Category - N/A | Responsibility - SE | Verifying Documents - This ITP | Date Completed: | Frequency - Prior to Commencing works
3.1 | Subcontractor ITP | Subcontractor ITP | Subcontractor ITP to be reviewed and approved by MRPA. | Document Review | Each Lot | WP | SE/PE | Sign ITP | 3.1 - Subcontractor ITP | Reference - Subcontractor ITP | Acceptance Criteria - Subcontractor ITP to be reviewed and approved by MRPA. | Method - Document Review | Frequency - Each Lot | Category - WP | Responsibility - SE/PE | Verifying Documents - Sign ITP | Date Completed: | Category - N/A
4.1 | Planting Section Approval | VicRoads Spec. - Cl.720.06 - Landscape Plus Planting ITP | Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works | Verify | Once | HP | SE | This ITP | 4.1 - Planting Section Approval | Reference - VicRoads Spec. - Cl.720.06 - Landscape Plus Planting ITP | Acceptance Criteria - Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works | Method - Verify | Frequency - Once | Category - HP | Responsibility - SE | Verifying Documents - This ITP | Date Completed: | Responsibility - SE
4.2 | Pest and Weed Control | - Cl.720.05 | The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations. Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing. | Verify | Once | HP* | SE | This ITP | 4.2 - Pest and Weed Control | Reference - - Cl.720.05 | Acceptance Criteria - The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations. Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing. | Method - Verify | Frequency - Once | Category - HP* | Responsibility - SE | Verifying Documents - This ITP | Date Completed: | Verifying Documents - This ITP
4.3 | Setting out planting areas | VicRoads Spec. - Cl.720.06 | Planting areas are to be set out to the location and shape specified in the landscape drawings. - Plant density requiremens and planting offsets established in the plant schedule are to be adhered to. - Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements. | Verify | Each Applicable Lot | N/A | SE | This ITP | 4.3 - Setting out planting areas | Reference - VicRoads Spec. - Cl.720.06 | Acceptance Criteria - Planting areas are to be set out to the location and shape specified in the landscape drawings. - Plant density requiremens and planting offsets established in the plant schedule are to be adhered to. - Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements. | Method - Verify | Frequency - Each Applicable Lot | Category - N/A | Responsibility - SE | Verifying Documents - This ITP | Date Completed: | Date Completed:
5.1 | Planting | VicRoads Spec. - Cl.720.09 - Landscape Plus Planting ITP | All planting will be undertaken in accordance to Landscpe Plus Planting ITP | Verify | Each Applicable Lot | NA | SE,Foreman | This ITP | 5.1 - Planting | Reference - VicRoads Spec. - Cl.720.09 - Landscape Plus Planting ITP | Acceptance Criteria - All planting will be undertaken in accordance to Landscpe Plus Planting ITP | Method - Verify | Frequency - Each Applicable Lot | Category - NA | Responsibility - SE,Foreman | Verifying Documents - This ITP | Date Completed: | 2.2 - Submission and records
6.1 | Site Final Inspection | Landscape Plus Planting ITP | Landscape Plus ITP signed and completed | Document review CHAR(AMP) Site Inspection | Following completion of planting works | N/A | SE | Sub-Contractor ITP completed, signed and to be attached | 6.1 - Site Final Inspection | Reference - Landscape Plus Planting ITP | Acceptance Criteria - Landscape Plus ITP signed and completed | Method - Document review CHAR(AMP) Site Inspection | Frequency - Following completion of planting works | Category - N/A | Responsibility - SE | Verifying Documents - Sub-Contractor ITP completed, signed and to be attached | Date Completed: | Reference - VicRoads Spec. - Cl.720.03
Acceptance Criteria - Inspections, Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery. Following information shall be provided to the superintendent: Inspections of plant stock for all plant species Records: -Evidence of origin of indigenous provenance plant material -Analysis certificates for grass seed -Details of suppliers -Copies/Photos of fertiliser labels
Method - Document Review
Frequency - Prior to Commencing works
Category - HP
Responsibility - SE,Superintendent
Verifying Documents - This ITP Attach Records to TeamBinder Approval Form
Date Completed:
2.3 - Supply of Plant Stock
Reference - VicRoads Spec. - Cl.720.04 - Table 720.041
Acceptance Criteria - All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans. - Plants are to conform to the supply properties specified in Table 720.041
Method - Verify
Frequency - Prior to Commencing works
Category - N/A
Responsibility - SE
Verifying Documents - This ITP
Date Completed:
2.4 - Supply of indigenous plant stock
Reference - VicRoads Spec. - Cl.720.04
Acceptance Criteria - A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750). - The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot: - species name - storage code - collection locality - Latitude/longitude or AMG - approximate number of parent plants sampled - approximate number of plants in that local population
Method - Verify
Frequency - Prior to Commencing works
Category - N/A
Responsibility - SE
Verifying Documents - This ITP
Date Completed:
2.5 - Supply of grass seed
Reference - VicRoads Spec. - Cl.720.04 - Table 720.045
Acceptance Criteria - Grass seed shall comply with Table 720.045
Method - Verify
Frequency - Prior to Commencing works
Category - N/A
Responsibility - SE
Verifying Documents - This ITP
Date Completed:
3.1 - Subcontractor ITP
Reference - Subcontractor ITP
Acceptance Criteria - Subcontractor ITP to be reviewed and approved by MRPA.
Method - Document Review
Frequency - Each Lot
Category - WP
Responsibility - SE/PE
Verifying Documents - Sign ITP
Date Completed:
4.1 - Planting Section Approval
Reference - VicRoads Spec. - Cl.720.06 - Landscape Plus Planting ITP
Acceptance Criteria - Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works
Method - Verify
Frequency - Once
Category - HP
Responsibility - SE
Verifying Documents - This ITP
Date Completed:
4.2 - Pest and Weed Control
Reference - - Cl.720.05
Acceptance Criteria - The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations. Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
Method - Verify
Frequency - Once
Category - HP*
Responsibility - SE
Verifying Documents - This ITP
Date Completed:
4.3 - Setting out planting areas
Reference - VicRoads Spec. - Cl.720.06
Acceptance Criteria - Planting areas are to be set out to the location and shape specified in the landscape drawings. - Plant density requiremens and planting offsets established in the plant schedule are to be adhered to. - Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
Method - Verify
Frequency - Each Applicable Lot
Category - N/A
Responsibility - SE
Verifying Documents - This ITP
Date Completed:
5.1 - Planting
Reference - VicRoads Spec. - Cl.720.09 - Landscape Plus Planting ITP
Acceptance Criteria - All planting will be undertaken in accordance to Landscpe Plus Planting ITP
Method - Verify
Frequency - Each Applicable Lot
Category - NA
Responsibility - SE,Foreman
Verifying Documents - This ITP
Date Completed:
6.1 - Site Final Inspection
Reference - Landscape Plus Planting ITP
Acceptance Criteria - Landscape Plus ITP signed and completed
Method - Document review CHAR(AMP) Site Inspection
Frequency - Following completion of planting works
Category - N/A
Responsibility - SE
Verifying Documents - Sub-Contractor ITP completed, signed and to be attached
Date Completed: