## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP 303 - Hydrant Installation - Hydrant/Hose Reel Install & Fit Off |  |  |  |  | Yes | ITP 303 - Hydrant Installation - Hydrant/Hose Reel Install & Fit Off | 117a17dd-5361-47e9-8db8-a42981dec36d
checkpoint-status |  |  | checkpoint | 1. Drg No / Revision
text | 423ec70b-f111-5a43-8e77-caeb7611c18e |  | textbox | Drawing No.
text | 13d7cfb9-2ebf-53d6-9a88-b78830971f5e |  | textbox | Revision No.
checkpoint-status |  |  | checkpoint | 2. Support spacing & fixing as per code
checkpoint-status |  |  | checkpoint | 3. Pipework installed as per drg
checkpoint-status |  |  | checkpoint | 4. Pipes left out as notes & reason
checkpoint-status |  |  | checkpoint | 5. Hyd valve installed at correct height
checkpoint-status |  |  | checkpoint | 6. Signage & labelling installed
checkpoint-status |  |  | checkpoint | 8. Hydrant valves locked open
checklist-sectioned |  |  | checklist | ITP 301 - Sprinkler Installation |  |  |  |  | Yes | ITP 301 - Sprinkler Installation | 24c4ed19-6363-4b48-835b-d2963443e878
checkpoint-group |  |  | section | Sprinkler Rough-In
checkpoint-status |  |  | checkpoint | 1. Drg No / Revision
text | 0117f07e-c3de-5497-b8c5-c8cf34d7508f |  | textbox | Drawing No.
text | 88243cfd-16c7-5fe0-a498-c8914847f3ca |  | textbox | Revision No.
checkpoint-status |  |  | checkpoint | 2. Supports spacing & fixing as per code
label | bb91cf84-c9ac-5f44-9551-18e41446b7e1 |  | note | Current issue check
checkpoint-status |  |  | checkpoint | 3. Pipework installed as per drg
checkpoint-status |  |  | checkpoint | 4. Concealed space sprinklers installed
checkpoint-status |  |  | checkpoint | 5. All ends blanked off/plugged for testing
checkpoint-status |  |  | checkpoint | 6. Pipes left out as noted below
checkpoint-status |  |  | checkpoint | 7. Flexibles installed
checkpoint-status |  |  | checkpoint | 8. Charge hand inspection
checklist-flat |  |  | checklist | ITP 401 - Sprinkler Hydrostatic Pressure Test |  |  |  |  | Yes | ITP 401 - Sprinkler Hydrostatic Pressure Test | 830cfaa2-8136-4dd4-835c-bbc8ffa11ce9
checkpoint-status |  |  | checkpoint | First Sighting
label | c62c58c1-6eb4-5c16-8091-951b19b52678 |  | note | Guidelines - “1400 kPa for 2 hours” with no pressure loss.
text | 99bc82e1-6f40-57d8-a4f2-807d0a17e607 |  | textbox | Date
text | 00aebfae-9bb0-5921-b8b2-5ba59db7a461 |  | textbox | Time
text | 3cc93ffa-1ac8-5df4-bc97-605546734a53 |  | textbox | Pressure
text | f1276ca7-2b63-5632-b388-80c7ff9eab77 |  | textbox | Witness (Contractfire)
text | fc4a3e6e-fb5a-53ed-8f8d-b88a492ebc7d |  | textbox | Witness (Multiplex)
checkpoint-status |  |  | checkpoint | Second Sighting
label | a61f3feb-e550-5549-8692-efe6c0e81261 |  | note | Guidelines - “1400 kPa for 2 hours” with no pressure loss.
text | 00213228-9510-5037-8417-1df3f7a73c5e |  | textbox | Date
text | d24ab7b0-00b8-5711-8ef2-58befe05d660 |  | textbox | Time
text | af349ae4-e19f-5809-af31-31a44fc0ff9a |  | textbox | Pressure
text | f210436b-1d34-55f9-85e0-b8f3b8a94a1f |  | textbox | Witness (Contractfire)
text | 602528db-5993-5622-960b-a64f35f2f7ba |  | textbox | Witness (Multiplex)
checkpoint-status |  |  | checkpoint | Subsequent Sightings, if required
text | ffe094b2-8233-5a33-b5dc-84dabcbac82b |  | textbox | Date
text | 797e87b7-a147-5ef1-9ff3-a827297c2234 |  | textbox | Time
text | a18b83a4-7ac2-5c0c-9450-9d83cfac10d5 |  | textbox | Pressure
text | 579de10b-a864-5389-a94d-bda1b01224d7 |  | textbox | Witness (Contractfire)
text | dda433c1-c981-5e96-b452-4fc1e6eba649 |  | textbox | Witness (Multiplex)
checklist-flat |  |  | checklist | ITP 801 - Project Completion/Certification Checklist |  |  |  |  | Yes | ITP 801 - Project Completion/Certification Checklist | b64ae5c3-c0d4-4316-8bd3-9f15ad2497ba
checkpoint-status |  |  | checkpoint | 1. Hydrostatic Test Completed (ITR401)
checkpoint-status |  |  | checkpoint | 2. Independent Certification
checkpoint-status |  |  | checkpoint | 3. Contractfire Completion Statement
checkpoint-status |  |  | checkpoint | 4. Contractfire Warranty Statement
checkpoint-status |  |  | checkpoint | 5. Operation & Maintenance Manuals
checkpoint-status |  |  | checkpoint | 6. Quality Assurance Documentation
checkpoint-status |  |  | checkpoint | 7. As Installed Documentation
checkpoint-status |  |  | checkpoint | 8. Testing & Maintenance Commences
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | 479816f2-efc3-5696-87b2-bd38eb4cd93a |  | textbox | Checked By:
text | 2e229dd8-c4d0-55e4-b8c9-2bcc55a73d3f |  | textbox | Date:
holdpoint |  |  | signoff | Contractfire Sign Off
checkpoint-status |  |  | checkpoint | Multiplex Sign Off
text | bf1a368b-74e8-53e6-9344-c00b494a2d01 |  | textbox | Checked By:
text | 9db2123e-467a-5bd1-840d-35fd7b1c1962 |  | textbox | Date:
holdpoint |  |  | signoff | Multiplex Sign Off
checklist-flat |  |  | checklist | ITP 701 - Booster Installation |  |  |  |  | Yes | ITP 701 - Booster Installation | be0186ff-0920-4859-932d-462a46262a25
checkpoint-status |  |  | checkpoint | 1. Installed as per drawing
checkpoint-status |  |  | checkpoint | 2. Drawing revision
checkpoint-status |  |  | checkpoint | 3. MFB required clearance confirmed
checkpoint-status |  |  | checkpoint | 4. Labelling per stage & level provided
checkpoint-status |  |  | checkpoint | 5. Isolations valves closed & locked
checkpoint-status |  |  | checkpoint | 6. Pressure gauges at T.M pressure
checkpoint-status |  |  | checkpoint | 7. Storz couplings installed to suction points
checkpoint-status |  |  | checkpoint | 8. Hydrostatic Test Completed (1700 kpa)
checkpoint-status |  |  | checkpoint | 9. Independent Certification
checkpoint-status |  |  | checkpoint | 10. Contractfire Completion Statement
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | 8a9aaacb-8ea9-5099-bb2a-5bb9f1ab93af |  | textbox | Checked By:
text | caff1a89-beda-5378-a689-f4033cf175a7 |  | textbox | Date:
holdpoint |  |  | signoff | Contractfire Sign Off
checkpoint-status |  |  | checkpoint | Multiplex Sign Off
text | e10d7e41-9d92-5728-8010-fff55f3efe23 |  | textbox | Checked By:
text | ade562ba-e5a5-575b-a6d3-01f1c09ca635 |  | textbox | Date:
holdpoint |  |  | signoff | Multiplex Sign Off
checklist-flat |  |  | checklist | ITP 402 - Hydrant Hydrostatic Pressure Test |  |  |  |  | Yes | ITP 402 - Hydrant Hydrostatic Pressure Test | d679ee34-2547-467e-9a80-7b38ad2121df
checkpoint-status |  |  | checkpoint | First Sighting
label | b0db5c80-aaaf-5715-8982-b06c22cf0f66 |  | note | Guidelines - “1700 kPa for 2 hours” with no pressure loss.
text | f3ee5dc4-2675-5491-8407-aab5da3911c4 |  | textbox | Date
text | 755fbd0c-b638-58a4-917e-f388d23d0559 |  | textbox | Time
text | 69c84887-9a5d-50be-8657-2fc7057ac9d2 |  | textbox | Pressure
text | 7d16ff18-95db-5abc-99e9-ce42a6e790f3 |  | textbox | Witness (Contractfire)
text | 624d051e-8d69-50bf-acfb-bfe81bffb152 |  | textbox | Witness (Multiplex)
checkpoint-status |  |  | checkpoint | Second Sighting
label | c14c3f8f-722a-5675-8be8-9215d36e9b1f |  | note | Guidelines - “1700 kPa for 2 hours” with no pressure loss.
text | be828aab-2c75-5874-b9b2-53beb4b8dc34 |  | textbox | Date
text | 5b1a41cc-1002-58ea-8ff9-93b2fc285365 |  | textbox | Time
text | 6966b15e-cbc3-5d6c-8731-0a290585cee0 |  | textbox | Pressure
text | 0cbfe629-4c61-5f3f-93ab-8f022cd88804 |  | textbox | Witness (Contractfire)
text | d5ee5558-5649-5958-ac40-ec1f934941e6 |  | textbox | Witness (Multiplex)
checkpoint-status |  |  | checkpoint | Subsequent Sightings, if required
text | e9569de1-daee-5f50-a2e9-22c7b59ece2c |  | textbox | Date
text | f6d4a725-5776-506a-978e-99605d1af3f9 |  | textbox | Time
text | 697cc3b1-f936-59a2-b53c-e2ac7d781c1a |  | textbox | Pressure
text | 367f3fe5-4bf5-5c1b-b772-ba5d867a1f47 |  | textbox | Witness (Contractfire)
text | c13eff4b-eaba-5310-b951-1d39eb734799 |  | textbox | Witness (Multiplex)
checklist-flat |  |  | checklist | ITP 501 - Fire Extinguisher Installation |  |  |  |  | Yes | ITP 501 - Fire Extinguisher Installation | e06e751e-6637-4d6f-bcfc-71306f63a261
checkpoint-status |  |  | checkpoint | 1. Installation locations as per drawing
checkpoint-status |  |  | checkpoint | 1. Drg No / Revision
text | bba8243f-d3f4-5f64-b12e-ad384b1789b3 |  | textbox | Drawing No.
text | 0ce9164d-f5e4-58f1-a763-ff04b95fa310 |  | textbox | Revision No.
checkpoint-status |  |  | checkpoint | Location confirmed with MFB stamped drawing or building surveyor descriptions
checkpoint-status |  |  | checkpoint | 4. Correct unit height & clearances
checkpoint-status |  |  | checkpoint | 5. Extinguishers tagged
checkpoint-status |  |  | checkpoint | 6. Extinguishers in new condition
checkpoint-status |  |  | checkpoint | 7. Instruction signage plate installed
checkpoint-status |  |  | checkpoint | 8. Location signage installed to code
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | d58dbb05-9638-5613-8af4-4c764ea14b18 |  | textbox | Checked By:
text | d99acbc1-f33d-5c2c-afe7-7c9fd254bdf2 |  | textbox | Date:
holdpoint |  |  | signoff | Contractfire Sign Off
checkpoint-status |  |  | checkpoint | Multiplex Sign Off
text | dbdacdad-273a-5d27-a73a-4ed2aed79d6b |  | textbox | Checked By:
text | 5c5baa57-5a2b-55f6-bb8f-62f795a936b6 |  | textbox | Date:
holdpoint |  |  | signoff | Multiplex Sign Off
checklist-sectioned |  |  | checklist | ITP 203 - Sprinkler Installation - Below Ceiling Fit-Off |  |  |  |  | Yes | ITP 203 - Sprinkler Installation - Below Ceiling Fit-Off | f6698b1a-aef5-4156-8bf4-84b59b5a5e4e
checkpoint-group |  |  | section | SPRINKLER ROUGH-IN
checkpoint-status |  |  | checkpoint | 1. Drg No / Revision
text | 6cb1ec1f-d671-50b2-9b01-45bdb1ef57c7 |  | textbox | Drawing No.
text | 4b040c54-0fd2-5d6a-a7d6-6933ecbaa312 |  | textbox | Revision No.
checkpoint-status |  |  | checkpoint | 2. Ceiling grid levelled
checkpoint-status |  |  | checkpoint | 3. Sprinklers installed as per drg
checkpoint-status |  |  | checkpoint | 4. All escutcheon plates installed
checkpoint-status |  |  | checkpoint | 5. Areas not fitted-off as noted below
checkpoint-status |  |  | checkpoint | 6. Pressure Tested (refer I&TR 401)
checkpoint-status |  |  | checkpoint | 7. Charge hand inspection