## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S114 - Wall And Slab Materials - Rev 1 | itp |  |  |  |  | DS2672-ITP-S114 - Wall And Slab Materials - Rev 1
section | 4.08 Concrete Materials
checkpoint | 4.08.01 - Embankment Walls and Foundations Mix Design
note | Acceptance / Conformance Criteria - The Contractor shall submit a concrete mix design certified by an independent testing laboratory no later than four weeks prior to the commencement of concrete placement to the Engineer for Approval.
note | Standard / Specification - RSV - CS - 1.4 / 1.6
note | Verifying Document - Approved Mix Design
note | Frequency - Four weeks prior to the commencement of concrete
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.08.02 - Spillway Mix Design
note | Acceptance / Conformance Criteria - The Contractor shall submit a concrete mix design certified by an independent testing laboratory no later than four weeks prior to the commencement of concrete placement to the Engineer for Approval.
note | Standard / Specification - RSV - CS - 1.4 / 1.6 DWG 41-32443-05-G002
note | Verifying Document - Approved Mix Design
note | Frequency - Four weeks prior to the commencement of concrete
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.08.03 - Overlay Slab & Pile Cap Mix Design
note | Acceptance / Conformance Criteria - The Contractor shall submit a concrete mix design certified by an independent testing laboratory no later than four weeks prior to the commencement of concrete placement to the Engineer for Approval.
note | Standard / Specification - RSV - CS - 1.4 / 1.6 DWG 41-32443-05-G002
note | Verifying Document - Approved Mix Design
note | Frequency - Four weeks prior to the commencement of concrete
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.08.04 - Stilling Basin Mix Design
note | Acceptance / Conformance Criteria - The Contractor shall submit a concrete mix design certified by an independent testing laboratory no later than four weeks prior to the commencement of concrete placement to the Engineer for Approval.
note | Standard / Specification - RSV - CS - 1.4 / 1.6 DWG 41-32443-05-G002
note | Verifying Document - Approved Mix Design
note | Frequency - Four weeks prior to the commencement of concrete
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.08.05 - Concrete Compression Testing Laboratory
note | Acceptance / Conformance Criteria - Compression testing shall be carried out at the cost of the Contractor by an independent laboratory to which the Engineer has no objection.
note | Standard / Specification - RSV - CS - 1.12
note | Verifying Document - Approval
note | Frequency - Prior to Placement
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.08.06 - Reinforcement
note | Acceptance / Conformance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001.
note | Standard / Specification - RSV - CS - 1.19
note | Verifying Document - Mill Certs
note | Frequency - Each Pour
note | Activity - R
note | By - PE