## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S116 - Wall And Slab Installation - Rev 1 | itp |  |  |  |  | DS2672-ITP-S116 - Wall And Slab Installation - Rev 1
section | 8.01 Concrete Subgrade Preparation
checkpoint | 8.01.01 - Wall Type 1 Subgrade Preparation
note | Acceptance / Conformance Criteria - Concrete of the existing dam surface to be water blast cleaned and roughened to provide NZS3109 Type B Construction Joint.
note | Standard / Specification - RSV - GS - 1.1
note | Verifying Document - Photo
note | Frequency - Prior to Pour
note | Activity - R
note | By - PE
checkpoint | 8.01.02 - Wall Type 2 Subgrade Preparation
note | Acceptance / Conformance Criteria - Existing concrete under and to the sides of the foundation to be thoroughly water blasted back to sound concrete.
note | Standard / Specification - RSV - GS - 1.1
note | Verifying Document - Photo
note | Frequency - Prior to Pour
note | Activity - R
note | By - PE
checkpoint | 8.01.03 - Wall Type 3 & 4 Subgrade Preparation
note | Acceptance / Conformance Criteria - Any soft soil or silts to be removed from site and subgrade to be inspected. Fill to underside of foundation with AP40 or approved fill. Fill to be compacted in 200mm layers.
note | Standard / Specification - RSV - GS - 1.1
note | Verifying Document - Approved Subgrade
note | Frequency - Prior to Pour
note | Activity - R
note | By - PE
checkpoint | 8.01.04 - Return Wall Subgrade Preparation
note | Acceptance / Conformance Criteria - Ground excavated to footing level. Backfill as required with AP40 or approved fill. Fill to be compacted in 200mm layers.
note | Standard / Specification - RSV - GS - 1.1
note | Verifying Document - Approved Backfill
note | Frequency - Prior to Pour
note | Activity - R
note | By - PE
section | 8.02 Concrete Pour (Pre and Post Pour Checksheet)
checkpoint | General Details
textbox | Pre Pour Date
textbox | Concrete Strength (mPa)
textbox | Volume (m3)
textbox | Mix Design
textbox | Additives
checkpoint | Reinforcing has been checked and conforms to the drawings included:
textbox | Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Bar Spacing, Cover
checkpoint | 8.02.01 - Construction Joint Locations
note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
note | Standard / Specification - RSV - CS - 1.15
note | Verifying Document - Approval
note | Frequency - Prior to Pour
note | Activity - HP
note | By - ENG
checkpoint | 8.02.02 - Grouting of Bars
note | Acceptance / Conformance Criteria - Reinforcement installed into existing concrete shall be epoxied into the cured concrete with Hilti HIT RE 500 V3 epoxy mortar to the depth shown on the drawings and all strictly installed to the manufacturers written instructions.
note | Standard / Specification - RSV - CS - 1.18
note | Verifying Document - Photos
note | Frequency - Prior to Pour
note | Activity - R
note | By - SE
checkpoint | 8.02.03 - Reinforcement Washdown
note | Acceptance / Conformance Criteria - Washdown all steel reinforcement prior to pouring concrete to remove salts.
note | Standard / Specification - RSV - CS - 1.19
note | Verifying Document - Pre-Pour Checksheet
note | Frequency - Prior to Pour
note | Activity - R
note | By - SE
checkpoint | 8.02.04 - Pre-Pour Inspections
note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - P&G 14
note | Verifying Document - Signed Pre-Pour
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Pour Details
textbox | Weather:
checkpoint | 8.02.05 - Delivery Dockets
note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
note | Standard / Specification - RSV - CS - 1.9
note | Verifying Document - Dockets
note | Frequency - Each Pour
note | Activity - R
note | By - PE
checkpoint | 8.02.06 - Slump Testing
note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
note | Standard / Specification - RSV - CS - 1.12
note | Verifying Document - Pre Pour
note | Frequency - Each Pour
note | Activity - R
note | By - PE
checkpoint | 8.02.07 - Compression Testing
note | Acceptance / Conformance Criteria - A set of specimens for concrete tests shall consist of four specimens from each major pour of concrete, one of which shall be tested at 7 days and the remaining three at 28 days after casting.
note | Standard / Specification - RSV - CS - 1.12
note | Verifying Document - Test Results
note | Frequency - Each Pour
note | Activity - R
note | By - PE
checkpoint | Post Pour Acceptance and Survey
section | 8.03 Pre-Past Concrete Placement
checkpoint | 8.03.01 - Bearing for Precast Concrete Tolerances
note | Acceptance / Conformance Criteria - In addition to the requirements of NZS 3109 insitu concrete surfaces to provide a bearing for precast concrete work shall be cast with a level tolerance of +0mm and -3mm.
note | Standard / Specification - RSV - CS - 1.17
note | Verifying Document - Survey
note | Frequency - Prior to Placement
note | Activity - D
note | By - SV