## Rail and Walkway Materials
Rail and Walkway Materials Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S117 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.09 | Timber Handrail Materials
4.09.01 | Timber Posts | Posts shall be a minimum SG8 grade and treated to TPA H5 requirements. | RSV - TS - 1.3 | Datasheet / Docket | Prior to use | R | SE
4.09.02 | Sawn timber rails | Sawn timber rails and palings shall be a minimum SG8 grade and treated to TPA H3 requirements. | RSV - TS - 1.3 | Datasheet / Docket | Prior to use | R | SE
4.09.03 | Timber Fixings | All fixings shall be stainless steel unless specifically stated. | RSV - TS - 1.4 | Datasheet | Prior to use | R | SE
4.1 | Rail and Walkway Materials
4.10.01 | Steel Conformance | Material certificates shall be in accordance with the requirements of the relevant steel standard with testing completed by a reputable ISO/IANZ or NATA accredited laboratory. | ALD-0424-REP - 2.5.2.1 | Material Certificates | Prior to Commissioning | R | SE
4.10.02 | Steel Plates | All steel plates shall be grade 300 or 350 to AS/NZs 3678 unless specified otherwise | DWG - ALD-0454-GAD | Mill Certs | Prior to Commissioning | R | SE
4.10.03 | Steel Sections | All steel sections shall be grade 300 to AS/NZs 3679 unless specified otherwise | DWG - ALD-0454-GAD | Mill Certs | Prior to Commissioning | R | SE
4.10.04 | Fasteners | All Fasteners To Be Grade 8.8 Galvanized Metric Threads | DWG - ALD-0454-GAD | Material Certificates | Prior to Commissioning | R | SE
4.10.05 | Roller Chain | The chain shall be a 12b-1 simplex roller chain to iso 606:2015 3/4" / 19.05mm pitch approx. length - 99m | DWG - ALD-0323-ASY | Material Certificates | Prior to Commissioning | R | SE

## Walkway Concrete Construction
Walkway Concrete Construction Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S118 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 8 – CONSTRUCTION ACTIVITY – GENERAL CONCRETE CONSTRUCTION
8.02 | Concrete Pour (Pre and Post Pour Checksheet)
| General Details |  |  | Pre-Pour Checksheet
Pre Pour Date
Concrete Strength (mPa)
Volume (m3)
Mix Design
Additives
| Reinforcing has been checked and conforms to the drawings included: |  |  | Pre-Pour Checksheet
Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Bar Spacing, Cover
8.02.01 | Construction Joint Locations | Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour. | RSV - CS - 1.15 | Approval | Prior to Pour | HP | ENG
8.02.02 | Grouting of Bars | Reinforcement installed into existing concrete shall be epoxied into the cured concrete with Hilti HIT RE 500 V3 epoxy mortar to the depth shown on the drawings and all strictly installed to the manufacturers written instructions. | RSV - CS - 1.18 | Photos | Prior to Pour | R | SE
8.02.03 | Reinforcement Washdown | Washdown all steel reinforcement prior to pouring concrete to remove salts. | RSV - CS - 1.19 | Pre-Pour Checksheet | Prior to Pour | R | SE
8.02.04 | Pre-Pour Inspections | Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area. | P&G 14 | Signed Pre-Pour | 48 Hours Notice Prior to Each Occurrence | HP | ENG
Pour Details
Weather:
8.02.05 | Delivery Dockets | The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size. | RSV - CS - 1.9 | Dockets | Each Pour | R | PE
8.02.06 | Slump Testing | Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor. | RSV - CS - 1.12 | Pre Pour | Each Pour | R | PE
8.02.07 | Compression Testing | A set of specimens for concrete tests shall consist of four specimens from each major pour of concrete, one of which shall be tested at 7 days and the remaining three at 28 days after casting. | RSV - CS - 1.12 | Test Results | Each Pour | R | PE
Post Pour Acceptance and Survey
8.03 | Pre-Past Concrete Placement
8.03.01 | Bearing for Precast Concrete Tolerances | In addition to the requirements of NZS 3109 insitu concrete surfaces to provide a bearing for precast concrete work shall be cast with a level tolerance of +0mm and -3mm. | RSV - CS - 1.17 | Survey | Prior to Placement | D | SV

## Welding Finishing and Coating
Welding Finishing and Coating Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S119 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 9 – CONSTRUCTION ACTIVITY – RAIL AND WALKWAY
9.01 | Steel Welding
9.01.01 | Welders | Welders to be competent and hold current relevant certificates to AS/NZS 1554.1 SP for carbon steel. | ALD-0424-REP - 2.5.2.3 | Qualification | Prior to Welding | R | PE
9.01.02 | Welding Methodology | Fabrication, testing and inspection of welded fabrications shall be in accordance with the welding standard specifically defined on the drawing or when no specific requirement is provided, the latest applicable version of AS/NZS 1554.1 SP for carbon steel. | ALD-0424-REP - 2.5.2.2 | Methodology | Prior to Welding | R | PE
9.01.03 | Welding Inspector | Welds shall be non-destructively tested in accordance with the requirements of the welding standard utilised by a CBIP-NZ qualified inspector. | ALD-0424-REP - 2.5.2.4 | Qualification | Prior to Welding | R | PE
9.01.04 | Periodic Inspection of Manufacturing Process’s | The Contractor shall provide the Principal with 2 weeks’ notice and ongoing co-ordination to allow for the Principal to witness Periodic inspection of manufacturing process’s (timing TBC). | ALD-0424-REP - 2.5.2.8 | Notice | 2 weeks’ notice | W | ENG
9.01.05 | Welding Records | Welding Should Be Performed By Qualified Personnel In Accordance With AS/NZS 1554. Manufacturer’s product code & batch number of all welding consumables must be Recorded by the supplier. | DWG - ALD-0454-GAD | Welding Records | Prior to Delivery | R | PE
9.01.06 | General NDT Welding Inspection | A minimum of 20% of welds in components shall be examined along their full-length using dye penetrant (PT) or magnetic particle inspection (MPI) techniques. It is important to include a variety of welds typically used on the fabrication under scrutiny to obtain a comprehensive understanding of the weld quality. NDT Acceptance levels shall be in accordance with the standard apply to the weld. | ALD-0424-REP - 2.5.2.4 | Inspector Report | 20% of Welds in Components | I | PE
9.01.07 | Fillet and But Welding Visual NDT | All fillet welds and butt welds shall be subjected to 100% visual examination. | DWG - ALD-0454-GAD | Inspector Report | 100% of Welds | I | PE
9.01.08 | Fabrication Fillet and But Welding MPE NDT | All fillet welds and butt welds carried out in the fabrication shall be subjected to 50% of magnetic particle examination (MPE). | DWG - ALD-0454-GAD | Inspector Report | 50% of Welds | I | PE
9.01.09 | Site Fillet and But Welding MPE NDT | All fillet welds and butt welds carried out on site shall be subjected to 100% MPE. | DWG - ALD-0454-GAD | Inspector Report | 100% of Welds | I | PE
9.01.10 | Failed NDT | The Contractor shall inform the Principal of the results as soon as practical, specifically where failures are noted, and shall submit a formal NDT report to the Principal within 14 calendar days of undertaking the tests. Failed Welds shall be subject to 100% re-examination by the same respective method after repair. | ALD-0424-REP - 2.5.2.4 | NCR and Retest Reports | As Required | R | PE
9.01.11 | Rails and Walkaway Fabrication Inspection | A Hold point shall be adhered to during the manufacturing of the rails and walkaway assembly After fabrication and NDT prior to assembly. | ALD-0424-REP - 2.5.2.9 | Hold Point Release | Prior to Assembly | HP | ENG
9.02 | Finishing / Coating
9.02.01 | Painting Methodology / Procedure / Certification | Where painting is specified, the structural weldment for each component shall be properly prepared by rounding any sharp edges and dry abrasive blasting the steel surfaces to satisfy preparation requirements specified on the manufacturing drawings. | ALD-0424-REP - 2.5.2.5 | Methodology / Procedure / Certification | Prior to Painting | R | PE
9.02.02 | Paint DFT | A three-coat protective coating shall be applied in accordance with paint supplier recommendations to achieve an overall Dry Film Thickness (DFT) as specified on manufacturing drawings. | ALD-0424-REP - 2.5.2.5 | Test Results | Random locations covering ≈10% of the painted product. | I | PE
9.02.03 | Paint Holiday testing | Post application holiday testing shall be completed in accordance with NACE PRO 1880 or equivalent procedure approved by the Principal. | ALD-0424-REP - 2.5.2.5 | Test Results | Each Occurance | I | PE
9.02.04 | Hot Dip Galvanising Methodology / Procedure / Certification | Parts shall be thoroughly pickled before galvanising. Matter likely to resist removal by pickling such as welding slag, paint and grease shall be removed prior to pickling by blast cleaning to AS 1627 Pt 9 Grade Sa 2 ½. Coatings shall be unbroken and of a minimum thickness of 80 microns to AS 1650:1989. Galvanising shall be applied by the hot dip process in accordance with AS / NZS 4680: 2006. | ALD-0424-REP - 2.5.2.6 | Methodology / Procedure / Certification | Prior to Galv | I | PE
9.02.05 | Rail Straightness | Confirm the rails straightness after galvanising. | ALD-0424-REP - 2.5.3 | Factory Acceptance Test Records | Prior to Installation | I | PE
9.02.06 | Hot Dip Galvanising NDT | Evidence of coating mass and local thickness shall be provided in accordance with AS/NZS 4680:2006 as part of the Contractors Quality Management plan | ALD-0424-REP - 2.5.2.6 | Test Results | Each Batch | I | PE
9.02.07 | Thermal Zinc Spraying Methodology / Procedure / Certification | Parts to be free of burrs, weld splatter and slag, and prepared in accordance with AS/NZS 4680:2006. Parts to be sand blasted to Sa 2.5 as per ISO 8501-1:2007 to achieve a minimum roughness of 50μm. All thermal zinc spraying to be done in accordance with AS/NZS 2312 and ISO 2063, with a nominal thickness of 150 μm of TSZ / zinc metal spray, with no spot less than 120μm, using Dichtol WFT 1532 penetrating sealer. The part shall then be finished with a 50μm epoxy sealer. | ALD-0424-REP - 2.5.2.7 | Methodology / Procedure / Certification | Prior to Zinc | I | PE
9.02.08 | Thermal Zinc Spraying NDT | Evidence of coating mass and local thickness shall be provided in accordance with AS/NZS 4680:2006 as part of the Contractors Quality Management plan. | ALD-0424-REP - 2.5.2.7 | Test Results | Each Batch | I | PE
9.02.09 | Rails and Walkaway Galvanising Inspection | A Hold point shall be adhered to during the manufacturing of the rails and walkaway assembly After galvanising. | ALD-0424-REP - 2.5.2.9 | Hold Point Release | Prior to Installation | HP | ENG
9.02.10 | Finishing / Coating Repair Methodology | The Contractor is responsible to make good any damage (i.e., paint abrasion etc.) arising from transportation, lifting and installation. | ALD-0424-REP - 2.6.3.4 | Methodology | Prior to Delivery | R | PE
9.02.11 | Final Inspection of Manufactured Goods Prior to Dispatch | The Contractor shall provide the Principal with 2 weeks’ notice and ongoing co-ordination to allow for the Principal to witness Final inspection of manufactured goods prior to dispatch. | ALD-0424-REP - 2.5.2.8 | Notice | 2 weeks’ notice | W | ENG

## Rail and Walkway Installation
Rail and Walkway Installation Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S120 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Submit a Construction Pack including a Methodology and JESA to the Engineer before works | Downer | Construction Pack | Submit Prior to commencement of works | H | PE
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
SECTION 9 – CONSTRUCTION ACTIVITY – RAIL AND WALKWAY
9.03 | Removal and Installation
9.03.01 | Safe Work Method Statements | The Contractor shall Provide detailed Safe Work Method Statements for review and approval by the Engineer at least 4 weeks prior to the commencement of site works. | ALD-0424-REP - 2.6.1 | Construction Pack | 4 weeks prior to the commencement of site works | HP | ENG
9.03.02 | Existing Concrete Pier Survey | Before any installation work commences, the contractor shall survey all 6 of the existing concrete pier structures and confirm the Horizontal alignment of the US face of the Stoplog slot and the Vertical alignment of the top face. | ALD-0424-REP - 2.6.3.1 | Survey Results | Before any installation work commences | D | SV
9.03.03 | Grout Pre-Pour Inspections | Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area. | P&G 14 | Signed Pre-Pour | 48 Hours Notice Prior to Each Occurrence | HP | ENG
9.04 | Installation and Alignment of Bottom Steel Corbels
9.04.01 | Bottom steel corbels Setout | The contractor shall install the Bottom steel corbels (ALD-0284-WLD) such that the top of all 11 steel corbels is with +/- 5mm. | ALD-0424-REP - 2.6.3.2 | Survey Records | Each steel corbel | D | SV
9.04.02 | Surface in contact with Grout | Ensure the back surface that will be Exposed to grout, is coated with carboguard 636 | DWG - ALD-0032-ASY | Site Records | Each Grout Location | I | SE
9.04.03 | Bolt pattern | The contractor shall mark out the bolt pattern for the bottom steel corbel drilling using their own methodology. | ALD-0424-REP - 2.6.3.2 | Site Records | Each steel corbel | I | SE
9.04.04 | Clean-out | Clean out drill holes such that no dust, silt, or debris remains in the hole. If anchors are not to be installed immediately, tightly plug the holes and clean out again just prior to anchor installation. | ALD-0424-REP - 2.6.3.2 | Site Records | Each steel corbel | I | SE
9.04.05 | Procedure | Install the anchors strictly as per the drawings and in accordance with the epoxy manufacturer’s instructions and in such a manner that bending of the bolt shank and/or damage to the projecting threads is avoided. | ALD-0424-REP - 2.6.3.2 | Site Records | Each steel corbel | I | SE
9.04.06 | Anchor Embedment Site Acceptance Tests | The Contractor shall provide the Principal with 2 weeks’ notice and ongoing co-ordination to allow for the Principal to witness Anchor embedment Site acceptance tests | ALD-0424-REP - 2.5.2.8 | Notice | 2 weeks’ notice | W | ENG
9.04.07 | Bolt Torqueing | All Bolted Connections To Be Assembled To The Correct Torque. | DWG - ALD-0454-GAD | Torque Checksheet | Each Bolt | I | SE
9.04.08 | Pull-Out Tests | The Contractor shall as part of the SAT, undertake pull-out tests to be conducted on a minimum of two anchors installed per corbel (chosen at random). When tested, the anchor shall be capable of withstanding without movement a pull-out test load equal to the ultimate strength of the threaded section of the bolt shank. | ALD-0424-REP - 2.6.3.2 | Test Report | Two anchors per corbel | I | SE
9.04.09 | Alignment check | The contractor shall survey the installed corbels to confirm alignment, prior to commencing further assembly. | ALD-0424-REP - 2.6.3.2 | Survey Results | Prior to commencing further assembly | D | SV
9.04.10 | Rails and Walkaway Bottom Steel Corbels Inspection | A Hold point shall be adhered to during the manufacturing of the rails and walkaway assembly After surveying the installation of bottom steel corbels prior to grouting. | ALD-0424-REP - 2.5.2.9 | Hold Point Release | Prior to Grouting | HP | ENG
9.05 | Installation and Alignment of Top Steel Corbels
9.05.01 | Top steel corbels Setout | The contractor shall install the Top steel corbels (ALD-0285-WLD) such that the top of all 11 steel corbels is with +/- 1mm. | ALD-0424-REP - 2.6.3.3 | Survey Records | Each steel corbel | D | SE
9.05.02 | Bolt Torqueing | All Bolted Connections To Be Assembled To The Correct Torque. | DWG - ALD-0454-GAD | Torque Checksheet | Each Bolt | I | SE
9.05.03 | Alignment check | The contractor shall survey the installed top corbels to confirm alignment, prior to commencing further assembly. | ALD-0424-REP - 2.6.3.3 | Survey Results | Prior to commencing further assembly | D | SV
9.05.04 | Rails and Walkaway Top Steel Corbels Inspection | A Hold point shall be adhered to during the manufacturing of the rails and walkaway assembly After surveying the installed top steel corbels. | ALD-0424-REP - 2.5.2.9 | Hold Point Release | After surveying the installed top steel corbels. | HP | ENG
9.06 | Lifting and Handling
9.06.01 | Lifting Plans and Certifications | Lifting shall be conducted by certified riggers in accordance with industry best practice using rated lifting apparatus and techniques. Where lifting chains are used, as opposed to strops, care shall be taken to guard against damage to paint work. | ALD-0424-REP - 2.6.3.4 | Plans and Certifications | Prior to Lifting | R | PE
9.06.02 | Finishing / Coating Repairs | The Contractor is responsible to make good any damage (i.e., paint abrasion etc.) arising from transportation, lifting and installation. | ALD-0424-REP - 2.6.3.4 | Photos | Each Occurrence | I | SE
9.07 | Rail and Assembly
9.07.01 | Rail Alignment | Rail alignment (verticality, parallelism, straightness (along assembly), rotational alignment) shall be confirmed. | ALD-0424-REP - 2.7 | Survey Records | On completion | D | SV
9.07.02 | Chain Position | Chain position with respect rails shall be confirmed. | ALD-0424-REP - 2.7 | Survey Records | On completion | D | SV
SECTION 10 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
10.01 | Site Post Construction Activities
10.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
10.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer P&G 20.1 | Records | Post construction | H | SV
10.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red-pen mark-up copies of the Drawings and Specifications and other design documentation showing any deviations from the specified details and requirements produced in accordance with industry good practice. | Downer P&G 20.1 | Redlines | Post construction | H | PE
10.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE