## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S118 - Walkway Concrete Construction - Rev 1 | itp |  |  |  |  | DS2672-ITP-S118 - Walkway Concrete Construction - Rev 1
section | 8.02 Concrete Pour (Pre and Post Pour Checksheet)
checkpoint | General Details
textbox | Pre Pour Date
textbox | Concrete Strength (mPa)
textbox | Volume (m3)
textbox | Mix Design
textbox | Additives
checkpoint | Reinforcing has been checked and conforms to the drawings included:
textbox | Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Bar Spacing, Cover
checkpoint | 8.02.01 - Construction Joint Locations
note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
note | Standard / Specification - RSV - CS - 1.15
note | Verifying Document - Approval
note | Frequency - Prior to Pour
note | Activity - HP
note | By - ENG
checkpoint | 8.02.02 - Grouting of Bars
note | Acceptance / Conformance Criteria - Reinforcement installed into existing concrete shall be epoxied into the cured concrete with Hilti HIT RE 500 V3 epoxy mortar to the depth shown on the drawings and all strictly installed to the manufacturers written instructions.
note | Standard / Specification - RSV - CS - 1.18
note | Verifying Document - Photos
note | Frequency - Prior to Pour
note | Activity - R
note | By - SE
checkpoint | 8.02.03 - Reinforcement Washdown
note | Acceptance / Conformance Criteria - Washdown all steel reinforcement prior to pouring concrete to remove salts.
note | Standard / Specification - RSV - CS - 1.19
note | Verifying Document - Pre-Pour Checksheet
note | Frequency - Prior to Pour
note | Activity - R
note | By - SE
checkpoint | 8.02.04 - Pre-Pour Inspections
note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - P&G 14
note | Verifying Document - Signed Pre-Pour
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Pour Details
textbox | Weather:
checkpoint | 8.02.05 - Delivery Dockets
note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
note | Standard / Specification - RSV - CS - 1.9
note | Verifying Document - Dockets
note | Frequency - Each Pour
note | Activity - R
note | By - PE
checkpoint | 8.02.06 - Slump Testing
note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
note | Standard / Specification - RSV - CS - 1.12
note | Verifying Document - Pre Pour
note | Frequency - Each Pour
note | Activity - R
note | By - PE
checkpoint | 8.02.07 - Compression Testing
note | Acceptance / Conformance Criteria - A set of specimens for concrete tests shall consist of four specimens from each major pour of concrete, one of which shall be tested at 7 days and the remaining three at 28 days after casting.
note | Standard / Specification - RSV - CS - 1.12
note | Verifying Document - Test Results
note | Frequency - Each Pour
note | Activity - R
note | By - PE
checkpoint | Post Pour Acceptance and Survey
section | 8.03 Pre-Past Concrete Placement
checkpoint | 8.03.01 - Bearing for Precast Concrete Tolerances
note | Acceptance / Conformance Criteria - In addition to the requirements of NZS 3109 insitu concrete surfaces to provide a bearing for precast concrete work shall be cast with a level tolerance of +0mm and -3mm.
note | Standard / Specification - RSV - CS - 1.17
note | Verifying Document - Survey
note | Frequency - Prior to Placement
note | Activity - D
note | By - SV