## Project Structure EG (hidden)
Folder Structure |  |  |  | Checklists
Site QA
Switchboards
S1
|  |  | S.1 Assembly | QA_TEM_013_Switchboard & Distribution Board Assembly
|  |  | S.1 Installation | QA_TEM_012_Switchboard & Distribution Board Installation
|  |  | S.1 Cable Termination | QA_TEM_014_Cable Terminations
|  |  | S.1 Accessories | QA_TEM_015_Accessories Installation
|  | S2 |  | Same as S1
|  | S3 |  | Same as S1
|  | S4 |  | Same as S1
|  | S5 |  | Same as S1
|  | S6 |  | Same as S1
|  | S7 |  | Same as S1
|  | S8 |  | Same as S1
|  | S9 |  | Same as S1
|  | S10 |  | Same as S1
Cable Support
Room 1
|  |  | Prior | QA_TEM_008_Cable Support Prior to Cabling
|  |  | Post | QA_TEM_009_Cable Support Post Cabling
|  | Room 2 |  | Same as per Room 1
|  | Room 3 |  | Same as per Room 1
|  | Room 4 |  | Same as per Room 1
|  | Room 5 |  | Same as per Room 1
|  | Room 6 |  | Same as per Room 1
Emergency Lighting
|  | Room 1 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 2 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 3 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 4 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 5 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 6 |  | QA_TEM_023_Emergency & Exit Lighting

## Project Structure
Folder Structure | [5 empty] | Checklists
Site QA
Electrical services
IN GROUNDS
E01
IN GROUND SERVICES INSTALL - HV STAGE 1 - TRENCH & BACKFILL
[5 empty] | QES-ITC-E01-001 | QA_TEM_004_Trench and Backfill
IN GROUND SERVICES INSTALL - HV STAGE 1 - UNDERGROUND CONDUIT INSTALL
[5 empty] | QES-ITC-E01-002 | QA_TEM_005_Underground Conduit Installation
IN GROUND SERVICES INSTALL - HV STAGE 1 - CABLE PIT INSTALLATION
[5 empty] | QES-ITC-E01-003 | QA_TEM_081_Cable Pit Installation
IN GROUND SERVICES INSTALL - HV STAGE 2 - TRENCH & BACKFILL
[5 empty] | QES-ITC-E01-004 | QA_TEM_004_Trench and Backfill
IN GROUND SERVICES INSTALL - HV STAGE 2 - UNDERGROUND CONDUIT INSTALL
[5 empty] | QES-ITC-E01-005 | QA_TEM_005_Underground Conduit Installation
IN GROUND SERVICES INSTALL - HV STAGE 2 - CABLE PIT INSTALLATION
[5 empty] | QES-ITC-E01-006 | QA_TEM_081_Cable Pit Installation
IN GROUND SERVICES INSTALL - EARTH RING
[5 empty] | QES-ITC-E01-007 | QA_TEM_003_Earth Electrode
IN SLAB
E02
CAST IN CONDUIT INSTALLATION BASEMENT POUR 1
[5 empty] | QES-ITC-E02-001 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION BASEMENT POUR 2
[5 empty] | QES-ITC-E02-002 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION LOWER GROUND POUR 1
[5 empty] | QES-ITC-E02-003 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION LOWER GROUND POUR 2
[5 empty] | QES-ITC-E02-004 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION GROUND POUR 1
[5 empty] | QES-ITC-E02-005 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION GROUND POUR 2
[5 empty] | QES-ITC-E02-006 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION LEVEL 1 POUR 1
[5 empty] | QES-ITC-E02-007 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION LEVEL 1 POUR 2
[5 empty] | QES-ITC-E02-008 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION LEVEL 2 POUR 1
[5 empty] | QES-ITC-E02-009 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION LEVEL 2 POUR 2
[5 empty] | QES-ITC-E02-010 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION STAIR 1
[5 empty] | QES-ITC-E02-011 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION STAIR 2
[5 empty] | QES-ITC-E02-012 | QA_TEM_007_Cast in Conduit Installation
CAST IN CONDUIT INSTALLATION BASEMENT SLAB
[5 empty] | QES-ITC-E02-013 | QA_TEM_007_Cast in Conduit Installation
CABLE ROUGH IN
E03
CABLE ROUGH IN - BASEMENT 1- B1.PUB.001 - AIRLOCK
[5 empty] | QES-ITC-E03-001 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ADM.030 - MEETING
[5 empty] | QES-ITC-E03-002 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ADM.032 - RECEPTION
[5 empty] | QES-ITC-E03-003 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.001a - FHR
[5 empty] | QES-ITC-E03-004 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PUB.002 - WHLR
[5 empty] | QES-ITC-E03-005 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.BOH.028 - LIFT LOBBY
[5 empty] | QES-ITC-E03-006 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.OSS.036 - DISPOSAL
[5 empty] | QES-ITC-E03-007 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.BOH.035 - STAFF AMENITIES
[5 empty] | QES-ITC-E03-008 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PUB.033 - WC-ACC AMENITIES
[5 empty] | QES-ITC-E03-009 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - BASEMENT 1- B1.BOH.034 - ENS ACC
[5 empty] | QES-ITC-E03-010 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - BASEMENT 1- B1.OSS.003 - CLNR
[5 empty] | QES-ITC-E03-011 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.OSS.004 - GENERAL STORE
[5 empty] | QES-ITC-E03-012 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.023 - BMDB
[5 empty] | QES-ITC-E03-013 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.022 - BMDB
[5 empty] | QES-ITC-E03-014 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.019 - UPS CLINICAL
[5 empty] | QES-ITC-E03-015 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.020 - UPS ICT
[5 empty] | QES-ITC-E03-016 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.017 - COMMS
[5 empty] | QES-ITC-E03-017 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.006 - FOCUS
[5 empty] | QES-ITC-E03-018 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.014 - OFF:2P
[5 empty] | QES-ITC-E03-019 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.015 - OFF:1P
[5 empty] | QES-ITC-E03-020 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.007 - FOCUS
[5 empty] | QES-ITC-E03-021 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.005 - FOCUS
[5 empty] | QES-ITC-E03-022 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.008 - SUBSTATION
[5 empty] | QES-ITC-E03-023 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.009 - SUBSTATION
[5 empty] | QES-ITC-E03-024 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.021 - AHU PLANT
[5 empty] | QES-ITC-E03-025 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.013 - WORKSTATION
[5 empty] | QES-ITC-E03-026 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.012 - MEETING
[5 empty] | QES-ITC-E03-027 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.011 - STAFF RM
[5 empty] | QES-ITC-E03-028 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.010 - SECURESTAFF COURTYARD
[5 empty] | QES-ITC-E03-029 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.BOH.026 - SECURE STAFF COURTYARD
[5 empty] | QES-ITC-E03-030 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.BOH.025 - SECURE LINK WAY
[5 empty] | QES-ITC-E03-031 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PUB.027 - SECURE ENTRY
[5 empty] | QES-ITC-E03-032 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.016 - COPIER
[5 empty] | QES-ITC-E03-033 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PLA.114 - FHR
[5 empty] | QES-ITC-E03-034 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PUB.029 - LIFT LOBBY
[5 empty] | QES-ITC-E03-035 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.PUB.031 - CORRIDOR
[5 empty] | QES-ITC-E03-036 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.BOH.024 - CORRIDOR
[5 empty] | QES-ITC-E03-037 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - BASEMENT 1- B1.ALL.038 - CORRIDOR
[5 empty] | QES-ITC-E03-038 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.004 - 1B
[5 empty] | QES-ITC-E03-039 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.003 - ENS
[5 empty] | QES-ITC-E03-040 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.005 - 1B
[5 empty] | QES-ITC-E03-041 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.006 - ENS
[5 empty] | QES-ITC-E03-042 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.008 - 1B
[5 empty] | QES-ITC-E03-043 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.007 - ENS
[5 empty] | QES-ITC-E03-044 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.009 - 1B
[5 empty] | QES-ITC-E03-045 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.010 - ENS
[5 empty] | QES-ITC-E03-046 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.012 - 1B
[5 empty] | QES-ITC-E03-047 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.011 - ENS
[5 empty] | QES-ITC-E03-048 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.013 - 1B
[5 empty] | QES-ITC-E03-049 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.014 - ENS
[5 empty] | QES-ITC-E03-050 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.016 - 1B
[5 empty] | QES-ITC-E03-051 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.015 - ENS
[5 empty] | QES-ITC-E03-052 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.018 - 1B
[5 empty] | QES-ITC-E03-053 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.019 - ENS ACC
[5 empty] | QES-ITC-E03-054 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.021 - TERRACE
[5 empty] | QES-ITC-E03-055 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.020 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E03-056 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.017 - BAY-LIN
[5 empty] | QES-ITC-E03-057 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.002 - LOUNGE
[5 empty] | QES-ITC-E03-058 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.001 - LIFT LOBBY
[5 empty] | QES-ITC-E03-059 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.034 - BAY-MEAL
[5 empty] | QES-ITC-E03-060 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.033 - BAY-EQ.
[5 empty] | QES-ITC-E03-061 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.032 - OFF-NUM
[5 empty] | QES-ITC-E03-062 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.040 - DU
[5 empty] | QES-ITC-E03-063 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.026 - EQUIPMENT STORE
[5 empty] | QES-ITC-E03-064 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.049 - CLEAN UTILITY
[5 empty] | QES-ITC-E03-065 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.022 - SUB SB
[5 empty] | QES-ITC-E03-066 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.035 - NURSING WORKSPACE
[5 empty] | QES-ITC-E03-067 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.031 - GENERAL STORE
[5 empty] | QES-ITC-E03-068 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.023 - MEDICAL OFFICERS
[5 empty] | QES-ITC-E03-069 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.083 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E03-070 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.077 - 1B-BARI
[5 empty] | QES-ITC-E03-071 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.078 - ENS-BARI
[5 empty] | QES-ITC-E03-072 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.029 - B-BEV
[5 empty] | QES-ITC-E03-073 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.038 - WR / MTG
[5 empty] | QES-ITC-E03-074 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.052 - STAFF BASE
[5 empty] | QES-ITC-E03-075 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.027 - MED
[5 empty] | QES-ITC-E03-076 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.024 - CLEAN UTILITY
[5 empty] | QES-ITC-E03-077 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.PLA.050 - COMMS
[5 empty] | QES-ITC-E03-078 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.042 - WC-ST
[5 empty] | QES-ITC-E03-079 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.043 - CLNR
[5 empty] | QES-ITC-E03-080 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.047 - INT
[5 empty] | QES-ITC-E03-081 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.PLA.080 - ELEC
[5 empty] | QES-ITC-E03-082 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.79 - BAY-EQ.
[5 empty] | QES-ITC-E03-083 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.51 - B-RESUS
[5 empty] | QES-ITC-E03-084 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.75 - 1B
[5 empty] | QES-ITC-E03-085 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.74 - ENS
[5 empty] | QES-ITC-E03-086 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.72 - 2B
[5 empty] | QES-ITC-E03-087 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.73 - ENS
[5 empty] | QES-ITC-E03-088 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.71 - 2B
[5 empty] | QES-ITC-E03-089 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.70 - ENS
[5 empty] | QES-ITC-E03-090 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.68 - 2B
[5 empty] | QES-ITC-E03-091 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.69 - ENS
[5 empty] | QES-ITC-E03-092 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.67 - 2B
[5 empty] | QES-ITC-E03-093 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.66 - ENS
[5 empty] | QES-ITC-E03-094 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.64 - 1B ASSESSMENT
[5 empty] | QES-ITC-E03-095 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.65 - ENS
[5 empty] | QES-ITC-E03-096 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.63 - 1B
[5 empty] | QES-ITC-E03-097 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.62 - ENS
[5 empty] | QES-ITC-E03-098 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.61 - LOUNGE
[5 empty] | QES-ITC-E03-099 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.60 - 1B
[5 empty] | QES-ITC-E03-100 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.59 - ENS
[5 empty] | QES-ITC-E03-101 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.57 - 1B
[5 empty] | QES-ITC-E03-102 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.58 - ENS
[5 empty] | QES-ITC-E03-103 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.56 - 1B
[5 empty] | QES-ITC-E03-104 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.55 - ENS
[5 empty] | QES-ITC-E03-105 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.53 - 1B
[5 empty] | QES-ITC-E03-106 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LOWER GROUND-LG.GEM.54 - ENS
[5 empty] | QES-ITC-E03-107 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.004 - 1B
[5 empty] | QES-ITC-E03-108 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.003 - ENS
[5 empty] | QES-ITC-E03-109 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.005 - 1B
[5 empty] | QES-ITC-E03-110 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.006 - ENS
[5 empty] | QES-ITC-E03-111 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.008 - 1B
[5 empty] | QES-ITC-E03-112 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.007 - ENS
[5 empty] | QES-ITC-E03-113 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.009 - 1B
[5 empty] | QES-ITC-E03-114 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.010 - ENS
[5 empty] | QES-ITC-E03-115 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.012 - 1B
[5 empty] | QES-ITC-E03-116 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.011 - ENS
[5 empty] | QES-ITC-E03-117 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.013 - 1B
[5 empty] | QES-ITC-E03-118 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.014 - ENS
[5 empty] | QES-ITC-E03-119 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.016 - 1B
[5 empty] | QES-ITC-E03-120 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.015 - ENS
[5 empty] | QES-ITC-E03-121 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.018 - 1B
[5 empty] | QES-ITC-E03-122 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.019 - ENS ACC
[5 empty] | QES-ITC-E03-123 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.021 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E03-124 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.003 - AIRLOCK
[5 empty] | QES-ITC-E03-125 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.MSU.032 - BAY-MEAL
[5 empty] | QES-ITC-E03-126 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.MSU.031 - BAY-EQ.
[5 empty] | QES-ITC-E03-127 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.MSU.030 - NUM MSU
[5 empty] | QES-ITC-E03-128 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.MSU.025 - EQUIPMENT STORE
[5 empty] | QES-ITC-E03-129 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.MSU.024 - CLEAN UTILITY
[5 empty] | QES-ITC-E03-130 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.MSU.022 - STAFF BASE
[5 empty] | QES-ITC-E03-131 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.MSU.023 - WR / MTG
[5 empty] | QES-ITC-E03-132 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.MSU.043 - 1B
[5 empty] | QES-ITC-E03-133 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.044 - ENS
[5 empty] | QES-ITC-E03-134 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.046 - 1B
[5 empty] | QES-ITC-E03-135 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.045 - ENS
[5 empty] | QES-ITC-E03-136 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.047 - 1B
[5 empty] | QES-ITC-E03-137 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.048 - ENS
[5 empty] | QES-ITC-E03-138 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.050 - 1B
[5 empty] | QES-ITC-E03-139 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.MSU.049 - ENS
[5 empty] | QES-ITC-E03-140 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.035 - INTERVIEW
[5 empty] | QES-ITC-E03-141 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.082 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E03-142 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.081 - MEDICAL OFFICERS
[5 empty] | QES-ITC-E03-143 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.073 - B1-BARI
[5 empty] | QES-ITC-E03-144 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.074 - EN - BARI
[5 empty] | QES-ITC-E03-145 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.077 - CLEAN UTILITY
[5 empty] | QES-ITC-E03-146 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.036 - BEV BAY
[5 empty] | QES-ITC-E03-147 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.080 - WR / MTG
[5 empty] | QES-ITC-E03-148 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.079 - STAFF BASE
[5 empty] | QES-ITC-E03-149 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.038 - MED
[5 empty] | QES-ITC-E03-150 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.053 - CLEAN UTILITY
[5 empty] | QES-ITC-E03-151 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.PLA.056 - COMMS
[5 empty] | QES-ITC-E03-152 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.054 - DU
[5 empty] | QES-ITC-E03-153 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.PLA.084 - ELEC
[5 empty] | QES-ITC-E03-154 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.075 - BAY - EQ.
[5 empty] | QES-ITC-E03-155 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - GROUND-00.GEM.071 - 1B
[5 empty] | QES-ITC-E03-156 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.070 - ENS
[5 empty] | QES-ITC-E03-157 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.068 - 2B
[5 empty] | QES-ITC-E03-158 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.069 - ENS
[5 empty] | QES-ITC-E03-159 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.067 - 2B
[5 empty] | QES-ITC-E03-160 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.066 - ENS
[5 empty] | QES-ITC-E03-161 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.064 - 2B
[5 empty] | QES-ITC-E03-162 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.065 - ENS
[5 empty] | QES-ITC-E03-163 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.063 - 2B
[5 empty] | QES-ITC-E03-164 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.062 - ENS
[5 empty] | QES-ITC-E03-165 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.060 - 1B
[5 empty] | QES-ITC-E03-166 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.061 - ENS
[5 empty] | QES-ITC-E03-167 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.059 - 1B
[5 empty] | QES-ITC-E03-168 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.058 - ENS
[5 empty] | QES-ITC-E03-169 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - GROUND-00.GEM.051 - LOUNGE
[5 empty] | QES-ITC-E03-170 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.004 - 1B
[5 empty] | QES-ITC-E03-171 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.003 - ENS
[5 empty] | QES-ITC-E03-172 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.005 - 1B
[5 empty] | QES-ITC-E03-173 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.006 - ENS
[5 empty] | QES-ITC-E03-174 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.008 - 1B
[5 empty] | QES-ITC-E03-175 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.007- ENS
[5 empty] | QES-ITC-E03-176 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.009 - 1B
[5 empty] | QES-ITC-E03-177 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.010 - ENS
[5 empty] | QES-ITC-E03-178 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.012 - 1B-BAR
[5 empty] | QES-ITC-E03-179 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.015 - ENS - BARI
[5 empty] | QES-ITC-E03-180 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.013 - EQUIPMENT STORE
[5 empty] | QES-ITC-E03-181 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.016 - 1B-BAR
[5 empty] | QES-ITC-E03-182 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.017 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E03-183 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.002 - LOUNGE
[5 empty] | QES-ITC-E03-184 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.001 - LIFT LOBBY
[5 empty] | QES-ITC-E03-185 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.031 - BAY-MEAL
[5 empty] | QES-ITC-E03-186 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.030 - BAY-EQ.
[5 empty] | QES-ITC-E03-187 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.034 - NURSING WORKSPACE
[5 empty] | QES-ITC-E03-188 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.028 - GENERAL STORE
[5 empty] | QES-ITC-E03-189 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.029 - OFF-NAM
[5 empty] | QES-ITC-E03-190 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.037 - DU
[5 empty] | QES-ITC-E03-191 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.023 - EQUIPMENT STORE
[5 empty] | QES-ITC-E03-192 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.023 - EQUIPMENT STORE
[5 empty] | QES-ITC-E03-193 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.055 - CLEAN UTILITY
[5 empty] | QES-ITC-E03-194 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.020 - SUB SB
[5 empty] | QES-ITC-E03-195 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.021 - MEDICAL OFFICERS
[5 empty] | QES-ITC-E03-196 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.079 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E03-197 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.035 - WR / MTG
[5 empty] | QES-ITC-E03-198 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.078 - STAFF BASE
[5 empty] | QES-ITC-E03-199 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.027 - B-BEV
[5 empty] | QES-ITC-E03-200 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.024 - MED
[5 empty] | QES-ITC-E03-201 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.036 - CLEAN UTILITY
[5 empty] | QES-ITC-E03-202 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.PLA.056 - COMMS
[5 empty] | QES-ITC-E03-203 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.053 - INTW
[5 empty] | QES-ITC-E03-204 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.PLA.084 - FHR
[5 empty] | QES-ITC-E03-205 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.PLA.100 - ELEC
[5 empty] | QES-ITC-E03-206 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.PLA.073 - BAY EQ.
[5 empty] | QES-ITC-E03-207 | QA_TEM_082_Room Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.074 - 1B
[5 empty] | QES-ITC-E03-208 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.075 - ENS
[5 empty] | QES-ITC-E03-209 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.071 - 1B
[5 empty] | QES-ITC-E03-210 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.070 - ENS
[5 empty] | QES-ITC-E03-211 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.068 - 2B
[5 empty] | QES-ITC-E03-212 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.069 - ENS
[5 empty] | QES-ITC-E03-213 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.067 - 2B
[5 empty] | QES-ITC-E03-214 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.066 - ENS
[5 empty] | QES-ITC-E03-215 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.064 - 2B
[5 empty] | QES-ITC-E03-216 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.065 - ENS
[5 empty] | QES-ITC-E03-217 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.063 - 2B
[5 empty] | QES-ITC-E03-218 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.062 - ENS
[5 empty] | QES-ITC-E03-219 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.060 - 1B
[5 empty] | QES-ITC-E03-220 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.061 - ENS
[5 empty] | QES-ITC-E03-221 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.059 - 1B
[5 empty] | QES-ITC-E03-222 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.058 - ENS
[5 empty] | QES-ITC-E03-223 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.051 - LOUNGE
[5 empty] | QES-ITC-E03-224 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.050 - 1B
[5 empty] | QES-ITC-E03-225 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.049 - ENS
[5 empty] | QES-ITC-E03-226 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.047 - 1B
[5 empty] | QES-ITC-E03-227 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.048 - ENS
[5 empty] | QES-ITC-E03-228 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.046 - 1B
[5 empty] | QES-ITC-E03-229 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.045 - ENS
[5 empty] | QES-ITC-E03-230 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.043 - 1B
[5 empty] | QES-ITC-E03-231 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.044 - ENS
[5 empty] | QES-ITC-E03-232 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 1-01.CMU.019 - LOUNGE
[5 empty] | QES-ITC-E03-233 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 2 02.PLA.001 - LIFT LOBBY
[5 empty] | QES-ITC-E03-234 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 2 02.PLA.002 - AHD 32840
[5 empty] | QES-ITC-E03-235 | QA_TEM_080_Room Body Protection Checklist
CABLE ROUGH IN - LEVEL 2 02.PLA.003 - COMMS
[5 empty] | QES-ITC-E03-236 | QA_TEM_080_Room Body Protection Checklist
CABLE TRAY INSTALLATION
E04
CABLE SUPPORT & PROTECTION- BASEMENT
[5 empty] | QES-ITC-E04-001 | QA_TEM_008_Cable Support Prior to Cabling
CABLE SUPPORT & PROTECTION- LOWER GROUND
[5 empty] | QES-ITC-E04-002 | QA_TEM_008_Cable Support Prior to Cabling
CABLE SUPPORT & PROTECTION- GROUND
[5 empty] | QES-ITC-E04-003 | QA_TEM_008_Cable Support Prior to Cabling
CABLE SUPPORT & PROTECTION- LEVEL 1
[5 empty] | QES-ITC-E04-004 | QA_TEM_008_Cable Support Prior to Cabling
CABLE SUPPORT & PROTECTION- LEVEL 2
[5 empty] | QES-ITC-E04-005 | QA_TEM_008_Cable Support Prior to Cabling
MSB
E05
MSB - 9.1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E05-001 | QA_TEM_012_Switchboard & Distribution Board Installation
MSB - 9.2 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E05-002 | QA_TEM_012_Switchboard & Distribution Board Installation
MSB - TX-1 TO MSB-9.1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-003 | QA_TEM_011_Mains & Submains Installation
MSB - TX-2 TO MSB-9.2 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-004 | QA_TEM_011_Mains & Submains Installation
DB-91B10E1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-005 | QA_TEM_011_Mains & Submains Installation
DB-92B10N1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-006 | QA_TEM_011_Mains & Submains Installation
DB-91B10E3 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-007 | QA_TEM_011_Mains & Submains Installation
DB-91LG1E1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-008 | QA_TEM_011_Mains & Submains Installation
DB-91B10E2 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-009 | QA_TEM_011_Mains & Submains Installation
DB-92LG1N1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-010 | QA_TEM_011_Mains & Submains Installation
DB - 91G1E1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-011 | QA_TEM_011_Mains & Submains Installation
DB - 92G1N1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-012 | QA_TEM_011_Mains & Submains Installation
DB - 91L11E1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-013 | QA_TEM_011_Mains & Submains Installation
DB - 92L11N1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-014 | QA_TEM_011_Mains & Submains Installation
DB - 91L21E1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-015 | QA_TEM_011_Mains & Submains Installation
DB - 92L21N1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-016 | QA_TEM_011_Mains & Submains Installation
BYP - 91B10MU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-017 | QA_TEM_011_Mains & Submains Installation
BYP - 92B10CU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-018 | QA_TEM_011_Mains & Submains Installation
EWIS - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-019 | QA_TEM_011_Mains & Submains Installation
FIP - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-020 | QA_TEM_011_Mains & Submains Installation
MSSB-H-B1-01-ESS - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-021 | QA_TEM_011_Mains & Submains Installation
MSSB-H-B1-02-NE - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-022 | QA_TEM_011_Mains & Submains Installation
MSSB-H-L02-01-ESS - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-023 | QA_TEM_011_Mains & Submains Installation
LIFT 1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-024 | QA_TEM_011_Mains & Submains Installation
LIFT 2 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-025 | QA_TEM_011_Mains & Submains Installation
LIFT 3 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-026 | QA_TEM_011_Mains & Submains Installation
MSSB-H-L02-02-ESS - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-027 | QA_TEM_011_Mains & Submains Installation
MSSB-H-L02-01-NE - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E05-028 | QA_TEM_011_Mains & Submains Installation
MSB - CABLE TERMINATIONS - (CONSUMERS MAINS) MSB-9.1
[5 empty] | QES-ITC-E05-029 | QA_TEM_014_Cable Terminations
MSB - CABLE TERMINATIONS - (CONSUMERS MAINS) MSB-9.2
[5 empty] | QES-ITC-E05-030 | QA_TEM_014_Cable Terminations
MSB - FINAL INSTALLATION TEST SHEET (CONSUMER & SUBMAINS) MSB-9.1
[5 empty] | QES-ITC-E05-031 | Final Installation Checklist
MSB - FINAL INSTALLATION TEST SHEET (CONSUMER & SUBMAINS) MSB-9.2
[5 empty] | QES-ITC-E05-032 | Final Installation Checklist
DB
E06
DB-91B10E1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-001 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91B10E1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-002 | QA_TEM_014_Cable Terminations
DB-91B10E1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-003 | Final Installation Checklist
DB-92B10N1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-004 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-92B10N1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-005 | QA_TEM_014_Cable Terminations
DB-92B10N1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-006 | Final Installation Checklist
DB-91B10E3 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-007 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91B10E3 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-008 | QA_TEM_014_Cable Terminations
DB-91B10E3 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-009 | Final Installation Checklist
DB-91LG1E1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-010 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91LG1E1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-011 | QA_TEM_014_Cable Terminations
DB-91LG1E1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-012 | Final Installation Checklist
DB-91B10E2 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-013 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91B10E2 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-014 | QA_TEM_014_Cable Terminations
DB-91B10E2 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-015 | Final Installation Checklist
DB-92LG1N1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-016 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-92LG1N1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-017 | QA_TEM_014_Cable Terminations
DB-92LG1N1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-018 | Final Installation Checklist
DB - 91G1E1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-019 | QA_TEM_012_Switchboard & Distribution Board Installation
DB - 91G1E1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-020 | QA_TEM_014_Cable Terminations
DB - 91G1E1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-021 | Final Installation Checklist
DB - 92G1N1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-022 | QA_TEM_012_Switchboard & Distribution Board Installation
DB - 92G1N1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-023 | QA_TEM_014_Cable Terminations
DB - 92G1N1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-024 | Final Installation Checklist
DB - 91L11E1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-025 | QA_TEM_012_Switchboard & Distribution Board Installation
DB - 91L11E1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-026 | QA_TEM_014_Cable Terminations
DB - 91L11E1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-027 | Final Installation Checklist
DB - 92L11N1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-028 | QA_TEM_012_Switchboard & Distribution Board Installation
DB - 92L11N1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-029 | QA_TEM_014_Cable Terminations
DB - 92L11N1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-030 | Final Installation Checklist
DB - 91L21E1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-031 | QA_TEM_012_Switchboard & Distribution Board Installation
DB - 91L21E1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-032 | QA_TEM_014_Cable Terminations
DB - 91L21E1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-033 | Final Installation Checklist
DB - 92L21N1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E06-034 | QA_TEM_012_Switchboard & Distribution Board Installation
DB - 92L21N1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E06-035 | QA_TEM_014_Cable Terminations
DB - 92L21N1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E06-036 | Final Installation Checklist
LUMINAIRES
E07
LIGHT FITTING INSTALLATION - BASEMENT 1
[5 empty] | QES-ITC-E07-001 | QA_TEM_016_Light Fitting Installation
QA_TEM_023_Emergency & Exit Lighting
LIGHT FITTING INSTALLATION - LOWER GROUND
[5 empty] | QES-ITC-E07-002 | QA_TEM_016_Light Fitting Installation
QA_TEM_023_Emergency & Exit Lighting
LIGHT FITTING INSTALLATION - GROUND
[5 empty] | QES-ITC-E07-003 | QA_TEM_016_Light Fitting Installation
QA_TEM_023_Emergency & Exit Lighting
LIGHT FITTING INSTALLATION - LEVEL 1
[5 empty] | QES-ITC-E07-004 | QA_TEM_016_Light Fitting Installation
QA_TEM_023_Emergency & Exit Lighting
LIGHT FITTING INSTALLATION - LEVEL 2
[5 empty] | QES-ITC-E07-005 | QA_TEM_016_Light Fitting Installation
QA_TEM_023_Emergency & Exit Lighting
FIT OFF
E08
FIT OFF - BASEMENT 1- B1.PUB.001 - AIRLOCK
[5 empty] | QES-ITC-E08-001 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ADM.030 - MEETING
[5 empty] | QES-ITC-E08-002 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ADM.032 - RECEPTION
[5 empty] | QES-ITC-E08-003 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.001a - FHR
[5 empty] | QES-ITC-E08-004 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PUB.002 - WHLR
[5 empty] | QES-ITC-E08-005 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.BOH.028 - LIFT LOBBY
[5 empty] | QES-ITC-E08-006 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.OSS.036 - DISPOSAL
[5 empty] | QES-ITC-E08-007 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.BOH.035 - STAFF AMENITIES
[5 empty] | QES-ITC-E08-008 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PUB.033 - WA-ACC AMENITIES
[5 empty] | QES-ITC-E08-009 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - BASEMENT 1- B1.BOH.034 - ENS ACC
[5 empty] | QES-ITC-E08-010 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - BASEMENT 1- B1.OSS.003 - CLNR
[5 empty] | QES-ITC-E08-011 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.OSS.004 - GENERAL STORE
[5 empty] | QES-ITC-E08-012 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.023 - BMDB
[5 empty] | QES-ITC-E08-013 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.022 - BMDB
[5 empty] | QES-ITC-E08-014 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.019 - UPS CLINICAL
[5 empty] | QES-ITC-E08-015 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.020 - UPS ICT
[5 empty] | QES-ITC-E08-016 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.017 - COMMS
[5 empty] | QES-ITC-E08-017 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.006 - FOCUS
[5 empty] | QES-ITC-E08-018 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.014 - OFF:2P
[5 empty] | QES-ITC-E08-019 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.015 - OFF:1P
[5 empty] | QES-ITC-E08-020 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.007 - FOCUS
[5 empty] | QES-ITC-E08-021 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.005 - FOCUS
[5 empty] | QES-ITC-E08-022 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.008 - SUBSTATION
[5 empty] | QES-ITC-E08-023 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.009 - SUBSTATION
[5 empty] | QES-ITC-E08-024 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.021 - AHU PLANT
[5 empty] | QES-ITC-E08-025 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.013 - WORKSTATION
[5 empty] | QES-ITC-E08-026 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.012 - MEETING
[5 empty] | QES-ITC-E08-027 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.011 - STAFF RM
[5 empty] | QES-ITC-E08-028 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.010 - SECURESTAFF COURTYARD
[5 empty] | QES-ITC-E08-029 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.BOH.026 - SECURE STAFF COURTYARD
[5 empty] | QES-ITC-E08-030 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.BOH.025 - SECURE LINK WAY
[5 empty] | QES-ITC-E08-031 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PUB.027 - SECURE ENTRY
[5 empty] | QES-ITC-E08-032 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.016 - COPIER
[5 empty] | QES-ITC-E08-033 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PLA.114 - FHR
[5 empty] | QES-ITC-E08-034 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PUB.029 - LIFT LOBBY
[5 empty] | QES-ITC-E08-035 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.PUB.031 - CORRIDOR
[5 empty] | QES-ITC-E08-036 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.BOH.024 - CORRIDOR
[5 empty] | QES-ITC-E08-037 | QA_TEM_082_Room Checklist
FIT OFF - BASEMENT 1- B1.ALL.038 - CORRIDOR
[5 empty] | QES-ITC-E08-038 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.004 - 1B
[5 empty] | QES-ITC-E08-039 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.003 - ENS
[5 empty] | QES-ITC-E08-040 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.005 - 1B
[5 empty] | QES-ITC-E08-041 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.006 - ENS
[5 empty] | QES-ITC-E08-042 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.008 - 1B
[5 empty] | QES-ITC-E08-043 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.007 - ENS
[5 empty] | QES-ITC-E08-044 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.009 - 1B
[5 empty] | QES-ITC-E08-045 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.010 - ENS
[5 empty] | QES-ITC-E08-046 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.012 - 1B
[5 empty] | QES-ITC-E08-047 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.011 - ENS
[5 empty] | QES-ITC-E08-048 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.013 - 1B
[5 empty] | QES-ITC-E08-049 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.014 - ENS
[5 empty] | QES-ITC-E08-050 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.016 - 1B
[5 empty] | QES-ITC-E08-051 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.015 - ENS
[5 empty] | QES-ITC-E08-052 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.018 - 1B
[5 empty] | QES-ITC-E08-053 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.019 - ENS ACC
[5 empty] | QES-ITC-E08-054 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.021 - TERRACE
[5 empty] | QES-ITC-E08-055 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.020 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E08-056 | QA_TEM_080_Room Body Protection Checklist
FIT OFF- LOWER GROUND-LG.GEM.017 - BAY-LIN
[5 empty] | QES-ITC-E08-057 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.002 - LOUNGE
[5 empty] | QES-ITC-E08-058 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.001 - LIFT LOBBY
[5 empty] | QES-ITC-E08-059 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.034 - BAY-MEAL
[5 empty] | QES-ITC-E08-060 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.033 - BAY-EQ.
[5 empty] | QES-ITC-E08-061 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.032 - OFF-NUM
[5 empty] | QES-ITC-E08-062 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.040 - DU
[5 empty] | QES-ITC-E08-063 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.026 - EQUIPMENT STORE
[5 empty] | QES-ITC-E08-064 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.049 - CLEAN UTILITY
[5 empty] | QES-ITC-E08-065 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.022 - SUB SB
[5 empty] | QES-ITC-E08-066 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.035 - NURSING WORKSPACE
[5 empty] | QES-ITC-E08-067 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.031 - GENERAL STORE
[5 empty] | QES-ITC-E08-068 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.023 - MEDICAL OFFICERS
[5 empty] | QES-ITC-E08-069 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.083 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E08-070 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.077 - 1B-BARI
[5 empty] | QES-ITC-E08-071 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.078 - ENS-BARI
[5 empty] | QES-ITC-E08-072 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.029 - B-BEV
[5 empty] | QES-ITC-E08-073 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.038 - WR / MTG
[5 empty] | QES-ITC-E08-074 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.052 - STAFF BASE
[5 empty] | QES-ITC-E08-075 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.027 - MED
[5 empty] | QES-ITC-E08-076 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.024 - CLEAN UTILITY
[5 empty] | QES-ITC-E08-077 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.PLA.050 - COMMS
[5 empty] | QES-ITC-E08-078 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.042 - WC-ST
[5 empty] | QES-ITC-E08-079 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.043 - CLNR
[5 empty] | QES-ITC-E08-080 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.047 - INT
[5 empty] | QES-ITC-E08-081 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.PLA.080 - ELEC
[5 empty] | QES-ITC-E08-082 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.79 - BAY-EQ.
[5 empty] | QES-ITC-E08-083 | QA_TEM_082_Room Checklist
FIT OFF - LOWER GROUND-LG.GEM.51 - B-RESUS
[5 empty] | QES-ITC-E08-084 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.75 - 1B
[5 empty] | QES-ITC-E08-085 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.74 - ENS
[5 empty] | QES-ITC-E08-086 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.72 - 2B
[5 empty] | QES-ITC-E08-087 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.73 - ENS
[5 empty] | QES-ITC-E08-088 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.71 - 2B
[5 empty] | QES-ITC-E08-089 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.70 - ENS
[5 empty] | QES-ITC-E08-090 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.68 - 2B
[5 empty] | QES-ITC-E08-091 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.69 - ENS
[5 empty] | QES-ITC-E08-092 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.67 - 2B
[5 empty] | QES-ITC-E08-093 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.66 - ENS
[5 empty] | QES-ITC-E08-094 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.64 - 1B ASSESSMENT
[5 empty] | QES-ITC-E08-095 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.65 - ENS
[5 empty] | QES-ITC-E08-096 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.63 - 1B
[5 empty] | QES-ITC-E08-097 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.62 - ENS
[5 empty] | QES-ITC-E08-098 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.61 - LOUNGE
[5 empty] | QES-ITC-E08-099 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.60 - 1B
[5 empty] | QES-ITC-E08-100 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.59 - ENS
[5 empty] | QES-ITC-E08-101 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.57 - 1B
[5 empty] | QES-ITC-E08-102 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.58 - ENS
[5 empty] | QES-ITC-E08-103 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.56 - 1B
[5 empty] | QES-ITC-E08-104 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.55 - ENS
[5 empty] | QES-ITC-E08-105 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.53 - 1B
[5 empty] | QES-ITC-E08-106 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LOWER GROUND-LG.GEM.54 - ENS
[5 empty] | QES-ITC-E08-107 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.004 - 1B
[5 empty] | QES-ITC-E08-108 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.003 - ENS
[5 empty] | QES-ITC-E08-109 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.005 - 1B
[5 empty] | QES-ITC-E08-110 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.006 - ENS
[5 empty] | QES-ITC-E08-111 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.008 - 1B
[5 empty] | QES-ITC-E08-112 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.007 - ENS
[5 empty] | QES-ITC-E08-113 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.009 - 1B
[5 empty] | QES-ITC-E08-114 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.010 - ENS
[5 empty] | QES-ITC-E08-115 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.012 - 1B
[5 empty] | QES-ITC-E08-116 | QA_TEM_080_Room Body Protection Checklist
FIT OFF- GROUND-00.MSU.011 - ENS
[5 empty] | QES-ITC-E08-117 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.013 - 1B
[5 empty] | QES-ITC-E08-118 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.014 - ENS
[5 empty] | QES-ITC-E08-119 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.016 - 1B
[5 empty] | QES-ITC-E08-120 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.015 - ENS
[5 empty] | QES-ITC-E08-121 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.018 - 1B
[5 empty] | QES-ITC-E08-122 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.019 - ENS ACC
[5 empty] | QES-ITC-E08-123 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.021 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E08-124 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.003 - AIRLOCK
[5 empty] | QES-ITC-E08-125 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.MSU.032 - BAY-MEAL
[5 empty] | QES-ITC-E08-126 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.MSU.031 - BAY-EQ.
[5 empty] | QES-ITC-E08-127 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.MSU.030 - NUM MSU
[5 empty] | QES-ITC-E08-128 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.MSU.025 - EQUIPMENT STORE
[5 empty] | QES-ITC-E08-129 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.MSU.024 - CLEAN UTILITY
[5 empty] | QES-ITC-E08-130 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.MSU.022 - STAFF BASE
[5 empty] | QES-ITC-E08-131 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.MSU.023 - WR / MTG
[5 empty] | QES-ITC-E08-132 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.MSU.043 - 1B
[5 empty] | QES-ITC-E08-133 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.044 - ENS
[5 empty] | QES-ITC-E08-134 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.046 - 1B
[5 empty] | QES-ITC-E08-135 | QA_TEM_080_Room Body Protection Checklist
FIT OFF- GROUND-00.MSU.045 - ENS
[5 empty] | QES-ITC-E08-136 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.047 - 1B
[5 empty] | QES-ITC-E08-137 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.048 - ENS
[5 empty] | QES-ITC-E08-138 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.050 - 1B
[5 empty] | QES-ITC-E08-139 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.MSU.049 - ENS
[5 empty] | QES-ITC-E08-140 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.035 - INTERVIEW
[5 empty] | QES-ITC-E08-141 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.GEM.082 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E08-142 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.081 - MEDICAL OFFICERS
[5 empty] | QES-ITC-E08-143 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.GEM.073 - B1-BARI
[5 empty] | QES-ITC-E08-144 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.074 - EN - BARI
[5 empty] | QES-ITC-E08-145 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.077 - CLEAN UTILITY
[5 empty] | QES-ITC-E08-146 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.GEM.036 - BEV BAY
[5 empty] | QES-ITC-E08-147 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.GEM.080 - WR / MTG
[5 empty] | QES-ITC-E08-148 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.GEM.079 - STAFF BASE
[5 empty] | QES-ITC-E08-149 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.GEM.038 - MED
[5 empty] | QES-ITC-E08-150 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.GEM.053 - CLEAN UTILITY
[5 empty] | QES-ITC-E08-151 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.PLA.056 - COMMS
[5 empty] | QES-ITC-E08-152 | QA_TEM_082_Room Checklist
FIT OFF- GROUND-00.GEM.054 - DU
[5 empty] | QES-ITC-E08-153 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.PLA.084 - ELEC
[5 empty] | QES-ITC-E08-154 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.GEM.075 - BAY - EQ.
[5 empty] | QES-ITC-E08-155 | QA_TEM_082_Room Checklist
FIT OFF - GROUND-00.GEM.071 - 1B
[5 empty] | QES-ITC-E08-156 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.070 - ENS
[5 empty] | QES-ITC-E08-157 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.068 - 2B
[5 empty] | QES-ITC-E08-158 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.069 - ENS
[5 empty] | QES-ITC-E08-159 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.067 - 2B
[5 empty] | QES-ITC-E08-160 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.066 - ENS
[5 empty] | QES-ITC-E08-161 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.064 - 2B
[5 empty] | QES-ITC-E08-162 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.065 - ENS
[5 empty] | QES-ITC-E08-163 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.063 - 2B
[5 empty] | QES-ITC-E08-164 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.062 - ENS
[5 empty] | QES-ITC-E08-165 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.060 - 1B
[5 empty] | QES-ITC-E08-166 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.061 - ENS
[5 empty] | QES-ITC-E08-167 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.059 - 1B
[5 empty] | QES-ITC-E08-168 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.058 - ENS
[5 empty] | QES-ITC-E08-169 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - GROUND-00.GEM.051 - LOUNGE
[5 empty] | QES-ITC-E08-170 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.004 - 1B
[5 empty] | QES-ITC-E08-171 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.003 - ENS
[5 empty] | QES-ITC-E08-172 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.005 - 1B
[5 empty] | QES-ITC-E08-173 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.006 - ENS
[5 empty] | QES-ITC-E08-174 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.008 - 1B
[5 empty] | QES-ITC-E08-175 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.007- ENS
[5 empty] | QES-ITC-E08-176 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.009 - 1B
[5 empty] | QES-ITC-E08-177 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.010 - ENS
[5 empty] | QES-ITC-E08-178 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.012 - 1B-BAR
[5 empty] | QES-ITC-E08-179 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.015 - ENS - BARI
[5 empty] | QES-ITC-E08-180 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.013 - EQUIPMENT STORE
[5 empty] | QES-ITC-E08-181 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.016 - 1B-BAR
[5 empty] | QES-ITC-E08-182 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.017 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E08-183 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.002 - LOUNGE
[5 empty] | QES-ITC-E08-184 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.001 - LIFT LOBBY
[5 empty] | QES-ITC-E08-185 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.031 - BAY-MEAL
[5 empty] | QES-ITC-E08-186 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.030 - BAY-EQ.
[5 empty] | QES-ITC-E08-187 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.034 - NURSING WORKSPACE
[5 empty] | QES-ITC-E08-188 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.028 - GENERAL STORE
[5 empty] | QES-ITC-E08-189 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.029 - OFF-NAM
[5 empty] | QES-ITC-E08-190 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.037 - DU
[5 empty] | QES-ITC-E08-191 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.023 - EQUIPMENT STORE
[5 empty] | QES-ITC-E08-192 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.023 - EQUIPMENT STORE
[5 empty] | QES-ITC-E08-193 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.055 - CLEAN UTILITY
[5 empty] | QES-ITC-E08-194 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.020 - SUB SB
[5 empty] | QES-ITC-E08-195 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.021 - MEDICAL OFFICERS
[5 empty] | QES-ITC-E08-196 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.079 - LOUNGE / ACTIVITY
[5 empty] | QES-ITC-E08-197 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.035 - WR / MTG
[5 empty] | QES-ITC-E08-198 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.078 - STAFF BASE
[5 empty] | QES-ITC-E08-199 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.027 - B-BEV
[5 empty] | QES-ITC-E08-200 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.024 - MED
[5 empty] | QES-ITC-E08-201 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.036 - CLEAN UTILITY
[5 empty] | QES-ITC-E08-202 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.PLA.056 - COMMS
[5 empty] | QES-ITC-E08-203 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.053 - INTW
[5 empty] | QES-ITC-E08-204 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.PLA.084 - FHR
[5 empty] | QES-ITC-E08-205 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.PLA.100 - ELEC
[5 empty] | QES-ITC-E08-206 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.PLA.073 - BAY EQ.
[5 empty] | QES-ITC-E08-207 | QA_TEM_082_Room Checklist
FIT OFF - LEVEL 1-01.CMU.074 - 1B
[5 empty] | QES-ITC-E08-208 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.075 - ENS
[5 empty] | QES-ITC-E08-209 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.071 - 1B
[5 empty] | QES-ITC-E08-210 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.070 - ENS
[5 empty] | QES-ITC-E08-211 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.068 - 2B
[5 empty] | QES-ITC-E08-212 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.069 - ENS
[5 empty] | QES-ITC-E08-213 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.067 - 2B
[5 empty] | QES-ITC-E08-214 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.066 - ENS
[5 empty] | QES-ITC-E08-215 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.064 - 2B
[5 empty] | QES-ITC-E08-216 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.065 - ENS
[5 empty] | QES-ITC-E08-217 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.063 - 2B
[5 empty] | QES-ITC-E08-218 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.062 - ENS
[5 empty] | QES-ITC-E08-219 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.060 - 1B
[5 empty] | QES-ITC-E08-220 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.061 - ENS
[5 empty] | QES-ITC-E08-221 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.059 - 1B
[5 empty] | QES-ITC-E08-222 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.058 - ENS
[5 empty] | QES-ITC-E08-223 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.051 - LOUNGE
[5 empty] | QES-ITC-E08-224 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.050 - 1B
[5 empty] | QES-ITC-E08-225 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.049 - ENS
[5 empty] | QES-ITC-E08-226 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.047 - 1B
[5 empty] | QES-ITC-E08-227 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.048 - ENS
[5 empty] | QES-ITC-E08-228 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.046 - 1B
[5 empty] | QES-ITC-E08-229 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.045 - ENS
[5 empty] | QES-ITC-E08-230 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.043 - 1B
[5 empty] | QES-ITC-E08-231 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.044 - ENS
[5 empty] | QES-ITC-E08-232 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 1-01.CMU.019 - LOUNGE
[5 empty] | QES-ITC-E08-233 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 2 02.PLA.001 - LIFT LOBBY
[5 empty] | QES-ITC-E08-234 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 2 02.PLA.002 - AHD 32840
[5 empty] | QES-ITC-E08-235 | QA_TEM_080_Room Body Protection Checklist
FIT OFF - LEVEL 2 02.PLA.003 - COMMS
[5 empty] | QES-ITC-E08-236 | QA_TEM_080_Room Body Protection Checklist
UPS
E11
BYP-91B10MU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-001 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91B10MU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-002 | QA_TEM_011_Mains & Submains Installation
BYP-91B10MU1 - CABLE TERMINATIONS (SUB MAINS)
[5 empty] | QES-ITC-E11-003 | QA_TEM_014_Cable Terminations
BYP-91B10MU1 - FINAL INSTALLATION TEST SHEET
[5 empty] | QES-ITC-E11-004 | Final Installation Checklist
DB-91B10MU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-005 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91B10MU2 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-006 | QA_TEM_011_Mains & Submains Installation
DB-91LG1MU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-007 | QA_TEM_011_Mains & Submains Installation
DB-91G1MU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-008 | QA_TEM_011_Mains & Submains Installation
DB-91L11MU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-009 | QA_TEM_011_Mains & Submains Installation
DB-91L11MU1 - CABLE TERMINATIONS (SUB MAINS)
[5 empty] | QES-ITC-E11-010 | QA_TEM_014_Cable Terminations
DB-91B10MU1 - FINAL INSTALLATION TEST SHEET
[5 empty] | QES-ITC-E11-011 | Final Installation Checklist
BYP-92B10CU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-012 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-92B10CU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-013 | QA_TEM_011_Mains & Submains Installation
BYP-92B10CU1 - CABLE TERMINATIONS (SUB MAINS)
[5 empty] | QES-ITC-E11-014 | QA_TEM_014_Cable Terminations
BYP-92B10CU1 - FINAL INSTALLATION TEST SHEET
[5 empty] | QES-ITC-E11-015 | Final Installation Checklist
DB-92B10CU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-016 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-92B10CU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-017 | QA_TEM_011_Mains & Submains Installation
DB-92LG1CU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-018 | QA_TEM_011_Mains & Submains Installation
DB-92G1CU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-019 | QA_TEM_011_Mains & Submains Installation
DB-92L11CU1 - MAINS & SUBMAINS INSTALLATION
[5 empty] | QES-ITC-E11-020 | QA_TEM_011_Mains & Submains Installation
DB-92L11CU1 - CABLE TERMINATIONS (SUB MAINS)
[5 empty] | QES-ITC-E11-021 | QA_TEM_014_Cable Terminations
DB-92B10CU1 - FINAL INSTALLATION TEST SHEET
[5 empty] | QES-ITC-E11-022 | Final Installation Checklist
DB-91B10MU2 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-023 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91B10MU2 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E11-024 | QA_TEM_014_Cable Terminations
DB-91B10MU2 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E11-025 | Final Installation Checklist
DB-91LG1MU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-026 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91LG1MU1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E11-027 | QA_TEM_014_Cable Terminations
DB-91LG1MU1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E11-028 | Final Installation Checklist
DB-91G1MU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-029 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91G1MU1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E11-030 | QA_TEM_014_Cable Terminations
DB-91G1MU1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E11-031 | Final Installation Checklist
DB-91L11MU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-032 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-91L11MU1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E11-033 | QA_TEM_014_Cable Terminations
DB-91L11MU1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E11-034 | Final Installation Checklist
DB-92B10CU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-035 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-92B10CU1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E11-036 | QA_TEM_014_Cable Terminations
DB-92B10CU1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E11-037 | Final Installation Checklist
DB-92LG1CU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-038 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-92LG1CU1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E11-039 | QA_TEM_014_Cable Terminations
DB-92LG1CU1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E11-040 | Final Installation Checklist
DB-92G1CU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-041 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-92G1CU1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E11-042 | QA_TEM_014_Cable Terminations
DB-92G1CU1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E11-043 | Final Installation Checklist
DB-92L11CU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-044 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-92L11CU1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E11-045 | QA_TEM_014_Cable Terminations
DB-92L11CU1 - FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E11-046 | Final Installation Checklist
DB-92L21CU1 - SWITCHBOARD & DISTRIBUTION BOARD INSTALLATION
[5 empty] | QES-ITC-E11-047 | QA_TEM_012_Switchboard & Distribution Board Installation
DB-92L21CU1 - CABLE TERMINATIONS (SUBMAIN)
[5 empty] | QES-ITC-E11-048 | QA_TEM_014_Cable Terminations
DB-92L21CU1- FINAL INSTALLATION TEST SHEET (SUBCIRCUITS)
[5 empty] | QES-ITC-E11-049 | Final Installation Checklist
LIGHTNING PROTECTION
E12
LIGHTNING PROTECTION
[5 empty] | QES-ITC-E12-001 | QA_TEM_029_Lightning Protection
FIRE SEALING
E13
FIRE SEALING - BASEMENT 1
[5 empty] | QES-ITC-E13-001 | QA_TEM_017_Fire Sealing
FIRE SEALING - LOWER GROUND
[5 empty] | QES-ITC-E13-002 | QA_TEM_017_Fire Sealing
FIRE SEALING - GROUND
[5 empty] | QES-ITC-E13-003 | QA_TEM_017_Fire Sealing
FIRE SEALING - LEVEL 1
[5 empty] | QES-ITC-E13-004 | QA_TEM_017_Fire Sealing
FIRE SEALING - LEVEL 2
[5 empty] | QES-ITC-E13-005 | QA_TEM_017_Fire Sealing

## example
Folder Structure |  |  |  |  | Checklists
Site QA
Electrical
Switchboards
MDB-A
|  |  |  | Cable Terminations | QA_TEM_014_Cable Terminations
|  |  |  | Fit Off | QA_TEM_043_Fit Off Checklist
|  |  |  | Power Commissioning | QA_TEM_041_Power Cable Commissioning
|  |  |  | Final Installation Checklist | Final Installation Checklist
DB-BOP
|  |  |  | Mains & Submains Installation | QA_TEM_011_Mains & Submains Installation
|  |  |  | Switchboard & DB Installation | QA_TEM_012_Switchboard & Distribution Board Installation
|  |  |  | Switchboard & Distribution Board Assembly | QA_TEM_013_Switchboard & Distribution Board Assembly
|  |  |  | Cable Terminations | QA_TEM_014_Cable Terminations
|  |  |  | Accessories Installation | QA_TEM_015_Accessories Installation
|  |  |  | Light Fitting Installation | QA_TEM_016_Light Fitting Installation
|  |  |  | LCP's & Field Devices | QA_TEM_018_LCP's & Field Devices
|  |  |  | Control Cables | QA_TEM_022_Control Cables
|  |  |  | Emergency & Exit Lighting | QA_TEM_023_Emergency & Exit Lighting
|  |  |  | Lighting Rough In | QA_TEM_042_Rough In Checklist
|  |  |  | Power Rough In | QA_TEM_042_Rough In Checklist
|  |  |  | Lighting Fit Off | QA_TEM_043_Fit Off Checklist
|  |  |  | Power Fit Off | QA_TEM_043_Fit Off Checklist
|  |  |  | Power Commissioning | QA_TEM_041_Power Cable Commissioning
|  |  |  | Multi Core Cable Commissioning | QA_TEM_040_Multi-Core Cable Commissioning
|  |  |  | Final Sub Circuit Installation | QA_TEM_010_Final Sub Circuit Installation
|  |  |  | Final Installation Checklist | Final Installation Checklist
MSSB-LAB
|  |  |  | Mains & Submains Installation | QA_TEM_011_Mains & Submains Installation
Cable Tray
Area 1
|  |  |  | Cable Support Prior to Cabling | QA_TEM_008_Cable Support Prior to Cabling
|  |  |  | Cable Support Post Cabling | QA_TEM_009_Cable Support Post Cabling
Conduit Installation
|  |  | Area 1 |  | QA_TEM_006_Surface Conduit Installation
Temporary Services
Temp DB 1
|  |  |  | September 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | October 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | November 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | December 2023 | QA_TEM_063_Construction Distribution Boards
Temp DB 2
|  |  |  | September 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | October 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | November 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | December 2023 | QA_TEM_063_Construction Distribution Boards
Communications
|  | Rough In |  |  | QA_TEM_042_Rough In Checklist
|  | Fit Off |  |  | QA_TEM_043_Fit Off Checklist
|  | Data & Comms Cabling |  |  | QA_TEM_025_Data & Communications Cabling
|  | Cable Terminations |  |  | QA_TEM_014_Cable Terminations
|  | Final Sub Circuit Installation |  |  | QA_TEM_010_Final Sub Circuit Installation