## Project Structure EG (hidden)
Folder Structure |  |  |  | Checklists
Site QA
Switchboards
S1
|  |  | S.1 Assembly | QA_TEM_013_Switchboard & Distribution Board Assembly
|  |  | S.1 Installation | QA_TEM_012_Switchboard & Distribution Board Installation
|  |  | S.1 Cable Termination | QA_TEM_014_Cable Terminations
|  |  | S.1 Accessories | QA_TEM_015_Accessories Installation
|  | S2 |  | Same as S1
|  | S3 |  | Same as S1
|  | S4 |  | Same as S1
|  | S5 |  | Same as S1
|  | S6 |  | Same as S1
|  | S7 |  | Same as S1
|  | S8 |  | Same as S1
|  | S9 |  | Same as S1
|  | S10 |  | Same as S1
Cable Support
Room 1
|  |  | Prior | QA_TEM_008_Cable Support Prior to Cabling
|  |  | Post | QA_TEM_009_Cable Support Post Cabling
|  | Room 2 |  | Same as per Room 1
|  | Room 3 |  | Same as per Room 1
|  | Room 4 |  | Same as per Room 1
|  | Room 5 |  | Same as per Room 1
|  | Room 6 |  | Same as per Room 1
Emergency Lighting
|  | Room 1 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 2 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 3 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 4 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 5 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 6 |  | QA_TEM_023_Emergency & Exit Lighting

## Project Structure
Folder Structure | [5 empty] | Checklists
Ripley Sub-Acute QA
Switchboards
Main Switchboards
SMSB-1
|  |  |  | Earth Electrode |  | QA_TEM_003_Earth Electrode
|  |  |  | Mains & Submains Installation |  | QA_TEM_011_Mains & Submains Installation
|  |  |  | Switchboard & DB Installation |  | QA_TEM_012_Switchboard & Distribution Board Installation
|  |  |  | Power Cable Commissioning |  | QA_TEM_041_Power Cable Commissioning
|  |  |  | Final Installation Test Sheet |  | Final Installation Checklist
SMSB-2
|  |  |  | Earth Electrode |  | QA_TEM_003_Earth Electrode
|  |  |  | Mains & Submains Installation |  | QA_TEM_011_Mains & Submains Installation
|  |  |  | Switchboard & DB Installation |  | QA_TEM_012_Switchboard & Distribution Board Installation
|  |  |  | Power Cable Commissioning |  | QA_TEM_041_Power Cable Commissioning
|  |  |  | Final Installation Test Sheet |  | Final Installation Checklist
MDB-SA-1
|  |  |  | AS ABOVE |  | AS ABOVE
MDB-SA-2
|  |  |  | AS ABOVE |  | AS ABOVE
MSB-CP
|  |  |  | AS ABOVE |  | AS ABOVE
EXISTING MSB-SHP
|  |  |  | AS ABOVE |  | AS ABOVE
Distritbution Boards
DB-FPR
|  |  |  | Mains & Submains Installation |  | QA_TEM_011_Mains & Submains Installation
|  |  |  | Switchboard & DB Installation |  | QA_TEM_012_Switchboard & Distribution Board Installation
|  |  |  | Power Cable Commissioning |  | QA_TEM_041_Power Cable Commissioning
|  |  |  | Final Installation Test Sheet |  | Final Installation Checklist
DB-WPR
|  |  |  | AS ABOVE |  | AS ABOVE
DB-SUB
|  |  |  | AS ABOVE |  | AS ABOVE
DB-SMSB
|  |  |  | AS ABOVE |  | AS ABOVE
PFC UNIT
|  |  |  | AS ABOVE |  | AS ABOVE
DB-UPS
|  |  |  | AS ABOVE |  | AS ABOVE
DB-H1
|  |  |  | AS ABOVE |  | AS ABOVE
DB-LG-1-E
|  |  |  | AS ABOVE |  | AS ABOVE
DB-LG-2-E
|  |  |  | AS ABOVE |  | AS ABOVE
DB-L1-1-E
|  |  |  | AS ABOVE |  | AS ABOVE
DB-L1-2-E
|  |  |  | AS ABOVE |  | AS ABOVE
DB-L2-1-E
|  |  |  | AS ABOVE |  | AS ABOVE
DB-L2-2-E
|  |  |  | AS ABOVE |  | AS ABOVE
DB-LG-C-E
|  |  |  | AS ABOVE |  | AS ABOVE
DB-LG-K-NE
|  |  |  | AS ABOVE |  | AS ABOVE
DB-LG-1-NE
|  |  |  | AS ABOVE |  | AS ABOVE
DB-LG-2-NE
|  |  |  | AS ABOVE |  | AS ABOVE
DB-L1-1-NE
|  |  |  | AS ABOVE |  | AS ABOVE
DB-L1-2-NE
|  |  |  | AS ABOVE |  | AS ABOVE
DB-L2-1-NE
|  |  |  | AS ABOVE |  | AS ABOVE
DB-L2-2-NE
|  |  |  | AS ABOVE |  | AS ABOVE
MSSB's
FDCIE
|  |  |  | Mains & Submains Installation |  | QA_TEM_011_Mains & Submains Installation
FOH LIFT 1
|  |  |  | AS ABOVE |  | AS ABOVE
FOH LIFT 2
|  |  |  | AS ABOVE |  | AS ABOVE
BOH LIFT
|  |  |  | AS ABOVE |  | AS ABOVE
MSSB-02-1
|  |  |  | AS ABOVE |  | AS ABOVE
MSSB-02-2
|  |  |  | AS ABOVE |  | AS ABOVE
MSSB-01-2
|  |  |  | AS ABOVE |  | AS ABOVE
MSSB-02-3
|  |  |  | AS ABOVE |  | AS ABOVE
MSSB-01-1
|  |  |  | AS ABOVE |  | AS ABOVE
MSSB-02-4
| Conduit & Pits |  |  | AS ABOVE |  | AS ABOVE
Underground Conduit & Pit Reticulation
Main Switchroom to Future Carpark (Electrical)
|  |  |  | Cable Pit Installation |  | QA_TEM_081_Cable Pit Installation
|  |  |  | Trench and Backfill |  | QA_TEM_004_Trench and Backfill
|  |  |  | Cast In Conduit Installation |  | QA_TEM_007_Cast in Conduit Installation
Main Switchroom to Future Carpark (Comms)
|  |  |  | AS ABOVE |  | AS ABOVE
Main Switchroom to Kitchen Pit
|  |  |  | AS ABOVE |  | AS ABOVE
Kitchen Pit to Outdoor Rehab
|  |  |  | AS ABOVE |  | AS ABOVE
Kitchen Pit to Electrical Cupboard
|  |  |  | AS ABOVE |  | AS ABOVE
Kitchen Pit to Electrical Cupboard (Lift)
|  |  |  | AS ABOVE |  | AS ABOVE
Outdoor Rehab to Electrical Cupboard (Lift)
|  |  |  | AS ABOVE |  | AS ABOVE
Electrical Cupboard (Lift) to PL3 Loading Bay
|  |  |  | AS ABOVE |  | AS ABOVE
Electrical Cupboard (Lift) to Internal Courtyard
|  |  |  | AS ABOVE |  | AS ABOVE
NBN to AIDP Comms Room
|  |  |  | AS ABOVE |  | AS ABOVE
Comms Pit to AIDP Room
|  |  |  | AS ABOVE |  | AS ABOVE
Electrical DB Cupboard
|  |  |  | AS ABOVE |  | AS ABOVE
Fire Pump Room to Van Service Pillar
|  |  |  | AS ABOVE |  | AS ABOVE
Water Pump Room to Van Service Pillar
|  |  |  | AS ABOVE |  | AS ABOVE
Main Switchroom to SHP Comms
|  |  |  | AS ABOVE |  | AS ABOVE
Main Switchroom to Diesel Gen
| Electrical |  |  | AS ABOVE |  | AS ABOVE
Level 0
East Zone - Front of House
AIRLOCK - 0.1.000
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
FOYER - 0.1.001
[5 empty] | AS ABOVE | AS ABOVE
FH - 0.E.008
[5 empty] | AS ABOVE | AS ABOVE
CAFE - 0.1.002
[5 empty] | AS ABOVE | AS ABOVE
QUIET ROOM - 0.1.003
[5 empty] | AS ABOVE | AS ABOVE
MULTI-PURPOSE - 0.1.004
[5 empty] | AS ABOVE | AS ABOVE
WC-AC - 0.1.005
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
PARENT - 0.1.006
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
WC-PU - 0.1.007
[5 empty] | AS ABOVE | AS ABOVE
WC-PU - 0.1.008
[5 empty] | AS ABOVE | AS ABOVE
RECEPTION - 0.1.009
[5 empty] | AS ABOVE | AS ABOVE
IHLO - 0.1.010
[5 empty] | AS ABOVE | AS ABOVE
CORR - 0.T.007
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
East Zone - Shared Therapy
CONS - 0.3.001
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CONS - 0.3.003
[5 empty] | AS ABOVE | AS ABOVE
INT - 0.3.005
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
INT - 0.3.004
[5 empty] | AS ABOVE | AS ABOVE
WORKSTATIONS - 0.3.006
[5 empty] | AS ABOVE | AS ABOVE
ADL BATH - 0.3.007
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ADL KIT - 0.3.010
[5 empty] | AS ABOVE | AS ABOVE
GYM OT - 0.3.013
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ST-EQ - 0.3.012
[5 empty] | AS ABOVE | AS ABOVE
ST-EQ - 0.3.009
[5 empty] | AS ABOVE | AS ABOVE
INT - 0.3.008
[5 empty] | AS ABOVE | AS ABOVE
GYM GROUP - 0.3.016
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
WRITE UP - 0.3.021
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CONS - 0.3.017
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ST-EQ - 0.3.019
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
WC-AC - 0.3.018
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
WRITE UP - 0.3.015
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ST-EQ - 0.3.000
[5 empty] | AS ABOVE | AS ABOVE
EDB - 0.E.003
[5 empty] | AS ABOVE | AS ABOVE
STAIR 2 - 0.T.005
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CORR - 0.T.006
[5 empty] | AS ABOVE | AS ABOVE
CORR - 0.T.004
[5 empty] | AS ABOVE | AS ABOVE
CORR - 0.T.010
[5 empty] | AS ABOVE | AS ABOVE
Central Zone - Rehabilitation
LOUNGE - 0.2.015
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
2 BR - 0.2.017
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.016
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 0.2.018
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.019
[5 empty] | AS ABOVE | AS ABOVE
B-Bev - 0.2.027
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
DINING - 0.2.028
[5 empty] | AS ABOVE | AS ABOVE
B-MT - 0.2.029
[5 empty] | AS ABOVE | AS ABOVE
B-MEQ - 0.2.025
[5 empty] | AS ABOVE | AS ABOVE
LAUNDRY - 0.2.020
[5 empty] | AS ABOVE | AS ABOVE
B-PRINT - 0.2.023
[5 empty] | AS ABOVE | AS ABOVE
SSTN - 0.2.021
[5 empty] | AS ABOVE | AS ABOVE
B-LIN - 0.2.022
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 0.2.024
[5 empty] | AS ABOVE | AS ABOVE
1 BR-BA - 0.2.063
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ENS - 0.2.064
[5 empty] | AS ABOVE | AS ABOVE
1 BR - 0.2.066
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.065
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 0.2.067
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.068
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 0.2.000
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.001
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 0.2.003
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.002
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 0.2.004
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.005
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 0.2.007
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.006
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 0.2.008
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.009
[5 empty] | AS ABOVE | AS ABOVE
4 BR - 0.2.011
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.010
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.012
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 0.2.014
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.013
[5 empty] | AS ABOVE | AS ABOVE
DISP - 0.2.043
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ST-GEN - 0.2.046
[5 empty] | AS ABOVE | AS ABOVE
B-WOW - 0.2.042
[5 empty] | AS ABOVE | AS ABOVE
B-LIN - 0.2.044
[5 empty] | AS ABOVE | AS ABOVE
CLRM - 0.2.047
[5 empty] | AS ABOVE | AS ABOVE
WC-ST - 0.2.045
[5 empty] | AS ABOVE | AS ABOVE
B-HWP - 0.2.041
[5 empty] | AS ABOVE | AS ABOVE
B-MEQ - 0.2.040
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 0.2.039
[5 empty] | AS ABOVE | AS ABOVE
CLN - 0.2.069
[5 empty] | AS ABOVE | AS ABOVE
WC-AC - 0.2.037
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
INT - 0.2.036
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
DTUR - 0.2.035
[5 empty] | AS ABOVE | AS ABOVE
CLN-MED - 0.2.034
[5 empty] | AS ABOVE | AS ABOVE
SSTN - 0.2.033
[5 empty] | AS ABOVE | AS ABOVE
B-RES - 0.2.032
[5 empty] | AS ABOVE | AS ABOVE
OFF-NUM - 0.2.031
[5 empty] | AS ABOVE | AS ABOVE
OFF-CLN - 0.2.030
[5 empty] | AS ABOVE | AS ABOVE
ST-EQ - 0.2.048
[5 empty] | AS ABOVE | AS ABOVE
FH - 0.E.010
[5 empty] | AS ABOVE | AS ABOVE
1 BR-BA - 0.2.055
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ENS-BA - 0.2.056
[5 empty] | AS ABOVE | AS ABOVE
1 BR-BA - 0.2.051
[5 empty] | AS ABOVE | AS ABOVE
ENS-BA - 0.2.052
[5 empty] | AS ABOVE | AS ABOVE
1 BR-BA - 0.2.054
[5 empty] | AS ABOVE | AS ABOVE
ENS-BA - 0.2.053
[5 empty] | AS ABOVE | AS ABOVE
ASSESS - 0.2.049
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.050
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 0.2.059
[5 empty] | AS ABOVE | AS ABOVE
ENS - 0.2.060
[5 empty] | AS ABOVE | AS ABOVE
1 BR-BA - 0.2.062
[5 empty] | AS ABOVE | AS ABOVE
ENS-BA - 0.2.061
[5 empty] | AS ABOVE | AS ABOVE
CORR - 0.T.014
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CORR - 0.T.015
[5 empty] | AS ABOVE | AS ABOVE
CORR - 0.T.001
[5 empty] | AS ABOVE | AS ABOVE
CORR - 0.T-002
[5 empty] | AS ABOVE | AS ABOVE
West Zone - Back of House
CHANGE-STM - 0.4.001
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CHANGE-STF - 0.4.000
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 0.4.021
[5 empty] | AS ABOVE | AS ABOVE
B-COMP - 0.4.019
[5 empty] | AS ABOVE | AS ABOVE
BODY HOLD - 0.4.002
[5 empty] | AS ABOVE | AS ABOVE
WC-AC - 0.4.003
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
EDB - 0.E.013
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
STAIR 1 - 0.T.000
[5 empty] | AS ABOVE | AS ABOVE
EDB - 0.E.012
[5 empty] | AS ABOVE | AS ABOVE
DOCK CLEAN - 0.4.004
[5 empty] | AS ABOVE | AS ABOVE
ST-BULK - 0.4.005
[5 empty] | AS ABOVE | AS ABOVE
KITCH - 0.4.006
[5 empty] | AS ABOVE | AS ABOVE
ST CENRAL EQ - 0.4.010
[5 empty] | AS ABOVE | AS ABOVE
DOCK DIRTY - 0.4.008
[5 empty] | AS ABOVE | AS ABOVE
ST-DLIN - 0.4.009
[5 empty] | AS ABOVE | AS ABOVE
CLRM - 0.4.013
[5 empty] | AS ABOVE | AS ABOVE
OFF-2P - 0.4.014
[5 empty] | AS ABOVE | AS ABOVE
WRITE UP - 0.4.053
[5 empty] | AS ABOVE | AS ABOVE
COMMS - 0.E.015
[5 empty] | AS ABOVE | AS ABOVE
ST-CLIN - 0.4.011
[5 empty] | AS ABOVE | AS ABOVE
ST-COMMS - 0.E.014
[5 empty] | AS ABOVE | AS ABOVE
AIRLOCK - 0.4.012
[5 empty] | AS ABOVE | AS ABOVE
ST-PHARM - 0.4.015
[5 empty] | AS ABOVE | AS ABOVE
PATH - 0.4.016
[5 empty] | AS ABOVE | AS ABOVE
ST GAS - 0.4.017
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CORR - 0.T.013
[5 empty] | AS ABOVE | AS ABOVE
CORR - 0.T.012
[5 empty] | AS ABOVE | AS ABOVE
RECYCLABLE WASTE - 0.4.050
[5 empty] | AS ABOVE | AS ABOVE
GENERAL WASTE - 0.4.051
[5 empty] | AS ABOVE | AS ABOVE
CLINICAL WASTE - 0.4.052
[5 empty] | AS ABOVE | AS ABOVE
Level 01
East Zone - Shared Administration
MEETING - 1.2.009
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
BREAKOUT - 1.2.008
[5 empty] | AS ABOVE | AS ABOVE
BREAKOUT - 1.2.007
[5 empty] | AS ABOVE | AS ABOVE
WORKSTATIONS - 1.2.000
[5 empty] | AS ABOVE | AS ABOVE
B-PRINT - 1.2.001
[5 empty] | AS ABOVE | AS ABOVE
OFF-2P - 1.2.010
[5 empty] | AS ABOVE | AS ABOVE
OFF-2P - 1.2.011
[5 empty] | AS ABOVE | AS ABOVE
OFF-2P - 1.2.012
[5 empty] | AS ABOVE | AS ABOVE
OFF-2P - 1.2.013
[5 empty] | AS ABOVE | AS ABOVE
MEETING - 1.2.014
[5 empty] | AS ABOVE | AS ABOVE
OFF-1P - 1.2.015
[5 empty] | AS ABOVE | AS ABOVE
PODS - 1.2.017
[5 empty] | AS ABOVE | AS ABOVE
LOCKERS - 1.2.016
[5 empty] | AS ABOVE | AS ABOVE
WC-AC - 1.2.004
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
WC-AC - 1.2.006
[5 empty] | AS ABOVE | AS ABOVE
WC-ST - 1.2.003
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
WC-ST - 1.2.005
[5 empty] | AS ABOVE | AS ABOVE
STAFF ROOM - 1.2.002
[5 empty] | AS ABOVE | AS ABOVE
STAIR 2 - 1.T.005
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CORR - 1.T.008
[5 empty] | AS ABOVE | AS ABOVE
Central Zone - GEM
2 BR - 1.1.014
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ENS - 1.1.015
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 1.1.017
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.016
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 1.1.018
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.019
[5 empty] | AS ABOVE | AS ABOVE
TRANSIT - 1.1.020
[5 empty] | AS ABOVE | AS ABOVE
CORR - 1.T.010
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
WC-PT - 1.1.021
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 1.1.025
[5 empty] | AS ABOVE | AS ABOVE
B-MT - 1.1.030
[5 empty] | AS ABOVE | AS ABOVE
DINING - 1.1.029
[5 empty] | AS ABOVE | AS ABOVE
B-BEV - 1.1.028
[5 empty] | AS ABOVE | AS ABOVE
B-MEQ - 1.1.026
[5 empty] | AS ABOVE | AS ABOVE
B-PRINT - 1.1.024
[5 empty] | AS ABOVE | AS ABOVE
SSTN - 1.1.022
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 1.1.027
[5 empty] | AS ABOVE | AS ABOVE
B-LIN - 1.1.023
[5 empty] | AS ABOVE | AS ABOVE
LOUNGE - 1.1.066
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
1 BR - 1.1.068
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.067
[5 empty] | AS ABOVE | AS ABOVE
1 BR - 1.1.069
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.070
[5 empty] | AS ABOVE | AS ABOVE
CORR - 1.T.011
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
LOBBY - 1.T.004
[5 empty] | AS ABOVE | AS ABOVE
TERRACE - 1.1.072
[5 empty] | AS ABOVE | AS ABOVE
STAIR 1 - 1.T.000
[5 empty] | AS ABOVE | AS ABOVE
GEM THERAPY - 1.1.000
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
2 BR - 1.1.002
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.001
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 1.1.003
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.004
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 1.1.006
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.005
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 1.1.007
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.008
[5 empty] | AS ABOVE | AS ABOVE
4 BR - 1.1.010
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.009
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.011
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 1.1.013
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.012
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 1.1.047
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
B-LIN - 1.1.046
[5 empty] | AS ABOVE | AS ABOVE
ST-GEN - 1.1.045
[5 empty] | AS ABOVE | AS ABOVE
DISP - 1.1.042
[5 empty] | AS ABOVE | AS ABOVE
CLN - 1.1.071
[5 empty] | AS ABOVE | AS ABOVE
WC-AC - 1.1.039
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
DTUR - 1.1.037
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CLN-MED - 1.1.036
[5 empty] | AS ABOVE | AS ABOVE
SSTN - 1.1.035
[5 empty] | AS ABOVE | AS ABOVE
B-RES - 1.1.034
[5 empty] | AS ABOVE | AS ABOVE
OFF-NUM - 1.1.033
[5 empty] | AS ABOVE | AS ABOVE
OFF-CLN - 1.1.032
[5 empty] | AS ABOVE | AS ABOVE
B-WOW - 1.1.031
[5 empty] | AS ABOVE | AS ABOVE
COMMS - 1.E.007
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 1.1.048
[5 empty] | AS ABOVE | AS ABOVE
B-MEQ - 1.1.044
[5 empty] | AS ABOVE | AS ABOVE
FH - 1.E.014
[5 empty] | AS ABOVE | AS ABOVE
CLRM - 1.1.043
[5 empty] | AS ABOVE | AS ABOVE
WC-ST - 1.1.040
[5 empty] | AS ABOVE | AS ABOVE
INT - 1.1.038
[5 empty] | AS ABOVE | AS ABOVE
ST-EQ - 1.1.049
[5 empty] | AS ABOVE | AS ABOVE
1 BR - 1.1.050
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ENS - 1.1.051
[5 empty] | AS ABOVE | AS ABOVE
1 BR - 1.1.053
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.052
[5 empty] | AS ABOVE | AS ABOVE
1 BR - 1.1.054
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.055
[5 empty] | AS ABOVE | AS ABOVE
1 BR - 1.1.057
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.056
[5 empty] | AS ABOVE | AS ABOVE
1 BR - 1.1.058
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.059
[5 empty] | AS ABOVE | AS ABOVE
1 BR - 1.1.061
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.060
[5 empty] | AS ABOVE | AS ABOVE
1 BR-BA - 1.1.062
[5 empty] | AS ABOVE | AS ABOVE
ENS-BA - 1.1.063
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 1.1.065
[5 empty] | AS ABOVE | AS ABOVE
ENS - 1.1.064
[5 empty] | AS ABOVE | AS ABOVE
LOUNGE - 1.1.066
[5 empty] | AS ABOVE | AS ABOVE
CORR - 1.T.001
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CORR - 1.T.002
[5 empty] | AS ABOVE | AS ABOVE
West Zone - Plant
EDB - 1.E.008
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
RISER - 1.E.009
[5 empty] | AS ABOVE | AS ABOVE
EDB - 1.E.010
[5 empty] | AS ABOVE | AS ABOVE
PLANT - 1.E.011
[5 empty] | AS ABOVE | AS ABOVE
PLANT - 1.E.012
[5 empty] | AS ABOVE | AS ABOVE
Level 02
East Zone - Plant
PLANT - 2.E.007
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
RISER - 2.E.006
[5 empty] | AS ABOVE | AS ABOVE
STAIR 2 - 2.T.005
[5 empty] | AS ABOVE | AS ABOVE
LOBBY - 2.T.006
[5 empty] | AS ABOVE | AS ABOVE
LOBBY - 2-T-009
[5 empty] | AS ABOVE | AS ABOVE
Central Zone - Pallative
LOUNGE - 2.1.006
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
1 BR-SP - 2.1.017
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.018
[5 empty] | AS ABOVE | AS ABOVE
OFF-2P - 2.2.003
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
OFF-1P - 2.2.004
[5 empty] | AS ABOVE | AS ABOVE
OFF-1P - 2.2.002
[5 empty] | AS ABOVE | AS ABOVE
OFF-1P - 2.2.001
[5 empty] | AS ABOVE | AS ABOVE
BATH - 2.1.019
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CORR - 2.T.012
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
DINING - 2.1.029
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
B-BEV - 2.1.028
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 2.1.025
[5 empty] | AS ABOVE | AS ABOVE
B-MT - 2.1.030
[5 empty] | AS ABOVE | AS ABOVE
B-MEQ - 2.1.026
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 2.1.027
[5 empty] | AS ABOVE | AS ABOVE
ST-GEN - 2.1.021
[5 empty] | AS ABOVE | AS ABOVE
B-PRINT - 2.1.023
[5 empty] | AS ABOVE | AS ABOVE
SSTN - 2.1.022
[5 empty] | AS ABOVE | AS ABOVE
B-LIN - 2.1.024
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.067
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ENS - 2.1.068
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.070
[5 empty] | AS ABOVE | AS ABOVE
ENS 2.1.069
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.071
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.072
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.074
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.073
[5 empty] | AS ABOVE | AS ABOVE
1 BR-BA - 2.1.075
[5 empty] | AS ABOVE | AS ABOVE
ENS-BA - 2.1.076
[5 empty] | AS ABOVE | AS ABOVE
CORR - 2.T.004
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
TERRACE - 2.1.078
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 2.1.000
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ENS - 2.1.001
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 2.1.003
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.002
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 2.1.004
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.005
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 2.1.007
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.006
[5 empty] | AS ABOVE | AS ABOVE
2 BR - 2.1.008
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.009
[5 empty] | AS ABOVE | AS ABOVE
4 BR - 2.1.011
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.010
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.013
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.015
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.014
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 2.1.047
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
B-LIN - 2.1.046
[5 empty] | AS ABOVE | AS ABOVE
ST-EQ - 2.1.044
[5 empty] | AS ABOVE | AS ABOVE
DISP - 2.1.043
[5 empty] | AS ABOVE | AS ABOVE
CLN - 2.1.077
[5 empty] | AS ABOVE | AS ABOVE
WC-AC - 2.1.039
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
DTUR - 2.1.037
[5 empty] | Rough-In | QA_TEM_082_Room Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_082_Room Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CLN-MED - 2.1.036
[5 empty] | AS ABOVE | AS ABOVE
SSTN - 2.1.035
[5 empty] | AS ABOVE | AS ABOVE
B-RES - 2.1.034
[5 empty] | AS ABOVE | AS ABOVE
OFF-NUM - 2.1.032
[5 empty] | AS ABOVE | AS ABOVE
OFF-CLN - 2.1.033
[5 empty] | AS ABOVE | AS ABOVE
B-WOW - 2.1.031
[5 empty] | AS ABOVE | AS ABOVE
B-HWB - 2.1.048
[5 empty] | AS ABOVE | AS ABOVE
B-MEQ - 2.1.045
[5 empty] | AS ABOVE | AS ABOVE
FH - 2.E.013
[5 empty] | AS ABOVE | AS ABOVE
CLRM - 2.1.042
[5 empty] | AS ABOVE | AS ABOVE
WC-ST - 2.1.041
[5 empty] | AS ABOVE | AS ABOVE
INT - 2.1.038
[5 empty] | AS ABOVE | AS ABOVE
COMMS - 2.E.008
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.050
[5 empty] | Rough-In | QA_TEM_080_Room Body Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Fit-Off | QA_TEM_080_Room Body Checklist
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
ENS - 2.1.049
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.051
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.052
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.054
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.053
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.055
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.056
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.058
[5 empty] | AS ABOVE | AS ABOVE
ENS 2.1.057
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.059
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.060
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.062
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.061
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.063
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.064
[5 empty] | AS ABOVE | AS ABOVE
1 BR-SP - 2.1.066
[5 empty] | AS ABOVE | AS ABOVE
ENS - 2.1.065
[5 empty] | AS ABOVE | AS ABOVE
CORR - 2.T.001
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
CORR - 2.T.002
[5 empty] | AS ABOVE | AS ABOVE
CORR - 2.T.003
[5 empty] | AS ABOVE | AS ABOVE
CORR - 2.T.013
[5 empty] | AS ABOVE | AS ABOVE
CORR - 2.T.010
[5 empty] | AS ABOVE | AS ABOVE
West Zone - Plant
MSSB - 2.E.016
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
UPS - 2.E.015
[5 empty] | AS ABOVE | AS ABOVE
PLANT - 2.E.012
[5 empty] | AS ABOVE | AS ABOVE
RISER - 2.E.011
[5 empty] | AS ABOVE | AS ABOVE
RISER - 2.E.010
[5 empty] | AS ABOVE | AS ABOVE
BOH LIFT - 2.E.009
[5 empty] | AS ABOVE | AS ABOVE
STAIR 1 - 2.T.000
[5 empty] | AS ABOVE | AS ABOVE
Exterior
Therapy Gardens
[5 empty] | Rough-In | QA_TEM_042_Rough In Checklist
[5 empty] | Fit-Off | QA_TEM_043_Fit Off Checklist
[5 empty] | Cable Support | QA_TEM_008_Cable Support Prior to Cabling
[5 empty] | Conduit | QA_TEM_006_Surface Conduit Installation
[5 empty] | Fire Sealing | QA_TEM_017_Fire Sealing
[5 empty] | Equipotential Bonding | QA_TEM_079_Equipotential Bonding
[5 empty] | Final Installation Test Sheet | Final Installation Checklist
Entry Courtyard
[5 empty] | AS ABOVE | AS ABOVE
Internal Courtyard
[5 empty] | AS ABOVE | AS ABOVE
Back of House Park
[5 empty] | AS ABOVE | AS ABOVE
Temporary Construction
Site Compound
|  |  |  | Construction Main Switchboards |  | QA_TEM_062_Construction Main Switchboards
|  |  |  | Construction Distribution Boards |  | QA_TEM_063_Construction Distribution Boards
|  |  |  | Construction Wiring & Accessories |  | QA_TEM_064_Construction Wiring & Accessories
|  |  |  | Construction Lighting |  | QA_TEM_061_Construction Lighting
|  |  |  | Construction Wiring Checklist |  | QA_TEM_058_Construction Wiring Checklist
General Site
|  |  |  | Construction Distribution Boards |  | QA_TEM_063_Construction Distribution Boards
|  |  |  | Construction Wiring & Accessories |  | QA_TEM_064_Construction Wiring & Accessories
|  |  |  | Construction Lighting |  | QA_TEM_061_Construction Lighting
|  |  |  | Construction Wiring Checklist |  | QA_TEM_058_Construction Wiring Checklist
Level 0
|  |  |  | AS ABOVE |  | AS ABOVE
Level 1
|  |  |  | AS ABOVE |  | AS ABOVE
Level 2
|  |  |  | AS ABOVE |  | AS ABOVE
Light Poles
Loading Dock
QA_TEM_020_Lighting Poles
Car Park
AS ABOVE

## example
Folder Structure |  |  |  |  | Checklists
Site QA
Electrical
Switchboards
MDB-A
|  |  |  | Cable Terminations | QA_TEM_014_Cable Terminations
|  |  |  | Fit Off | QA_TEM_043_Fit Off Checklist
|  |  |  | Power Commissioning | QA_TEM_041_Power Cable Commissioning
|  |  |  | Final Installation Checklist | Final Installation Checklist
DB-BOP
|  |  |  | Mains & Submains Installation | QA_TEM_011_Mains & Submains Installation
|  |  |  | Switchboard & DB Installation | QA_TEM_012_Switchboard & Distribution Board Installation
|  |  |  | Switchboard & Distribution Board Assembly | QA_TEM_013_Switchboard & Distribution Board Assembly
|  |  |  | Cable Terminations | QA_TEM_014_Cable Terminations
|  |  |  | Accessories Installation | QA_TEM_015_Accessories Installation
|  |  |  | Light Fitting Installation | QA_TEM_016_Light Fitting Installation
|  |  |  | LCP's & Field Devices | QA_TEM_018_LCP's & Field Devices
|  |  |  | Control Cables | QA_TEM_022_Control Cables
|  |  |  | Emergency & Exit Lighting | QA_TEM_023_Emergency & Exit Lighting
|  |  |  | Lighting Rough In | QA_TEM_042_Rough In Checklist
|  |  |  | Power Rough In | QA_TEM_042_Rough In Checklist
|  |  |  | Lighting Fit Off | QA_TEM_043_Fit Off Checklist
|  |  |  | Power Fit Off | QA_TEM_043_Fit Off Checklist
|  |  |  | Power Commissioning | QA_TEM_041_Power Cable Commissioning
|  |  |  | Multi Core Cable Commissioning | QA_TEM_040_Multi-Core Cable Commissioning
|  |  |  | Final Sub Circuit Installation | QA_TEM_010_Final Sub Circuit Installation
|  |  |  | Final Installation Checklist | Final Installation Checklist
MSSB-LAB
|  |  |  | Mains & Submains Installation | QA_TEM_011_Mains & Submains Installation
Cable Tray
Area 1
|  |  |  | Cable Support Prior to Cabling | QA_TEM_008_Cable Support Prior to Cabling
|  |  |  | Cable Support Post Cabling | QA_TEM_009_Cable Support Post Cabling
Conduit Installation
|  |  | Area 1 |  | QA_TEM_006_Surface Conduit Installation
Temporary Services
Temp DB 1
|  |  |  | September 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | October 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | November 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | December 2023 | QA_TEM_063_Construction Distribution Boards
Temp DB 2
|  |  |  | September 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | October 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | November 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | December 2023 | QA_TEM_063_Construction Distribution Boards
Communications
|  | Rough In |  |  | QA_TEM_042_Rough In Checklist
|  | Fit Off |  |  | QA_TEM_043_Fit Off Checklist
|  | Data & Comms Cabling |  |  | QA_TEM_025_Data & Communications Cabling
|  | Cable Terminations |  |  | QA_TEM_014_Cable Terminations
|  | Final Sub Circuit Installation |  |  | QA_TEM_010_Final Sub Circuit Installation