## Folder Structure
Ground Level | Generator A | A. Airseal Checklist
| Generator B | A. Airseal Checklist
| Generator C | A. Airseal Checklist
| Generator D | A. Airseal Checklist
| Generator Hallway | A. Airseal Checklist
| IT Switchroom | A. Airseal Checklist
| Circulation Corridor | A. Airseal Checklist
| Data Hall | A. Airseal Checklist
| Client Store Room | A. Airseal Checklist
| Hydraulic/Spinkler Room | A. Airseal Checklist
Level 1 | Generator A | A. Airseal Checklist
| Generator B | A. Airseal Checklist
| Generator C | A. Airseal Checklist
| Generator D | A. Airseal Checklist
| Generator Hallway | A. Airseal Checklist
| IT Switchroom | A. Airseal Checklist
| Circulation Corridor | A. Airseal Checklist
| Data Hall | A. Airseal Checklist
| Client Store Room | A. Airseal Checklist
| Hydraulic/Spinkler Room | A. Airseal Checklist
| Perimeter Panels | A. Airseal Checklist

## A. Airseal Checklist
Type | Name | Value
Checklist | Joint Sealant Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer to horizontal & vertical joints | Photo Required
Checkpoint | Apply sealant to horizontal & vertical joints | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required