## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 74f3eb4f-9a6e-431f-b72c-b26cf2679d63 |  | checklist | V52 Firebarrier. Date: |  |  |  |  | Yes | QA - V52 Firebarrier | 174e9b78-1bd3-424b-9132-9b53a25416ac
checkpoint-status | 49f4ec61-7df7-4e81-b206-a3dc29ca2c0b |  | checkpoint | Location/Gridline details entered
text | 5b026adf-f622-5118-9c14-ca54659243e4 |  | textbox | Location/Gridline:
checkpoint-status | b2afc647-e720-4915-beb8-4dffe7d5d360 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | bf07c1ac-f23b-4e4d-ba4c-073fa3653d80 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 1f3cefa3-dc4c-4aa9-8e5b-48848c38499c |  | checkpoint | Compress and fit off rockwool strips to required compression depth for any other product allowance
checkpoint-status | 1c54bdad-d75c-4f80-8b58-01eb26c608b4 |  | checkpoint | 3mm thick Intusil applied evenly to one side only
checkpoint-status | 541ee6c5-846d-4b3d-8828-15930f8bf913 |  | checkpoint | Check full coverage is achieved
checklist-flat | 706c9161-5440-4d3c-acf9-b5aa2f10c61f |  | checklist | SSRGZ. Date: |  |  |  |  | Yes | QA - SSRGZ | 98342848-85ec-44b3-b0c2-8e74f5400761
checkpoint-status | 2d386a47-88e9-47d9-85d3-b844a358f7b7 |  | checkpoint | Location/Gridline details entered
text | 0c753d73-a78b-5d51-b313-899a0223a84e |  | textbox | Location/Gridline:
checkpoint-status | 96259368-b3e9-4045-82e9-481b78239dbb |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 1ad75b05-59ee-4421-a7a0-91cbc737c122 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 2f10e0c9-56bc-4f78-abdb-3ce409d27325 |  | checkpoint | Rebates correct depth / width
checkpoint-status | b93f719c-a9c2-42ab-befd-557e5ef1f104 |  | checkpoint | FFL height confirmed
checkpoint-status | b5f91a47-4645-4d04-8d11-a5e5c52d7e4a |  | checkpoint | Packer / grout installed with retainers fix securely to floor
checkpoint-status | c5c6eb34-8a59-487f-aaab-0fcece602779 |  | checkpoint | Inner retainers installed to solid substrate securely
checkpoint-status | e55b1dbd-97f3-4d88-bb2d-7d5b932161e1 |  | checkpoint | Turnbars installed with centre plate securely
checkpoint-status | ca7121d0-53ec-4455-9a82-5bb0ed83e5c7 |  | checkpoint | Clean finished product installed
checklist-flat | 5a7595e5-5a04-4365-b939-134f9b410e97 |  | checklist | Wavebar / All Gap Sizes |  |  |  |  | Yes | Wavebar / All Gap Sizes | 7c56aec9-6513-4483-8a6f-e395958fea84
checkpoint-status | 5f0d97ca-ef01-4c48-b2a3-d5da1c8a612e |  | checkpoint | Location/Gridline details entered
text | c34a77ad-a7c0-5f6c-a51d-5de036978057 |  | textbox | Location/Gridline:
checkpoint-status | 4b46bc9d-a9e1-4d10-bd77-d6d043d4f5e9 |  | checkpoint | Location of Wavebar install is watertight
checkpoint-status | 8332cb54-035b-4e96-9611-e0b106dce45a |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | cdfaf2ea-a0df-4f88-a123-dc4726a115db |  | checkpoint | Smooth substrate
checkpoint-status | 9f4ccb2d-1d38-4d4d-9bb9-ae6aa51c37e8 |  | checkpoint | Substrate correct gap size
checkpoint-status | f4754d91-19b8-436a-aa76-512a5931c4c1 |  | checkpoint | No services to penetrate Wavebar
checkpoint-status | f81107f2-f04f-431a-91d2-1035e9a67faa |  | checkpoint | Detail correct IE Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 22390c33-700e-46db-98eb-5bc32f250ef9 |  | checkpoint | Wavebar sealed to concrete or other substrate as per application details
checkpoint-status | 29fff787-e668-433b-8720-c6f822991706 |  | checkpoint | Pressure bar applied
checkpoint-status | 78c2ad9b-85b7-44cb-a704-06d3083b5967 |  | checkpoint | Screw bolt fixings installed at correct intervals
checkpoint-status | f9c44a37-ea7a-4dae-babd-c3aa44938537 |  | checkpoint | Joins/intersections lapped and riveted as per manufacturer’s specifications
checkpoint-status | 2cc7252f-576a-4507-a76b-d11f9145da9c |  | checkpoint | Final check to ensure a correct sound cell has been created as per detail
checklist-sectioned | 955a8f14-714d-4792-9f3c-862bca899fcf |  | checklist | SHP. Date: |  |  |  |  | Yes | QA - SHP | a3f6bdd0-3944-463f-ad0e-4f33ac6d9896
checkpoint-group | 9ca5021f-4950-4080-8690-e4db511dcdc0 |  | section | Details
checkpoint-status | 26bc26d4-8a71-49fe-bbe3-e42dbca3fbb3 |  | checkpoint | Location/Gridline details entered
text | ce71a600-a4da-5b77-a038-abac7529eef1 |  | textbox | Location/Gridline:
checkpoint-status | 8961de86-542e-479f-a9ef-603e0166f30a |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | f98007b8-2c84-49f2-8a24-38cf4c109531 |  | checkpoint | Seismic gap correct width
checkpoint-status | 7faedfce-dfd3-4530-9bd4-6d5d1aae76c2 |  | checkpoint | Smooth parallel and level substrate
checkpoint-status | 17d9de7c-162b-48d7-892f-df08de9a28b4 |  | checkpoint | FFL height confirmed
checkpoint-status | 371bb6db-b691-40da-9145-ae8075d8b955 |  | checkpoint | Install vapour barrier if required
checkpoint-status | f01d7a45-34e6-4e29-9666-47a65cb07d1a |  | checkpoint | EPDM installation well sealed with movement allowed and terminations / transitions complete
checkpoint-status | a13ba936-6e9c-408c-a9e6-61031a7e72c3 |  | checkpoint | Install Firebarrier if required - fill out checklist for associated Firebarrier
checkpoint-status | 54c0ea18-6cce-453e-9cd6-5aadd4134e02 |  | checkpoint | Sealant applied between retainer and plate edge
checkpoint-status | 636b1f98-d8a9-476e-90e2-4e6fc9c3008d |  | checkpoint | Clean finished product installed
checklist-flat | 09d4caef-3260-4eba-bd66-e3bfe4a7eeb7 |  | checklist | SF 6"+. Date: |  |  |  |  | Yes | QA - SF 6inch+ Wall Joints | a30cdfdb-9940-4fe9-b3de-57df69034c04
checkpoint-status | a2c509df-371b-4ec2-9676-c78fc1d1e604 |  | checkpoint | Location/Gridline details entered
text | a5879a62-26c2-525d-8051-af312be92bc1 |  | textbox | Location/Gridline:
checkpoint-status | e89928ef-5ef8-41c6-8b5b-7e8957ee6e95 |  | checkpoint | Materials checked
checkpoint-status | 9fbbb7dc-8a3d-42fe-a214-401ed093d168 |  | checkpoint | Smooth substrate
checkpoint-status | 7d8fff1d-aff2-49d8-946a-2205a7b0eb9a |  | checkpoint | Flashing installed (if required)
checkpoint-status | e45d490d-1344-4f4c-968f-a43f4a68db64 |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 9cdf4950-3511-4de3-b076-7221fb289de2 |  | checkpoint | Retainer fixing to substrate secure and watertight
checkpoint-status | 86fdb6c7-dfa6-4516-a03b-6f82d00a9da7 |  | checkpoint | EPDM (or secondary seal) installation well sealed with movement allowed
checkpoint-status | 2c91a335-b713-4d9a-b512-2c6027707bec |  | checkpoint | EPDM Boot at base formed correctly and tested for fall
checkpoint-status | 19ad088a-711a-40fe-bfd6-f2b0c0131780 |  | checkpoint | Turnbars installed correctly, right angle / centres
checkpoint-status | bacb57a6-b912-47ea-81c6-4d7fe26015e4 |  | checkpoint | Centre mullions securely installed
checkpoint-status | 98d30107-35f0-4ca3-b3d2-1233d0440cce |  | checkpoint | Primary gasket fitted correct pressed in fully
checklist-flat | 201a7e98-a108-4fbb-be4a-75efd9390d4c |  | checklist | ASM/ASMC. Date: |  |  |  |  | Yes | QA - ASM/ASMC | 5b6ad4f3-a292-4808-85ec-39e5b9b13699
checkpoint-status | 9488f0e5-5448-4511-973a-322a5658fd4a |  | checkpoint | Location/Gridline details entered
text | 0c43895b-93e0-5c09-881f-6e8c83f4909a |  | textbox | Location/Gridline:
checkpoint-status | 9d6d6978-cefc-4b1c-9de0-e7c1b5f3b257 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 73dd0724-f24e-4ab1-9df7-c295bff93070 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 7ce12a3f-4d51-4ae4-b812-4cfa64154e55 |  | checkpoint | Extrusion secured properly to substrate
checkpoint-status | 446b1c3a-6081-4c24-8fd3-e7a515e42abb |  | checkpoint | Centre plate affixed into retainer securely
checkpoint-status | 9f25750c-0bc8-463b-acb7-60aebf4cb737 |  | checkpoint | Clean finished product installed
checklist-flat | 8c4af0a0-890b-41bf-8e4c-3fc12067898b |  | checklist | QA - Production Checklist |  |  |  |  | Yes | QA - Production Checklist | 6d5b9c59-728c-47b7-a4f7-73ae4dc2da74
checkpoint-status | 43972aaa-8c7b-44d1-af2f-66ad28e355f1 |  | checkpoint | WIP Uploaded
text | 34dd8632-0334-5088-8037-42dd77f420ec |  | textbox | Type of Product/s:
checkpoint-status | 07563b55-9af3-47a8-ae08-1dd4cc4e191c |  | checkpoint | Materials checked
checkpoint-status | 3e5cb2ec-eca9-43f4-ac98-6fb05566184d |  | checkpoint | Before shipment photo
checkpoint-status | d0e2d0c9-67a9-4a8a-a060-7a28acb6c9be |  | checkpoint | Shipping Photo
checkpoint-status | fb06a69e-1b2d-443b-a4c8-5e9ccc61afda |  | checkpoint | Signed WIP uploaded
checklist-flat | bdb33479-37f8-4f7e-981c-a6f4bb198339 |  | checklist | RSV 5700 Louvres Date: |  |  |  |  | Yes | QA - RSV 5700 Louvres | cae3e410-7ec6-4143-84ba-07621cbf5c39
checkpoint-status | 08d92e09-ac40-409f-8a23-eaacbf030c0e |  | checkpoint | Location/Gridline details entered
text | 4f472955-6f32-5ef1-bf69-6158066b2b0e |  | textbox | Location/Gridline:
checkpoint-status | bd174175-c55b-4aa2-b704-95ba26e1461b |  | checkpoint | Materials checked and correct quantity for Opening
checkpoint-status | a3c93fcd-8ebc-43e8-be5d-828c84ea28b4 |  | checkpoint | Check level, size plumb at opening
checkpoint-status | dc7074db-c545-44d8-aaed-717f0a24967e |  | checkpoint | Use laser to find narrowest and smallest point in opening
checkpoint-status | 75f82d19-531c-4bc0-854e-d79debd65b75 |  | checkpoint | Set up the packers and install the bottom support angles with the correct fasteners
checkpoint-status | 6597df9f-8049-43cf-8fac-80d2d7b6f5aa |  | checkpoint | Flashings installed with sealant underneath and rivets in joints
checkpoint-status | 122d63e3-7f13-4810-8d6a-d01e162d4d8f |  | checkpoint | Install vertical angles with isolating washers
checkpoint-status | a2e0a133-7f6b-4706-a092-0172bf46f891 |  | checkpoint | Install top flashing and support angle with isolating washers
checkpoint-status | 4f6e11dc-43ef-4a96-b689-a772e4923dae |  | checkpoint | Install middle section flashing on top of steel plate support using sealant and folding ends accordingly
checkpoint-status | 7a7985b7-db37-47b3-bc63-e1ac21b66620 |  | checkpoint | Install Louvres using lifting system
checkpoint-status | 854def91-2bb4-407b-a5f2-c9373c692c2c |  | checkpoint | Fix Louvres to support angle at 600mm centres using appropriate fasteners
checkpoint-status | f55a1648-77a3-4bdc-b4bd-3ad4bd23f468 |  | checkpoint | Install joint flat bars using correct fasteners and spacings
checkpoint-status | 2283a570-8f30-4b44-9346-77e4ee0322e7 |  | checkpoint | Install perimeter angle for PEF rod using rivets
checkpoint-status | cb57b367-b560-4736-8c3f-e8071766d132 |  | checkpoint | Put PEF roof around perimeters
checkpoint-status | c3f40313-f74a-4140-a67a-089389096cb7 |  | checkpoint | Seal the gaps around the Louvres according to the details
checkpoint-status | 60b07513-bac8-4495-a34a-c73607a8ad1b |  | checkpoint | Clean up dust and touch up paint Louvres
checkpoint-status | 46fa25a5-3f74-4b19-addc-d2faddd1f327 |  | checkpoint | Install lip flashing once it has been sealed
checkpoint-status | 055f2b1d-b85c-45be-b236-8b2401191867 |  | checkpoint | Finished product
checklist-flat | 1d0e474a-03e9-467a-8791-2c3d567d9a20 |  | checklist | SRJ. Date: |  |  |  |  | Yes | QA - SRJ | 9ef4772b-5459-493e-9984-4fabd5eb098f
checkpoint-status | 33409ef5-46eb-4329-a76a-61cd986c3f2b |  | checkpoint | Location/Gridline details entered
text | d7701b27-80f7-57b6-87e3-542ab7ae0d42 |  | textbox | Location/Gridline:
checkpoint-status | 99a87ccf-dabd-42e2-8b65-a0002bf94c7c |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | fdff2a85-e703-4cfd-859a-9286a4b69057 |  | checkpoint | Smooth substrate
checkpoint-status | 154a3423-8348-4c63-a5ed-db879affa658 |  | checkpoint | Correct upstand angle
checkpoint-status | c87f3c8d-b2c9-4f34-9c8e-728cadbbc023 |  | checkpoint | Flashing or Torch On installed
checkpoint-status | 98aadee3-b4b2-48cc-94a7-c6ecfe460f7e |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | f3a19130-ff09-43e9-8026-f33b321ee596 |  | checkpoint | Fall to Vertical/Drain acceptable
checkpoint-status | b137d926-8499-49a4-8480-e472272ff4f9 |  | checkpoint | Drain placements correct (if required)
checkpoint-status | c17a9a8f-0a1e-452b-a1f8-4c6b74192cef |  | checkpoint | Correct Sealant used (Black Jack or Seal N Flex in conjunction with butyl tape)
checkpoint-status | 8c0bc053-dcff-49d0-beae-9857a5db6804 |  | checkpoint | EPDM installation well sealed with movement allowed and terminations / transitions complete
checkpoint-status | 0f08d23f-47be-424e-a5fb-fb73c1470e33 |  | checkpoint | Retainer fixing to substrate secure and watertight
checkpoint-status | a0d9ed0c-9c95-46c0-b05b-022e55084b8d |  | checkpoint | Fall / watertest complete and archived
checkpoint-status | 76192280-438e-47de-b4e8-a82c3b5b9258 |  | checkpoint | Roof cap installed with turn bars ready to tighten
checkpoint-status | d409f06a-7f95-42a9-9a7d-1299f0d307e4 |  | checkpoint | Turnbars installed correctly, right angle / centers
checkpoint-status | 036b79ad-3cee-42aa-8034-b1b8458cfff6 |  | checkpoint | Soakers installed with sealant underneath
checkpoint-status | 3e8db612-b509-4b49-932c-9c0537a8381f |  | checkpoint | End caps and transitions installed
checkpoint-status | 618276bc-65a7-4e76-98bc-5396e35c92f7 |  | checkpoint | Sealant applied to roof cap upstand top edge
checklist-flat | d5288fb2-888f-4b80-8b22-d4c53a4d7510 |  | checklist | QA - XLS + XLP All sizes |  |  |  |  | Yes | QA - XLS + XLP All sizes | ac67724e-2ca7-4392-b332-0fc0095b407f
checkpoint-status | 67feed72-896e-448c-a6c4-32901b754fd7 |  | checkpoint | Location/Gridline details entered
text | 10d8507e-9f65-5837-94eb-6efb80ae8b1f |  | textbox | Location/Gridline:
checkpoint-status | 555f3c35-c249-41d6-8faa-694cdb04b678 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 9c78c922-d57e-4931-8b84-cf149b370b71 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 742c4722-f857-49cf-815e-bfdd94dbeb78 |  | checkpoint | Rebates correct depth / width
checkpoint-status | e4e4cfc6-0879-4b49-9e8e-df6df12d4b5a |  | checkpoint | E.P.D.M installed and well sealed
checkpoint-status | 8e795c5f-2bb7-477b-bc13-185c30d9247a |  | checkpoint | Boot at bottom of joint formed correctly
checkpoint-status | d53bdc1b-7567-46b8-89f7-08eab19b0d10 |  | checkpoint | Hinge and plate side of joint installed plumb and securely
checkpoint-status | bc65d61e-89fa-45c0-b459-576802de6fca |  | checkpoint | Wall retainer on opposite side installed to solid substrate securely and parallel to hinge side
checkpoint-status | 279bd5cd-02c4-4f0f-9402-f6a1f1121b01 |  | checkpoint | Cardboard removed from magnet and sash weight checked to be operating correctly
checkpoint-status | bfe15124-f8f1-4982-8efa-7c26a2f37352 |  | checkpoint | Close panel carefully to magnets and re check for parallel
checkpoint-status | 4f288329-d539-45e2-8f7e-60f7915d8f20 |  | checkpoint | Clean of installed finished product
checklist-flat | ffcf431d-96d6-4f0b-aec6-d65b3bbe66d5 |  | checklist | Intubatt |  |  |  |  | Yes | QA - Intubatt | a46b20a1-0c66-4aec-9645-7fbd11463c6e
checkpoint-no-status | ae9ed720-1474-43fe-babe-1aa52ae020cf |  | checkpoint | Location/Gridline
text | 94dd1e17-bb8c-5863-9103-3aa9ba1b0e55 |  | textbox | Location/Gridline details
checkpoint-status | b72a9363-7885-405b-84ba-97d14c6238f4 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 59d06fbb-5eaa-4b17-b550-97031666d966 |  | checkpoint | Substrate checked to be smooth and flat
checkpoint-status | 337dc604-6cc7-47ab-8e62-d2219e5ad060 |  | checkpoint | Product installed with compression to gap
checkpoint-status | 8a23ef41-c74c-4348-a22c-f238d021e0e9 |  | checkpoint | All sides sealed with appropriate sealant
checkpoint-status | 6dca32f1-8675-4ffc-b6da-b5370d9592dd |  | checkpoint | Any butt joints sealed with appropriate sealant
checkpoint-status | 1437a84e-c0bc-41e6-a095-36c019054a9d |  | checkpoint | Final check and clean up completed
checklist-flat | 23019bce-7149-4ed7-832c-c6f94c99ebdb |  | checklist | PTCP. Date: |  |  |  |  | Yes | QA - PTCP | 467df665-2783-409c-914f-ebf1aee84d4f
checkpoint-status | 7374d691-8df0-47b6-bd12-bdd3656cccbb |  | checkpoint | Location/Gridline details entered
text | 3887d728-8d7c-5b3d-96b8-8e6dca6deed6 |  | textbox | Location/Gridline:
checkpoint-status | fa40fdc6-6dec-41cd-aca0-c6a66e2b6e54 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 29d1955b-9827-4726-b7b1-344fcb52db93 |  | checkpoint | Seismic gap correct width
checkpoint-status | d57ca297-58cc-47c6-a39d-98f75c294fc4 |  | checkpoint | Smooth parallel and level substrate
checkpoint-status | f59f6e7d-adce-4946-bca1-ea04fde3ce29 |  | checkpoint | Rebates correct depth / width
checkpoint-status | 5c3ad4d5-5a48-47ec-b3b1-668f3949a3bc |  | checkpoint | FFL height confirmed
checkpoint-status | ff1dbcfb-f19c-4938-bcb7-3d07da4188ed |  | checkpoint | Install vapour barrier if required
checkpoint-status | 437e39b0-8a98-4d00-a187-d8820fc8ea99 |  | checkpoint | Packer / grout installed with retainers fixed securely to floor
checkpoint-status | eb222561-487d-4cd9-aab8-57d6dfc1c714 |  | checkpoint | Install EPDM pad level and true to ensure finished plate will sit flat
checkpoint-status | 59058b24-770e-4436-b847-303670da5827 |  | checkpoint | Wall retainers installed to solid substrate securely (PTCW ONLY)
checkpoint-status | d2342962-5b7f-4e35-884c-e358f2989786 |  | checkpoint | Sealant applied between retainer and plate edge
checkpoint-status | ca499290-f075-47b9-9d4d-4c26f46fbae0 |  | checkpoint | Clean finished product installed
checklist-flat | 7021cd16-d1c8-41a2-80d5-994e0149e07f |  | checklist | QA - SSRZ 400+ Floor to floor joint |  |  |  |  | Yes | QA - SSRZ 400+ Floor to floor joint | f831e476-5042-49f8-aad6-e9a0908e12c7
checkpoint-status | 8b40ef59-e7e9-4a6d-a790-1678b1bfcc35 |  | checkpoint | Location/Gridline details entered
text | 98057dd8-e75a-5dec-a950-292c74cb6893 |  | textbox | Location/Gridline:
checkpoint-status | e2bdb4f3-9956-4beb-a991-32ed0b2f7c10 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | df24533d-3b62-44b5-8b5a-b3b720e846b0 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 1896d753-b14f-4a74-9c40-2ed66416c89b |  | checkpoint | Floor Rebates correct depth / width
checkpoint-status | 21a5b98a-012f-48f1-ae2b-78423370e38e |  | checkpoint | FFL height confirmed
checkpoint-status | bb6ce51c-1347-4dae-9fdc-fe7e72fcce5b |  | checkpoint | Packers / grout installed with retainers fix securely
checkpoint-status | 79753124-bf88-4680-b94f-a01b2ad45c01 |  | checkpoint | Turnbars installed with centre plate securely
checkpoint-status | 10335b86-da68-4676-9830-da7bd67e49c2 |  | checkpoint | Centre plate installed and checked for correct alignment with outside retainers
checkpoint-status | 96b53a12-b0b5-4a53-8c9c-6e74b8756bb4 |  | checkpoint | Sealant applied to retainer edge
checkpoint-status | 7583f8e1-816b-4c36-a730-7a364f5351ba |  | checkpoint | Clean of installed finish product
checklist-flat | db098782-2c38-47e2-ba48-7fc7e457ce30 |  | checklist | SF 2" - 6". Date: |  |  |  |  | Yes | QA - SF 2-6inch Wall Joints | a2fe4eb5-f86e-4794-93b2-89682189351c
checkpoint-status | 171ca86a-5e73-44a4-91d7-ba66654826c4 |  | checkpoint | Location/Gridline details entered
text | 89347ec5-6a3f-52b2-b994-9808381846f5 |  | textbox | Location/Gridline:
checkpoint-status | 6cc7cb47-5c1c-4dc1-9d7e-c35628c2a60e |  | checkpoint | Materials checked
checkpoint-status | aac02d7f-cc92-41d5-8b38-63d5c26f971b |  | checkpoint | Smooth substrate
checkpoint-status | 308d8018-6837-44ed-bba1-fe2455b3a362 |  | checkpoint | Flashing installed (if required)
checkpoint-status | d1c75489-bc69-4989-80c5-6c3fda354224 |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | c8d5c890-6f66-4d2a-beac-c77897eeddd9 |  | checkpoint | Retainer fixing to substrate secure and watertight
checkpoint-status | 4dfe526a-6723-4c47-9d6e-a593f1099e59 |  | checkpoint | EPDM (or secondary seal) installation well sealed with movement allowed
checkpoint-status | b0fd897e-5bc0-4832-8be7-a4e6d973bdd9 |  | checkpoint | EPDM Boot at base formed correctly and tested for fall
checkpoint-status | 2e339ca6-b6f6-4f5b-a51c-46bb04645bbb |  | checkpoint | Primary gasket fitted correct pressed in fully
checklist-flat | f3c6047d-7b1e-4ebe-9e68-d6b260a0b084 |  | checklist | PC/PCW. Date: |  |  |  |  | Yes | QA - PC/PCW | 17efd46c-1678-47c6-a864-bae2ec76a284
checkpoint-status | 72ec60a2-7d7d-4bf2-b55b-2c9bc3ac4cf7 |  | checkpoint | Location/Gridline details entered
text | ee36532d-1ebc-510b-88bf-84a41787b7ae |  | textbox | Location/Gridline:
checkpoint-status | f50509e4-99fc-43b5-b30f-cee965b10d39 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 87404c00-d356-46ca-854b-6db96db0ac77 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 139bf426-0e2b-44a3-9ad6-af906794fe63 |  | checkpoint | Ensure slabs are level either side of seismic gap (PC Only)
checkpoint-status | 94b50e17-c444-4e47-9e7c-57de4c9f750d |  | checkpoint | Check if plate is to be fixed over top of floor coverings or directly to slab
checkpoint-status | 34c837df-effc-4ec3-a32c-f829d386bea5 |  | checkpoint | Plate secured properly to substrate
checkpoint-status | 2d987caa-cbe3-4245-a453-2664326af2dc |  | checkpoint | Clean finished product
checklist-flat | 1dc6ee6c-5bcb-46cf-93bf-1c12b291dc1a |  | checklist | Pedigrid Entrance mats |  |  |  |  | Yes | QA - Pedigrid Entrance mats | bc1bfd00-c171-4f06-88b4-e7c9b7eee2c1
checkpoint-status | 2534d3f1-3a7f-4fa0-a14d-e4e5b8ca5881 |  | checkpoint | Location/Gridline details entered
text | a15e6ee8-b60f-5be9-91df-5771872ac830 |  | textbox | Location/Gridline:
checkpoint-status | b618e0e7-f094-4f01-9982-0abb2f2cfca8 |  | checkpoint | Matwell Prep in good condition and correct size
checkpoint-status | b63bfdc3-d95e-4801-9496-55aa5b508561 |  | checkpoint | Materials Checked and correct for install
checkpoint-status | d75f2464-0bcd-4b52-9737-ce42fed8916f |  | checkpoint | Mat perimeter frame installed (if required)
checkpoint-status | 6602337f-3026-4113-9b80-01eba68a29d8 |  | checkpoint | Mat installed and secure in place take note of cut outs.
checkpoint-status | 53765295-e4f4-4ee0-bcd6-25a634afd567 |  | checkpoint | Final check to ensure mat is clean installed evenly and perimeter gap / frame are sound
checklist-flat | 5de5beb0-48b5-4989-8b7f-aded53ff7036 |  | checklist | ZB/HB. Date: |  |  |  |  | Yes | QA - ZB/HB | 463b2c9e-0333-42a0-92cb-58155f6f123e
checkpoint-status | 5c651eda-22a2-4bb0-b092-12194eb2b85c |  | checkpoint | Location/Gridline
text | 50dfe1f8-c035-5972-90cd-eff9b3b057bc |  | textbox | Location/Gridline details
checkpoint-status | ad1324c3-826f-4546-a9d8-bd24f87a8c09 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 76b1b92b-2531-463e-ad44-add46751339d |  | checkpoint | Substrate checked to be smooth and flat
checkpoint-status | 88140a2f-0968-45da-8acc-14d50193cf4d |  | checkpoint | check blockouts in slab are the correct width/depth
checkpoint-status | 6d5b8b4e-f033-4671-a974-8183e1b27e62 |  | checkpoint | Correct width / depth of product supplied
checkpoint-status | 98990639-bd83-4fb0-8e8b-5ba70b8c195b |  | checkpoint | Detail correct i.e Gap size, Parallel and straight, surrounding products / substrates as per details
checkpoint-status | e1a2dee8-af24-4ffc-8899-269bb077bbe1 |  | checkpoint | Masking / temporary cover required and setup
checkpoint-status | ee5e6741-8d75-46eb-869e-11945dfea023 |  | checkpoint | Epoxy applied to substraight
checkpoint-status | 68a969ea-a53c-4084-a635-f5f7d787e106 |  | checkpoint | ZH/HB fittted into place at the correct depth
checkpoint-status | a2dfdd26-29fa-42ab-aa6a-d9adf337aa5e |  | checkpoint | Epoxy butt joins accordingly
checkpoint-status | 5a72c6a2-4db3-4573-8420-82edde9d9d3f |  | checkpoint | Continue until all lengths are completed
checkpoint-status | c8390d5e-ed5f-48fc-a722-1b22e2392a99 |  | checkpoint | Final clean up, removal of masking tape / temporary covers and inspection of joint and surrounding areas
checklist-flat | ffbc919c-893f-49cb-807d-ea57ca4087c1 |  | checklist | QA - XLSC |  |  |  |  | Yes | QA - XLSC | 48933a23-a4ad-4109-a40d-70a61feb9e4e
checkpoint-status | 14f06171-7fe7-4ce6-a670-09e1ec08b84e |  | checkpoint | Location/Gridline details entered
text | c8888044-d445-5b1a-97cb-0c72999298a2 |  | textbox | Location/Gridline:
checkpoint-status | 1e8c0c1a-4ea4-4ac8-84c0-92ce62d0ee97 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 2cfd0c07-50c8-4834-8703-be16f5b92bc8 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 070c3b78-95ec-44e0-9d9b-509396b537b5 |  | checkpoint | Rebates correct depth / width
checkpoint-status | 8b955812-11fa-40a2-9768-4d907c755393 |  | checkpoint | E.P.D.M installed and well sealed
checkpoint-status | d4c44f53-fc70-4cbf-af97-964cc44bf2e4 |  | checkpoint | Boot at bottom of joint formed correctly
checkpoint-status | 67927a85-0648-48b1-af13-a0835dc56118 |  | checkpoint | Hinge and plate side of joint installed plumb and securely
checkpoint-status | 6cf89a00-2b97-4ca1-b9c1-f128d300e98b |  | checkpoint | Wall retainer on opposite side installed to solid substrate securely and parallel to hinge side
checkpoint-status | f13c6c6a-627c-45b5-85f8-3ff565c74805 |  | checkpoint | Cardboard removed from magnet and sash weight checked to be operating correctly
checkpoint-status | 0950d769-4da2-4959-8bae-6fd524fe782f |  | checkpoint | Close panel carefully to magnets and re check for parallel
checkpoint-status | 74683969-def0-4db8-9b97-fa7b1e969dda |  | checkpoint | Clean of installed finished product
checklist-flat | 56a370c4-dc5c-489b-b9a8-676b34cb2445 |  | checklist | SGR. Date: |  |  |  |  | Yes | QA - SGR | 994d52ef-c1b7-495b-85d1-308807bbddfb
checkpoint-status | 9fc469e1-bc7b-4bcb-b820-cd1640a11a9d |  | checkpoint | Location/Gridline details entered
text | abc791d9-1f80-5b07-a4bc-bda53a1ba1ad |  | textbox | Location/Gridline:
checkpoint-status | 861b1c80-e1e8-4d30-9b71-9764b352ee0c |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 319a86ac-fa8b-4875-bb34-c7c27f42b1e2 |  | checkpoint | Smooth parallel substrate
checkpoint-status | d17434e7-7d8f-49f5-bcc4-ede417f4800a |  | checkpoint | Rebates correct depth / width
checkpoint-status | d989750e-dffb-4618-9062-7a204be85bff |  | checkpoint | FFL height confirmed
checkpoint-status | 2570a1e8-840b-4b54-94bb-b188c60e007f |  | checkpoint | Packer / grout installed with retainers fix securely
checkpoint-status | d2f406db-6293-4b7e-8aa7-08cbdd402bea |  | checkpoint | Turnbars installed with centre plate securely (If required)
checkpoint-status | ad27df91-d182-4d14-af58-752d04b1d76f |  | checkpoint | Gaskets installed
checkpoint-status | a0c908a8-e407-43ef-9c57-01a4af58c791 |  | checkpoint | Clean finished product installed
checklist-flat | 9ccacc2b-c19e-45cc-a334-54ff5712aa88 |  | checklist | Acrovyn. Date: |  |  |  |  | Yes | QA - Acrovyn Wall Protection | 65214e6c-450d-4193-b2e6-7da86992ffc3
checkpoint-status | 42869fb3-ec03-44fb-a0be-3325fef48f35 |  | checkpoint | Location/Gridline details entered
text | 447aee0e-8862-5cfa-88d1-54daeaa23b78 |  | textbox | Location/Gridline:
checkpoint-status | c63f0c55-8fda-48a2-982f-cce2b3e308dd |  | checkpoint | Materials checked
checkpoint-status | 916cb04f-714a-455c-8c89-186d41cfd8c2 |  | checkpoint | Clean and straight smooth substrate
checkpoint-status | 39a887bf-22e4-450d-9bf9-f59939fdc7e1 |  | checkpoint | Floor / skirting level correct minimal variance
checkpoint-status | 5cf62ac3-941a-449f-9949-fdf1cfa1037a |  | checkpoint | Wall sheet height correct and confirmed
checkpoint-status | f59d0187-2424-4911-8711-3ec8eebc3288 |  | checkpoint | Adhesive applied
checkpoint-status | e898bd46-79f9-4dd7-a6b3-b05047577722 |  | checkpoint | Sheets rolled
checkpoint-status | aa7dcde4-7f39-4c40-bbed-8ef76430299c |  | checkpoint | Sheets cleaned
checkpoint-status | a12841a4-7dd6-45f1-ae10-fe8584ef9b90 |  | checkpoint | Silicone applied
checkpoint-status | 7819f5fd-20d1-4174-b586-dababd38920c |  | checkpoint | Final Photos
checklist-flat | 6a3ac43f-a7ab-4e85-9390-41d27d7b471a |  | checklist | GTR. Date: |  |  |  |  | Yes | QA - GTR | 4bbab6a6-8d17-46ae-a988-1f1a46f574ea
checkpoint-status | ea98f8fa-7518-45f2-a2d5-4388c791c6d0 |  | checkpoint | Location/Gridline details entered
text | f10add4f-2f8b-54b1-b0be-89d1ac306ee7 |  | textbox | Location/Gridline:
checkpoint-status | 33cc552f-5f62-4617-b67e-01406d4b6cb6 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 24889b67-5cd1-4f07-be4b-53b3a79176a7 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 17f91a10-7002-4676-8f77-f00ff78ab061 |  | checkpoint | Rebates correct depth / width
checkpoint-status | b1c2b464-9224-42a0-9a66-be70e154562f |  | checkpoint | FFL height confirmed
checkpoint-status | e1d16fa4-5e72-47d0-afe0-b4e131a842c7 |  | checkpoint | Packer / grout installed with retainers fixed securely
checkpoint-status | d9538956-6653-4c69-856c-4546be9c0e37 |  | checkpoint | Turnbars installed with centre plate securely (If required)
checkpoint-status | a444aabc-2b7f-4443-9269-7665b35b80e6 |  | checkpoint | Gaskets installed
checkpoint-status | 4fed1599-3e52-4ba4-a157-df8dceec685f |  | checkpoint | Clean finished product installed
checklist-flat | 1e1c3182-373c-411d-86be-ee03de81eeb4 |  | checklist | QA - L.A.S / L.A.S.C 4" + Wall Joints |  |  |  |  | Yes | QA - L.A.S / L.A.S.C 4" + Wall Joints | 539190f2-ed2d-4b31-ac2a-e8f32bafba22
checkpoint-status | d9dc28dc-da04-4003-8981-962142d24f83 |  | checkpoint | Location/Gridline details entered
text | 07eb41aa-e07a-59c6-b243-5a170366d89c |  | textbox | Location/Gridline:
checkpoint-status | 374b9d3c-b180-4e9a-89f5-32a0a8b02f60 |  | checkpoint | Materials checked
checkpoint-status | ad9c04c0-7a2b-4219-80be-b6fb7a9eff47 |  | checkpoint | Smooth substrate
checkpoint-status | 448b2cc9-fbad-4a2d-ae7f-e27b33752168 |  | checkpoint | Walls finish stopped and painted
checkpoint-status | 8ac60f73-0090-4258-a266-7f31c2425255 |  | checkpoint | Detail correct â€“ IE Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 0cd3f570-176e-4c02-bc3e-a31245a5433f |  | checkpoint | Sufficient continuous fixing has been provided
checkpoint-status | b9919f26-d402-4aae-b5dd-00de321fb4bb |  | checkpoint | Retainers cut to length and fixed off accordingly
checkpoint-status | 988a6ee9-a019-446b-9948-4d8570555832 |  | checkpoint | Shock cord installed
checkpoint-status | 155b5881-0f92-4fa0-b2fe-37e3d6c27311 |  | checkpoint | Plates cut to length and S hooks installed on the back
checkpoint-status | 8db52900-2e43-4281-884e-45cff3c0dc63 |  | checkpoint | Velcro pads line up on retainers and back of plates
checkpoint-status | a72c76f6-061b-4671-bc54-0f3c339258db |  | checkpoint | S hooks on back of pate connected to bungee and plates pressed back firmly
checkpoint-status | 6923cd4f-daa9-46ac-bf39-035a8b19cc34 |  | checkpoint | Clean of installed finished product
checklist-flat | eb868630-c9d2-449e-8694-383adefc9b9c |  | checklist | SSRZ. Date: |  |  |  |  | Yes | QA - SSRZ | a110492f-a8b8-4200-af8d-b66ddd3e5668
checkpoint-status | 19a3310a-ec53-4fde-a44c-afc72f9160f8 |  | checkpoint | Location/Gridline details entered
text | 747d74e0-cf1c-57bf-82b2-28b91f4853a7 |  | textbox | Location/Gridline:
checkpoint-status | 5ea0c47a-a1fd-4a10-ba58-2c2627cf37af |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 50c48f95-cbaa-40c3-a543-a4baaeec568e |  | checkpoint | Smooth parallel substrate
checkpoint-status | 4d9cccde-0ac4-4cbe-b9bd-0afaf198f0b2 |  | checkpoint | Rebates correct depth / width
checkpoint-status | 7a3a9429-d29e-4d31-992e-0d9efdd51b27 |  | checkpoint | FFL height confirmed
checkpoint-status | e6c055a6-b147-4b9f-acef-1b11bec584ab |  | checkpoint | Packer / grout installed with retainers fix securely
checkpoint-status | 2fa2421e-4178-4b47-b019-bd5becc642df |  | checkpoint | Turnbars installed with centre plate securely
checkpoint-status | dfbe647e-7637-43a1-9134-207a9c91532f |  | checkpoint | Sealant applied to retainer edge
checkpoint-status | 14b4b0b7-6d0d-4552-bad4-482aa93858b9 |  | checkpoint | Clean finished product installed
checklist-flat | 7822d54e-cc67-4401-968b-fcafd6278cc0 |  | checklist | SRJV. Date: |  |  |  |  | Yes | QA - SRJV | 724cd1a9-0425-4388-871c-6e1f7f58b6d1
checkpoint-status | 6a13c07f-e57b-4808-bda1-625386fbeabe |  | checkpoint | Location/Gridline details entered
text | b330dca4-04c2-526a-ad4b-7d3a6e95f78a |  | textbox | Location/Gridline:
checkpoint-status | 3babe5f9-5ac4-40c5-b06f-b6ce84d80a05 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | e935c1d6-e81d-4050-9c7a-47a9cdf123e0 |  | checkpoint | Smooth substrate
checkpoint-status | d154985c-8ba0-4ded-a52b-fdd436dbdcfb |  | checkpoint | Correct upstand angle
checkpoint-status | fd14c0c0-4dbb-4286-84ae-477c9020eb66 |  | checkpoint | Flashing or Torch On installed
checkpoint-status | 5e639f34-5b24-4214-9e28-45eaca1a3aec |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | cc1eea6c-d31f-48be-add2-3f47de6c4416 |  | checkpoint | Fall to Vertical/Drain acceptable
checkpoint-status | ddcd7020-5385-4fdd-a461-7d5787b9cfec |  | checkpoint | Drain placements correct (if required)
checkpoint-status | 60fc77d6-9e2d-49c8-b68f-f7ff128f30b9 |  | checkpoint | Correct Sealant used (Black Jack or Seal N Flex in conjunction with butyl tape)
checkpoint-status | 1dbb2595-ae68-44d4-8178-045de547ca4c |  | checkpoint | EPDM installation well sealed with movement allowed and terminations / transitions complete
checkpoint-status | cafe2e99-a0a6-4f32-aebf-463920629208 |  | checkpoint | Retainer fixing to substrate secure and watertight
checkpoint-status | 549f76ae-7528-4b45-8f91-9d5ead1f432a |  | checkpoint | Fall / water test complete and archived
checkpoint-status | 9aa7515b-36de-4d68-a5f9-4ab88a593949 |  | checkpoint | Roof cap installed with turn bars ready to tighten
checkpoint-status | abfe67fe-d39d-40d3-b8e7-44e36fa77201 |  | checkpoint | Turnbars installed correctly, right angle / centres
checkpoint-status | 24baea99-5a44-45cf-a041-1fb2da2827a9 |  | checkpoint | Soakers installed with sealant underneath
checkpoint-status | 2513e17b-8a7a-43fa-bed6-15803e4d2570 |  | checkpoint | End caps and transitions installed
checkpoint-status | 31843409-bcd9-438b-85b2-2a0280586628 |  | checkpoint | Sealant applied to roof cap upstand top edge
checklist-flat | edb2a550-4f01-4fda-b3ba-ed99a62d8f8f |  | checklist | Firefly wall + ceilings / All gap sizes |  |  |  |  | Yes | QA - Firefly wall + ceilings / All gap sizes | dcb04f4c-69ed-4f46-8dc9-ffab9939f0f7
checkpoint-status | 5a36e053-c96f-421f-a529-048382b81859 |  | checkpoint | Location/Gridline details entered
text | dc176d5c-8b8c-5832-89e7-579156afd444 |  | textbox | Location/Gridline:
checkpoint-status | ca5d4605-7bbe-411b-b12f-b2f4f28e124d |  | checkpoint | Location of Firefly install is watertight
checkpoint-status | 1a3b3e35-219b-4736-974f-5b1c78de3c70 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 2075ec0a-9153-41e7-8f6c-13453b117840 |  | checkpoint | Smooth substrate
checkpoint-status | 5fb48466-6e45-4093-aed4-80926d9bf2a7 |  | checkpoint | Substrate appropriately fire rated
checkpoint-status | d4b6d14c-4a91-4ad1-a895-a7c684ee6bca |  | checkpoint | No services to penetrate Firefly
checkpoint-status | d1814917-4a7e-45c9-9ccf-3b5bdebd066b |  | checkpoint | Detail correct â€“ IE Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 0ae720c4-f12a-42e8-bb20-b7e8979c37f8 |  | checkpoint | 100mm flap to be protruding beyond the steel pressure bar
checkpoint-status | 44f2d87b-be63-435c-80b2-fa921b5e43b5 |  | checkpoint | Screw bolt fixings installed at correct intervals
checkpoint-status | a060bd64-12fd-4f92-b65d-c7003739bc65 |  | checkpoint | Joins/intersections lapped and stapled as per manufacturers specifications
checkpoint-status | adbd114d-ad58-4196-806d-539e66ce59d6 |  | checkpoint | Final check to ensure a compliant fire cell has been created
checklist-flat | f7a602ec-718b-4e4a-9055-10a96690931f |  | checklist | RFDW. Date: |  |  |  |  | Yes | QA - RFDW | 009c8bcb-02ed-4ef3-9f5f-aee7f4695960
checkpoint-status | 4b566f61-79e2-4c70-b85b-5fe34d80fd9e |  | checkpoint | Location/Gridline details entered
text | 8a85da63-aed9-58e4-be93-e8497b98b39b |  | textbox | Location/Gridline:
checkpoint-status | 64feb603-949e-4944-a29e-8f0ef81d4e44 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | fa4c59ed-3c78-4e1f-8797-4692d174b2fe |  | checkpoint | Smooth parallel and level substrate
checkpoint-status | 42f79cde-e22a-4b79-8eb0-0ad43ecb49aa |  | checkpoint | Confirm FFL
checkpoint-status | 627c9f10-56f0-4da1-a212-3b4b38af6841 |  | checkpoint | Extrusion secured properly to substrate
checkpoint-status | b6312aae-46c4-47ae-9fae-18f5244db671 |  | checkpoint | Clean finished product
checklist-flat | 82ba2639-f924-41c1-a73f-ea436565b45f |  | checklist | QA - CSX Expandiseal |  |  |  |  | Yes | QA - CSX Expandiseal | 4ec62e4e-68c8-40d2-8453-d2ed5f023976
checkpoint-no-status | 4c7e1dcd-a490-469c-8524-40103add0948 |  | checkpoint | Location/Gridline
text | 77ff907a-ab2b-5d66-b663-1972147f9cb6 |  | textbox | Location/Gridline details
checkpoint-status | 9e60e9d3-4c27-4934-9ee1-9c32c5b485ce |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | c6ef8702-7e15-4f21-a450-81ae98242cf0 |  | checkpoint | Substrate checked to be smooth and flat
checkpoint-status | 86ae73bb-5f6d-4d76-a8a7-7542b7bcb035 |  | checkpoint | check blockouts in wall are the correct width/depth
checkpoint-status | a61ef142-bf84-4e2d-8e58-01d318926864 |  | checkpoint | Correct width / depth of product supplied
checkpoint-status | 44fc5053-2f5a-4455-b38d-249637802663 |  | checkpoint | Detail correct i.e Gap size, Parallel and straight, surrounding products / substrates as per details
checkpoint-status | 43a3f171-926c-4612-827c-2a46e50caca2 |  | checkpoint | Masking / temporary cover required and setup
checkpoint-status | 3c6a1a20-cf96-4466-bbfb-a38c8f9c96b2 |  | checkpoint | Epoxy applied to substraight
checkpoint-status | c35820b8-7589-4204-b9e2-5adff17fd69b |  | checkpoint | CSX fit into place at the correct depth
checkpoint-status | c2026960-fd29-47d6-bf55-70330a067f7f |  | checkpoint | Epoxy butt joins accordingly
checkpoint-status | 7885fd79-50f8-4fad-939d-ff81e0175d86 |  | checkpoint | Continue until all lengths are completed
checkpoint-status | 56da4f8e-0169-4dc6-b875-d3def81b1781 |  | checkpoint | Final clean up, removal of masking tape / temporary covers and inspection of joint and surrounding areas
checklist-flat | 44f9a1b8-0f2f-4323-979f-89fd522700a2 |  | checklist | QA - SSRZW 400+ Floor to wall joint |  |  |  |  | Yes | QA - SSRZW 400+ Floor to wall joint | a0e40a25-0fe0-4da0-b2d5-1a81c797a26e
checkpoint-status | d324db66-d08e-4cff-91cd-e1a28af75c22 |  | checkpoint | Location/Gridline details entered
text | e5db09e3-0a1b-5090-8a3d-99bbcdd2ea98 |  | textbox | Location/Gridline:
checkpoint-status | 072d61c3-55d2-4aa2-a498-0976cada9136 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 8e60c3df-9952-40a6-8ebc-5318f101cad2 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 0f839a5a-1e37-4829-9dcb-7e4a7a55f40c |  | checkpoint | Floor Rebates correct depth / width
checkpoint-status | 86202000-c900-4e7e-93d4-188d55703471 |  | checkpoint | Solid Substraight on hinge side to fix too
checkpoint-status | 22d2b53d-72c3-4df8-9065-5778f55d210f |  | checkpoint | FFL height confirmed
checkpoint-status | d7faf3dc-ca7c-493e-a815-2e132f0260a1 |  | checkpoint | Packers / grout installed with retainers fixed securely
checkpoint-status | b26ca1d4-7609-4fa5-a341-9d7a8dd8640e |  | checkpoint | Hinge set to height and fixed off securely
checkpoint-status | 572c165a-5c9b-40c6-acf8-7b9f045cf33c |  | checkpoint | Centre plate installed and checked for correct alignment with outside retainer
checkpoint-status | 8c8e9e6d-22ce-4b91-8060-7c1a5dc03971 |  | checkpoint | Sealant applied to retainer edge
checkpoint-status | 79fcf4af-1981-49e1-af5d-41f340087f73 |  | checkpoint | Clean of installed product
checklist-flat | ecb8f843-47d7-4980-bedf-4a4922bd18ca |  | checklist | Intuspan |  |  |  |  | Yes | QA - Intuspan | 57fd7d27-7823-47d4-9f4c-76d3cb5a21ca
checkpoint-no-status | c2b473c0-fc8e-4101-a0da-e53fc0194d5b |  | checkpoint | Location/Gridline
text | 8f18e386-34a1-5959-8084-47ed69f937a7 |  | textbox | Location/Gridline details
checkpoint-status | 06083321-095a-4f65-bfb0-ad4001b0c52c |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 2e8819e0-f817-45cb-9140-3d9277e3c3d8 |  | checkpoint | Substrate checked to be smooth and flat
checkpoint-status | d8b60518-99ec-455a-81f9-043f3834f9c3 |  | checkpoint | Product installed with compression to gap
checkpoint-status | 91de92fa-fa0d-49b9-8a39-e90ebddbda2d |  | checkpoint | All sides sealed with appropriate sealant
checkpoint-status | b0b1da62-8124-4329-96e6-396d827750b2 |  | checkpoint | Any butt joints sealed with appropriate sealant
checkpoint-status | 731a9870-9c88-4b3f-9182-f5531cea8d13 |  | checkpoint | Final check and clean up completed
checklist-flat | fc5064ba-0d18-4d6e-8e9d-4e6f6de8630e |  | checklist | FWF-400. Date: |  |  |  |  | Yes | QA - FWF-400 | 65d66ef7-048e-4836-9594-8addef314b74
checkpoint-status | 62565dd9-2b8b-43b9-8626-b76221074394 |  | checkpoint | Location/Gridline details entered
text | 49497f22-98cf-509e-b1c0-a84ae65ef959 |  | textbox | Location/Gridline:
checkpoint-status | 5f96beb0-dfe9-40a6-94cd-d8919f385d54 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 14bfc0cd-f983-4aea-82f7-e455c8620a32 |  | checkpoint | Smooth parallel substrate
checkpoint-status | ebde2743-9393-46e5-ae5a-2c0915af513f |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | d007ff44-c7af-455f-8faf-ef2829705ce9 |  | checkpoint | Solid substrate behind plasterboard to fix into
checkpoint-status | 0b48d45b-722e-43c8-87e3-2f6cfec2f60c |  | checkpoint | Retainers fixed securely
checkpoint-status | 94a3374b-3907-4178-89be-50f96d47fd81 |  | checkpoint | Gasket installed and is flush - no lumps or un evenness
checkpoint-status | 1e7a284d-8184-4a60-bc60-2733f8d6c1ff |  | checkpoint | Clean of installed finished product
checklist-flat | 11ea843f-3f66-4aeb-8897-473887c41e50 |  | checklist | AFW. Date: |  |  |  |  | Yes | QA - AFW | f60bd43f-d66a-4fe8-9a7e-e0c6a93fd68c
checkpoint-status | 473308d0-b7d3-4c71-b80d-94991620286d |  | checkpoint | Location/Gridline details entered
text | 8383e6fb-eedd-58e9-8c18-218d2e8fe5bb |  | textbox | Location/Gridline:
checkpoint-status | 9e5882c7-e89e-4e3f-8ec4-4eb8d6ad98ff |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 924edca5-b0d2-4a03-bbfe-d0521df76fc6 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 11d89947-56bd-4419-ad2b-b49065c1ef69 |  | checkpoint | Retainers installed and secured properly to substrate
checkpoint-status | fde2fce8-b7fa-4930-9f14-7c196fed218d |  | checkpoint | Centre plate affixed into retainer securely
checkpoint-status | b83b088d-8c83-45d4-bdbb-4578826e5c00 |  | checkpoint | Top retainer clipped into place securely
checkpoint-status | c50ff1fc-bf7b-478a-affc-d7bee506361e |  | checkpoint | Clean finished product installed
checklist-flat | f680d599-f552-423f-b098-9fb20b97dd6d |  | checklist | QA - Insulation wall + ceiling |  |  |  |  | Yes | QA - Insulation wall + ceiling | 3c51c78d-471a-419b-98c2-d68d4d85bb0d
checkpoint-status | 3a851f23-967d-4405-8b36-326d692891fb |  | checkpoint | Location/Gridline details entered
text | 434569c2-358a-5ab6-80b8-b3e8133871e1 |  | textbox | Location/Gridline:
checkpoint-status | 45fe88e7-e84b-47f9-805c-cf7178c46fd0 |  | checkpoint | Location where insulation is to be installed is watertight
checkpoint-status | 667ec0bd-4db9-4436-a19b-9f2fc947f5ee |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 877fbb8d-19df-4a1f-9438-b3c28a07fad8 |  | checkpoint | Smooth substrate
checkpoint-status | ebf05819-f67b-4cc0-b0ba-3d2e3ca73437 |  | checkpoint | Insulation is the correct R value
checkpoint-status | a1f917d7-d4cf-4616-b814-52375696fc3d |  | checkpoint | Sufficient fixing proved
checkpoint-status | 927c5a59-f65f-4d22-bfe3-511ba5b1ea98 |  | checkpoint | Insulation firmly fixed and support straps installed if required
checklist-flat | 25fdfb8b-ba1d-4db8-b4a7-23506fcdb554 |  | checklist | LVR Louvres (Penthouse). Date: |  |  |  |  | Yes | QA - LVR Louvres (Penthouse) | e61da80e-b389-4d99-9e51-b9934f600374
checkpoint-status | 063c2476-1834-48af-8c89-b80b8d5120db |  | checkpoint | Location/Gridline details entered
text | 5fb2581f-06b5-5e84-bbc3-b1a2441cf169 |  | textbox | Location/Gridline:
checkpoint-status | 0c5272fa-4cb1-485d-a761-4d92c685e03b |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | ac645fcf-1d44-424e-b846-6c2ea8abfa12 |  | checkpoint | Check concrete nib substrate squarness, level, size
checkpoint-status | 2a57a223-107f-4cd3-a0dc-a00c49bb30ca |  | checkpoint | Use laser to find highest point on the substrate
checkpoint-status | 774048b6-9593-47eb-9eb8-92aba56dbf17 |  | checkpoint | Set up height and install corner angle posts
checkpoint-status | bb64ad4e-0813-4d23-9493-12a98af32e14 |  | checkpoint | Check plumb on posts before bolting them
checkpoint-status | 6fef8ca6-ecf9-4caf-a728-76a3cccab6ec |  | checkpoint | Bolting posts/washers
checkpoint-status | 0c618adb-4566-46ec-b151-862966b561d1 |  | checkpoint | Louvres installation with correct fasteners to posts with correct spacing
checkpoint-status | 785ac3c5-7a5e-4912-9134-b19c9ec17ea8 |  | checkpoint | Install bird mesh with correct fasteners and washers
checkpoint-status | 76dbfa3f-dd22-4dbc-8582-148cd031d742 |  | checkpoint | Check squareness on Louvres before fixing roof cap on
checkpoint-status | 161b0308-7997-4448-b4d2-0973eff3ec0e |  | checkpoint | Roof cap assambly/installation including soakers and sealant
checkpoint-status | bd54c225-bba4-4b76-85bf-d3a4e83dd942 |  | checkpoint | Corner flashing install with rivets and sealant
checklist-flat | ef72b0b1-d6f3-4ee0-a312-f80335627994 |  | checklist | QA - L.A.F / L.A.F.C 4"+ Wall Joints |  |  |  |  | Yes | QA - L.A.F / L.A.F.C 4"+ Wall Joints | 1b714494-cf16-4750-8dbb-e2866f6eed68
checkpoint-status | 654fdb5d-c634-4c9e-95e7-ccac7839f703 |  | checkpoint | Location/Gridline details entered
text | b91a9d11-c997-5ff0-bd49-6719722f29e2 |  | textbox | Location/Gridline:
checkpoint-status | 8a9e56ba-756e-4b94-aa6e-5b5a070c07e8 |  | checkpoint | Materials checked
checkpoint-status | f5350afb-5c7d-481e-b10f-24a5d564059b |  | checkpoint | Smooth substrate
checkpoint-status | ba1706f6-df95-4277-b989-ad8cb13aa8a7 |  | checkpoint | Rebate in gib correct width and depth
checkpoint-status | 63d9945b-c972-47ab-9091-b8aa5d748424 |  | checkpoint | Detail correct â€“ IE Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 2417fd28-fddd-441f-907f-f14425b85a3f |  | checkpoint | Sufficient continuous fixing has been provided
checkpoint-status | 9a7820b2-1b6e-497d-85e6-d1ced70c180f |  | checkpoint | Retainers cut to length and fixed off accordingly
checkpoint-status | 7400df54-69b7-4584-91c7-f370e6ac452a |  | checkpoint | Shock cord installed
checkpoint-status | 79978b75-7b23-48db-8229-9dece1b0e6ff |  | checkpoint | Plates cut to length and S hooks installed on the back
checkpoint-status | 83f3ddb0-1081-4e8b-b6f2-ea6a2132bd21 |  | checkpoint | Velcro pads line up on retainers and back of plates
checkpoint-status | 6749296f-6636-4137-b7f1-97fbad7f9cbd |  | checkpoint | S hooks on back of plate connected to bungee and plates pressed back firmly
checkpoint-status | 989bf94d-d600-4e7f-b1ac-5d278b9d95b2 |  | checkpoint | Clean of installed finished product
checklist-flat | e779471f-3fd7-4d8b-ad4b-b91a599b1bbb |  | checklist | GTWC 200/300. Date: |  |  |  |  | Yes | QA - GTWC 200/300 | 35840e2a-ddb1-4b23-8f89-8bc94c3a2458
checkpoint-status | f2bfd4d8-8909-49ef-ae03-63b17797fe8a |  | checkpoint | Location/Gridline details entered
text | 40795963-f817-57b9-bbc3-2d39e0ab7198 |  | textbox | Location/Gridline:
checkpoint-status | 7f0cd130-63f1-44a1-8211-53fdd1516aa4 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 8b25871c-484f-49bd-ae06-4bb607bed710 |  | checkpoint | Smooth parallel substrate
checkpoint-status | ab379279-cda6-4e3a-958d-6de5569ef545 |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | 1954310c-9eee-4f19-b6e0-30265dc90129 |  | checkpoint | Plasterboard cut back to correct Setout
checkpoint-status | d980265e-f6fb-4b59-8053-db4ea66b04a3 |  | checkpoint | Solid substrate to fix into
checkpoint-status | b5748a88-8f61-4707-bae1-5e7949076cc5 |  | checkpoint | Retainers fixed securely
checkpoint-status | d1906ac5-0d64-4907-9d96-5ac3b068264b |  | checkpoint | Centre plate fixed securely
checkpoint-status | 1ddfe1c6-af07-42dc-9ac5-ded451b3db1a |  | checkpoint | Infill plate D/S in place evenly
checkpoint-status | 1e2d568c-ce48-44c5-9878-d30412bc7730 |  | checkpoint | Gasket installed and is flush - no lumps or un evenness
checkpoint-status | 3f3ff7ba-4ee0-4cc5-a8f6-a908ed4e63fc |  | checkpoint | Clean of installed finished product
checklist-flat | 6e6229e8-d2f2-453c-b2e7-4dd3f1ad422d |  | checklist | FCF+FWF-100/200. Date: |  |  |  |  | Yes | QA - FCF+FWF-100/200 | ef1da245-4734-45d0-a7ab-ea98337c8f30
checkpoint-status | 9c7f238c-4c35-461f-9e44-84fc401fe69f |  | checkpoint | Location/Gridline details entered
text | 40dfa8d8-e22f-57b3-b8f3-a551b2571887 |  | textbox | Location/Gridline:
checkpoint-status | 6cdb9d26-c427-4851-adef-3ab23ad89ec4 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 5ef86bb4-3311-4bcf-baa2-bf45159160e1 |  | checkpoint | Smooth parallel substrate
checkpoint-status | eca7266b-07d1-463c-b7b5-106c6c1b439c |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | 8c165c50-0e31-407d-9d76-5edb61b05975 |  | checkpoint | Solid substrate behind plasterboard to fix into
checkpoint-status | 3d18035d-cfb4-480b-be08-f3e9c647ff6a |  | checkpoint | Retainers fixed securely
checkpoint-status | ca50eb80-45e0-425e-a588-9aebf24e7d63 |  | checkpoint | Gasket installed and is flush - no lumps or un evenness
checkpoint-status | 52853f4e-ae7c-4fc7-baad-19d00d433ad5 |  | checkpoint | Clean of installed finished product
checklist-flat | e281b2d0-ce61-466e-b5c1-527d4ef366ef |  | checklist | VF. Date: |  |  |  |  | Yes | QA - VF | 0aa617c6-93dc-4d3e-8f70-533bfe278f45
checkpoint-status | cf169fa0-578e-45eb-bbb8-13aa26ccb1e1 |  | checkpoint | Location/Gridline details entered
text | 61a7ebc6-2931-5338-bbef-97bbf9f80d80 |  | textbox | Location/Gridline:
checkpoint-status | 2effb7a4-21ee-4289-b9ae-781e7f773a25 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | cd92e4e9-b831-494e-864f-b1f18078fabe |  | checkpoint | Smooth parallel substrate
checkpoint-status | c53f6d6f-275b-4afe-b596-21ab8f383002 |  | checkpoint | Clean sub straights
checkpoint-status | 598e1e96-8315-45fe-a540-8488ccfcdb65 |  | checkpoint | Epoxy applied well to product and sub straight
checkpoint-status | dbd60991-5d45-4f14-98fd-ba31c9718ba5 |  | checkpoint | Install VF product to correct depth or flush
checkpoint-status | 8faefc15-3314-44b9-9620-84e365d5abf3 |  | checkpoint | Silicone applied
checkpoint-status | 77004d53-c5b0-4075-8868-2fdc70878881 |  | checkpoint | Clean finished product installed
checklist-sectioned | 952e683b-7e57-4f94-b1e5-79f67c0aa3b7 |  | checklist | KB. Date: |  |  |  |  | Yes | QA - KB | c02d9cf2-5442-44e3-af39-365e7f079b93
checkpoint-group | b897aded-6baa-4929-9804-501bfb150fb4 |  | section | Details
checkpoint-status | b8d9b2da-3411-46b8-bd76-7c6a90924f69 |  | checkpoint | Location/Gridline details entered
text | 37a2b533-03df-5f3f-bc0f-7e6734a08e9a |  | textbox | Location/Gridline:
checkpoint-status | 373909b7-eec4-4f64-a540-3c451e29aeb0 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 66c26f8b-abfc-467c-9ef9-adcb89fdc38b |  | checkpoint | Smooth parallel substrate
checkpoint-status | 77938608-72c3-43d2-829c-da67dbd2db4d |  | checkpoint | Rebates correct depth / width
checkpoint-status | 3930c7d3-1de6-48a2-9a6a-76c7e82ea14d |  | checkpoint | FFL height confirmed
checkpoint-status | 8fcd0f76-d91b-41c8-9ace-83bcee88ee21 |  | checkpoint | EPDM installation well sealed with movement allowed and terminations / transitions complete
checkpoint-status | f406af26-bd6d-41ce-bb00-539d26c26a88 |  | checkpoint | Packer / grout installed with retainers fix securely
checkpoint-status | 7aa48ae9-02bf-45be-a3ed-0268850afd12 |  | checkpoint | Turnbars installed with centre plate securely (If required)
checkpoint-status | a315eb46-0c56-4de9-8f20-a37fcc7c0559 |  | checkpoint | Concrete backfill completed
checkpoint-status | 50754332-2c55-4b7a-8366-533dc7eeedfe |  | checkpoint | Clean finished product installed
checklist-flat | fa779ee1-e661-4b30-b6c8-65adc37821a5 |  | checklist | SSRZW. Date: |  |  |  |  | Yes | QA - SSRZW | 4c7d8195-1a74-451a-8952-b22d35fc775b
checkpoint-status | 7cac0883-af4f-44aa-8dcc-93e0ecb10b8a |  | checkpoint | Location/Gridline details entered
text | d89293f5-b83c-5c13-b0ff-338fb01c3a2e |  | textbox | Location/Gridline:
checkpoint-status | 192d979a-aced-4c88-bd44-334a543b2a65 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 42dc31b5-543d-409f-a6e9-7f6392826869 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 90dce189-09de-40d2-9f5e-07290a56a950 |  | checkpoint | Rebates correct depth / width
checkpoint-status | c79071f2-cc4e-4887-8437-88880b9c6214 |  | checkpoint | FFL height confirmed
checkpoint-status | 1f8fde2f-7a6b-4d6b-a27e-98d6f837132d |  | checkpoint | Packer / grout installed with retainers fix securely to floor
checkpoint-status | cbb600a3-9c05-4041-a7b2-2287de0b5abb |  | checkpoint | Wall retainers installed to solid substrate securely
checkpoint-status | 5ed499bf-7f8a-4f90-b9bb-31754be26597 |  | checkpoint | Turnbars installed with centre plate securely
checkpoint-status | 15be64ce-5a00-4a17-969f-0b4ea80111d6 |  | checkpoint | Sealant applied to retainer edge
checkpoint-status | 2c086104-c8f3-4b2b-abdb-68b974ed6cd7 |  | checkpoint | Clean finished product installed
checklist-flat | 94b98ed3-3b59-4eab-8e0d-0b6679d4584a |  | checklist | QA - FCF+FWF-1"/6" Internal wall + ceiling |  |  |  |  | Yes | QA - FCF+FWF-1"/6" Internal wall + ceiling | b8d0b7f3-56b7-49a6-aa9b-2508b1e18ad5
checkpoint-status | cef6f3cc-cbc4-4cbb-958a-967ef8549b2c |  | checkpoint | Location/Gridline details entered
text | dd15f636-92b2-5903-a799-0fe1e1eb0f5c |  | textbox | Location/Gridline:
checkpoint-status | 00e5539d-6afc-43b3-8112-006fcbdf463c |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 4be6fa8c-e25d-46c7-b6fd-4665de7f0219 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 3715a0f5-5edf-4167-8027-c4ecf50c6ed2 |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | 8fd2b4b7-c1c9-4308-a71e-837acff5eb74 |  | checkpoint | Solid Substraight behind plasterboard to fix into
checkpoint-status | 43e344d3-c2b0-4e02-b01b-70578cbd9b91 |  | checkpoint | Retainers fixed securely
checkpoint-status | c78e3cf7-0e49-4cae-a036-a52d404df3b0 |  | checkpoint | Gasket installed and is flush )no lumps or un evenness
checkpoint-status | 2efff9bf-d522-4455-990e-e3f1a1af569f |  | checkpoint | Clean of installed finished product
checklist-flat | 6e4639d3-6578-47c4-ae79-26df6417444e |  | checklist | RSV 605 Louvres. Date: |  |  |  |  | Yes | QA - RSV 605 Louvres | 5383b60f-c142-4f93-9977-4343da3b65ce
checkpoint-status | e5526326-f319-4bfd-9248-7396a37e049c |  | checkpoint | Location/Gridline details entered
text | a0cc4540-0357-57d5-89dd-7ec7c8382d14 |  | textbox | Location/Gridline:
checkpoint-status | 2f11ccda-9f33-46d9-bfe9-87aa5bbb875e |  | checkpoint | Materials checked and correct quantity for Opening
checkpoint-status | e211c30e-3553-4464-9632-0c52a9f4fd49 |  | checkpoint | Check level, size plumb at opening
checkpoint-status | f7cc081e-471b-444f-9227-4bacdef87f07 |  | checkpoint | Use laser to find narrowest and smallest point in opening
checkpoint-status | 36efe1a7-3f59-4171-9c51-005bffb93911 |  | checkpoint | Set up the packers and install the bottom support angles with the correct fasteners
checkpoint-status | 2344896f-aff0-4dec-8a3c-183921b66253 |  | checkpoint | Flashings installed with sealant underneath and rivets in joints
checkpoint-status | e87411d7-918d-4818-8ead-4ae43a13bb44 |  | checkpoint | Install vertical angles with isolating washers
checkpoint-status | ac9b96b8-2c32-4011-bd7a-8b86f92b8fdd |  | checkpoint | Install top flashing and support angle with isolating washers
checkpoint-status | 972b769a-cc66-448a-b722-cad31607dba8 |  | checkpoint | Install middle section flashing on top of steel plate support using sealant and folding ends accordingly
checkpoint-status | 52bb7307-0949-4859-b8ec-711fa6aaeffc |  | checkpoint | Install Louvres using lifting system
checkpoint-status | 35bf2acc-af45-4034-aef6-06fb37a9daae |  | checkpoint | Fix Louvres to support angle at 600mm centres using appropriate fasteners
checkpoint-status | 30e39e61-bd4f-48bd-8c4e-127f0fd24908 |  | checkpoint | Fix/bolt aluminium bracket to steel plate support, ensure appropriate fixings and spacings
checkpoint-status | eb4b7488-129b-4705-8c69-33a4ac632105 |  | checkpoint | Install joint flat bars using correct fasteners and spacings
checkpoint-status | 1938b000-484a-492f-b055-fb9cd8f2ef74 |  | checkpoint | Install perimeter angle for PEF rod using rivets
checkpoint-status | 2fa815c3-b797-4855-96c6-174a9370a55a |  | checkpoint | Put PEF roof around perimeters
checkpoint-status | c4423311-a938-43ae-ba52-7477f9927b01 |  | checkpoint | Seal the gaps around the Louvres according to the details
checkpoint-status | d82d26df-9c25-4d35-9b89-44856d4658cf |  | checkpoint | Clean up dust and touch up paint Louvres
checkpoint-status | 54eef694-8def-48d2-a7fc-4c14e9847371 |  | checkpoint | Install lip flashing once it has been sealed
checkpoint-status | dcfa0de4-df4b-4acb-bd00-4e9bc62816e8 |  | checkpoint | Finished product
checklist-flat | 0b67444e-8afa-4c36-bbd1-b1524e15116c |  | checklist | QA - FCF+FWF-8" + Internal wall / ceiling |  |  |  |  | Yes | QA - FCF+FWF-8" + Internal wall / ceiling | d7135ebe-95f6-4b69-ba6b-fafa777af418
checkpoint-status | 49c3340f-106b-4fc2-a164-c284cf8e08ab |  | checkpoint | Location/Gridline details entered
text | 1e92ee9b-346d-505f-b454-2cffbf04e15e |  | textbox | Location/Gridline:
checkpoint-status | e3f8c3cb-ce42-4299-ac22-ed7d322a0ba3 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | c429c530-8d08-433b-a5c2-87757c3c5378 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 821a493e-87ce-4683-ac91-55fe54cdf8a6 |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | e2ce5df9-c412-45e8-bd9f-955119d1eea6 |  | checkpoint | Plasterboard cut back to correct Setout
checkpoint-status | 9dc6b370-6ad0-49c0-a4e6-e4918a092cbc |  | checkpoint | Solid Substraight to fix into
checkpoint-status | 1aa3c406-fa44-47bb-a5ba-05f24143cf8d |  | checkpoint | Retainers fixed securely
checkpoint-status | f53efd0a-a55d-4ec8-aee4-b630e20320e1 |  | checkpoint | Turnbars and centre mullion installed securely and at correct spacings
checkpoint-status | 56b911a4-704f-4128-a892-70a372689a76 |  | checkpoint | Gasket installed and is flush )no lumps or un evenness
checkpoint-status | 3ce98ee2-7617-481a-ba38-99086024e105 |  | checkpoint | Clean of installed finished product
checklist-flat | bcaaf28d-9378-46e0-a1a7-8a94d5928c7f |  | checklist | SRJW. Date: |  |  |  |  | Yes | QA - SRJW | 6a34cb42-d8e6-4c55-a4ff-2f1e7c53706b
checkpoint-status | 6d15d58e-ec92-40ec-b95b-d83b2154b6c1 |  | checkpoint | Location/Gridline details entered
text | 762ece2e-9e1b-52f3-8819-f596e8e1bc1a |  | textbox | Location/Gridline:
checkpoint-status | 5d4336b1-cf3e-4b07-8174-1d0498e1a7ad |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 20e99d8f-334a-4427-9066-f1ff68724ed0 |  | checkpoint | Smooth substrate
checkpoint-status | 7529cb50-b7e4-4f52-bab6-0b9c0841c0c2 |  | checkpoint | Correct upstand angle
checkpoint-status | 7556885d-38fd-4d10-b1e3-8875098dfa3e |  | checkpoint | Flashing or Torch On installed
checkpoint-status | f4d8339b-cfdb-4a54-a8c4-117b2a53d9ad |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 3c23b0ac-900c-4fc2-ba03-be2281924fdf |  | checkpoint | Fall to Vertical/Drain acceptable
checkpoint-status | 40bf9b3f-5c65-49d4-a445-00073ae6e4cc |  | checkpoint | Drain placements correct (if required)
checkpoint-status | 5bf8ace9-86e7-4ea7-a918-509d6cab109b |  | checkpoint | Correct Sealant used (Black Jack or Seal N Flex in conjunction with butyl tape)
checkpoint-status | c1cb4543-e5a4-4de4-bc4e-840d20283ff2 |  | checkpoint | EPDM installation well sealed with movement allowed and terminations / transitions complete
checkpoint-status | 4245ec22-194c-453a-9706-26930d64c6e5 |  | checkpoint | Retainer fixing to substrate secure and watertight
checkpoint-status | 0af2d5ad-b629-4f7f-ab47-1e03e93ee2cd |  | checkpoint | Fall / water test complete and archived
checkpoint-status | c714fd17-5e4f-4028-80e6-a9e5e7f8475f |  | checkpoint | Roof cap installed with turn bars ready to tighten
checkpoint-status | 9f6ae710-2dea-4487-9774-3ea9c44e8ea8 |  | checkpoint | Turnbars installed correctly, right angle / centres
checkpoint-status | 11102cab-232c-44f4-93fa-2969870ad050 |  | checkpoint | Soakers installed with sealant underneath
checkpoint-status | f92c816e-4b93-4ad2-ae26-81278b824b67 |  | checkpoint | End caps and transitions installed
checkpoint-status | 32f57a65-15b5-4b0e-95ad-1f353e6ab824 |  | checkpoint | Sealant applied to roof cap upstand top edge
checklist-flat | 6b2fa821-5f53-4c5b-9e72-298e28ec4f50 |  | checklist | Flexjoint. Date: |  |  |  |  | Yes | QA - Flexjoint | fdd32781-3087-4397-b65a-6d636bcf666d
checkpoint-status | d9a896c1-9fd0-4555-b232-a094f5422655 |  | checkpoint | Location/Gridline details entered
text | 67bc5139-e8ad-570d-90cf-ecef9fbbd8bb |  | textbox | Location/Gridline:
checkpoint-status | de8cd699-3b5b-4649-bf0d-f0e74a2fe313 |  | checkpoint | Location of flexjoint
checkpoint-status | 3875e54f-c7e1-46af-8485-de852c1b3534 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 080cfc8e-048c-4d86-bc98-9db6de9264dc |  | checkpoint | Smooth clean substrate with base membrane installed correctly OR Smooth and clean Substraight for epoxy
checkpoint-status | 17ec9986-ed48-401d-b7d2-9246f576d666 |  | checkpoint | No services to penetrate flexjoint
checkpoint-status | eeaa8975-ef1b-4287-a298-1dd1987a29a2 |  | checkpoint | Detail correct IE Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 709f61df-a724-4131-8309-f9cb2c682554 |  | checkpoint | Vulcanising joints to correct pressure/time and bond achieved appropriately
checkpoint-status | 0fad3cc3-1f45-4cc8-8cc2-b760007e222e |  | checkpoint | Bleed on thourch on and bond sufficent OR epoxy coverage sufficent
checkpoint-status | b8c1a31a-b905-44f7-b659-9c5b8a98210d |  | checkpoint | Pressure bars secured well for epoxiy applications
checklist-flat | 51e62c73-5a21-4c40-9350-92baee6266f9 |  | checklist | Document Name: |  |  |  |  | Yes | Add New Document | 7caa3ca8-4dda-4f65-8e42-2989f6180efa
checkpoint-status | df375054-0560-4956-9f47-b46c1478c4ad |  | checkpoint | Please upload document
checklist-flat | 6efb70ad-af29-4efb-99af-693468164c72 |  | checklist | ESC/ESW. Date: |  |  |  |  | Yes | QA - ESC/ESW | af374607-0895-4b84-b3e4-8370ab23519e
checkpoint-status | 4dc13d46-3ba7-4d32-8539-93360bcb4c15 |  | checkpoint | Location/Gridline details entered
text | 61980ec3-de5f-5055-966d-1c0fe17eb931 |  | textbox | Location/Gridline:
checkpoint-status | a647dd57-11d4-4526-b5cb-1048417c58f4 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | dc45df57-efb3-4b79-bc24-b017cee36a95 |  | checkpoint | Smooth substrate
checkpoint-status | 14638c34-2e0a-43f4-a22c-b1127c174199 |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | e47b0c5d-c2b8-4272-ac4d-cf9b9336158b |  | checkpoint | EPDM installation well sealed with movement allowed and terminations / transitions complete
checkpoint-status | 02289a61-4da9-4b99-a465-67cccac9793a |  | checkpoint | Correct upstand angle
checkpoint-status | 80d4ff06-4ae6-4d1a-8293-9535f8f3986a |  | checkpoint | Frame/Retainers installed properly using supplied fixings
checkpoint-status | 7389e75d-2f8c-4e33-99a5-0668c20bae35 |  | checkpoint | Turnbars installed with centre plate secured
checkpoint-status | 702429b0-e0e2-4fcf-a032-20f97b694718 |  | checkpoint | Soakers installed with sealant underneath
checkpoint-status | 386cc0a7-9182-44bd-a72f-1c44a9c3a69e |  | checkpoint | Clean finished product installed