## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-009 - Spray Seal | itp |  |  |  |  | ITP-009 - Spray Seal
section | 1 - Materials
checkpoint | 1.1 - Bitumen
label | FREQUENCY: Test cert upon request
label | ACCEPTANCE CRITERIA: AS (Section 175) for residual bitumen for pavements
label | REFERENCE DOCUMENTS: 408.08 (a)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Lab Manager
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 1.2 - Bitumen Emulsion
label | FREQUENCY: Test cert upon request
label | ACCEPTANCE CRITERIA: ARS or CRS comply with AS (Section 175) – Bitumen emulsions for the construction and maintenance of pavements
label | REFERENCE DOCUMENTS: 408.08 (b)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Sign off
label | IP
label | RESPONSIBILITY: Lab Manager
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 1.3 - PMB
label | FREQUENCY: Test cert upon request
label | ACCEPTANCE CRITERIA: Austroads Specification Framework for Polymer Modified Binders and Multigrade Bitumen’s (AGPT/T190 - section 175) & table 408.161. Alternative PMB'S shall not be used without approval by Superintendent. Evidence of satisfactory field performance for 3 years required.
label | ○ (i) HSS - S10e,S35e,10Pts CR, or alternative approved by superintendent
label | ○ Field Produced CR - >5pts by mass of binder, Carrier oil <4Pts by volume of binder
label | ○ (ii)SAM - S45R,S20e,18Pts CR or alternative as approved by the superintendent
label | ○ Field Produced CR - >18pts by mass of binder, Carrier oil <4Pts by volume of binder
label | ○ (iii)SAMI - S25e,20PtsCR or alternative as approved by the superintendent
label | ○ Field Produced CR - >20pts by mass of binder, Carrier oil <4Pts by volume of binder
label | ○ XSS treatments – Class S20E,S45R or S15RF or alternative as approved by the Superintendent.
label | ○ XSS treatments are applied as a double/double application and the same binder shall be used for both applications.
label | REFERENCE DOCUMENTS: 408.08 (d)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Lab Manager
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 1.4 - Primer
label | FREQUENCY: Test cert upon request
label | ACCEPTANCE CRITERIA: Cutback bitumen only. NB: bitumen emulsion alternative acceptable upon providing evidence of its characteristics.
label | REFERENCE DOCUMENTS: 408.08 (e)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Lab Manager
date | Date Completed:
holdpoint | Request Signoff
section | 2 - Aggregate
checkpoint | 2.1 - Aggregate Specification
label | FREQUENCY: Maximum lot size 350t of same class and size
label | ACCEPTANCE CRITERIA: VicRoads Standard Specification Sections:
label | ○ 801 - Source Rock, 831 - Aggregate & 832 - Sands
label | REFERENCE DOCUMENTS: 408.11 (a)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | HP*
label | RESPONSIBILITY: Lab Manager
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 2.2 - Precoating
label | FREQUENCY: All works carried out
label | ACCEPTANCE CRITERIA: Supply plant precoated aggregate from supplier or field precoated aggregate from stacksite.
label | ○ Aggregate shall be uniformly precoated to the satisfaction of the Superintendent.
label | REFERENCE DOCUMENTS: 408.11 (b)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Supervisor
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 2.3 - Removal of loose aggregate
label | FREQUENCY: All works carried out
label | ACCEPTANCE CRITERIA: All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent.
label | ○ NB: For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
label | REFERENCE DOCUMENTS: 408.14
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Supervisor
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 2.4 - Stack Site
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Stack sites to be approved by Superintendent.
label | ○ Stack site to be at Kent Street where road is closed.
label | REFERENCE DOCUMENTS: 408.12
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Supervisor
date | Date Completed:
holdpoint | Request Signoff
section | 3 - Operation
checkpoint | 3.1 - Rates of Application
label | FREQUENCY: All works carried out
label | ACCEPTANCE CRITERIA: In accordance with the current Update of the Austroads Sprayed Seal Design Method
label | ○ (Section 175) rates of application - residual binder at 15 C
label | ○ Traffic Data and default rates -Table 3040.066 (Traffic Volumes)
label | ○ 1 week prior, design rates of application, aggregate and rates for pre-treatment to be reviewed by Superintendent.
label | REFERENCE DOCUMENTS: 408.15 (a)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | HP
label | RESPONSIBILITY: Site/Project Engineer
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.2 - Surface Pre-treatment
label | FREQUENCY: All works carried out
label | ACCEPTANCE CRITERIA: Refer Table 408.171, 408.132, 408.133
label | REFERENCE DOCUMENTS: 408.13 (b)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Supervisor
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.3 - Calibration of Bitumen Sprayer
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Calibration Certificate to be provided
label | REFERENCE DOCUMENTS: 408.07
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | WP
label | RESPONSIBILITY: Supervisor
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.4 - Commencement of works
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: NB: Works shall not commence until the Contractor & Superintendent of works agree that the prepared surface is ready & fit for sealing. This includes a review of the material and evidence that the pavement passes compaction testing to Superintendents approval.
label | ○ Primersealing shall not be carried out within 12 hours of forecast rain.
label | REFERENCE DOCUMENTS: 408.04
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off, QD2190370 Sealing Checklist
label | HP
label | RESPONSIBILITY: Site/Project Engineer/ Supervisor / Superintendent
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.5 - Records
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Job completed within spec requirements.
label | ○ Job completion report, i.e. Spray Sheets to be submitted within 7 days of completion of sealing works
label | REFERENCE DOCUMENTS: 408.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off, Spray Sheets, Section 408 Attachment A
label | WP
label | RESPONSIBILITY: Site/Project Engineer
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.6 - Acceptance of work- Binder rates
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Actual vs design rates. Variation between actual & design assessed by Table 408.121
label | ○ ie. Variation from the Design Rates of Application for Bituminous Material < 0.1 l/m² below the design rate of application
label | REFERENCE DOCUMENTS: 408.15 (a)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Site/Project Engineer
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.7 - Acceptance of work- Surface Texture
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Acceptance - visual assessment or (where required) as per Table 408.122
label | ○ ie. 7mm Primerseal Mean Texture Depth between 1.0mm to 2.0mm
label | REFERENCE DOCUMENTS: 408.15 (b)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Site/Project Engineer
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.8 - Acceptance of work- Aggregate retention
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Acceptance -visual assessment or (where required) as per Table 408.123
label | ○ Degree of Aggregate Stripping is 0 - 2
label | REFERENCE DOCUMENTS: 408.15 (c)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Site/Project Engineer
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.09 - Acceptance of work- Visual Uniformity
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Provide a surface with uniform colour, texture and consistent appearance
label | REFERENCE DOCUMENTS: 408.15 (d)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | IP
label | RESPONSIBILITY: Site/Project Engineer
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.10 - Maintenance of seals
label | FREQUENCY: All works carried out
label | ACCEPTANCE CRITERIA: The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period.
label | ○ The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work.
label | REFERENCE DOCUMENTS: 408.16
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | HP
label | RESPONSIBILITY: Site/Project Engineer, Superintendent
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.11 - Maintenance of seals
label | FREQUENCY: All works carried out
label | ACCEPTANCE CRITERIA: Where the treatment for protection or repair of a seal involves the application of a further seal coat, the Contractor shall obtain the agreement of the Superintendent of the proposed treatment before undertaking the work.
label | REFERENCE DOCUMENTS: 408.16
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed Off
label | HP
label | RESPONSIBILITY: Site/Project Engineer
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.12 - Defects Liability Period
label | FREQUENCY: All works carried out
label | ACCEPTANCE CRITERIA: All defects should be rectified six months prior to the conclusion of the Defects liability period. As stated in 408.15
label | ○ The Contractor shall carry out at least two inspections of each job during the Defects Liability Period and provide a condition report to the Superintendent. The condition report shall detail the condition of the seal, any defects and the proposed corrective action.
label | REFERENCE DOCUMENTS: 408.18
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed off
label | WP
label | RESPONSIBILITY: Site/Project Engineer
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.13 - Dryback
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment
label | ○ 6 randomly selected test sites per lot required
label | ○ If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required
label | ○ If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm
label | ○ Testing shall be undertaken no more than 24 hours before primersealing.
label | ○ Testing schedule in accordance with 310.03 (c) and QD2190370 Sealing Checklist
label | REFERENCE DOCUMENTS: 310.03(a), 310.03(b) Table 310.031, 310.03(c) Table 310.032
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed off
label | TP
label | RESPONSIBILITY: Site/Project Engineer/ Supervisor
date | Date Completed:
holdpoint | Request Signoff
checkpoint | 3.14 - Ride Quality
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ride quality measurement shall be undertaken within 3 months of the completion of primerseal and prior to practical completion being awarded by the Superintendent.
label | ○ The finished surface of the Primersealed pavement shall have a smooth longitudinal profile and comply with the minimum ride qaulity requirements of Scale C road as specified in Table 180.092.
label | – Maximum Individual Lane Roughness Value for any 100 m Subsection = 2.70 m/km/lane
label | – Maximum Mean Lane Roughness Value for Lot = 2.00 n/km/lane
label | – Maximum length of lot is 2km of continuous traffic lane
label | REFERENCE DOCUMENTS: 180.04, 180.092
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed off
label | TP
label | RESPONSIBILITY: Site/Project Engineer/ Supervisor
date | Date Completed:
holdpoint | Request Signoff
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: