## Hychem MataCryl (hidden)
type | name | values | prefix | postfix | usage count
checklist-flat | MataCryl Application
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Preliminary Substrate Assessment for Potential Rectification
button | Adequate fall in substrate? | Yes,No
text | Provide description, photos and plan identifying any areas where the client is required to repair/remediate the substrate
checkpoint | Substrate Assessment for Acceptance, and Adhesion Testing
button | Substrate deemed acceptable for membrane application | Yes,No
button | Test area completed for adhesion test | Yes,No
button | Adhesion test passed | Yes,No
checkpoint | Substrate Preparation
button | Substrate to be washed/cleaned | Yes,No
text | If any damage has occurred since initial assessment and/or rectification please identify and alert builder.
button | Substrate ready for membrane application. | Yes,No
checkpoint | Matacryl Primer H Application
button | Substrate free from surface water | Yes,No
button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
text | Record (Photo) batch number and date of manufacture of primer
text | Record date/time, temperature and % catalyst at time of mixing primer
button | Substrate free from surface water - record moisture reading | Yes,No
button | Installation of fillets/bandage to junctions as required? | Yes,No
button | Primer installed before pot life expiry? | Yes,No
text | Record date and time of primer installation
button | Quartz aggregate broadcast into primer | Yes,No
text | Record date and time of quartz broadcast
checkpoint | Matacryl Manual Base Coat Application
button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
text | Record (Photo) batch number and date of manufacture of MataCryl Manual
text | Record date/time, temperature and % catalyst at time of mixing MataCryl Manual
button | Substrate free from surface water - photos attached below | Yes,No
button | MataCryl Manual installed before pot life expiry? | Yes,No
text | Record date and time of MataCryl Manual installation
checkpoint | Matacryl STC Clear Top Coat Application
button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
text | Record (Photo) batch number and date of manufacture of MataCryl STC Clear
text | Record date/time, temperature and % catalyst at time of mixing MataCryl STC Clear
button | Substrate free from surface water - photos attached below | Yes,No
button | MataCryl STC Clear installed before pot life expiry? | Yes,No
text | Record date and time of MataCryl STC Clear installation
text | Record date and time of quartz broadcast
label | Attach Client Signature Below

## Hychem MataCryl Trial
type | name | values | prefix | postfix | usage count
checklist-flat | MataCryl Application
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
text | Attach TDS for application (Download from Simpro)
checkpoint | 1: Concrete Pour of Bridge Deck
text | 1.01: Confirmation of date of concrete pour
1.02: Substrate inspection
checkpoint | 2: Lead up to installation
text | 2.01: Confirmation of product batch numbers and use by dates (photograph) WITNESS POINT
2.02: Conduct preparation to substrates including shot blasting, grinding, other methods HOLD POINT
2.03: Minimum 7 days after concrete pour. Install pull off test equipment to deck and conduct test. Minimum 0.75mpa. Photograph HOLD POINT
2.04: Conduct moisture test ( < 7%) WITNESS POINT
checkpoint | 3: Day prior to commencement
text | 3.01: Inspect concrete deck condition, assess cleanliness and readiness for installation.. HOLD POINT
text | 3.02: Conduct moisture test ( < 7% ). HOLD POINT
3.03: Review suitability of weather forecast for next 4 days, photograph WITNESS POINT
checkpoint | 4: Day of works commencement
text | 4.01: Prior to commencement, inspect concrete deck condition, assess cleanliness and readiness for installation. Photograph. HOLD POINT
text | 4.02: Test substrate moisture content ( < 7% ). HOLD POINT
text | 4.03: Test ambient temperature (10-35 degrees) Photograph WITNESS POINT
4.04: Test substrate temperature (10-35 degrees) Photograph HOLD POINT
4.05: Test dew point temperature (minimum 3 degrees less than ambient temperature). HOLD POINT
checkpoint | 5: Matacryl Primer H Application
text | 5.01: Mix primer liquid component separately, sprinkle catalyst and mix thoroughly until homogenous (fully mixed through)
text | 5.02: Install product to required coverage rate and record quantity of product installed (40m2 per kit/unit). Photograph WITNESS POINT
text | 5.03: Quartz aggregate broadcast into primer at 1kg/m2. Photograph. HOLD POINT
checkpoint | 6: Matacryl Manual Base Coat Application
text | 6.01: Test primer for suitability to proceed to membrane installation. Photograph. HOLD POINT
text | 6.02: Test substrate moisture content ( < 7% ). HOLD POINT
text | 6.03: Test ambient temperature (10-35 degrees) Photograph WITNESS POINT
text | 6.04: Test substrate temperature (10-35 degrees) Photograph HOLD POINT
text | 6.05 Test dew point temperature (3 degrees greater than ambient temperature). HOLD POINT
text | 6.06: Mix liquid membrane component separately, sprinkle catalyst and mix thoroughly until homogenous (fully mixed through) WITNESS POINT
text | 6.04: Install membrane to required coverage rate (2.8kg/m2) and record quantity of product installed (maximum 8.9m2/mixed kit). Photograph WITNESS POINT
text | 6.05: Measure wet film thickness of membrane during installation - minimum 1 measurement per membrane kit (8.9m2/kit) . Photograph WITNEESS POINT
checkpoint | 7: Matacryl STC Clear Top Coat Application
text | 7.01: Test primer for suitability to proceed to membrane installation. Photograph. HOLD POINT
text | 7.02: Test substrate moisture content ( < 7% ). HOLD POINT
text | 7.03: Test ambient temperature (10-35 degrees) Photograph WITNESS POINT
text | 7.04: Test substrate temperature (10-35 degrees) Photograph HOLD POINT
text | 7.05: Test dew point temperature (3 degrees greater than ambient temperature). HOLD POINT
text | 7.06: Mix liquid topcoat component separately, sprinkle catalyst and mix thoroughly until homogenous (fully mixed through)
text | 6.04: Install topcoat to required coverage rate (40m2/mixed kit) and record quantity of product installed. Photograph
text | 7.05: Broadcast sand aggregate into wet top coat (4kg/m2). Photograph
checkpoint | 8: Post installation - immediate
text | 8.01: Test membrane system for suitability to proceed to pull off test (minimum 1hr). HOLD POINT
text | 8.02: Install pull off test dollys at rate of 1/100m2, conduct pull off test minimum 45 mins after installation
text | 8.03: Measure and record pull off test result, minimum 0.75mpa photograph HOLD POINT
text | 8.04: Measure and record pull off test result for membrane dry film thickness (2mm) HOLD POINT
8.05: Repair pull off test areas including concrete repair, Martacryl Primer H, Matacryl Manual, Matacryl STC with broadcast aggregate WITNESS POINT
checkpoint | 9: Post installation
text | 9.01: Remedy test results uploaded into Bravada CONQA QA platform. Photograph, WITNESS POINT
9.02: Review Bravada CONQA QA/ITP, confirm compliance, handover to SEPA. SIGNATURE