## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Retaining Wall (Liquid) |  |  |  |  | Yes | Retaining Wall (Liquid) | f2408195-41bb-438c-8136-532454d6a443
checkpoint-no-status |  |  | checkpoint | Scope
label | 55382fce-7b7f-5401-b909-16afe9dcd713 |  | note | Scope Description (from Bravada SOW) and item numbers
text | 8583a526-51ba-562e-b2bf-c9edb009eb6a |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
button | 7be925a5-c873-5f84-a1b0-45dffc1a5a72 |  | button | Installation of liquid membrane as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? (Attach photos)
button | a961f6c2-4aa4-5a8c-95b4-1f44c824478a |  | button | Cement sheet installed? | Yes,No,N/A
button | f4813d74-8268-584f-881b-b135314ada18 |  | button | Corflute installed installed? | Yes,No,N/A
button | 6e1b9b59-c73e-5391-94ab-937968f3479e |  | button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Backfilled within manufacturer's specified timeframe?
label | 1553c7ea-f385-5090-a18a-2ac00e7ff87a |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Planter (PVC/Butynol Membranes) |  |  |  |  | Yes | Planter (PVC/Butynol Membranes) | e8f23b64-39c4-472a-a757-c0ce23821604
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 6385cdfb-584c-5484-8cf0-89b942696a49 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
checkpoint-status |  |  | checkpoint | Sufficient fall in planter base?
button | e58806ba-3500-59dd-bf9d-a634afd5be14 |  | button | Adequate fall in substrate? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water?
label | 9120d6ac-b79f-5638-98bc-27ae54e817ed |  | note | If any of these checkpoints fail please provide information and required action by builder
text | a54d7a1f-e2fd-54ad-af98-15b5cd2aebfb |  | textbox | Add Comment
checkpoint-status |  |  | checkpoint | Sheet membrane installed to manufacturer's specification?
checkpoint-status |  |  | checkpoint | Termination pressure bar installed?
checkpoint-status |  |  | checkpoint | Signoff of compliant installation.
label | 13a895d8-1016-5913-ba46-12351a90dad5 |  | note | Attach Client Signature Below
label | 4c32e160-99bc-5891-bf27-731f691ba471 |  | note | Client Signature
checklist-flat |  |  | checklist | Planter (Torch-on Membrane) |  |  |  |  | Yes | Planter (Torch-on Membrane) | 03188f17-04db-4616-9c98-3fe37468f3ef
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | d429615e-3614-51fa-9d54-eb8dffd7304f |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
checkpoint-status |  |  | checkpoint | Sufficient fall in planter base?
button | 4b660411-e908-56ae-8c2e-8b590368dc37 |  | button | Adequate fall in substrate? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water?
label | 98fbdf31-d16e-5252-b2e9-6a0dc04a7687 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 1092271e-f779-5b88-8f6f-f6572056249a |  | textbox | Add Comment
checkpoint-status |  |  | checkpoint | Base layer membrane installed to manufacturer's specification?
checkpoint-status |  |  | checkpoint | Base layer membrane installed to manufacturer's specification?
checkpoint-status |  |  | checkpoint | Anti-root layer membrane applied to manufacturer's specification?
checkpoint-status |  |  | checkpoint | Termination pressure bar installed?
checkpoint-status |  |  | checkpoint | Signoff of compliant installation.
label | 8cc58af8-a282-5d42-9662-38d2a2db4483 |  | note | Client Signature
checklist-flat |  |  | checklist | Screed |  |  |  |  | Yes | Screed | c0ee6532-ea4f-434e-bc70-f1925b85ff81
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 3b65925b-c9f4-538a-a35e-7b32327294d1 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate cleaned & assessed for suitability to screed to - photos attached below
checkpoint-status |  |  | checkpoint | Sufficient setdown depth available to create adequate fall to wastes?
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water?
checkpoint-status |  |  | checkpoint | Minimum screed thickness of 20mm at waste available to achieve 1:100 fall?
label | eaf08061-bc1a-5ae4-a1c3-dffd84468e82 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | d89c7388-56d8-577c-a91a-472b837ee843 |  | textbox | Add Comment
button | a05daf21-0b4a-5c0b-91e6-073db66a4575 |  | button | Screed mixed to manufacturer's specifications? | Yes,No
button | 6dc157d3-aa0c-5fa7-a4ba-d8cef20e914b |  | button | Slurry applied for bonding as per manufacturer's specification? | Yes,No
checkpoint-status |  |  | checkpoint | Screed completed and suitable for membrane application - photos attached below
label | 60712525-fb33-5b1c-bd95-163798d73b72 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Internal |  |  |  |  | Yes | Internal | 11a11c00-8ca7-4ab0-95eb-ce2ccb0ce838
checkpoint-no-status |  |  | checkpoint | Scope
label | 4d51a533-c9f0-5d5b-966d-16fdf1d86c7c |  | note | Scope Description (from Bravada SOW) and item numbers
text | cc61a791-9f38-5a38-8ab5-99d3200b2187 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
button | 869b5318-907b-5380-b944-718ac7f08b0d |  | button | Adequate fall in substrate? | Yes,No
label | fc96a2dc-836e-5291-ac2d-b1baf2c92e90 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 3012f7c6-7b7c-5b5d-9402-e7fb5dfe735f |  | textbox | Add Comment
button | fb24a488-9153-5589-a9f1-9368b9cb9cef |  | button | Installation of tape or caulk to junctions. | Yes,No
button | 2a591944-09dd-5fa6-a55a-6ea10e0f1196 |  | button | Penetrations correctly detailed? | Yes,No
button | 010a0299-59e6-5c50-b7ad-4cf1ad1f966a |  | button | Waterstop correctly detailed? | Yes,No,N/A
button | 7e9fae6e-5532-50b1-a341-60ebb4c31574 |  | button | Installation of liquid membrane to manufacturer's specification? | Yes,No
button | 8076184d-8423-5402-8e43-2a0e396b2c72 |  | button | Installation of liquid membrane to perimeters, incl. compatible sealant as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - attach photos below
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of membrane
label | b24b58c1-87d2-56e3-918f-64a45620d7d3 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Bituthene 6000EIM Installation |  |  |  |  | Yes | Bituthene 6000EIM Installation | d4a30be0-a604-4c28-892c-46e2742f1f6b
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | df1ae2d3-4833-5aa9-aca0-57d38b324a9f |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
label | be745d8d-664f-54ff-85b5-652312ae3ab8 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | bac745dc-012c-5c2e-9d1a-9059a9f532c4 |  | textbox | Add Comment
checkpoint-status |  |  | checkpoint | Installation of Bituthene Type C primer as required?
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of primer
checkpoint-status |  |  | checkpoint | Curing time for primer (Minimum 2 hours)
checkpoint-status |  |  | checkpoint | Installation of base sheet
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of Bituthene 6000EIM base sheet
checkpoint-status |  |  | checkpoint | Installation of top sheet
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of Bituthene 6000EIM top sheet
checkpoint-status |  |  | checkpoint | Installation of Bituthene LM Mastic to perimeters
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of top sheet
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
checklist-flat |  |  | checklist | Bentonite - Anchor Boxouts |  |  |  |  | Yes | Bentonite - Anchor Boxouts | b267b441-e833-4b4a-a376-9303d4634422
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 4c7b06d1-d1ea-5c6d-a5d1-27a5c87ce0f3 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 5bebbfb0-05d0-5a69-949b-d6834b903d01 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 633aefe1-b73b-5d0b-8b89-9cc4d79069df |  | button | Membrane, Bentoseal & waterstop installed? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | cdacfa9c-3605-582f-8a4d-e9c5cf09be11 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | d9ca658c-1ec6-5f7f-bc81-676b3bb3b8d5 |  | button | Manufacturer Inspection Requested? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | f6327ac1-07db-5699-8ffc-5bcc1ca3d4a1 |  | note | Attach Manufacturer's Signature Below
label | 99fdc77b-061b-5ba9-acd9-bf763e25edc5 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Park and Ride - Green Roof Sarnafil Installation |  |  |  |  | Yes | Park and Ride - Green Roof Sarnafil Installation | 178e36ce-5946-4c49-93dc-0311066813cb
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 409a702c-466b-51c7-a905-7d1741649b69 |  | textbox | SOW description entered
checkpoint-status |  |  | checkpoint | Attach TDS for application
checkpoint-status |  |  | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
checkpoint-status |  |  | checkpoint | Adequate fall in substrate?
label | 93913b53-55f0-5427-8614-f5f3c1a5340c |  | note | If any of these checkpoints fail information and required action by builder provided in comments below
checkpoint-status |  |  | checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane junctions able to accept Type 5 profile?
checkpoint-status |  |  | checkpoint | Installation of Type 6 profile for junction with Watertite membrane?
checkpoint-status |  |  | checkpoint | Installation of Type 8 profile on upturn?
checkpoint-status |  |  | checkpoint | Adhesive installed to manufacturer's specification?
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of adhesive
checkpoint-status |  |  | checkpoint | Installation of sheet membrane to floor areas (min. 50mm overlaps)?
checkpoint-status |  |  | checkpoint | Siphonic drains detailed to manufacturers specification?
checkpoint-status |  |  | checkpoint | Installation of Type 5 profile to junction?
checkpoint-status |  |  | checkpoint | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)?
checkpoint-status |  |  | checkpoint | Installation of Dilatec tape detail to existing P-1200 membrane?
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
checklist-flat |  |  | checklist | Park and Ride - Busway Sarnafil Installation |  |  |  |  | Yes | Park and Ride - Busway Sarnafil Installation | 68e4b566-6fb4-4be7-a7a4-e78e41fda697
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | ffb449bb-c4e6-5a2c-9ed3-33b7ebd2a759 |  | textbox | SOW description entered
checkpoint-status |  |  | checkpoint | Attach TDS for application
checkpoint-status |  |  | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
checkpoint-status |  |  | checkpoint | Adequate fall in substrate?
label | c2216853-72c7-508f-9a28-586c18591746 |  | note | If any of these checkpoints fail information and required action by builder provided in comments below
checkpoint-status |  |  | checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane junctions able to accept Type 5 profile?
checkpoint-status |  |  | checkpoint | Installation of Type 6 profile for junction with Watertite membrane?
checkpoint-status |  |  | checkpoint | Installation of Type 8 profile on upturn?
checkpoint-status |  |  | checkpoint | Adhesive installed to manufacturer's specification?
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of adhesive
checkpoint-status |  |  | checkpoint | Installation of sheet membrane to floor areas (min. 50mm overlaps)?
checkpoint-status |  |  | checkpoint | Column bases (24) detailed to manufacturers specification?
checkpoint-status |  |  | checkpoint | Installation of Type 5 profile to junction?
checkpoint-status |  |  | checkpoint | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)?
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
checklist-flat |  |  | checklist | Concrete Injection |  |  |  |  | Yes | Concrete Injection | 1c93b074-31f8-487a-a0f8-dc71b397c0ec
checkpoint-status |  |  | checkpoint | Investigate location and document.
button | 9a197116-df9e-57ab-a7a4-e76e31ee9891 |  | button | Is injection required? | Yes,No
checkpoint-status |  |  | checkpoint | Record product, batch number and TDS.
text | 110aa801-923e-574b-97ae-cf7de0625723 |  | textbox | Drill, insert and record packers as required.
text | 69ef3c13-d9c7-5b04-9d4f-3000318dd71a |  | textbox | Record results of injection including (but not limited to) quantity of material injected per packer and relevant observations. Include sketch/markup if required.
button | 20888a7d-ea3d-50d8-a967-a7a3ddd6328e |  | button | Injection completed as per manufacturer's specification | Yes,No
checklist-flat |  |  | checklist | Planter (Liquid Membrane) |  |  |  |  | Yes | Planter (Liquid Membrane) | 9c35b224-d34c-4656-abdf-0fb1c4aec786
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 55f65dfe-760b-5b73-bdb4-8997a2f087bd |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
checkpoint-status |  |  | checkpoint | Sufficient fall in planter base?
button | 864ee1dd-6493-5f57-b087-011219daa789 |  | button | Adequate fall in substrate? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water?
label | 84d00589-e713-58c8-8bd2-e8d1ce1b36d0 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | c146c4e7-73dd-5f93-9540-c41f6f5bb5ab |  | textbox | Add Comment
checkpoint-status |  |  | checkpoint | Liquid membrane installed to manufacturer's specification?
checkpoint-status |  |  | checkpoint | Anti-root additive applied to manufacturer's specification?
checkpoint-status |  |  | checkpoint | Signoff of compliant installation.
label | dc461f20-5f0c-559d-8d2e-4708a95a4c1f |  | note | Client Signature
checklist-flat |  |  | checklist | Park and Ride - Watertite Membrane Junction Installation |  |  |  |  | Yes | Park and Ride - Watertite Membrane Junction Installation | 1cb0a33a-55e0-4890-8686-871458d17b32
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | f2edc11d-034a-5740-a0f8-61ce2009ef08 |  | textbox | SOW description entered
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
label | b7aebcc3-5236-541b-a059-1c52768cb25a |  | note | If any of these checkpoints fail information and required action by builder provided in comments below
checkpoint-status |  |  | checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane (Watertite side) junctions able to accept Type 5 profile?
checkpoint-status |  |  | checkpoint | Installation of Type 5 profile to junction?
checkpoint-status |  |  | checkpoint | Adhesive installed to manufacturer's specification?
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of adhesive
checkpoint-status |  |  | checkpoint | Installation of sheet membrane (min. 50mm overlaps) to ?
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
checklist-flat |  |  | checklist | Leak Remediation |  |  |  |  | Yes | Leak Remediation | c8121bcc-88d1-4e3a-99f3-e68035525780
checkpoint-status |  |  | checkpoint | Locate and identify source of leak
text | 2481d615-6d87-538a-98d8-a8984a3f0ad1 |  | textbox | Enter description and location of leak
button | b9b68fd3-0d9c-515c-b2bb-288da4254e7b |  | button | Can Bravada offer a solution to the leak? | Yes,No
checkpoint-status |  |  | checkpoint | Methodology to resolve leak
text | 204b828a-c3b7-54e5-9a1f-5f3898b920f5 |  | textbox | Enter methodology
label | f71cd974-cad2-5ad6-a5a4-11413ef3903f |  | note | Attach TDS for any products used
checkpoint-status |  |  | checkpoint | Provide photos of completed remediation
button | f644056f-7d91-5260-b27f-5744125dcc8f |  | button | Is ILD testing required? | Yes,No
button | 450135f3-e303-5541-bf94-8f2695e05a18 |  | button | If ILD testing is required, did it pass? | Yes,No,N/A
button | 38db331b-8adf-5cb1-bed3-1b061e92e7d0 |  | button | Has the leak been remediated? | Yes,No
checklist-flat |  |  | checklist | Retaining Wall (Sheet) |  |  |  |  | Yes | Retaining Wall (Sheet) | d125bc12-6b81-4452-b54e-8329025e1eb3
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | bd2ecaf4-f6c3-5713-844a-31d581378dc8 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
button | ae27e60e-049d-5e9e-bc00-842e9667ab99 |  | button | Granules installed at cold joint? | Yes,No,N/A
button | 3fc97ba5-af3f-55b1-b989-184b5b3eeedd |  | button | Installation of sheet membrane as required? | Yes,No
button | 96b13be9-072a-5ae7-bce1-a188e823f842 |  | button | Termination pressure bar installed as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? (Attach photos)
text | e887b86d-1439-5365-bb45-2c90594ad23c |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 5e3a574c-288d-537a-b40e-efded9fcf5e0 |  | button | Cement sheet installed? | Yes,No,N/A
button | bd9ae0c8-0582-5cc0-b246-cf7bef68adc2 |  | button | Corflute installed installed? | Yes,No,N/A
button | f32401ee-515d-5cf8-9444-dfdf8efc4006 |  | button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Backfilled within manufacturer's specified timeframe?
label | e15e78d2-b48b-5ee2-a15e-90127b1f3c6b |  | note | Attach Client Signature Below
checklist-sectioned |  |  | checklist | Fatra Walls |  |  |  |  | Yes | Fatra Walls | c040c331-bbbc-483e-95ee-2a145cd6d486
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | c3b5fd87-b2f2-5d8b-8fc1-240ef1d37e35 |  | textbox | Enter SOW description and attach TDS
checkpoint-status |  |  | checkpoint | Substrate Preparation
text | 8f1ad69f-ba66-51c0-879f-ed5ccafaa855 |  | textbox | Substrate assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Membrane installation
text | 8082483a-a102-54ae-bafd-dcda9a7d872e |  | textbox | Record (Photo) batch number and date of manufacture of all materials
text | 1da0891b-7d73-5c3b-a894-cf603f1bf7a9 |  | textbox | Install Fatrafol 803V PVC membrane
button | 250ffe27-e5ce-56c3-92f8-5a65f09c39be |  | button | Install FatraArmour protection board | Yes/No
button | aebc3b83-6170-57ef-af09-3cd8e39854b9 |  | button | Install Coreflute protection board | Yes/No
text | 0fcd76f5-d7ed-5e13-986e-6f1d7ebcb2f3 |  | textbox | Install PVC termination profile
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
checklist-flat |  |  | checklist | Butynol Installation (External) |  |  |  |  | Yes | Butynol Installation (External) | bdc104a5-2b2d-4540-9879-d430dd4cfd27
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 6dc99cdc-faa2-52aa-8cd3-cb0c8627fa46 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water? (Attach moisture gauge photo)
button | 3fbdef10-c6bd-523b-8f6a-85d7e4cab951 |  | button | Adequate fall in substrate? | Yes,No
label | aa19ec6e-c043-5a97-9554-70401fcd702f |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 92b06a76-965b-5411-9401-bfde9807db56 |  | textbox | Add Comment
button | cb1aac0d-a5f8-5d9d-b84d-2f7a80554648 |  | button | Installation of primer as required? | Yes,No
checkpoint-status |  |  | checkpoint | Substrate free from surface water? (Attach moisture gauge photo)
button | 6fc854fb-1aa3-5fbf-81ca-e9297e4a1a78 |  | button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
button | 288bf048-1697-5794-adb2-1e62ed9e7b37 |  | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
label | 62c5d79a-aa16-565e-8c87-e672785f64c9 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | External (Non-Exposed) |  |  |  |  | Yes | External (Non-Exposed) | c7b76de3-a0fe-4057-bf94-d02d1c31c42e
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 9cdafd14-ff00-581f-9a62-264cb7467b95 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from surface - Moisture gauge photo attached below
button | f69bc01b-d28c-5cf3-bf2b-d2bfd6e82ea8 |  | button | Adequate fall in substrate? | Yes,No
label | ea6f2f7f-cbe2-58a4-adb7-ca59ef80f519 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 1d896c19-a0af-57e8-b214-9b996aa22dcd |  | textbox | Add Comment
button | 52802da8-9083-5d85-ba05-041f077fa2f9 |  | button | Installation of primer as required? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of primer
checkpoint-status |  |  | checkpoint | Substrate free from surface water - photos attached below
button | e1c88a62-4a13-50dd-b783-4c96f2098cee |  | button | Installation of fillets/bandage to junctions as required? | Yes,No
button | b5951553-87e0-54f4-9f34-73e201e58912 |  | button | Installation of base coat? | Yes,No
button | d153b2ad-a9e1-5bc5-b847-1804c9ff3a64 |  | button | Base coat installed to minimum film thickness? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of base coat
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
label | 89035656-ffd3-5a98-a77b-32aa6515b923 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Bentonite - Underslab Membrane (Non-Hydrostatic) |  |  |  |  | Yes | Bentonite - Underslab Membrane (Non-Hydrostatic) | aedfb01e-3ea8-4b7e-9c65-e41e1ab56650
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 7823b74b-8933-5ce1-a21a-13ad01b57af3 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | b8f966f9-1efe-51f3-abc2-552aba65dd42 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
checkpoint-status |  |  | checkpoint | Dewatered
text | 8139d3f3-3584-5f66-9e97-83ada1188a62 |  | textbox | Notes on dewatering for Project Manager
button | ce95436f-afcc-517b-9c6c-21a7e0b7af0b |  | button | Membrane Installed? | Yes,No
select | 5217f3c5-0cf4-5496-a86a-f92684865cc7 |  | dropdown | Minimum lap required | 150mm,200mm
button | 54a3c460-388c-504e-83d0-ed0975adc95e |  | button | Detailing to pile caps | Yes,No,N/A
button | c5f11fdf-ebbf-51a2-b449-efc2a70e5347 |  | button | Detailing of penetrations | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 08aac69c-8776-5f4d-a24b-bdd889b6711d |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 6bc2cf39-7fae-5676-ab4e-7df9adfc7448 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | c4f5574f-956c-54cf-9bec-a80d74fd143c |  | note | Attach Manufacturer's Signature Below
label | 0c24de3e-7588-52a5-97be-34c708663ed9 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Bentonite - Capping Beam Waterstop |  |  |  |  | Yes | Bentonite - Capping Beam Waterstop | 3a8fa130-4869-4d44-9abe-087c08e61805
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | e23c3863-5178-5ef0-ad5e-3bf35def1a22 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 23250503-46af-5100-995d-48175c071220 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 9526201f-c069-50b5-b930-8305dfda774f |  | button | Waterstop installed? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 264e20c9-a1c8-595c-9822-d0e92d9bc7b9 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 72b8eb06-db21-52b7-a865-f85a23c652c3 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | dad277c9-d7e5-5c26-b3e4-2e10203f4d9e |  | note | Attach Manufacturer's Signature Below
label | b1b1f226-bb63-5700-a32c-d3e6cc8cc48e |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Bentonite - Underslab Membrane (Hydrostatic) |  |  |  |  | Yes | Bentonite - Underslab Membrane (Hydrostatic) | 5eda08c9-8f42-43d7-9ccb-abb3a480eca6
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 5d5c04d0-14ea-522b-abe0-45f5d383735b |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 6aba74f9-1db9-566b-b339-506b39844fc1 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
checkpoint-status |  |  | checkpoint | Dewatered
text | 38afa2f2-5a98-5107-8f44-525b4c96aa5e |  | textbox | Notes on dewatering for Project Manager
button | 794f576b-e7b3-5d29-b91d-4bf6f7c79c3f |  | button | Membrane Installed? | Yes,No
select | 83adaa0f-6c64-51fa-b614-080faf889333 |  | dropdown | Minimum lap required | 150mm,200mm
button | 2a326046-c308-51e1-a8ea-c7f3bf5db829 |  | button | Waterstop to pile caps | Yes,No,N/A
button | 47d7a6f5-48d7-5bdb-a7d0-661bfb4507c0 |  | button | Detailing of penetrations | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 3caee4dd-9670-5b01-bb32-d9f387d18ba3 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 8e025066-9b65-526a-ac21-7da10d4a7a0b |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 6ca13afd-657b-5c44-8c89-4f681f7d1233 |  | note | Attach Manufacturer's Signature Below
label | b3f7b342-3283-58f8-8cb7-e50c838e9369 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | PVC Installation (Sarnafil and Cosmofin) |  |  |  |  | Yes | PVC Installation (Sarnafil and Cosmofin) | 9350c59e-6fdc-485e-8611-85a5f46cf85b
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | a24842c1-6839-5ab3-bc79-de779a7aea9e |  | textbox | SOW description entered
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
button | 50c2b7d1-fc5d-519d-8ad6-99e1c413f3f7 |  | button | Adequate fall in substrate? | Yes,No
label | cc4e28ab-6952-55e9-8433-8513d8a51e62 |  | note | If any of these checkpoints fail information and required action by builder provided in comments below
button | 2e3e37f3-0231-5d44-a14a-567d0cd4e841 |  | button | Adhesive installed to manufacturer's specification? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of adhesive
label | cf871860-27b0-574e-9daf-5691153f7fd5 |  | note | If any of these checkpoints fail information and required action by builder provided in comments below
button | 9e204e94-ff4b-51c7-b069-68bdfd57e394 |  | button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No,N/A
button | 8a873277-9ffd-52c5-9636-96a3afb49e74 |  | button | Installation of sheet membrane (min. 50mm overlaps)? | Yes,No
button | 1c9a2e48-224b-556b-8338-47bdfdd0c930 |  | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
checklist-flat |  |  | checklist | Butynol Installation (Internal) |  |  |  |  | Yes | Butynol Installation (Internal) | 99c6c49c-7f20-441c-95fc-a8b44639114f
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | fdba740c-3ad2-5562-850c-784b8e575e13 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
label | a517516d-30cb-51b8-a5ef-d63dba2ffd22 |  | note | If substrate failed please provide information and required action by builder
text | 23b10c1e-05d3-52b0-9d8e-713fdede3c77 |  | textbox | Add Comment
button | bc50826f-6f40-5792-ae0c-1757b1e5505e |  | button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
button | 8a4dd41e-3630-54e0-a416-332b2b7dc709 |  | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
label | 8820a6f5-5957-58f1-824d-bd9131145a91 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Bentonite - PT Slab Wall Junction Termination |  |  |  |  | Yes | Bentonite - PT Slab Wall Junction Termination | ea8c1777-27ed-4a1e-b9e6-ae6ace5bfeba
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 6e9b8646-de21-5c24-a017-0e8699a25264 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 3b67dcc4-9a39-5907-ac8b-74d2cbda5775 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | c51b238e-dfd7-5fbc-9adf-d83e8b440214 |  | button | Waterstop installed? | Yes,No
button | 832a0be4-b411-5c18-9129-8720ecfc9641 |  | button | Termination bar installed? | Yes,No,N/A
button | 81a30ed1-03b8-50b2-a5e0-722254503313 |  | button | Bentoseal installed? | Yes,No,N/A
button | e14c8e6a-0491-5c98-b58b-adaff04ccf20 |  | button | Cetinject installed? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 638a3856-62d4-565a-922a-bccd5eb7306d |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 16c4889d-8a80-536e-a26c-f9ec2c68b755 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 2e25e2b2-e694-5ea4-ac53-cb1b90e4444c |  | note | Attach Manufacturer's Signature Below
label | 8b26d37f-d643-5bf4-9a87-249265c641bd |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | PVC Installation (Wolfin) |  |  |  |  | Yes | PVC Installation (Wolfin) | e7863054-93cd-4fd6-b82f-35cd97b0b799
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 5e87aaf3-848d-54dc-aed4-fb299b5d3e1f |  | textbox | SOW description entered
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint-status |  |  | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water, and adequate fall in substrate (Moisture gauge photo attached below)
label | ab2e9244-5b07-5e30-9e9c-5a192118bbed |  | note | If any of these checkpoints fail information and required action by builder provided in comments below
button | 0154b2c6-7140-5524-9aba-64f5bdb912ef |  | button | Bitunamel primer installed to manufacturer's specification? | Yes,No
button | b1a1edef-d018-52b0-b69f-5f84a94f4917 |  | button | Bitunamel primer given adequate time (4 hours) to cure – as per manufacturer's specification? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch numbers and dates of manufacture of bitunamel primer
checkpoint-status |  |  | checkpoint | Area primed and suitable for membrane application. Substrate free of contaminants - photos attached below
text | 71ddeaa2-c7f8-5ae8-a125-df17c8d31eb0 |  | textbox | If inspection failed, please provide reasons and recommended course of action
button | 43afe1ca-b3d2-5fc3-a48e-f0a2f54c5e0b |  | button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No,N/A
button | 4b655e9d-8d96-58e7-a62c-fd139265f701 |  | button | Installation of sheet membrane (min. 50mm overlaps)? | Yes,No
button | 870274a2-8afd-53fc-a7ea-931fbf24eb93 |  | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 0e2e8602-7fa9-5e2f-bb20-775f7eeac4a9 |  | note | Manufacturer's Warranty Certificate attached below
checklist-flat |  |  | checklist | Bentonite - Strip/Pad Footings (Hydrostatic) |  |  |  |  | Yes | Bentonite - Strip/Pad Footings (Hydrostatic) | 3ec7a42a-9583-44ec-b25f-1235e42b57c1
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | a72017de-09cc-558c-9848-3090ee7c6b03 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 8be87338-cf3c-53c0-8b5e-a8885f5c87f1 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
checkpoint-status |  |  | checkpoint | Dewatered
text | bd97c8b7-135a-516b-a629-d099864cc249 |  | textbox | Notes on dewatering for Project Manager
button | 747122e0-130c-5c21-9236-96e67e9488d6 |  | button | Granules to perimeter? | Yes,No
button | baba0ae6-9ad7-5398-aeed-7748abe49194 |  | button | Membrane Installed? | Yes,No
select | 70e62807-d2b7-5479-82ee-9dd7e5b64d21 |  | dropdown | Minimum lap required | 150mm,200mm
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | bc1fc3d0-b08f-56a6-8ddb-ee52ccdb1121 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 1e97c4f9-929d-5525-b280-6b243abb1281 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 16fdeee3-0e28-56c0-971a-423fd5a8ca12 |  | note | Attach Manufacturer's Signature Below
label | 1c7cfd90-92b9-5587-8337-5633bfc56b7b |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Torch-On Installation |  |  |  |  | Yes | Torch-On Installation | 69424b12-9600-4d79-860a-e028b8243c46
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | d220d04b-c396-5512-a5c7-30991ea9e57d |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
button | 121b9edb-af20-5e98-ad90-0202333ac2d6 |  | button | Adequate fall in substrate? | Yes,No
button | eee796fc-cb76-54e8-b9d0-3a7362804ccc |  | button | Bitumen primer installed to manufacturer's specification? | Yes,No
button | 43e05bc0-a958-5eea-92b0-7490f58b8e23 |  | button | Primer given adequate time to cure – as per manufacturers specification? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed and suitable for membrane application - photos attached below
checkpoint-status |  |  | checkpoint | Substrate clear of dust, debris and contaminants - photos attached below
checkpoint-status |  |  | checkpoint | Substrate free from surface water? (Moisture gauge photo attached below)
button | 468068ea-86d3-5ba6-a2f1-93241294c350 |  | button | Installation of base layer membrane (min. 50mm overlaps) ? | Yes,No
select | da69695a-e9db-5e18-9787-cc0fbd4946a7 |  | dropdown | Type of second layer | Normal,Mineral,Antiroot
button | a11ea690-2aa9-5555-bb80-81a36dc94c05 |  | button | Installation of second layer membrane (min. 50mm overlaps) ? | Yes,No
button | 2f16b0d9-7fcb-5c04-bba6-4badca2e001b |  | button | Termination pressure bar installed to all upturns where required? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification? - photos attached below
label | bf630246-37ce-58b2-904e-699c1b348510 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Eradix (Backfilled Downturns) |  |  |  |  | Yes | Eradix (Backfilled Downturns) | a8b29387-84b7-46c2-bbbe-8fbd702ba49f
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 262c072e-f20f-5553-9cfb-2832106a2cdb |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Diaphragm Wall Preparation
button | 519e7f42-7aff-5d66-bfac-4ee097eb6d59 |  | button | Transition compound to D-Wall installed as per manufacturer's specification | Yes,No
checkpoint-status |  |  | checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
button | d97923e7-6cab-5e9d-9541-1d9c871d0016 |  | button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
button | bc8b2226-32ce-518f-be88-1e7ec09585b6 |  | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
button | 9f33d685-58a1-5224-955e-7b585d71c83b |  | button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
checkpoint-status |  |  | checkpoint | Priming
label | 78b46b01-8cf2-51ab-8dec-13fd61cad1b1 |  | note | Record batch numbers
button | 32653558-0436-5349-8b1e-2c20587246c3 |  | button | Dermaprimer installed to manufacturer's specification - photos attached below | Yes,No
button | 9bbdf920-c6c6-57df-89ee-5e21c4ffde90 |  | button | Primer given adequate time to cure as per manufacturers specification | Yes,No
button | 68497c8a-5ed4-5ddd-ae17-a04269f0cd5f |  | button | Area completed and suitable for membrane application - photos attached below | Yes,No
checkpoint-status |  |  | checkpoint | Eradix Installation
label | 1ef6aeef-dee7-59c1-af9f-273284ed7e05 |  | note | Record batch numbers
button | 782f94c7-ea0b-5de6-9f53-572ffbf98a81 |  | button | Substrate clear of dust, debris and contaminants - photos attached below | Yes,No
button | cbb5c353-e48c-5701-a2c7-40590c4dd837 |  | button | Installation of base layer membrane (min. 100mm overlaps) - photos attached below | Yes,No
button | 8e99c39c-cfae-5c88-9dfa-47d024b8963c |  | button | Termination pressure bar installed where required- photos attached below | Yes,No
checkpoint-status |  |  | checkpoint | ILD Testing
button | 87e9195e-2365-5249-9e37-597b36c83d9b |  | button | ILD test requested | Yes,No
button | e65c5adc-621e-5390-8ab7-6d4e8af6951e |  | button | ILD test performed | Yes,No
text | f7293006-b20d-59ee-ae8f-4c3286f2eec7 |  | textbox | Any rectifications performed
button | 97a50da0-40f1-5c24-8d28-9e731d18d90c |  | button | ILD test report issued | Yes,No
checkpoint-status |  |  | checkpoint | Protection
button | 562202d8-9c34-59e8-a26f-0cd03bf785a2 |  | button | Casali Protector installed - photos attached below | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
label | f196104a-7cba-5767-baba-3ed0a421acd5 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Bentonite - Shotcrete Wall Membrane |  |  |  |  | Yes | Bentonite - Shotcrete Wall Membrane | 65d2e8c0-4d6c-42b9-a510-c899b16d5314
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 807d2ddf-a8d1-5253-873a-e38c63d2b0cc |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 78c21440-9a7d-5d84-8045-c3b311d261be |  | textbox | If inspection failed, please provide reasons and recommended course of action.
select | 24f3f366-f752-53a1-8078-b0ceb637d9dd |  | dropdown | Join Coverage | 50mm,75mm,100mm,50-100mm
button | 0d786c86-b748-52e6-8c29-ac1f4c1d18e9 |  | button | Capping Beam Part Of Installation? | Yes,No
button | 83694976-b33f-5b98-add1-f6d1f1aa1f62 |  | button | Capping Beam Waterstop Installed? | Yes,No
select | dd3b011a-78e7-5d5a-91fe-216f6c67278c |  | dropdown | Waterstop Type | RX-102,Akwaswell,Both
button | 51feb509-2db7-58f9-a8b6-b56c072757c3 |  | button | Waterstop to drop join installed ? | Yes,No,N/A
button | 878f19cd-4085-5ce7-96b3-252333dabe34 |  | button | Detailing of penetrations | Yes,No,N/A
button | ecd894a8-f68e-5a9f-9439-f31c9813ee8c |  | button | Membrane Installed? | Yes,No
select | 035a9248-f827-56a5-a190-8f9eaf316940 |  | dropdown | Minimum lap required | 150mm,200mm
checkpoint-status |  |  | checkpoint | Starter bars detailed
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 87910686-9f5b-5520-b8b3-e943aa335846 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
label | 7401e2a9-8cd3-51b4-910e-2711d8c42e57 |  | note | Attach Manufacturer's Report Below
checklist-flat |  |  | checklist | Control Joints |  |  |  |  | Yes | Control Joints | cffd06c6-c223-4455-8515-b588af1b68a6
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 79301476-5a91-51f2-87a7-f1c5fe195d99 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Channel cut to sufficient width
text | af095250-1167-5223-8e7c-413956204204 |  | textbox | Enter width
checkpoint-status |  |  | checkpoint | Polyurethane caulk applied to channel
checklist-flat |  |  | checklist | Dermafil (Concrete Lid) |  |  |  |  | Yes | Dermafil (Concrete Lid) | 58e94a7f-a013-44ce-ad52-f08fb15444a8
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | cca6913e-fb5b-55c6-93d6-29493708f733 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
button | a86744d1-63ac-5c78-95e5-67bbc2baf2ad |  | button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
button | 48dc42fc-4175-5212-8dcd-385f9f69f2e4 |  | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
button | 8d29f25e-117b-5056-80fd-e6cb2a896c33 |  | button | Substrate free from pooling or ponding water | Yes,No
button | 7d4e00a7-a4df-55b6-91d2-8f1096746d7e |  | button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
button | b317272a-d287-5054-8966-8b0b8e4990ee |  | button | Adequate fall in substrate | Yes,No
checkpoint-status |  |  | checkpoint | Priming
label | 0aec156f-1625-50fa-8e47-81183cc345f7 |  | note | Record batch numbers
button | a6339416-d7b0-59ed-8279-06d758703004 |  | button | Dermaprimer installed to manufacturer's specification - photos attached below | Yes,No
button | 3058dc84-bdd9-58b3-91c5-cd489c662a50 |  | button | Primer given adequate time to cure as per manufacturers specification | Yes,No
button | 75b90a27-fd14-5418-bf98-42379c758493 |  | button | Area completed and suitable for membrane application - photos attached below | Yes,No
checkpoint-status |  |  | checkpoint | Dermafil Installation
label | 56cbf7c5-501e-51e6-946f-c16b8956151f |  | note | Record batch numbers
button | 910b7b5f-e194-5442-8061-3ec7493db1eb |  | button | Substrate clear of dust, debris and contaminants - photos attached below | Yes,No
button | b5ad3662-d35d-5e5c-a6d6-6dfd162a35ee |  | button | Installation of base layer membrane (min. 100mm overlaps) - photos attached below | Yes,No
button | 7fce1b43-16af-57af-b3df-10edbe109ff9 |  | button | Termination pressure bar installed where required - photos attached below | Yes,No
checkpoint-status |  |  | checkpoint | ILD Testing
button | 9b78a4c4-0334-5b26-bdb4-95cb762b598a |  | button | ILD test requested | Yes,No
button | acba65c0-0eda-50c7-9874-00414504f247 |  | button | ILD test performed | Yes,No
text | b01e44e0-617f-59ac-a998-3bd4c2cbbc35 |  | textbox | Any rectifications performed
button | 55574ec3-34dc-52de-b15b-134f6c2e5f13 |  | button | ILD test report issued | Yes,No
checkpoint-status |  |  | checkpoint | Protection
button | 0f632de3-d252-5a89-baec-0a4aaefc45ec |  | button | Casali Protector installed - photos attached below | Yes,No
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
label | 55e980be-0b47-5561-ae4e-c5822f9f0160 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Floor Coatings |  |  |  |  | Yes | Floor Coatings | 99d711c5-ecff-4d6c-bda1-d3de3a725025
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 3f26cada-e56b-584c-8dcb-1536b6470f73 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate to be cleaned, mechanically grinded & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less then 5*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
button | ce8a85ac-a492-5a15-b7aa-33aad1d29bc9 |  | button | Adequate fall in substrate? | Yes,No
label | fb6c15f0-f9a3-5405-bbf7-2db45d72213d |  | note | If any of these checkpoints fail please provide information and required action by builder
text | 703ec741-71ab-5a4e-8496-b721de9b1c95 |  | textbox | Add Comment
button | 39022404-8c57-5cc7-9f41-4c816e758b86 |  | button | Installation of epoxy primer? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of primer
checkpoint-status |  |  | checkpoint | Substrate free from surface water?
button | 5e2aad06-60aa-51a4-927d-654f2d161d0e |  | button | Construction joints marked for mirroring after application? | Yes,No,N/A
button | 4819f37d-f025-5486-8628-cbeb76111e21 |  | button | Installation of base coat? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of base coat
button | 8bc5e7d6-77f3-5cc2-89cb-1eb88d579c2f |  | button | Broadcast of non-slip application if required | Yes,No,N/A
button | f170ef3f-2982-5fbc-80c8-244ca6a4d027 |  | button | Installation of top coat (UV stable if required)? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of top coat
button | c6d4c1e6-ac84-5fd8-8604-3c12d9b7d7c4 |  | button | Chase out onstruction joints and caulk? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
label | ce4d57fa-7f27-5142-a0f3-3aef7126876e |  | note | Add Comment
label | ac965013-4f0e-5fe8-9a78-e6cd4885b163 |  | note | Attach Client Signature Below
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | Handover | aa9bb1f3-2b04-4200-bd6b-f139e83df835
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 3b38f2ae-4fbf-5eba-a72e-17576cf2ec03 |  | textbox | SOW description entered
label | f5e5e7e0-7d19-555d-897d-aa0b47fcdb62 |  | note | Bravada and Client Representative name/(s) and signature/(s) attached below
checklist-flat |  |  | checklist | VerseSeal (Exposed) |  |  |  |  | Yes | VerseSeal (Exposed) | 58146530-11d5-4924-bb70-3fc94808e941
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 6f06d353-3dd6-5bf7-96b4-d75dbad1d3b0 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
label | a3c34d00-a293-5232-8c95-9323634dae25 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | de69f744-6ffd-50cc-9821-bd6ee42cdec1 |  | textbox | Add Comment
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of primer
button | 8d35f484-c9a5-5ac5-9ec0-280ec61875d8 |  | button | Installation of primer as required (90 minute dry time)? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of base coat
button | 9c2b8149-c2f9-50fc-bdbd-d9cb088447ea |  | button | Installation of base coat within required maximum curing time of primer (2kg per m2 or 7.5m2 per 15kg pail)? | Yes,No
button | db4fdae4-d6d8-5bf9-8f01-6d801ed461bf |  | button | Base coat installed to minimum film thickness? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of top coat
button | 8f1a8f9f-e0cc-51b5-9104-e848401bb9d7 |  | button | Installation of top coat (4kg per m2 or 3.75m2 per 15kg pail)? | Yes,No,N/A
button | ad89507b-1c01-5d23-8473-5fdce70b2618 |  | button | Top coat installed to minimum film thickness? | Yes,No,N/A
button | e9429f72-8586-5f99-bd58-a1c83787ab81 |  | button | Broadcast of 7mm Basalt Scoria into wet / uncured liquid rubber (trowel scoria into liquid rubber 50% depth)? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
checkpoint-status |  |  | checkpoint | BARPA inspection & sign off (project completion)
checklist-flat |  |  | checklist | External (Exposed) |  |  |  |  | Yes | External (Exposed) | 585469a7-a333-48af-b705-fe416932a98b
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | d28a7764-9542-5c8d-8808-0e24012aec8b |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Attach TDS for application (Download from Simpro)
checkpoint-status |  |  | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
checkpoint-status |  |  | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
checkpoint-status |  |  | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
button | 7fc11175-5e68-592f-9a08-ddd5f7eeb7b4 |  | button | Adequate fall in substrate? | Yes,No
label | f8ed1ef4-afc4-5601-b139-1a2c67988105 |  | note | If any of these checkpoints fail please provide information and required action by builder
text | d4446a5c-1929-51f9-8a74-0f234ccca01e |  | textbox | Add Comment
button | b462a3d0-8373-5ab9-b9ee-895a55df48a1 |  | button | Installation of primer as required? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of primer
select | 819686ac-ab1b-5a68-b684-df1d9012436a |  | dropdown | Curing time for primer (hours) | 6,12,18,24
checkpoint-status |  |  | checkpoint | Substrate free from surface water - Moisture gauge photo attached below
button | b85b128d-cae0-51c9-b535-a234c792ad07 |  | button | Installation of fillets/bandage to junctions as required? | Yes,No
button | 462de1b6-b119-54de-b736-6f75a46a778e |  | button | Installation of base coat within rquired maximum curing time of primer? | Yes,No
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of base coat
button | ef7a5954-54f7-5ac7-a69b-dbf5d57377b1 |  | button | Base coat installed to minimum film thickness? | Yes,No
button | 672970c9-996a-5f5b-b80e-25f723705934 |  | button | Installation of UV-stable top coat? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Record (Photo) batch number and date of manufacture of top coat
button | 00c50874-66dd-5c4e-967d-a5f62f45e2f7 |  | button | Top coat installed to minimum film thickness? | Yes,No,N/A
button | b5bce0d6-63a2-572c-8c9e-5d0fd89efc84 |  | button | Broadcast of 30/60 quartz if trafficable? | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
checklist-flat |  |  | checklist | ILD Testing |  |  |  |  | Yes | ILD Testing | 31a98a89-a627-4ebc-a506-40f38981d51e
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 18316e6c-f288-5b53-add2-59f9e7bc75b3 |  | textbox | SOW description entered
button | 947c8c9c-3d16-53a4-8bc9-171e68c683c5 |  | button | ILD Test Requested? | Yes,No
button | 32bb3202-947f-5d37-bf1c-7737096492c0 |  | button | ILD Test Performed | Yes,No
checkpoint-status |  |  | checkpoint | ILD Test
label | a7d46359-d914-5d09-9434-ad143437f7b3 |  | note | ILD technician signature attached below
label | fb9ff672-0620-5cc0-bcd4-758d7e8b0e77 |  | note | ILD report attached below
checklist-flat |  |  | checklist | Bentonite - Dewatering Wells |  |  |  |  | Yes | Bentonite - Dewatering Wells | f81fd71b-e80e-42c0-96bb-b0096019f1ac
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 0ab407d1-7b97-54ff-81f8-3b5c463ef208 |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 6d4507dd-d2e4-5c66-928a-96aaa67453fb |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | cf43e0b8-3d1c-54c9-8aab-512f4b2429ed |  | button | PureGold Chips Installed | Yes,No
button | 6133f56e-e57f-5f70-a6be-ac93ac5523d2 |  | button | Builder installed Concrete Grout | Yes,No
button | af11c48a-9d7a-5d77-931f-f4dd154f6403 |  | button | Membrane Installed? | Yes,No
button | 8943eb3b-e178-564d-8b8d-cef65d68f9d6 |  | button | Waterstop installed? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 5e8f4f8f-9a1f-55c9-a683-b9b02ef24e41 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | a73effa1-314b-588f-9ee1-3e4367fad00b |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | a0cff7dd-2884-5e76-985c-b8774bc9f2ee |  | note | Attach Manufacturer's Signature Below
label | ae57e7b4-63c9-5dfe-b86d-57e577aa690f |  | note | Attach Manufacturer's Report Below
checklist-sectioned |  |  | checklist | Fatra Underslab |  |  |  |  | Yes | Fatra Underslab | 59626d8e-e598-4e98-951f-20afc306cf90
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 4fd8b23c-5741-5f5a-8704-f5a91ce4d594 |  | textbox | Enter SOW description and attach TDS
checkpoint-status |  |  | checkpoint | Substrate Preparation
text | 4b5b5cd9-0259-52fa-a7b8-c0b1d6f73cd1 |  | textbox | Substrate assessed for surface uniformity - photos attached below
text | e6b3c568-a5af-51d3-b875-079311fc92b7 |  | textbox | Substrate free from pooling, ponding of flowing water
checkpoint-status |  |  | checkpoint | Membrane installation
text | 92849ad1-40bc-59f2-9c9d-5cdc9755ac29 |  | textbox | Record (Photo) batch number and date of manufacture of all materials
text | ca3955f1-df65-53a9-b959-1f4408899297 |  | textbox | Install Fatratex geotextile fabric
text | 590592b9-ffa7-57aa-81b7-5777b400422c |  | textbox | Install Fatrafol 803V PVC membrane
text | e488ba1b-661a-52cb-a21a-f76542fb31b3 |  | textbox | Install Fatrafol 803V reinforcement PVC membrane to slab/wall junction
text | 7bc2f05c-1e96-5b06-a3a3-8944722701c5 |  | textbox | Install FatraArmour protection board
checkpoint-status |  |  | checkpoint | Area completed to manufacturer's specification - photos attached below
checklist-flat |  |  | checklist | Bespoke Task |  |  |  |  | Yes | Add Bespoke Task | c50d11ae-0e5a-449f-ad82-65c014528368
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 13672680-43c2-5fbf-9b90-beacfc406d47 |  | textbox | Enter SOW description
button | 13ab94a7-67c1-51f9-a096-4cf077f00eef |  | button | Warrantable Works | Yes, No
text | d3294e6f-2eca-5338-a20b-3853ecfd380f |  | textbox | Notes Relating To Works Performed
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
checklist-flat |  |  | checklist | Bentonite - Wall / Slab Junction |  |  |  |  | Yes | Bentonite - Wall / Slab Junction | 1006e06c-7ddb-4aeb-b28a-6d934b13b919
checkpoint-status |  |  | checkpoint | Scope Description (from Bravada SOW) and item numbers
text | 562f5c13-adff-5175-9e62-6f21a6474c7e |  | textbox | Enter SOW description
checkpoint-status |  |  | checkpoint | Substrate suitable for application
text | 1c05c36c-d15d-5824-807b-de561507c110 |  | textbox | If inspection failed, please provide reasons and recommended course of action.
select | c8788c95-e324-5600-9fc8-9312d51f8e2c |  | dropdown | Slab Thickness | <450mm,>=450mm
select | f087d916-e39a-5776-a62c-45e29d1e2adf |  | dropdown | No. of waterstops to install | 1,2
button | 335b2842-0c56-5efe-93d1-5306e4c233d2 |  | button | Waterstop installed? | Yes,No
button | e8896aac-b439-5954-bbac-f0a42010875d |  | button | Granules to junction? | Yes,No
button | 2790ebeb-4606-50ac-a01c-5661f74bb770 |  | button | Akwaswell to lowest 2 laps? | Yes,No
checkpoint-status |  |  | checkpoint | Area completed - photos attached below
text | 42e19aeb-2fc1-5b41-8860-cac511e1adab |  | textbox | If inspection failed, please provide reasons and recommended course of action.
button | 4b8febfa-0d9f-50ae-aecf-3c867808cd69 |  | button | Manufacturer Inspection Requested? | Yes,No
checkpoint-status |  |  | checkpoint | Manufacturer Inspection
label | 9069bf98-9d35-5444-b547-68b747bb4460 |  | note | Attach Manufacturer's Signature Below
label | 33fa6737-9fdc-5e78-9072-2c635bc8eba7 |  | note | Attach Manufacturer's Report Below