## Project Structure EG (hidden)
Folder Structure |  |  |  | Checklists
Site QA
Switchboards
S1
|  |  | S.1 Assembly | QA_TEM_013_Switchboard & Distribution Board Assembly
|  |  | S.1 Installation | QA_TEM_012_Switchboard & Distribution Board Installation
|  |  | S.1 Cable Termination | QA_TEM_014_Cable Terminations
|  |  | S.1 Accessories | QA_TEM_015_Accessories Installation
|  | S2 |  | Same as S1
|  | S3 |  | Same as S1
|  | S4 |  | Same as S1
|  | S5 |  | Same as S1
|  | S6 |  | Same as S1
|  | S7 |  | Same as S1
|  | S8 |  | Same as S1
|  | S9 |  | Same as S1
|  | S10 |  | Same as S1
Cable Support
Room 1
|  |  | Prior | QA_TEM_008_Cable Support Prior to Cabling
|  |  | Post | QA_TEM_009_Cable Support Post Cabling
|  | Room 2 |  | Same as per Room 1
|  | Room 3 |  | Same as per Room 1
|  | Room 4 |  | Same as per Room 1
|  | Room 5 |  | Same as per Room 1
|  | Room 6 |  | Same as per Room 1
Emergency Lighting
|  | Room 1 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 2 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 3 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 4 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 5 |  | QA_TEM_023_Emergency & Exit Lighting
|  | Room 6 |  | QA_TEM_023_Emergency & Exit Lighting

## Project Structure
AIDP Ripley Sub-Acute Site QA
In-Ground Services Install
In-Ground Services Install - Zone 1
QA_TEM_004_Trench and Backfill
QA_TEM_005_Underground Conduit Installation
QA_TEM_081_Cable Pit Installation
In-Ground Services Install - Zone 2
AS ABOVE
In-Ground Services Install - Zone 3
AS ABOVE
In-Ground Services Install - Temps
QA_TEM_004_Trench and Backfill
QA_TEM_005_Underground Conduit Installation
In Slab Services Install
Cast in Conduit Installation - Level 00 - Pour 1
QA_TEM_007_Cast in Conduits Installation
Cast in Conduit Installation - Level 00 - Pour 2
AS ABOVE
Cast in Conduit Installation - Level 00 - Pour 3
AS ABOVE
Cast in Conduit Installation - Level 01 - Pour 1
AS ABOVE
Cast in Conduit Installation - Level 01 - Pour 2
AS ABOVE
Cast in Conduit Installation - Level 01 - Pour 3
AS ABOVE
Cast in Conduit Installation - Level 02 - Pour 1
AS ABOVE
Cast in Conduit Installation - Level 02 - Pour 2
AS ABOVE
Cast in Conduit Installation - level 02 - Pour 3
AS ABOVE
Cast in Conduit Installation - Stair 1
AS ABOVE
Cast in Conduit Installation - Stair 2
AS ABOVE
Cast in Conduit Installation - External slabs
AS ABOVE
Cast in Conduit Installation - Outbuildings
AS ABOVE
Equipotential Bonding
Equipotential Bonding - Level 00 - Pour 1
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Level 00 - Pour 2
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Level 00 - Pour 3
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Level 01 - Pour 1
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Level 01 - Pour 2
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Level 01 - Pour 3
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Level 02 - Pour 1
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Level 02 - Pour 2
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - level 02 - Pour 3
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Stair 1
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Stair 2
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - External slabs
QA_TEM_079_Equipotential Bonding
Equipotential Bonding - Outbuildings
QA_TEM_079_Equipotential Bonding
Cable Tray Installation
Cable Tray Installation - Level 00
QA_TEM_008_Cable Support Prior to Cabling
Cable Tray Installation - Level 01
AS ABOVE
Cable Tray Installation - Level 02
AS ABOVE
Cable Tray Installation - Outbuildings
AS ABOVE
Fire Sealing
Fire Sealing - Level 00
QA_TEM_017_Fire Sealing
Fire Sealing - Level 01
AS ABOVE
Fire Sealing - Level 02
AS ABOVE
Fire Sealing - Outbuildings
AS ABOVE
Lightning Protection
Lightning Protection
QA_TEM_029_Lightning Protection
Luminaires
Pole 1
QA_TEM_020_Lighting Poles
Luminaires
Pole 2
QA_TEM_020_Lighting Poles
MSB
MSB - SMSB-1
QA_TEM_003_Earth Electrode
QA_TEM_012_Switchboard & Distribution Board Installation
QA_TEM_011_Mains & Submains Installation
QA_TEM_014_Cable Terminations
Final Installation Checklist
MSB - SMSB-2
AS ABOVE
MSB - MDB-SA-1
QA_TEM_012_Switchboard & Distribution Board Installation
QA_TEM_011_Mains & Submains Installation
QA_TEM_014_Cable Terminations
Final Installation Checklist
MSB - MDB-SA-2
AS ABOVE
MSB - MSB-SHP
QA_TEM_003_Earth Electrode
QA_TEM_011_Mains & Submains Installation
QA_TEM_014_Cable Terminations
MSB - MSB-CP
QA_TEM_011_Mains & Submains Installation
QA_TEM_014_Cable Terminations
DB
DB - DB-FPR
QA_TEM_012_Switchboard & Distribution Board Installation
QA_TEM_014_Cable Terminations
Final Installation Checklist
DB - DB-WPR
AS ABOVE
DB - DB-SUB
AS ABOVE
DB - DB-SMSB
AS ABOVE
DB - DB-PFC
AS ABOVE
DB - DB-UPS
AS ABOVE
DB - DB-H1
AS ABOVE
DB - DB-LG-1-E
AS ABOVE
DB - DB-LG-2-E
AS ABOVE
DB - DB-L1-1-E
|  |  | AS ABOVE |  | `
DB - DB-L1-2-E
AS ABOVE
DB - DB-L2-1-E
AS ABOVE
DB - DB-L2-2-E
AS ABOVE
DB - DB-LG-C-E
AS ABOVE
DB - DB-LG-K-NE
AS ABOVE
DB - DB-LG-1-NE
AS ABOVE
DB - DB-LG-2-NE
AS ABOVE
DB - DB-L1-1-NE
AS ABOVE
DB - DB-L1-2-NE
AS ABOVE
DB - DB-L2-1-NE
AS ABOVE
DB - DB-L2-2-NE
AS ABOVE
UPS
DB - DB-LG-1-U
QA_TEM_012_Switchboard & Distribution Board Installation
QA_TEM_014_Cable Terminations
Final Installation Checklist
DB - DB-LG-2-U
AS ABOVE
DB - DB-L1-1-U
AS ABOVE
DB - DB-L1-2-U
AS ABOVE
DB - DB-L2-1-U
AS ABOVE
DB - DB-L2-2-U
AS ABOVE
DB - DB-LG-C-U
AS ABOVE
Electrical Services
Level 00
Kitchen 0.4.006
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bulk Store/ Materials Management 04.005
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Loading Dock/Clean 0.4.004
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Body Hold 0.4.002
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet Accessible 0.4.003
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Loading Dock/Dirty 0.4.008
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store/Dirty Linen 0.4.009
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cleaners Room 10m2 0.4.013
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office/Write Up 5m2 0.4.053
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Airlock/Entry 0.4.012
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store/Clean Linen 0.4.011
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Communications Store 0.E.014
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Comms Room L00 0.E.015
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office/2 Person 0.4.014
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Central Equioment Store 0.4.010
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store/Equipment 30m2 0.2.048
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store/Pharmacy 0.4.015
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Pathology 0.4.016
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Staff Change Male 0.4.001
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Staff Change Female 0.4.000
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
2 Bed Room - Inboard Ensuite Type 2 0.2.000
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
2 Bed Room - Inboard Ensuite Type 2 0.2.003
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite Type 2 0.2.004
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite Type 2 0.2.007
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite Type 2 0.2.008
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
4 Bed Room - Inboard Ensuite 0.2.011
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite Type 2 0.2.014
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Lounge/ Patient Family 30m2 0.2.015
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room Bariatic 0.2.063
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room Bariatic 0.2.062
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite Type 2 0.2.059
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Independent Assessment Suite 0.2.049
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room Bariatic 0.2.054
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room Bariatic 0.2.051
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room Bariatic 0.2.055
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Disposal Room 10m2 0.2.043
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store/General 0.2.046
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cleaners Room 5m2 0.2.047
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet Staff 0.2.045
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Interview Room 0.2.036
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet/Accessible 0.2.037
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Clean Store 10m2 0.2.069
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Dirty Utility 14m2 0.2.035
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Clean Utility/Medication Room 0.2.034
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Staff Station 14m2 0.2.033
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office 1 Person/NUM 0.2.031
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office/Clinical Workroom 0.2.030
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Comms Room L00 0.E.009
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Dining/Recreation Therapy Room 0.2.028
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Store/Gas 0.4.017
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor/Patient Treatment Areas 0.T.001
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor/Patient Treatment Areas 0.T.002
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor/Patient Treatment Areas 0.T.006
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor/Patient Treatment Areas 0.T.007
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor/Patient Treatment Areas 0.T.010
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor/Patient Treatment Areas 0.T.012
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor/Patient Treatment Areas 0.T.014
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor/Patient Treatment Areas 0.T.015
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
2 Bed Room - Inboard Ensuite Type 2 0.2.017
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite Type 2 0.2.018
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Store/Equipment 0.3.019
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Consult Room 0.3.017
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Toilet/Accessible 0.3.018
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Office /Write up 5m2 0.3.021
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Gymnasium/Group Therapy 0.3.016
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Occupational Therapy Room 0.3.013
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Airlock/Entry 0.1.000
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Waiting/Entry Foyer 0.1.001
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Café/Retail 0.1.002
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Indigenous Health Liaison Office 0.1.010
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Quiet Room 0.1.003
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Multi Purpose Room 0.1.004
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
1 Bed Room - Inboard Ensuite Type 2 0.2.066
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite Type 2 0.2.067
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Laundry/Patient 6m2 0.2.020
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Staff Station 10m2 0.2.021
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Consult Room 0.3.001
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Consult Room 0.3.003
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Toilet/Accessible 0.1.005
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Parenting Room 0.1.006
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet/Public 0.1.007 & 0.1.008
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Reception 10m2 0.1.009
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Interview Room/Allied Health 0.3.004
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Interview Room/Allied Health 0.3.005
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Workstation 0.3.006
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Interview Room/Allied Health 0.3.008
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
ADL Bathroom 0.3.007
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
ADL Kitchen 0.3.010
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Electronic Distribution Board 0.E.013
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Electronic Distribution Board 0.E.012
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay/Workastation on Wheel 0.2.042
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay/Linen 0.2.044
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Linen 0.2.022
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Mobile Equipment 0.2.025
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay Photocopy/Stationary 0.2.023
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing Type B 0.2.024
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Meal Trolley 4m2 0.2.029
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing Type B 0.2.026
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Electronic Distribution Board 0.E.003
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store Equipment 14m2 0.3.000
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
[5 empty] | QA_TEM_082_Room Checklist | `
Level 01
Plant Room 1.E.011
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Electronic Distribution Board 1.E.010
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
GEM Terrace 1.1.072
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Therapy / Multipurpose Room 1.1.000
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite - Type 2 1.1.002
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite - Type 2 1.1.003
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite - Type 2 1.1.006
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite - Type 2 1.1.007
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite - Type 2 1.1.003
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
4 Bed Room - Inboard Ensuite 1.1.010
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite - Type 2 1.1.013
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite - Type 2 1.1.014
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Dining / Recreation / Therapy Room 1.1.029
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Comms Room 1.E.007
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Workstation on Wheels 1.1.031
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Beverage, Open Plan 4m2 1.1.028
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing, Type B 1.1.027
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office - 1 Person NUM 1.1.033
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office - Clinical Workroom 1.1.032
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Staff Station 14m2 1.1.035
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Clean Utility / Medication Room 1.1.036
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Dirty Utility 14m2 1.1.037
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Interview Room 1.1.038
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet - Accessible 1.1.039
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Clean Store 10m2 1.1.040
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Disposal Room 10m2 1.1.042
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cleaners Room 5m2 1.1.043
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet - Staff 1.1.040
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store - General 1.1.045
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Linen 1.1.046
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing Type B 1.1.047
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing Type B 1.1.048
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Mobile Equipment 1.1.044
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Electronic Distribution Board 1.E.008
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Plant Room 1.E.012
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store - Equipment 20m2 1.1.049
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.050
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.053
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.054
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.057
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.058
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.061
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.062
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.065
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Lounge - Patient / Family 20m2 1.1.066
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.068
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Inboard Ensuite, Type 2 1.1.069
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Meeting Room 20m2 1.2.009
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Breakout Room 1.2.008
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Breakout Room 1.2.007
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Workstations 1.2.000
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office 2 Person 1.2.010
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office 2 Person 1.2.011
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office 2 Person 1.2.012
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office 2 Person 1.2.013
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store - Photocopy / Stationery 8m2 1.2.001
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Meeting Room 30m2 1.2.014
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office 1 Person 1.2.015
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet - Accessible 1.2.004
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Toilet - Accessible 1.2.006
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Staff Room 1.2.002
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet - Staff 1.2.005
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet - Staff 1.2.003
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Lounge - Patient / Transit 1.1.020
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite - Type 2 1.1.018
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite - Type 2 1.1.017
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
FoH Lift Lobby 1.T.004
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet - Patient 1.1.021
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Staff Station 10m2 1.1.022
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Photocopy / Stationary 1.1.024
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Linen 1.1.023
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing Type B 1.1.025
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Meal Trolley 4m2 1.1.030
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Mobile Equipment 1.1.026
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Services Riser 1.E.006
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.001
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.002
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.003
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.012
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.010
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.011
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.008
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.008
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.009
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 1.T.010
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Level 02
Main Switch Board 2.E.016
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Plant Room 2.E.012
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
UPS Room 2.E.015
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Palliative Care Terrace 2.1.078
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Services Riser 2.E.011
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.050
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.051
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.054
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.055
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.058
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.059
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.062
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.063
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.066
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.067
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Lounge - Patient 2.1.016
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.015
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
4 Bed Room - Inboard Ensuite 2.1.015
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.008
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.007
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.004
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.003
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.000
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Services Riser 2.E.010
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing, Type B 2.1.047
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Linen 2.1.046
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing, Type B 2.1.048
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Mobile Equipment 2.1.045
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store - Equipment, 20m2 2.1.044
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Disposal Room 10m2 2.1.043
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Clean Store 10m2 2.1.077
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cleaners Room 5m2 2.1.042
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet - Staff 2.1.041
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Interview Room 2.1.038
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Toilet - Accessible 2.1.039
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Dirty Utility 14m2 2.1.037
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Clean Utility / Medication Room 2.1.036
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Staff Station 14m2 2.1.035
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office - Clinical Workroom 2.1.033
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office - 1 Person, NUM 2.1.032
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Comms Room 2.E.008
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Mobile Equipment 2.1.012
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Workstation on Wheels 2.1.031
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Dining / Recreation / Therapy Room 2.1.029
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Plant Room 2.E.007
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Services Riser 2.E.006
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
FoH Lift Lobby 2.T.009
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Store - General 2.1.021
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Staff Station 10m2 2.1.022
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Linen 2.1.024
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Mobile Equipment 2.1.026
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Photocopy / Stationary 2.1.023
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Meal trolley 4m2 2.1.030
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing, Type B 2.1.025
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bay - Handwashing, Type B 2.1.027
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office - 1 Person 9m2 2.2.004
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office - 2 Person 2.2.003
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office - 1 Person 9m2 2.2.002
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Office - 1 Person 9m2 2.2.001
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
BoH Lift Lobby 2.T.006
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Bathroom 2.1.019
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.017
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.070
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.071
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.074
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.075
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.075
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Corridor - Patient Treatment Areas 2.T.012
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 2.T.004
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 2.T.001
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 2.T.002
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 2.T.003
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 2.T.013
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Corridor - Patient Treatment Areas 2.T.010
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Stairs
Stair 1
QA_TEM_082_Room Checklist
Stair 2
QA_TEM_082_Room Checklist
Lifts
Lift 1
QA_TEM_082_Room Checklist
Lift 2
QA_TEM_082_Room Checklist
Lift 3
QA_TEM_082_Room Checklist
Temp Construction
Level - 00
QA_TEM_063_Construction Distribution Boards
QA_TEM_064_Construction Wiring & Accessories
Level - 01
AS ABOVE
Level - 02
AS ABOVE
External
AS ABOVE

## example
Folder Structure |  |  |  |  | Checklists
Site QA
Electrical
Switchboards
MDB-A
|  |  |  | Cable Terminations | QA_TEM_014_Cable Terminations
|  |  |  | Fit Off | QA_TEM_043_Fit Off Checklist
|  |  |  | Power Commissioning | QA_TEM_041_Power Cable Commissioning
|  |  |  | Final Installation Checklist | Final Installation Checklist
DB-BOP
|  |  |  | Mains & Submains Installation | QA_TEM_011_Mains & Submains Installation
|  |  |  | Switchboard & DB Installation | QA_TEM_012_Switchboard & Distribution Board Installation
|  |  |  | Switchboard & Distribution Board Assembly | QA_TEM_013_Switchboard & Distribution Board Assembly
|  |  |  | Cable Terminations | QA_TEM_014_Cable Terminations
|  |  |  | Accessories Installation | QA_TEM_015_Accessories Installation
|  |  |  | Light Fitting Installation | QA_TEM_016_Light Fitting Installation
|  |  |  | LCP's & Field Devices | QA_TEM_018_LCP's & Field Devices
|  |  |  | Control Cables | QA_TEM_022_Control Cables
|  |  |  | Emergency & Exit Lighting | QA_TEM_023_Emergency & Exit Lighting
|  |  |  | Lighting Rough In | QA_TEM_042_Rough In Checklist
|  |  |  | Power Rough In | QA_TEM_042_Rough In Checklist
|  |  |  | Lighting Fit Off | QA_TEM_043_Fit Off Checklist
|  |  |  | Power Fit Off | QA_TEM_043_Fit Off Checklist
|  |  |  | Power Commissioning | QA_TEM_041_Power Cable Commissioning
|  |  |  | Multi Core Cable Commissioning | QA_TEM_040_Multi-Core Cable Commissioning
|  |  |  | Final Sub Circuit Installation | QA_TEM_010_Final Sub Circuit Installation
|  |  |  | Final Installation Checklist | Final Installation Checklist
MSSB-LAB
|  |  |  | Mains & Submains Installation | QA_TEM_011_Mains & Submains Installation
Cable Tray
Area 1
|  |  |  | Cable Support Prior to Cabling | QA_TEM_008_Cable Support Prior to Cabling
|  |  |  | Cable Support Post Cabling | QA_TEM_009_Cable Support Post Cabling
Conduit Installation
|  |  | Area 1 |  | QA_TEM_006_Surface Conduit Installation
Temporary Services
Temp DB 1
|  |  |  | September 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | October 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | November 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | December 2023 | QA_TEM_063_Construction Distribution Boards
Temp DB 2
|  |  |  | September 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | October 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | November 2023 | QA_TEM_063_Construction Distribution Boards
|  |  |  | December 2023 | QA_TEM_063_Construction Distribution Boards
Communications
|  | Rough In |  |  | QA_TEM_042_Rough In Checklist
|  | Fit Off |  |  | QA_TEM_043_Fit Off Checklist
|  | Data & Comms Cabling |  |  | QA_TEM_025_Data & Communications Cabling
|  | Cable Terminations |  |  | QA_TEM_014_Cable Terminations
|  | Final Sub Circuit Installation |  |  | QA_TEM_010_Final Sub Circuit Installation
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_080_Room Body Protection Checklist
Power Fit Off
QA_TEM_080_Room Body Protection Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist
Cable Rough In
QA_TEM_082_Room Checklist
Power Fit Off
QA_TEM_082_Room Checklist