## struct
resource | resource | resource | resource | resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
[5 empty] | step |  |  | Tier 1: AIDP Ripley Sub-Acute Site QA
[5 empty] | step |  |  | Tier 2: In-Ground Services Install
QA_TEM_004_Trench and Backfill | QA_TEM_005_Underground Conduit Installation | QA_TEM_081_Cable Pit Installation |  |  | folder-with-checklists |  |  | Tier 3: In-Ground Services Install - Zone 1
QA_TEM_004_Trench and Backfill | QA_TEM_005_Underground Conduit Installation | QA_TEM_081_Cable Pit Installation |  |  | folder-with-checklists |  |  | Tier 3: In-Ground Services Install - Zone 2
QA_TEM_004_Trench and Backfill | QA_TEM_005_Underground Conduit Installation | QA_TEM_081_Cable Pit Installation |  |  | folder-with-checklists |  |  | Tier 3: In-Ground Services Install - Zone 3
QA_TEM_004_Trench and Backfill | QA_TEM_005_Underground Conduit Installation |  |  |  | folder-with-checklists |  |  | Tier 3: In-Ground Services Install - Temps
[5 empty] | step |  |  | Tier 2: In Slab Services Install
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Level 00 - Pour 1
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Level 00 - Pour 2
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Level 00 - Pour 3
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Level 01 - Pour 1
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Level 01 - Pour 2
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Level 01 - Pour 3
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Level 02 - Pour 1
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Level 02 - Pour 2
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Level 02 - Pour 3
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Stair 1
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Stair 2
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - External slabs
QA_TEM_007_Cast in Conduit Installation |  |  |  |  | checklist |  |  | Tier 3: Cast in Conduit Installation - Outbuildings
[5 empty] | step |  |  | Tier 2: Equipotential Bonding
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Level 00 - Pour 1
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Level 00 - Pour 2
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Level 00 - Pour 3
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Level 01 - Pour 1
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Level 01 - Pour 2
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Level 01 - Pour 3
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Level 02 - Pour 1
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Level 02 - Pour 2
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Level 02 - Pour 3
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Stair 1
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Stair 2
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - External slabs
QA_TEM_079_Equipotential Bonding |  |  |  |  | checklist |  |  | Tier 3: Equipotential Bonding - Outbuildings
[5 empty] | step |  |  | Tier 2: Cable Tray Installation
QA_TEM_008_Cable Support Prior to Cabling |  |  |  |  | checklist |  |  | Tier 3: Cable Tray Installation - Level 00
QA_TEM_008_Cable Support Prior to Cabling |  |  |  |  | checklist |  |  | Tier 3: Cable Tray Installation - Level 01
QA_TEM_008_Cable Support Prior to Cabling |  |  |  |  | checklist |  |  | Tier 3: Cable Tray Installation - Level 02
QA_TEM_008_Cable Support Prior to Cabling |  |  |  |  | checklist |  |  | Tier 3: Cable Tray Installation - Outbuildings
[5 empty] | step |  |  | Tier 2: Fire Sealing
QA_TEM_017_Fire Sealing |  |  |  |  | checklist |  |  | Tier 3: Fire Sealing - Level 00
QA_TEM_017_Fire Sealing |  |  |  |  | checklist |  |  | Tier 3: Fire Sealing - Level 01
QA_TEM_017_Fire Sealing |  |  |  |  | checklist |  |  | Tier 3: Fire Sealing - Level 02
QA_TEM_017_Fire Sealing |  |  |  |  | checklist |  |  | Tier 3: Fire Sealing - Outbuildings
[5 empty] | step |  |  | Tier 2: Lightning Protection
QA_TEM_029_Lightning Protection |  |  |  |  | checklist |  |  | Tier 3: Lightning Protection
[5 empty] | step |  |  | Tier 2: Luminaires
QA_TEM_020_Lighting Poles |  |  |  |  | checklist |  |  | Tier 3: Pole 1
[5 empty] | step |  |  | Tier 2: Luminaires
QA_TEM_020_Lighting Poles |  |  |  |  | checklist |  |  | Tier 3: Pole 2
[5 empty] | step |  |  | Tier 2: MSB
QA_TEM_003_Earth Electrode | QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_011_Mains & Submains Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist | folder-with-checklists |  |  | Tier 3: MSB - SMSB-1
QA_TEM_003_Earth Electrode | QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_011_Mains & Submains Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist | folder-with-checklists |  |  | Tier 3: MSB - SMSB-2
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_011_Mains & Submains Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  | folder-with-checklists |  |  | Tier 3: MSB - MDB-SA-1
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_011_Mains & Submains Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  | folder-with-checklists |  |  | Tier 3: MSB - MDB-SA-2
QA_TEM_003_Earth Electrode | QA_TEM_011_Mains & Submains Installation | QA_TEM_014_Cable Terminations |  |  | folder-with-checklists |  |  | Tier 3: MSB - MSB-SHP
QA_TEM_011_Mains & Submains Installation | QA_TEM_014_Cable Terminations |  |  |  | folder-with-checklists |  |  | Tier 3: MSB - MSB-CP
step | bar: Tier 1 to Tier 5
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-FPR
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-WPR
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-SUB
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-SMSB
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-PFC
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-UPS
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-H1
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-LG-1-E
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-LG-2-E
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L1-1-E
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L1-2-E
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L2-1-E
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L2-2-E
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-LG-C-E
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-LG-K-NE
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-LG-1-NE
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-LG-2-NE
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L1-1-NE
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L1-2-NE
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L2-1-NE
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L2-2-NE
[5 empty] | step |  |  | Tier 2: UPS
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-LG-1-U
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-LG-2-U
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L1-1-U
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L1-2-U
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L2-1-U
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-L2-2-U
QA_TEM_012_Switchboard & Distribution Board Installation | QA_TEM_014_Cable Terminations | Final Installation Checklist |  |  | folder-with-checklists |  |  | Tier 3: DB - DB-LG-C-U
[5 empty] | step |  |  | Tier 2: Electrical Services
[5 empty] | step |  |  | Tier 3: Level 00
[5 empty] | step |  |  | Tier 4: Kitchen 0.4.006
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bulk Store/ Materials Management 04.005
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Loading Dock/Clean 0.4.004
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Body Hold 0.4.002
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet Accessible 0.4.003
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Loading Dock/Dirty 0.4.008
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store/Dirty Linen 0.4.009
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Cleaners Room 10m2 0.4.013
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office/Write Up 5m2 0.4.053
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Airlock/Entry 0.4.012
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store/Clean Linen 0.4.011
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Communications Store 0.E.014
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Comms Room L00 0.E.015
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office/2 Person 0.4.014
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Central Equioment Store 0.4.010
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store/Equipment 30m2 0.2.048
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store/Pharmacy 0.4.015
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Pathology 0.4.016
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Staff Change Male 0.4.001
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Staff Change Female 0.4.000
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite Type 2 0.2.000
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite Type 2 0.2.003
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite Type 2 0.2.004
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite Type 2 0.2.007
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite Type 2 0.2.008
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 4 Bed Room - Inboard Ensuite 0.2.011
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite Type 2 0.2.014
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Lounge/ Patient Family 30m2 0.2.015
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room Bariatic 0.2.063
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room Bariatic 0.2.062
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite Type 2 0.2.059
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Independent Assessment Suite 0.2.049
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room Bariatic 0.2.054
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room Bariatic 0.2.051
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room Bariatic 0.2.055
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Disposal Room 10m2 0.2.043
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store/General 0.2.046
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Cleaners Room 5m2 0.2.047
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet Staff 0.2.045
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Interview Room 0.2.036
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet/Accessible 0.2.037
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Clean Store 10m2 0.2.069
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Dirty Utility 14m2 0.2.035
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Clean Utility/Medication Room 0.2.034
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Staff Station 14m2 0.2.033
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office 1 Person/NUM 0.2.031
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office/Clinical Workroom 0.2.030
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Comms Room L00 0.E.009
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Dining/Recreation Therapy Room 0.2.028
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store/Gas 0.4.017
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor/Patient Treatment Areas 0.T.001
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor/Patient Treatment Areas 0.T.002
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor/Patient Treatment Areas 0.T.006
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor/Patient Treatment Areas 0.T.007
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor/Patient Treatment Areas 0.T.010
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor/Patient Treatment Areas 0.T.012
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor/Patient Treatment Areas 0.T.014
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor/Patient Treatment Areas 0.T.015
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite Type 2 0.2.017
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite Type 2 0.2.018
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store/Equipment 0.3.019
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Consult Room 0.3.017
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet/Accessible 0.3.018
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office /Write up 5m2 0.3.021
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Gymnasium/Group Therapy 0.3.016
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Occupational Therapy Room 0.3.013
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Airlock/Entry 0.1.000
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Waiting/Entry Foyer 0.1.001
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Café/Retail 0.1.002
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Indigenous Health Liaison Office 0.1.010
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Quiet Room 0.1.003
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Multi Purpose Room 0.1.004
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite Type 2 0.2.066
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite Type 2 0.2.067
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Laundry/Patient 6m2 0.2.020
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Staff Station 10m2 0.2.021
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Consult Room 0.3.001
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Consult Room 0.3.003
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet/Accessible 0.1.005
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Parenting Room 0.1.006
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet/Public 0.1.007 & 0.1.008
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Reception 10m2 0.1.009
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Interview Room/Allied Health 0.3.004
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Interview Room/Allied Health 0.3.005
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Workstation 0.3.006
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Interview Room/Allied Health 0.3.008
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: ADL Bathroom 0.3.007
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: ADL Kitchen 0.3.010
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Electronic Distribution Board 0.E.013
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Electronic Distribution Board 0.E.012
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay/Workastation on Wheel 0.2.042
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay/Linen 0.2.044
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Linen 0.2.022
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Mobile Equipment 0.2.025
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay Photocopy/Stationary 0.2.023
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing Type B 0.2.024
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Meal Trolley 4m2 0.2.029
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing Type B 0.2.026
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Electronic Distribution Board 0.E.003
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store Equipment 14m2 0.3.000
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 3: Level 01
[5 empty] | step |  |  | Tier 4: Plant Room 1.E.011
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Electronic Distribution Board 1.E.010
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: GEM Terrace 1.1.072
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Therapy / Multipurpose Room 1.1.000
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite - Type 2 1.1.002
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite - Type 2 1.1.003
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite - Type 2 1.1.006
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite - Type 2 1.1.007
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite - Type 2 1.1.003
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 4 Bed Room - Inboard Ensuite 1.1.010
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite - Type 2 1.1.013
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite - Type 2 1.1.014
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Dining / Recreation / Therapy Room 1.1.029
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Comms Room 1.E.007
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Workstation on Wheels 1.1.031
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Beverage, Open Plan 4m2 1.1.028
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing, Type B 1.1.027
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office - 1 Person NUM 1.1.033
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office - Clinical Workroom 1.1.032
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Staff Station 14m2 1.1.035
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Clean Utility / Medication Room 1.1.036
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Dirty Utility 14m2 1.1.037
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Interview Room 1.1.038
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet - Accessible 1.1.039
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Clean Store 10m2 1.1.040
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Disposal Room 10m2 1.1.042
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Cleaners Room 5m2 1.1.043
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet - Staff 1.1.040
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store - General 1.1.045
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Linen 1.1.046
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing Type B 1.1.047
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing Type B 1.1.048
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Mobile Equipment 1.1.044
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Electronic Distribution Board 1.E.008
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Plant Room 1.E.012
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store - Equipment 20m2 1.1.049
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.050
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.053
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.054
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.057
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.058
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.061
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.062
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.065
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Lounge - Patient / Family 20m2 1.1.066
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.068
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Inboard Ensuite, Type 2 1.1.069
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Meeting Room 20m2 1.2.009
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Breakout Room 1.2.008
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Breakout Room 1.2.007
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Workstations 1.2.000
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office 2 Person 1.2.010
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office 2 Person 1.2.011
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office 2 Person 1.2.012
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office 2 Person 1.2.013
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store - Photocopy / Stationery 8m2 1.2.001
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Meeting Room 30m2 1.2.014
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office 1 Person 1.2.015
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet - Accessible 1.2.004
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet - Accessible 1.2.006
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Staff Room 1.2.002
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet - Staff 1.2.005
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet - Staff 1.2.003
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Lounge - Patient / Transit 1.1.020
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite - Type 2 1.1.018
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite - Type 2 1.1.017
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: FoH Lift Lobby 1.T.004
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet - Patient 1.1.021
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Staff Station 10m2 1.1.022
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Photocopy / Stationary 1.1.024
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Linen 1.1.023
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing Type B 1.1.025
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Meal Trolley 4m2 1.1.030
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Mobile Equipment 1.1.026
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Services Riser 1.E.006
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.001
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.002
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.003
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.012
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.010
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.011
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.008
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.008
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.009
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 1.T.010
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 3: Level 02
[5 empty] | step |  |  | Tier 4: Main Switch Board 2.E.016
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Plant Room 2.E.012
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: UPS Room 2.E.015
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Palliative Care Terrace 2.1.078
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Services Riser 2.E.011
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.050
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.051
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.054
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.055
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.058
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.059
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.062
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.063
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.066
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.067
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Lounge - Patient 2.1.016
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.015
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 4 Bed Room - Inboard Ensuite 2.1.015
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.008
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.007
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.004
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.003
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.000
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Services Riser 2.E.010
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing, Type B 2.1.047
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Linen 2.1.046
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing, Type B 2.1.048
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Mobile Equipment 2.1.045
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store - Equipment, 20m2 2.1.044
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Disposal Room 10m2 2.1.043
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Clean Store 10m2 2.1.077
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Cleaners Room 5m2 2.1.042
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet - Staff 2.1.041
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Interview Room 2.1.038
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Toilet - Accessible 2.1.039
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Dirty Utility 14m2 2.1.037
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Clean Utility / Medication Room 2.1.036
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Staff Station 14m2 2.1.035
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office - Clinical Workroom 2.1.033
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office - 1 Person, NUM 2.1.032
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Comms Room 2.E.008
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Mobile Equipment 2.1.012
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Workstation on Wheels 2.1.031
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Dining / Recreation / Therapy Room 2.1.029
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Plant Room 2.E.007
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Services Riser 2.E.006
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: FoH Lift Lobby 2.T.009
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Store - General 2.1.021
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Staff Station 10m2 2.1.022
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Linen 2.1.024
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Mobile Equipment 2.1.026
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Photocopy / Stationary 2.1.023
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Meal trolley 4m2 2.1.030
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing, Type B 2.1.025
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bay - Handwashing, Type B 2.1.027
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office - 1 Person 9m2 2.2.004
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office - 2 Person 2.2.003
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office - 1 Person 9m2 2.2.002
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Office - 1 Person 9m2 2.2.001
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: BoH Lift Lobby 2.T.006
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Bathroom 2.1.019
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.017
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.070
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.071
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.074
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.075
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.075
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_080_Room Body Protection Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 2.T.012
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 2.T.004
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 2.T.001
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 2.T.002
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 2.T.003
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 2.T.013
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 4: Corridor - Patient Treatment Areas 2.T.010
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Cable Rough In
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 5: Power Fit Off
[5 empty] | step |  |  | Tier 3: Stairs
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 4: Stair 1
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 4: Stair 2
[5 empty] | step |  |  | Tier 3: Lifts
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 4: Lift 1
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 4: Lift 2
QA_TEM_082_Room Checklist |  |  |  |  | checklist |  |  | Tier 4: Lift 3
[5 empty] | step |  |  | Tier 3: Temp Construction
QA_TEM_063_Construction Distribution Boards | QA_TEM_064_Construction Wiring & Accessories |  |  |  | folder-with-checklists |  |  | Tier 4: Level - 00
QA_TEM_063_Construction Distribution Boards | QA_TEM_064_Construction Wiring & Accessories |  |  |  | folder-with-checklists |  |  | Tier 4: Level - 01
QA_TEM_063_Construction Distribution Boards | QA_TEM_064_Construction Wiring & Accessories |  |  |  | folder-with-checklists |  |  | Tier 4: Level - 02
QA_TEM_063_Construction Distribution Boards | QA_TEM_064_Construction Wiring & Accessories |  |  |  | folder-with-checklists |  |  | Tier 4: External