## ITP Cover Page
Traffic Signals Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 019 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 019
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Draft
ITP Description: |  |  | Traffic Signals |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | WSP-DR-ITS 0001, 0003,0102,0202,0204,0205,0206
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project Specification Section 24 (24.3), NZTA P43
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2025-01-17 |  | Cordelia Girdler-Brown | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM |  | CHRIS BENSON
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 2025-01-17 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body (2)
Traffic signals Inspection and test plan
Project: Tauriko Enabling Project
Number and revision DN1210 - 019 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – MATERIAL, PERSONEL & THIRD PARTY APPROVALS
3.1 | Material Compliance
3.1.1 | Underground Services | Pothole all services prior to commencement of trenching. Suitably protect the existing services from construction damage. | All underground services marked on site before pot holing or excavation | PS23.5.3 b) | Survey Data/Site Photos | Pre Excavation | H | PE/SE
3.1.2 | Ducting and Cabling Route | Confirm on site the exact location of cabling routes before trenching. Where connecting and or coordinating with existing services, engineers shall make local modifications necessary for the correct operation of the entire system. | Markings match design drawings | PS 23.1.5 p) & 23.5.3 a) | Survey data/Comms with Client | Prior to Installation | H | PE
3.1.3 | Location of Signal Poles, Cameras, Cable Pits | Confirm with surveyor and mark out the exact locations of lighting poles, Cameras, Cable Pits and Montrose boxes before installation. | Survey Records/Checks | 8287 | Survey data/Comms with Client | Prior to Installation | H | PE/SE
3.1.4 | Bedding and Overlay | Bedding and overlay material for the ducts will be coarse sand | Coarse Sand Visual Inspection | PS23.11.8.a) ii-iii | Coase Sand - PSD Report | Prior to Construction | HP | ENG
3.1.5 | Backfilling of ducts, loops, cable pits | Under roads and paved areas: Coarse sand, controlled low strength material or fine crushed rock. In topsoil areas: Complete the backfilling with topsoil for at least the top 50mm. | Visual Inspection | PS23.11.8.a) ii-iii | Material data sheet and Engineers Approval | Prior to Construction | HP | ENG
3.1.6 | Ducts and Fittings | Use heavy duty HD PVC for underground services. Use best practice PVC where possible. Orange colour for all conduits containing consumer mains, sub-mains or final sub-circuits cabling | All the materials meets the specification requirements and Engineers Approval | PS23.11.8.a) iv | Material data sheet and engineers approval | Prior to Construction | HP | ENG
3.1.7 | Cable Pit | Aco Cablemate Polycrete "type 66" Dimension: 665mm x 665mm x 620mm with heavy duty steel lid. | All the materials meets the specification requirements and Engineers Approval | PS 23.1.5 d) & Drawing 0122 | Material data sheet and engineers approval | Prior to Construction | HP | ENG
3.1.8 | Signal Poles | The design requirements for all traffic poles shall be in accordance with AS/NZS 4677 with Design working life 50 years. Pole shall be finished internally and externally in accordance with AS/NZS 4680. Ready galvanized steel, Spray on galvanising or thermal zinc will not be accepted. | All the materials meets the specification requirements and Engineers Approval | Section 24.2.1b (Project Specification PS ) NZTA P43 | Material Data Sheets/Test Results/Eng approval | 100% of critical materials | C, W | QE, PE
3.1.9 | Aspects/ Displays/Visor | All LED lanterns, visors, louvres and target boards shall comply with NZTA P43. In addition LED lanterns shall have an independent NZTA certified laboratory report confirming compliance with AS/NZS 2144. This must be supplied to the RCA traffic signal Engineer on request. | Materials meet specified quality standards | Section 24.2.1b (Project Specification PS ) NZTA P43 | Lab report and confirmation from sub contractor | 100% of critical materials | C, W | QE, PE
3.1.10 | Cycle and Pedestrain push button assemblies | Pedestrain push-button assemblies shall contain audio and tactile facilities and shall comply with AS 2353. in addition it requires 1. The call box with audible locating and walk signal 2. The audible locator shall incorporate ambient noise control 3. the tactile function shall be continually operational, however the audio signal should be able to be muted. | Sub contractor's installation MS confirming Waka Kotahi P43 standards | Section 24.3 (Project Specification PS) | Installation MS | Once | I | PE
3.1.11 | Signal lanterns | The technical requirements for traffic signal lanterns including cowls, visors, and louvres shall be as stipulated in AS/NZS 2144, including amendments as issued from time to time. The signal size of pedstrain and general purpose signals to be 200mm. The size of extended range signals as refered to in 3.3 of AS/NZS 2144 shall be 300mm | Sub contractor's installation MS confirming Waka Kotahi P43 standards | Section 24.3 (Project Specification PS) | Installation MS | Once | I | PE
3.1.12 | Controller personality software | In case Signal installer needs assistance from TCC | Discussion and agreement with TCC | Section 24.2.1 (Project Specification PS) | Meeting and agreements | Once | R | QE, PE, ENG
3.2 | MATERIAL DELIVERY
3.2.1 | Delivery of Materials | Ensure materials are delivered as per project schedule and specifications meeting P43 | Materials delivered in good condition, within specified timelines | Section 24.4.1 (Project Specification PS) | Delivery receipts, inspection records | 100% of material deliveries | I | SE, QE, SUP
3.2.2 | Storage of Materials On-Site | Verify that materials are stored properly to prevent damage | Materials stored according to safety and handling requirements | Section 24.4.1 (Project Specification PS) | Storage inspection reports | 100% of materials on-site | I, V | SE, QE, SUP
3.2.3 | Joint Use Poles (JUSP and JUMA) Painting | Ensure that JUSP and JUMA poles are painted yellow as required | Poles painted and installed as per project specifications | Section 24.2.1f (Project Specification PS) | Painting and installation inspection records | 100% of JUSP and JUMA poles | V, C | SE, QE, SUP
SECTION 4 – CONSTRUCTION ACTIVITY - DUCTING, CABLING PIT, CABLING ROUTE, SIGNAL POLES AND LANTERNS
4.1 | Foundation & Bedding Compliance | Keep trenches free of water No sharp projections, roots and other obstructions. Then bedding with sand for 50mm | Visual Inspection: clean trenches, smooth trenches and bedding material placed | PS23.11.8.a) ii | Photo/Visual Inspection | Each excavation | V, C | SE, SUP
4.2 | Ducting | Minimum 50mm separation from other conduits; Also follow separation requirements by utility operators when in shared trench. Depth as per drawing (survey data): ≥900mm under Roadways, ≥600mm under Sidewalks/Berm; Or Client Instruction on site. Where services cross, install electrical conduit at the topmost | Visual Inspection: 50mm separation from conduits, depth check as per specification | PS23.11.8.a) v | Photo/Visual Inspection/Comms | Each installation | V, C | SE, SUP
4.3 | Sealing Ducts | Seal buried entries of ducts and conduits using waterproof seals and/or conduit fittings. Seal spare ducts and conduits immediately after installation and seal other ducts and conduits after cable installation. | Visual Inspection: checks for waterproof seals | PS23.11.8.a) vi | Photo/Visual Inspection | Each installation | V, C | SE, SUP
4.4 | Backfilling | Backfill trenches as soon as possible after approval of laid and bedded service. Place the backfill in layers < 150mm thick and compact to the density which applies to the location of the trenches to minimize settlement. - Under maintenance pad, Clegg test will be used, with target CIV 25 for GAP65. - Under berm area, no test needed on topsoil. | Visual Inspection: checks for specified materials for backfilling | PS23.11.8.a) iii | Photo/Visual Inspection/Compaction result when under Road or paved areas | Each installation | M | SE
4.5 | Cable Pit | Install cable pits as detailed on the drawings. | Visual Inspection: checks for specified cable pit location as per dwg | PS 23.1.5 d) | Comms with WSP/ Photo/Visual Inspection | Each installation | W | ENG
4.6 | Installation of Poles and Lanterns | Verify correct installation of all poles and lanterns. All lantern mounting barckets,bolts,nuts and mounting hardware shall comply with section 3 of AS2339, all lower lantern nut and bolt assemblies shall be installed complete with a locking mechanism. | Installed per design, stable, operational, as per Waka Kotahi P43 | Section 24.3.1 (Project Specification PS) | Installation checklists, as-built drawings | 100% of installations | I, W | SE, QE, SUP
4.7 | Ducting and Access Chambers Installation | Ensure correct trenching, duct laying, backfilling, and reinstatement | Ducting installed as per design, trench reinstated properly | Section 24.3.2 (Project Specification PS 1) | Duct installation logs, inspection reports | 100% of ducts and access chambers | I, C | SE, SUP
4.8 | CCTV and ANPR Camera Installation | Verify correct installation and operation of CCTV and ANPR cameras | Cameras operational, meeting field of view and accuracy requirements | Section 24.4 (Project Specification PS) | CCTV & ANPR installation checklists, test results | 100% of camera installations | I, W | SE
4.9 | Signal Controller Installation & Testing | Conduct pre-commissioning checks on signal controllers | Controllers installed and operational, tested successfully | Section 24.7.2 (Project Specification PS 1) | Pre-commissioning reports, bench test results | 100% of controller installations | C, W | ENG, SE
4.1 | CCTV Camera Field of View Verification | Verify CCTV field of view before foundation construction | Field of view meets design requirements, photos taken from proposed camera height | Section 24.4.1 (Project Specification PS) | Field of view verification reports, site photos | 100% of CCTV installation | I, H | SPEC, ENG, SE
SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5.1 | Final Inspection and Audit | Conduct final inspection and audit of all installations |  | Section 24.7.4 (Project Specification PS) | Final inspection reports, Certificate of Electrical Compliance | 100% of installations | R, HP | ENG, SE, CR, QM
5.2 | Final Inspection and Commissioning of Traffic Signals & ITS: Electrical Certificate of Compliance (CoC) and record of inspection Electrical Safety Certificate(ESC) | Conduct final inspection and audit of all installations; Ensure signals and ITS equipment are fully operational and integrated with SCATS | Installation meets all design and safety standards; Fully operational, integrated with SCATS, accepted by Waka Kotahi/TCC | Section 24.7.4 & 24.7.5 (Project Specification PS) ITS-01-010-202008-STD-DUCT | Certificate of Electrical Compliance; Commissioning reports, SCATS integration logs | 100% of signals and ITS installations | R, HP | SPEC, ENG, SE
5.3 | Handover Documentation | Submit all required as-built documents and records | Documents complete, accurate, submitted as per schedule | Section 24.7.6 (Project Specification PS) | As-built drawings, system schematics, manuals | 100% of system component | R, HP | PM, ENG, QM
5.4 | Warranty and Maintenance Arrangements | Establish warranty and maintenance protocols post-handover | Warranty and maintenance agreements in place, responsibilities defined | Section 24.8.1,24.8.5 (Project Specification PS) | Warranty documentation, maintenance agreements | 100% of installations covered | R, W | ENG, PM, CR
5.5 | Battery Backup Systems Testing | Test battery backup systems for CCTV cameras | Backup systems functional, providing images during power failure | Section 24.4.1f (Project Specification PS) | Battery backup test results, operational logs | 100% of CCTV installations | I, C | SPEC, ENG, QE
5.6 | As built and RAMM Requirements | All ITS and signal equipment, including software shall be recorded in electronic format into the RAMM database. As built drawings are required in advance of the 80% walkovers prior to handover. | Final As built as per Waka Kotahi ITS specification Testing, commissioning and handover (ITS-10-01) | Section 24.7.6 (Project Specification PS) | As built reports | 100% of CCTV and Signal installations | R, HP | PM, ENG, QE