## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-019 ITP Traffic signals | itp |  |  |  |  | DN1210-019 ITP Traffic signals Rev 0
section | SECTION 3 – MATERIAL, PERSONEL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Underground Services
label | Detail - Pothole all services prior to commencement of trenching. Suitably protect the existing services from construction damage.
label | Acceptance / Conformance Criteria - All underground services marked on site before pot holing or excavation
label | Standard / Specification - PS23.5.3 b)
label | Verifying Document - Survey Data/Site Photos
label | Testing Quantity Required (based from schedule qtys) - Pre Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE/SE
checkpoint | 3.1.2 - Ducting and Cabling Route
label | Detail - Confirm on site the exact location of cabling routes before trenching.
label | ○ Where connecting and or coordinating with existing services, engineers shall make local modifications necessary for the correct operation of the entire system.
label | Acceptance / Conformance Criteria - Markings match design drawings
label | Standard / Specification - PS 23.1.5 p) & 23.5.3 a)
label | Verifying Document - Survey data/Comms with Client
label | Testing Quantity Required (based from schedule qtys) - Prior to Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.1.3 - Location of Signal Poles, Cameras, Cable Pits
label | Detail - Confirm with surveyor and mark out the exact locations of lighting poles, Cameras, Cable Pits and Montrose boxes before installation.
label | Acceptance / Conformance Criteria - Survey Records/Checks
label | Standard / Specification - 8287
label | Verifying Document - Survey data/Comms with Client
label | Testing Quantity Required (based from schedule qtys) - Prior to Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE/SE
checkpoint | 3.1.4 - Bedding and Overlay
label | Detail - Bedding and overlay material for the ducts will be coarse sand
label | Acceptance / Conformance Criteria - Coarse Sand Visual Inspection
label | Standard / Specification - PS23.11.8.a) ii-iii
label | Verifying Document - Coase Sand - PSD Report
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.5 - Backfilling of ducts, loops, cable pits
label | Detail - Under roads and paved areas: Coarse sand, controlled low strength material or fine crushed rock.
label | ○ In topsoil areas: Complete the backfilling with topsoil for at least the top 50mm.
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - PS23.11.8.a) ii-iii
label | Verifying Document - Material data sheet and Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.6 - Ducts and Fittings
label | Detail - Use heavy duty HD PVC for underground services.
label | ○ Use best practice PVC where possible.
label | ○ Orange colour for all conduits containing consumer mains, sub-mains or final sub-circuits cabling
label | Acceptance / Conformance Criteria - All the materials meets the specification requirements and Engineers Approval
label | Standard / Specification - PS23.11.8.a) iv
label | Verifying Document - Material data sheet and engineers approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.7 - Cable Pit
label | Detail - Aco Cablemate Polycrete "type 66" Dimension: 665mm x 665mm x 620mm with heavy duty steel lid.
label | Acceptance / Conformance Criteria - All the materials meets the specification requirements and Engineers Approval
label | Standard / Specification - PS 23.1.5 d) & Drawing 0122
label | Verifying Document - Material data sheet and engineers approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.8 - Signal Poles
label | Detail - The design requirements for all traffic poles shall be in accordance with AS/NZS 4677 with Design working life 50 years. Pole shall be finished internally and externally in accordance with AS/NZS 4680. Ready galvanized steel, Spray on galvanising or thermal zinc will not be accepted.
label | Acceptance / Conformance Criteria - All the materials meets the specification requirements and Engineers Approval
label | Standard / Specification - Section 24.2.1b (Project Specification PS ) NZTA P43
label | Verifying Document - Material Data Sheets/Test Results/Eng approval
label | Testing Quantity Required (based from schedule qtys) - 100% of critical materials
label | Verification Activity: Activity - C, W
label | Verification Activity: By - QE, PE
checkpoint | 3.1.9 - Aspects/ Displays/Visor
label | Detail - All LED lanterns, visors, louvres and target boards shall comply with NZTA P43. In addition LED lanterns shall have an independent NZTA certified laboratory report confirming compliance with AS/NZS 2144. This must be supplied to the RCA traffic signal Engineer on request.
label | Acceptance / Conformance Criteria - Materials meet specified quality standards
label | Standard / Specification - Section 24.2.1b (Project Specification PS ) NZTA P43
label | Verifying Document - Lab report and confirmation from sub contractor
label | Testing Quantity Required (based from schedule qtys) - 100% of critical materials
label | Verification Activity: Activity - C, W
label | Verification Activity: By - QE, PE
checkpoint | 3.1.10 - Cycle and Pedestrain push button assemblies
label | Detail - Pedestrain push-button assemblies shall contain audio and tactile facilities and shall comply with AS 2353. in addition it requires 1. The call box with audible locating and walk signal 2. The audible locator shall incorporate ambient noise control 3. the tactile function shall be continually operational, however the audio signal should be able to be muted.
label | Acceptance / Conformance Criteria - Sub contractor's installation MS confirming Waka Kotahi P43 standards
label | Standard / Specification - Section 24.3 (Project Specification PS)
label | Verifying Document - Installation MS
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 3.1.11 - Signal lanterns
label | Detail - The technical requirements for traffic signal lanterns including cowls, visors, and louvres shall be as stipulated in AS/NZS 2144, including amendments as issued from time to time. The signal size of pedstrain and general purpose signals to be 200mm. The size of extended range signals as refered to in 3.3 of AS/NZS 2144 shall be 300mm
label | Acceptance / Conformance Criteria - Sub contractor's installation MS confirming Waka Kotahi P43 standards
label | Standard / Specification - Section 24.3 (Project Specification PS)
label | Verifying Document - Installation MS
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 3.1.12 - Controller personality software
label | Detail - In case Signal installer needs assistance from TCC
label | Acceptance / Conformance Criteria - Discussion and agreement with TCC
label | Standard / Specification - Section 24.2.1 (Project Specification PS)
label | Verifying Document - Meeting and agreements
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - R
label | Verification Activity: By - QE, PE, ENG
checkpoint | 3.2.1 - Delivery of Materials
label | Detail - Ensure materials are delivered as per project schedule and specifications meeting P43
label | Acceptance / Conformance Criteria - Materials delivered in good condition, within specified timelines
label | Standard / Specification - Section 24.4.1 (Project Specification PS)
label | Verifying Document - Delivery receipts, inspection records
label | Testing Quantity Required (based from schedule qtys) - 100% of material deliveries
label | Verification Activity: Activity - I
label | Verification Activity: By - SE, QE, SUP
checkpoint | 3.2.2 - Storage of Materials On-Site
label | Detail - Verify that materials are stored properly to prevent damage
label | Acceptance / Conformance Criteria - Materials stored according to safety and handling requirements
label | Standard / Specification - Section 24.4.1 (Project Specification PS)
label | Verifying Document - Storage inspection reports
label | Testing Quantity Required (based from schedule qtys) - 100% of materials on-site
label | Verification Activity: Activity - I, V
label | Verification Activity: By - SE, QE, SUP
checkpoint | 3.2.3 - Joint Use Poles (JUSP and JUMA) Painting
label | Detail - Ensure that JUSP and JUMA poles are painted yellow as required
label | Acceptance / Conformance Criteria - Poles painted and installed as per project specifications
label | Standard / Specification - Section 24.2.1f (Project Specification PS)
label | Verifying Document - Painting and installation inspection records
label | Testing Quantity Required (based from schedule qtys) - 100% of JUSP and JUMA poles
label | Verification Activity: Activity - V, C
label | Verification Activity: By - SE, QE, SUP
section | SECTION 4 – CONSTRUCTION ACTIVITY - DUCTING, CABLING PIT, CABLING ROUTE, SIGNAL POLES AND LANTERNS
checkpoint | 4.1 - Foundation & Bedding Compliance
label | Detail - Keep trenches free of water
label | ○ No sharp projections, roots and other obstructions.
label | ○ Then bedding with sand for 50mm
label | Acceptance / Conformance Criteria - Visual Inspection: clean trenches, smooth trenches and bedding material placed
label | Standard / Specification - PS23.11.8.a) ii
label | Verifying Document - Photo/Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Each excavation
label | Verification Activity: Activity - V, C
label | Verification Activity: By - SE, SUP
checkpoint | 4.2 - Ducting
label | Detail - Minimum 50mm separation from other conduits; Also follow separation requirements by utility operators when in shared trench.
label | ○ Depth as per drawing (survey data):
label | — ≥900mm under Roadways, ≥600mm under Sidewalks/Berm;
label | — Or Client Instruction on site.
label | — Where services cross, install electrical conduit at the topmost
label | Acceptance / Conformance Criteria - Visual Inspection: 50mm separation from conduits, depth check as per specification
label | Standard / Specification - PS23.11.8.a) v
label | Verifying Document - Photo/Visual Inspection/Comms
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - V, C
label | Verification Activity: By - SE, SUP
checkpoint | 4.3 - Sealing Ducts
label | Detail - Seal buried entries of ducts and conduits using waterproof seals and/or conduit fittings.
label | ○ Seal spare ducts and conduits immediately after installation and seal other ducts and conduits after cable installation.
label | Acceptance / Conformance Criteria - Visual Inspection: checks for waterproof seals
label | Standard / Specification - PS23.11.8.a) vi
label | Verifying Document - Photo/Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - V, C
label | Verification Activity: By - SE, SUP
checkpoint | 4.4 - Backfilling
label | Detail - Backfill trenches as soon as possible after approval of laid and bedded service.
label | ○ Place the backfill in layers < 150mm thick and compact to the density which applies to the location of the trenches to minimize settlement.
label | — Under maintenance pad, Clegg test will be used, with target CIV 25 for GAP65.
label | — Under berm area, no test needed on topsoil.
label | Acceptance / Conformance Criteria - Visual Inspection: checks for specified materials for backfilling
label | Standard / Specification - PS23.11.8.a) iii
label | Verifying Document - Photo/Visual Inspection/Compaction result when under Road or paved areas
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.5 - Cable Pit
label | Detail - Install cable pits as detailed on the drawings.
label | Acceptance / Conformance Criteria - Visual Inspection: checks for specified cable pit location as per dwg
label | Standard / Specification - PS 23.1.5 d)
label | Verifying Document - Comms with WSP/ Photo/Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 4.6 - Installation of Poles and Lanterns
label | Detail - Verify correct installation of all poles and lanterns. All lantern mounting barckets,bolts,nuts and mounting hardware shall comply with section 3 of AS2339, all lower lantern nut and bolt assemblies shall be installed complete with a locking mechanism.
label | Acceptance / Conformance Criteria - Installed per design, stable, operational, as per Waka Kotahi P43
label | Standard / Specification - Section 24.3.1 (Project Specification PS)
label | Verifying Document - Installation checklists, as-built drawings
label | Testing Quantity Required (based from schedule qtys) - 100% of installations
label | Verification Activity: Activity - I, W
label | Verification Activity: By - SE, QE, SUP
checkpoint | 4.7 - Ducting and Access Chambers Installation
label | Detail - Ensure correct trenching, duct laying, backfilling, and reinstatement
label | Acceptance / Conformance Criteria - Ducting installed as per design, trench reinstated properly
label | Standard / Specification - Section 24.3.2 (Project Specification PS 1)
label | Verifying Document - Duct installation logs, inspection reports
label | Testing Quantity Required (based from schedule qtys) - 100% of ducts and access chambers
label | Verification Activity: Activity - I, C
label | Verification Activity: By - SE, SUP
checkpoint | 4.8 - CCTV and ANPR Camera Installation
label | Detail - Verify correct installation and operation of CCTV and ANPR cameras
label | Acceptance / Conformance Criteria - Cameras operational, meeting field of view and accuracy requirements
label | Standard / Specification - Section 24.4 (Project Specification PS)
label | Verifying Document - CCTV & ANPR installation checklists, test results
label | Testing Quantity Required (based from schedule qtys) - 100% of camera installations
label | Verification Activity: Activity - I, W
label | Verification Activity: By - SE
checkpoint | 4.9 - Signal Controller Installation & Testing
label | Detail - Conduct pre-commissioning checks on signal controllers
label | Acceptance / Conformance Criteria - Controllers installed and operational, tested successfully
label | Standard / Specification - Section 24.7.2 (Project Specification PS 1)
label | Verifying Document - Pre-commissioning reports, bench test results
label | Testing Quantity Required (based from schedule qtys) - 100% of controller installations
label | Verification Activity: Activity - C, W
label | Verification Activity: By - ENG, SE
checkpoint | 4.10 - CCTV Camera Field of View Verification
label | Detail - Verify CCTV field of view before foundation construction
label | Acceptance / Conformance Criteria - Field of view meets design requirements, photos taken from proposed camera height
label | Standard / Specification - Section 24.4.1 (Project Specification PS)
label | Verifying Document - Field of view verification reports, site photos
label | Testing Quantity Required (based from schedule qtys) - 100% of CCTV installation
label | Verification Activity: Activity - I, H
label | Verification Activity: By - SPEC, ENG, SE
section | SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - Final Inspection and Audit
label | Detail - Conduct final inspection and audit of all installations
label | Acceptance / Conformance Criteria -
label | Standard / Specification - Section 24.7.4 (Project Specification PS)
label | Verifying Document - Final inspection reports, Certificate of Electrical Compliance
label | Testing Quantity Required (based from schedule qtys) - 100% of installations
label | Verification Activity: Activity - R, HP
label | Verification Activity: By - ENG, SE, CR, QM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Final Inspection and Commissioning of Traffic Signals & ITS: Electrical Certificate of Compliance (CoC) and record of inspection Electrical Safety Certificate(ESC)
label | Detail - Conduct final inspection and audit of all installations;
label | ○ Ensure signals and ITS equipment are fully operational and integrated with SCATS
label | Acceptance / Conformance Criteria - Installation meets all design and safety standards;
label | ○ Fully operational, integrated with SCATS, accepted by Waka Kotahi/TCC
label | Standard / Specification - Section 24.7.4 & 24.7.5 (Project Specification PS) ITS-01-010-202008-STD-DUCT
label | Verifying Document - Certificate of Electrical Compliance;
label | ○ Commissioning reports, SCATS integration logs
label | Testing Quantity Required (based from schedule qtys) - 100% of signals and ITS installations
label | Verification Activity: Activity - R, HP
label | Verification Activity: By - SPEC, ENG, SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Handover Documentation
label | Detail - Submit all required as-built documents and records
label | Acceptance / Conformance Criteria - Documents complete, accurate, submitted as per schedule
label | Standard / Specification - Section 24.7.6 (Project Specification PS)
label | Verifying Document - As-built drawings, system schematics, manuals
label | Testing Quantity Required (based from schedule qtys) - 100% of system component
label | Verification Activity: Activity - R, HP
label | Verification Activity: By - PM, ENG, QM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Warranty and Maintenance Arrangements
label | Detail - Establish warranty and maintenance protocols post-handover
label | Acceptance / Conformance Criteria - Warranty and maintenance agreements in place, responsibilities defined
label | Standard / Specification - Section 24.8.1,24.8.5 (Project Specification PS)
label | Verifying Document - Warranty documentation, maintenance agreements
label | Testing Quantity Required (based from schedule qtys) - 100% of installations covered
label | Verification Activity: Activity - R, W
label | Verification Activity: By - ENG, PM, CR
checkpoint | 5.5 - Battery Backup Systems Testing
label | Detail - Test battery backup systems for CCTV cameras
label | Acceptance / Conformance Criteria - Backup systems functional, providing images during power failure
label | Standard / Specification - Section 24.4.1f (Project Specification PS)
label | Verifying Document - Battery backup test results, operational logs
label | Testing Quantity Required (based from schedule qtys) - 100% of CCTV installations
label | Verification Activity: Activity - I, C
label | Verification Activity: By - SPEC, ENG, QE
checkpoint | 5.6 - As built and RAMM Requirements
label | Detail - All ITS and signal equipment, including software shall be recorded in electronic format into the RAMM database. As built drawings are required in advance of the 80% walkovers prior to handover.
label | Acceptance / Conformance Criteria - Final As built as per Waka Kotahi ITS specification Testing, commissioning and handover (ITS-10-01)
label | Standard / Specification - Section 24.7.6 (Project Specification PS)
label | Verifying Document - As built reports
label | Testing Quantity Required (based from schedule qtys) - 100% of CCTV and Signal installations
label | Verification Activity: Activity - R, HP
label | Verification Activity: By - PM, ENG, QE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature