## Table 1
INSPECTION AND TEST PLAN
Details
ITP Activity: |  | Clear and grubbing | [7 empty] | Project: |  |  |  | EVA Copper | [6 empty] | Date Lot Opened:
ITP Number: |  | EVAMP001-THS- QA-ITP-0001 |  |  |  | Rev. No. |  | B |  | Contract Number: | [10 empty] | Date Lot Closed:
Lot Number: | [9 empty] | Client: |  |  |  | Harmony
Location or Area: | [9 empty] | Client Reference: | [10 empty] | JSA/SWMS Ref:
Chainage / Coordinates: | [9 empty] | Contractor / Subcontractor / Supplier: | [10 empty] | SOP Reference:
No. | Inspection / Test Point |  | Responsibility |  |  |  | Method |  | Conformance Criteria |  | Specification Clause |  | Frequency |  | Verification from Thiess / Client (H/W/R/M) | [6 empty] | Records or Comments
[15 empty] | THIESS (Initial) |  |  |  |  | Client (Initial)
1 | Pre-Construction
1 | Drawings supplied most current IFC |  | ENG |  |  |  | Visual |  | Reviewed drawing register |  | Reviewed drawing register |  | Prior to works |  | HP |  |  |  |  | W
2 | Management Plans submitted and approved as per PMP |  | ENG |  |  |  | Visual |  | Approved Package MP’s |  | Approved Package MP’s |  | Prior to works |  | HP |  |  |  |  | W
3 | Inspection Test Plan (ITP) submitted and approved |  | ENG |  |  |  | Visual |  | Approved ITP revision |  | Approved ITP revision |  | Prior to works |  | HP |  |  |  |  | W
4 | Lot Register/ WBS submitted and approved |  | ENG |  |  |  | Visual |  | Approved WBS |  | Approved WBS |  | Prior to works |  | WP |  |  |  |  | W
5 | Erosion and sediment control plan approved |  | ENV/ENG |  |  |  | Visual |  | Approved erosion and sediment control plan |  | EVAMP001-EVA- 7340-PE-PRM- 0001 |  | Prior to works |  | HP |  |  |  |  | HP
6 | Check existing services and dial before you dig |  | ENG |  |  |  | Visual |  | DBYD certificate and EP |  | Excavation Permit (EP) Doc no. |  | Prior to works |  | HP |  |  |  |  | W
7 | Ground Disturbance Procedure (GDP) obtained |  | ENG/ENV |  |  |  | Visual |  | GDP permit with work packs |  | EVAMP001-EVA- 7340-PE-PRM- 0001 |  | Prior to works |  | HP |  |  |  |  | HP
8 | Area of works pegged and clearly defined to GDP. Pre- strip area survey pick-up |  | SURV |  |  |  | Visual |  | Clearing pegs installed at nominal intervals to ensure no over-clearing |  | EVAMP001-EVA- 7340-PE-PRM- 0001 to ensure no over-clearing |  | Prior to works |  | HP |  |  |  |  | HP
9 | Area of works been pre-cleared for Fauna/ Flora |  | ENG/ENV |  |  |  | Visual |  | All areas to be pre-cleared prior to clearing operations. |  | EVAMP001-EVA- EN-PLA-0001 |  | Prior to works |  | HP |  |  |  |  | HP
2 | Construction
10 | Clearing of vegetation and removal to nominated stockpile location |  | SV ENV |  |  |  | Visual |  | Spotter/ catcher in place during clearing operations Habitat vegetation, threatened species and cultural heritage areas demarcated |  | - EVAMP001- EVA-EN-PLA- 0001 - EVAMP001- EVA-7340-PE- PRM-0001 - C22 of EVAMP001-QVT- PE-PRM-0001 |  | As required |  | HP |  |  |  |  | W
11 | All Erosion sediment control measures installed prior to construction |  | ENG/ENV |  |  |  | Visual |  | All control measures for erosion sediment control need to be implemented after clearing has been completed. |  | EVAMP001-EVA- 7340-PE-PRM- 0001 EVAMP001-EVA- EN-PLA-0001 |  | After clearing completed |  | HP |  |  |  |  | HP
12 | Inspection of foundation prior to next stage of construction |  | SV ENG |  |  |  | Field Test |  | Proof roll where required |  | EVAMP001-EVA- EN-PLA-0001 |  | As required |  | HP |  |  |  |  | HP
13 | Surface level check/ post-strip area survey pick-up |  | SV/SURV |  |  |  | Survey/ Field Test |  | DXF file submitted to Company |  | EVAMP001-EVA- 7340-PE-PRM- 0001 |  | As required |  | HP |  |  |  |  | W
3 | Post Construction
14 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP |  | ENG |  |  |  | Visual |  | GDP permits closed. ITP closed. Approved MDR |  | - EVAMP001- EVA-7340-PE- PRM-0001 - EVA PMP |  | As required |  | HP |  |  |  |  | HP
☐ Conformance to Specification |  |  |  |  | ☐ Requires Re-Work: (Provide Details): | [13 empty] | ☐ Non-Conformance |  |  | NCR No:
Approved by THIESS QA Representative | [5 empty] | Date |  |  | Approved by THIESS Project Manager | [5 empty] | Date |  | Approved by Client | [7 empty] | Date
Name (print): | [8 empty] | Name (print): | [7 empty] | Name (print):
Signature: | [8 empty] | Signature: | [7 empty] | Signature:
RESPONSIBILITY |  |  |  | METHOD | [6 empty] | VERIFICATION TYPE |  |  |  |  | ITP REVISIONS
Symbol | Legend |  |  | Symbol |  |  | Legend |  |  |  | Symbol | Legend |  |  |  | Rev No. |  | Amendment Details |  |  |  |  | Date | Approver
C | Client |  |  | W |  |  | Written |  |  |  | HP | Hold
SV | THIESS Supervisor |  |  | A |  |  | Application |  |  |  | W | Witness
Eng | THIESS Engineer |  |  | D |  |  | Design |  |  |  | R | Review
Surv | Surveyor |  |  | S |  |  | Survey Data |  |  |  | M | Monitor
SC | Subcontractor |  |  | V |  |  | Visual
PM | Project Manager |  |  | T |  |  | Test
CM | Construction Manager |  |  | C |  |  | Certificate
MC | Material Controller |  |  | TA |  |  | Test / Approval
ENV | Enviro officer |  |  | M |  |  | Measure
Please transfer information into THIESS Data System ‘Inspection and Test’ Register.