## Table 1
INSPECTION AND TEST PLAN
Details
ITP Activity: |  |  | Subgrade Preparation | [8 empty] | Project: |  |  |  |  | EVA Copper | [6 empty] | Date Lot Opened:
ITP Number: |  |  | EVAMP001-THS- QA-ITP-0003 |  |  |  | Rev. No. |  |  | 0 |  | Contract Number: | [11 empty] | Date Lot Closed:
Lot Number: | [11 empty] | Client: |  |  |  |  | Harmony
Location or Area: | [11 empty] | Client Reference: | [11 empty] | JSA/SWMS Ref:
Chainage / Coordinates: | [11 empty] | Contractor / Subcontractor / Supplier: | [11 empty] | SOP Reference:
No. | Inspection / Test Point |  |  | Responsibility |  |  | Method |  |  | Conformance Criteria |  |  | Specification Clause |  |  | Frequency |  | Verification from Thiess / Client (H/W/R/M) | [6 empty] | Records or Comments
[18 empty] | THIESS (Initial) |  |  |  |  | Client (Initial)
1 | Pre-Construction
1 | Drawings supplied most current IFC Retrieved from InEight |  |  | ENG |  |  | Visual |  |  | Reviewed drawing register |  |  | Reviewed drawing register |  |  | Prior to works |  | HP |  |  |  |  | W
2 | Management Plans submitted and approved as per PMP |  |  | ENG |  |  | Visual |  |  | Approved Package MP’s |  |  | Approved Package MP’s |  |  | Prior to works |  | HP |  |  |  |  | W
3 | Inspection Test Plan (ITP) submitted and approved |  |  | ENG |  |  | Visual |  |  | Approved ITP revision |  |  | Approved ITP revision |  |  | Prior to works |  | HP |  |  |  |  | W
4 | Lot Register/ WBS submitted and approved |  |  | ENG |  |  | Visual |  |  | Approved WBS |  |  | Approved WBS |  |  | Prior to works |  | WP |  |  |  |  | W
5 | Check existing services and dial before you dig |  |  | ENV/ENG |  |  | Visual |  |  | Approved erosion and sediment control plan |  |  | EVAMP001-EVA- EN-PLA-0001 |  |  | Prior to works |  | HP |  |  |  |  | HP
6 | Underlying lot & ITP signed off and conforming |  |  | ENG |  |  | Visual |  |  | Topsoil stripping ITP signed off |  |  | Approved QMP |  |  | Prior to works |  | HP |  |  |  |  | W
2 | Construction
7 | Removal and replacement of unsuitable material |  |  | SV |  |  |  | Visual |  | Determination of unsuitable material by the Level 1 GITA or Principal is required prior to the removal of any unsuitable material. Unsuitable material shall be disposed as directed by the company or in areas specified in the annexure. |  |  | EVAMP001-THS- CV-SPE-0001 |  |  | As required |  | HP |  |  |  |  | W
8 | Subgrade preparation – 200mm depth |  |  | SV |  |  |  | Visual |  | Area to be ripped and conditioned to suit a minimum CBR value of 10. |  |  | C10 and C14 107501-EB- 00000-27280-001 Rev A EVAMP001-THS- CV-SPE-0001 clause 4.16 |  |  | As required |  | HP |  |  |  |  | HP
9 | Proof-roll subgrade surface prior to placement of embankment fill |  |  | SV |  |  |  | Field Test |  | All subgrades and foundations shall be proof rolled under a standard 8 tonne axle load to confirm that, in the principal’s opinion, deflections are negligible. |  |  | EVAMP001-THS- CV-SPE-0001 clause 4.16 |  |  | As required |  | HP |  |  |  |  | W
10 | Surface level check/ and survey pick-up |  |  | Surv |  |  |  | Survey/ Field test |  | Surface level as per Table 10 C15 DXF file submitted to Company |  |  | EVAMP001-THS- CV-SPE-0001 clause 4.16 |  |  | As required |  | HP |  |  |  |  | HP
3 | Post Construction
11 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP |  |  | ENG |  |  |  | Visual |  | GDP permits closed. ITP closed. Approved MDR |  |  | - EVAMP001- EVA-EN-PLA- 0001 - EVA PMP |  |  | As required |  | HP |  |  |  |  | HP
☐ Conformance to Specification | [5 empty] | ☐ Requires Re-Work: (Provide Details): | [15 empty] | ☐ Non-Conformance |  |  | NCR No:
Approved by THIESS QA Representative | [6 empty] | Date |  |  |  | Approved by THIESS Project Manager | [7 empty] | Date |  | Approved by Client | [6 empty] | Date
Name (print): | [10 empty] | Name (print): | [9 empty] | Name (print):
Signature: | [10 empty] | Signature: | [9 empty] | Signature:
RESPONSIBILITY |  |  |  |  | METHOD | [8 empty] | VERIFICATION TYPE | [5 empty] | ITP REVISIONS
Symbol |  | Legend |  |  | Symbol |  |  |  | Legend |  |  |  |  | Symbol | Legend |  |  |  |  | Rev No. |  | Amendment Details |  |  |  | Date | Approver
C |  | Client |  |  | W |  |  |  | Written |  |  |  |  | HP | Hold
SV |  | THIESS Supervisor |  |  | A |  |  |  | Application |  |  |  |  | W | Witness
Eng |  | THIESS Engineer |  |  | D |  |  |  | Design |  |  |  |  | R | Review
Surv |  | Surveyor |  |  | S |  |  |  | Survey Data |  |  |  |  | M | Monitor
SC |  | Subcontractor |  |  | V |  |  |  | Visual
PM |  | Project Manager |  |  | T |  |  |  | Test
CM |  | Construction Manager |  |  | C |  |  |  | Certificate
MC |  | Material Controller |  |  | TA |  |  |  | Test / Approval
ENV |  | Enviro officer |  |  | M |  |  |  | Measure
Please transfer information into THIESS Data System ‘Inspection and Test’ Register.