## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | EVAMP001-THS-QA-ITP-0001 - Clear and Grubbing | itp |  |  |  |  | EVAMP001-THS-QA-ITP-0001 - Clear and Grubbing - Rev B
section | 1 - Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Management Plans submitted and approved as per PMP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved Package MP’s
label | Specification Clause - Approved Package MP’s
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved ITP revision
label | Specification Clause - Approved ITP revision
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 4 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - WP
label | Verification: Client (Initial) - W
checkpoint | 5 - Erosion and sediment control plan approved
label | Responsibility - ENV/ENG
label | Method - Visual
label | Conformance Criteria - Approved erosion and sediment control plan
label | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 6 - Check existing services and dial before you dig
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - DBYD certificate and EP
textbox | Specification Clause - Excavation Permit (EP) Doc no.
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 7 - Ground Disturbance Procedure (GDP) obtained
label | Responsibility - ENG/ENV
label | Method - Visual
label | Conformance Criteria - GDP permit with work packs
label | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 8 - Area of works pegged and clearly defined to GDP. Pre- strip area survey pick-up
label | Responsibility - SURV
label | Method - Visual
label | Conformance Criteria - Clearing pegs installed at nominal intervals to ensure no over-clearing
label | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001 to ensure no over-clearing
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 9 - Area of works been pre-cleared for Fauna/ Flora
label | Responsibility - ENG/ENV
label | Method - Visual
label | Conformance Criteria - All areas to be pre-cleared prior to clearing operations.
label | Specification Clause - EVAMP001-EVA- EN-PLA-0001
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
section | 2 - Construction
checkpoint | 10 - Clearing of vegetation and removal to nominated stockpile location
label | Responsibility - SV ENV
label | Method - Visual
label | Conformance Criteria - Spotter/ catcher in place during clearing operations
label | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
label | Specification Clause - EVAMP001- EVA-EN-PLA- 0001
label | — EVAMP001- EVA-7340-PE- PRM-1
label | — C22 of EVAMP001-QVT- PE-PRM-1
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 11 - All Erosion sediment control measures installed prior to construction
label | Responsibility - ENG/ENV
label | Method - Visual
label | Conformance Criteria - All control measures for erosion sediment control need to be implemented after clearing has been completed.
label | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
label | — EVAMP001-EVA- EN-PLA-0001
label | Frequency - After clearing completed
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 12 - Inspection of foundation prior to next stage of construction
label | Responsibility - SV ENG
label | Method - Field Test
label | Conformance Criteria - Proof roll where required
label | Specification Clause - EVAMP001-EVA- EN-PLA-0001
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 13 - Surface level check/post-strip area survey pick-up
label | Responsibility - SV/SURV
label | Method - Survey/ Field Test
label | Conformance Criteria - DXF file submitted to Company
label | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
section | 3 - Post Construction
checkpoint | 14 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - GDP permits closed.
label | ○ ITP closed. Approved MDR
label | Specification Clause - EVAMP001- EVA-7340-PE- PRM-0001
label | — EVA PMP
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | Final Inspection
bool | Conformance to Specification
bool | Requires Re-Work:
textbox | (Provide Details):
bool | Non-Conformance
textbox | NCR No:
holdpoint | Approved by THIESS QA Representative / THIESS Project Manager / Client
checklist | EVAMP001-THS-QA-ITP-0002 - Topsoil Stripping | itp |  |  |  |  | EVAMP001-THS-QA-ITP-0002 - Topsoil Stripping - Rev B
section | 1 - Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Management Plans submitted and approved as per PMP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved Package MP’s
label | Specification Clause - Approved Package MP’s
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved ITP revision
label | Specification Clause - Approved ITP revision
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 4 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - WP
label | Verification: Client (Initial) - W
checkpoint | 5 - Check existing services and dial before you dig
label | Responsibility - ENV/ENG
label | Method - Visual
label | Conformance Criteria - Approved erosion and sediment control plan
label | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 6 - Ground Disturbance Procedure (GDP) obtained
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - DBYD certificate and EP
label | Specification Clause - Excavation Permit (EP) Doc no.
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 7 - Area of works pegged and clearly defined to GDP. Pre-strip area survey pick-up
label | Responsibility - ENG/ENV
label | Method - Visual
label | Conformance Criteria - Boundary pegs installed at nominal intervals to ensure no over-stripping
label | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
section | 2 - Construction
checkpoint | 8 - Stripped topsoil load and hauled to nominated stockpile location
label | Responsibility - SV
label | Method - Visual
label | Conformance Criteria - Stockpile locations located 40m from watercourses and not exceed 2m in height.
label | ○ Native seeding of topsoil stockpiles as agreed with Company.
label | ○ The provisional depth of stripping shall be 150 mm unless shown otherwise on the drawings
label | Specification Clause - C9 of EVAMP001-QVT-PE-PRM-1
label | — EVAMP001-EVA-EN-DCR-0002
label | — EVAMP001-EVA- EN-PLA-0001
label | — 107501-EB- 00000-27280-001 Rev A
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 9 - Topsoil location, destination and quantity catalogued.
label | Responsibility - SV
label | Method - Field Test
label | Conformance Criteria - A topsoil inventory will be maintained with information on topsoil volumes and stockpile locations
label | Specification Clause - EVAMP001-EVA-EN-PLA-0001
label | ○ EVAMP001-THS- CV-REG-0003
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 10 - Surface level check/post-strip area and volume survey pick-up
label | Responsibility - SV/SURV
label | Method - Survey/Field Test
label | Conformance Criteria - DXF file submitted to Company and inventory updated
label | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
section | 3 - Post Construction
checkpoint | 11 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - GDP permits closed.
label | ○ ITP closed. Approved MDR
label | Specification Clause - EVAMP001- EVA-7340-PE- PRM-0001
label | — EVA PMP
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | Final Inspection
bool | Conformance to Specification
bool | Requires Re-Work:
textbox | (Provide Details):
bool | Non-Conformance
textbox | NCR No:
holdpoint | Approved by THIESS QA Representative / THIESS Project Manager / Client
checklist | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation | itp |  |  |  |  | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation - Rev 0
section | 1 - Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC Retrieved from InEight
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Management Plans submitted and approved as per PMP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved Package MP’s
label | Specification Clause - Approved Package MP’s
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved ITP revision
label | Specification Clause - Approved ITP revision
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 4 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - WP
label | Verification: Client (Initial) - W
checkpoint | 5 - Check existing services and dial before you dig
label | Responsibility - ENV/ENG
label | Method - Visual
label | Conformance Criteria - Approved erosion and sediment control plan
label | Specification Clause - EVAMP001-EVA- EN-PLA-0001
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 6 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Topsoil stripping ITP signed off
label | Specification Clause - Approved QMP
label | Frequency - Prior to works
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
section | 2 - Construction
checkpoint | 7 - Removal and replacement of unsuitable material
label | Responsibility - SV
label | Method - Visual
label | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Principal is required prior to the removal of any unsuitable material.
label | ○ Unsuitable material shall be disposed as directed by the company or in areas specified in the annexure.
label | Specification Clause - EVAMP001-THS- CV-SPE-0001
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 8 - Subgrade preparation – 200mm depth
label | Responsibility - SV
label | Method - Visual
label | Conformance Criteria - Area to be ripped and conditioned to suit a minimum CBR value of 10.
label | Specification Clause - C10 and C14 107501-EB-00000-27280-001 Rev A
label | — EVAMP001-THS- CV-SPE-0001 clause 4.16
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 9 - Proof-roll subgrade surface prior to placement of embankment fill
label | Responsibility - SV
label | Method - Field Test
label | Conformance Criteria - All subgrades and foundations shall be proof rolled under a standard 8 tonne axle load to confirm that, in the principal’s opinion, deflections are negligible.
label | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - W
holdpoint | HOLD POINT
checkpoint | 10 - Surface level check/ and survey pick-up
label | Responsibility - Surv
label | Method - Survey/ Field test
label | Conformance Criteria - Surface level as per Table 10 C15
label | ○ DXF file submitted to Company
label | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
section | 3 - Post Construction
checkpoint | 11 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - GDP permits closed.
label | ○ ITP closed. Approved MDR
label | Specification Clause - EVAMP001- EVA-EN-PLA- 0001
label | — EVA PMP
label | Frequency - As required
label | Verification: THIESS (Initial) - HP
label | Verification: Client (Initial) - HP
holdpoint | HOLD POINT
checkpoint | Final Inspection
bool | Conformance to Specification
bool | Requires Re-Work:
textbox | (Provide Details):
bool | Non-Conformance
textbox | NCR No:
holdpoint | Approved by THIESS QA Representative / THIESS Project Manager / Client