## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-249-CIV-General Concrete
ITP Description: |  | General Concrete
Discipline (e.g. CIV/STR/RAIL: |  | 249-CIV
Revision Number: |  | 1
Revision Date: |  | 2025-03-31
ITP created by: |  | Jason Quan
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Calder Park only
Inspection & Test Plan - General Concrete
|  |  | Document No.: | #REF! |  |  |  |  | Revision: | 1
[9 empty] | Date: | 2025-03-31
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 703 August 2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Non Dependent | VicRoads Section 812 July 2016 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | AS1379-2007 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Non Dependent | AS3610-2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.5 | Non Dependent | AS4671-2019 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries - Materials
2.1 | Bedding Material / Base Layer | IFC Drawings 703.21 812.04 | Bedding material conform to specified requirements applicable to the class of product as detailed on the drawings. Material is registered with VicRoads in accordance with Code of Practice RC500.02. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each mix design, prior to placement of material | HP | Nominated Authority | ConQA Hold Point Release
2.2 | Concrete Mix | IFC Drawings 703.05 (a) 703.07 MRPA Quality Management Plan | Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings. Paving concrete mix conforms to AS1379. SUP concrete mix is registered with VicRoads. No air entraining chemical admixtures shall be used without approval from the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each mix design, prior to placement of concrete | IP | Nominated Authority | ConQA Hold Point Release
2 | Preliminaries - Materials (Continued)
2.3 | Reinforcement Certification (or ACRS Certification) | 703.13 MRPA Quality Management Plan | Reinforcement shall comply with AS4671. Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification) Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, prior to placement of order | IP | Nominated Authority | This ITP
2.4 | Evaporative Retardant | 703.09 | Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of concrete | WP | Nominated Authority | This ITP
2.5 | Curing Compound | 703.10 (a) | Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of concrete | IP | Nominated Authority | This ITP
3 | Pre-construction Activities
3.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
3.2 | Survey Set-out | IFC Drawings 703.17 | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. The Nominated Authority will review and confirm the set out. Attach: Survey Report | Document Review Measure Visual | Where applicable, each lot | HP | Nominated Authority | ConQA Hold Point Release
4 | Construction Activities
4.1 | Excavation | 703.20 | Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving. Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face. Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face. | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
4.2 | Bedding Material Placement & Compaction | 703.21 | Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings). Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted. The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary. All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation. Attach: Bedding Material Delivery Dockets | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
4.3 | Formwork Construction & Placement | IFC Drawings 703.12 | Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional comformance. Joints in formwork shall be constructed such that loss of mortar is prevented. Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation. | Visual Measure | Each lot | IP | SE/PE/SPE | This ITP
4 | Construction Activities (Continued)
4.4 | Construction Joints & Matching Exisiting Surfaces | IFC Drawings 703.24 Relevant Council Standard Drawings | Where applicable, construction joints shall be placed where the new construction ties into existing structures. Consult the relevant Council Standard drawings for the joint detail, these may require: i. Concrete cutting of a shear-key ii. Surface rouighening iii. Drilling and insertion of dowel bars (may also be galvanised) iv. Cutting a groove for sealant Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre. Transitions between different profiles shall be made in accordance with the drawings. Matching of new to existing concrete paving shall be such that it appears identical to the existing section. | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
4.5 | Isolation Joints | IFC Drawings 703.26 (c) Relevant Council Standard Drawings | Where applicable, isolation joints shall be placed: i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features ii. at any location marked on the drawings The joint shall be made with a compressable material extending for the full width and full depth of the paving and secured into position prior to concrete operations. | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
4 | Construction Activities (Continued)
4.6 | Reinforcement Placement | IFC Drawings 703.13 | The correct mesh type and location as shown on the IFC drawings. Any splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum). Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement. Minimum cover of 50mm at edges has been achieved (including tie wire locations). | Measure Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
4.7 | Pre-pour Inspection | IFC Drawings 703.15 703.21 | Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings. | Measure Visual | Each lot | IP | SE/PE/SPE | This ITP
4 | Construction Activities (Continued)
4.8 | Weather Conditions & Evaporation Limits | 703.09 | Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record. | Measure Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
4.9 | Concrete Testing - Sampling Frequencies | 703.11 | Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 50m³ = 1 sample Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum. Compressive strength cylinders = 2 no. 28 day strength. Record: Required information on the Concrete Pour Record. | Test | Each lot | IP | Concrete Tester Foreman SE/PE/SPE | This ITP
4.10 | Concrete Testing - Slump | 703.11 | Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record. | Test | Each sample | IP | Concrete Tester | This ITP
4 | Construction Activities (Continued)
4.11 | Concrete Testing - Compressive Strength Cylinders | 703.11 | Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record. | Test | Each sample | IP | Concrete Tester | This ITP
4.12 | Supply & Discharge Rates | 703.08 AS1379 Clause 4.4.1 AS1379 Clause 4.2.3 AS1379 Clause 4.2.5 | Concrete is supplied at an adequate rate to ensure no cold joints are formed. Maximum elapsed time for discharge (including compaction) is 90 minutes from batching. Concrete that stiffens or is showing signs of stiffening shall not be used. If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record. Record: Required information on the Concrete Pour Record. | Measure Visual | Each load | IP | Foreman SE/PE/SPE | This ITP
4 | Construction Activities (Continued)
4.13 | Placement & Compaction | 703.08 | All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints. Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects. Vibration continued at each point until air bubbles cease to emerge from the concrete. Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets | Visual | Each load | SP | Foreman SE/PE/SPE
4.14 | Surface Finishes | IFC Drawings Relevant Council Drawings 703.25 | Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool. | Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
4 | Construction Activities (Continued)
4.15 | Marking of Conduit Locations | IFC Drawings Relevant Council Drawings 703.28 | The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings. | Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
4.16 | Crack-control Joints / Weaken Plane Joints | IFC Drawings Relevant Council Drawings 703.26 (b) (ii) | Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings. | Visual | Where applicable, each lot | IP | Foreman SE/PE/SPE | This ITP
4.17 | Curing | 703.10 | The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these. Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS. The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings. Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred. | Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
5 | Post-construction Activities
5.1 | Protection of Newly Poured Concrete | 703.27 | All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause. Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days. | Visual | Where applicable, each lot | IP | Foreman SE/PE/SPE | This ITP
5.2 | Stripping Formwork | 703.12 AS3610 Table C2 | Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete: i. 2 days for vertical formwork on external surfaces; and ii. 1 day for vertical forms on permanently hidden surfaces | Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
5.3 | Backfilling & Pavement Restoration | 703.29 | At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging. | Visual Measure | Each lot | IP | Foreman SE/PE/SPE | This ITP
5.4 | Surface Inspection - Cracks | 703.3 | No cracks greater than 0.2mm. If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair. | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
5 | Post-construction Activities (Continued)
5.5 | Surface Inspection - Surface Finish | IFC Drawings Relevant Council Drawings 703.25 703.10 (a) AS3610 Clause 3.2 | After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. Class of finish: Permanently hidden surfaces = Class 4 All other surfaces = Class 3 At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair. | Visual | Each lot | IP | SE/PE/SPE | This ITP
5.6 | Compressive Strength Test Results | IFC Drawings Relevant Council Drawings 703.11 Table 703.111 | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results | Document Review | Each cylinder | IP | SE/PE/SPE | This ITP
5 | Post-construction Activities (Continued)
5.7 | As-built Survey | IFC Drawings 703.15 | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from alinment = ±10mm Rate of change of deviation from RL or alignment = 10mm in 10m Irregularities in alignment = 5mm in 3m Section dimensions = ±5mm Section dimensions (less than 25mm) = ±3mm Width of pavement = -5mm, +15mm Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges. Attach: Survey As-builts / Survey Report | Document Review | Where applicable, each lot | IP | Surveyor SE/PE/SPE | This ITP
5.8 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /