## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
ff6e00b1-fa75-46d1-8134-21f99024d96d | checklist | ITP-225-CIV-Ferris-Subgrade Preparation - Road Rev 0 | itp | ITP-225-CIV-Ferris-Subgrade Preparation - Road | e2f40730-87d1-420c-acfe-2863dacbdf28
7b52391b-ac4c-46eb-aa97-c87e43a5693c | section | 1. Referenced Documentation
91c7839a-a511-4b35-b05b-2542bbd97dbf | checkpoint-no-value | Referenced Documentation
bf33e101-ad81-5f2e-9964-02e0e1b3d770 | note | Document Title: ITP-225-CIV-Ferris-Subgrade Preparation - Road
c5dd3542-f14d-52db-8ecb-f037b967331c | note | ITP Description: Ferris-Subgrade Preparation - Road
9daedb8e-ee59-56fa-8559-fe277f14a176 | note | Discipline (e.g. CIV/STR/RAIL): 225-CIV
e60f056c-9e3b-5d66-aa18-8c112dbe0929 | note | Revision Number: 0
3ae169bf-8e9d-50f2-9534-36550dc8f3b3 | note | Revision Date: 29/01/2025
c433abcf-e7e8-53e2-9dde-694500980ffb | note | ITP created by: Kamel ALSHOBAKI
1926a7c0-4f7c-516d-a20a-2ed04920f8f1 | note | ITP approved for use by: Pradeep Talasila
677013aa-75a6-5e61-9713-1fec4345eca4 | note | 1.1 - Non Dependent
0c2f88b5-cf09-52ae-bc2f-0a3d570f2f4b | note | Reference - VicRoads Section 204
a55d49e8-0822-59d1-a3b1-aabea34c42a9 | note | 1.2 - Non Dependent
61296dc7-5a89-54fe-9c8e-d7e62c0d18bd | note | Reference - VicRoads Section 173
053c52e9-6bdf-4482-9e14-d898b6777902 | section | 2. Preliminaries-Materials
7458ce6c-0294-4a73-8e44-3fb50eb7603b | checkpoint | 2.1 - Material Approval
3ffb6e92-bb18-5f32-99d9-e5fb5fd5a575 | note | Reference - VR 204.4 ©
f5081114-e64d-5155-9d8d-cb8b2db514d2 | note | Acceptance Criteria - Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
cd53a4b2-148e-54e9-bea1-f19eef2c2d3e | note | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
e80a7def-2c51-56e7-ae52-18171bdf4de1 | textbox | Enter: Teambinder Material Approval number
61b8257e-0828-587c-b7fe-197e95432d19 | note | Method - Document Review
caa6cc22-b394-5d60-92de-40bc49992345 | note | Frequency - Once, for each mix material
7e6ac380-ef2e-50cc-8569-356d2b936fc9 | note | Category - HP
57a64b11-3cbf-52f7-a011-44f2334c415c | note | Responsibility - Nominated Authority
cefeabd9-d4f5-587c-a511-2a74756600de | note | Verifying Documents - ConQA Hold Point Release
9a2d04e9-9b33-5b83-b108-42414b054ad3 | date | Date Completed:
4c55ead9-6dd1-47a7-8688-8ab84c22bbbc | signoff | AUTHORITY HOLDPOINT
c66d8a3e-4830-450e-ad87-a946b2930e54 | section | 3. Preliminaries-Documentations
a566f287-4302-4c28-b7b3-c1ba252bb057 | checkpoint-no-value | 3.1 - Non Dependent
bacf7db2-9c70-4551-b70e-7b7d05b6ef46 | section | 4. Pre-construction / Pre-installation Activities
fd261655-c7ef-4635-a0d0-7fdb7db4707e | checkpoint | 4.1 - Survey Set-Out
7e012c5f-4ecc-5bae-9245-09d3842bb4a9 | note | Reference - IFC Drawings
a7a10d69-b7ee-5d55-98e1-45ec12f5cbf5 | note | Acceptance Criteria - Area has been set out in accordance with the drawings
0f85ce9b-1043-5d83-a8fb-6aeccea9e2c7 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
18c2de51-fd6d-5f8d-bbe4-e7d53f1544d4 | note | Method - Verify
a780c087-756f-5950-9a7b-ba30bbecbc54 | note | Frequency - Prior to commencement of excavation
20957b8e-4635-5187-a7f8-586ccf020357 | note | Category - IP
24ad4ea5-5c91-5ad5-8714-77605761072e | note | Responsibility - SE/Surveyor
1003e945-1259-57e0-bd1d-d3da6d0eae2d | note | Verifying Documents - This ITP
5ec7d648-dff8-5425-815c-a2bd9587bd63 | date | Date Completed:
df582e2e-c453-4418-9d78-0885bded7aa9 | section | 5. Construction / Installation Activities
a88e2d55-5ce9-45a5-8a4d-87aeacc1b5dd | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
8ee9c714-7e25-5363-8a31-66484e8f06ee | note | Reference - Section 204.06 (c), Section 204.06 (e) IFC Drawings
903517f0-d367-5fe3-ab79-5892848dd2d0 | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
f41c3d5b-36d3-5a53-a49d-5b0ee0a9a4f7 | note | ○ Assigned CBR ≥ 2.0%
21741f37-206a-5d83-8515-61c2be6bdf2d | note | ○ Assigned Swell less than 2.5%
084294ce-7fab-509f-bb1e-a4c03bff4c87 | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
ff581b6e-96d1-5a22-8ce5-d85650d2d892 | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type B fill.
a79bd214-81e8-59ba-bccc-06c0a0e4b9ac | note | ○ If existing material needs to be removed and replaced with Type B Fill, ITP-CIV Type A/B Fill - Road is to be utilised.
ba1fa54e-c6ce-5671-a6ac-33bf39e192f9 | note | ○ Attach: Laboratory testing Verification:
fe74a465-4b0e-5988-a1ba-a45fec50724d | textbox | Enter: Type A/B fill Lot Number:
c69618f3-9645-58d8-ba72-8c08a24647ae | note | Method - Verify-Document Review
222c9a6b-6ed1-5191-b386-69c81ec067be | note | Frequency - Each lot
7f5c4927-dcd5-5772-a6c0-a2fcd4c7ebab | note | Category - HP
a87c3dac-e016-589c-8b96-4d626d1ddcc3 | note | Responsibility - PE/Nominated Authority
2e5e3a2b-ea20-5402-a08a-cf330180551d | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
6a580748-91db-5929-8591-133f9a5660b7 | date | Date Completed:
c58e3e26-5258-419f-9885-5f2fdff63b13 | signoff | AUTHORITY HOLDPOINT
d974f8b1-b714-4500-9d2d-8de6adabcf0e | checkpoint | 5.2 - Material classified as silt
5561dc3a-c3d3-59f2-894e-bb80206f0871 | note | Reference - Section 204.04 b)
daf19a94-3a08-57e9-9d30-2f63d69f3c4e | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
5e3cb6b1-db8a-5e2d-8793-876637a59d0c | note | Method - Document Review
3fe9fb78-933b-55a0-b274-1e6ae5427a53 | note | Frequency - Prior to commencing
8f94f79f-6eff-541a-afe8-250ad9e86d09 | note | Category - HP
9b7d74c9-3151-5fd0-b4e4-18955a2e8e81 | note | Responsibility - SE/Nominated Authority
85432a43-c4f4-5345-a59d-3e79dda65f20 | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
63f4f722-e839-50c1-99f1-cadd85cb7b7a | date | Date Completed:
5b058efa-e993-4f0c-87b1-0378f77f67f6 | signoff | AUTHORITY HOLDPOINT
2863433e-ebf1-400d-8866-e250248cab22 | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
0884a149-fe73-5b9e-912d-69b8c901e283 | note | Reference - Section 204.06 f)
677600ff-5e3f-571a-9363-3cd8552088ad | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
279f658f-8860-5fbf-a69e-4efbf95a29ca | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
8ab98008-ab9a-5ef5-a33d-fbd670c91881 | note | Method - Site Inspection/ Document Review
a2614f61-b412-5023-b453-ae9711ba55c9 | note | Frequency - Prior construction of the regulating layer
14290d39-3072-548c-ab8b-172ae5b6245b | note | Category - HP
84f9e883-8a61-594b-9926-a3e13a5fb2bc | note | Responsibility - SE/Nominated Authority
427fdc69-1e92-5770-8722-aac602b8c3d3 | note | Verifying Documents - This ITP
281425a1-5f40-5000-bff5-c31a986f3252 | date | Date Completed:
5222c264-cefb-4ab8-aefb-206ec37a054d | signoff | AUTHORITY HOLDPOINT
b45fc5c7-7156-4408-9fa2-a09a9cdf69ae | checkpoint | 5.4 - Unsuitable Material
920e1a88-63a7-5235-9601-d7e053eb9488 | note | Reference - Section 204.07 d)
3323b40d-63f5-5b2f-8395-040eda67fc53 | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
d808f85e-adce-566e-b7d9-304ace381dd3 | note | Method - Visual inspection
1e80a9bf-268e-5338-9a92-afaf6a3af930 | note | Frequency - Each lot
3266c92a-401a-51ce-80c5-2ae08c867079 | note | Category - HP
27a25fbe-df7a-592d-8767-6344630ed9ff | note | Responsibility - SE/Nominated Authority
2f337b49-7182-5911-997d-fe9638ac0e8c | note | Verifying Documents - This ITP
33a7e6a9-6d23-5f3e-9e89-b1e56ae8d5aa | date | Date Completed:
555b6d41-b254-4f1a-91de-d107134f8da1 | signoff | AUTHORITY HOLDPOINT
35d28ce1-e9ca-4056-a45e-f4d3951ec9d6 | checkpoint | 5.5 - Groundwater
c9de7442-2a04-5660-b334-2424f80efb7d | note | Reference - Section 204.06 h)
4302d040-b0fb-5711-b92c-500f3c10e87f | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
fc865157-fb31-580f-90d5-ec0d2ebc2a96 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
af5108ca-9a9e-5400-9da4-e5d91eafad3c | note | Method - Visual inspection
7b42affd-1cc2-5e9a-b690-f5607f7777c4 | note | Frequency - Each lot
d2db9434-da08-5fcd-8ff3-f4c5bbb8f82c | note | Category - HP
8ef2db1c-9a3e-546d-b033-db37086f4ffb | note | Responsibility - SE/Nominated Authority
6f24e728-a028-5ffb-bb06-21c1dd8a9fb2 | note | Verifying Documents - This ITP
edd2e88a-82fa-5484-973e-9a4a0cd31c67 | date | Date Completed:
66d85a0c-7c16-4f1c-9316-19d6048ca0ec | signoff | AUTHORITY HOLDPOINT
d4fc7723-7150-48f3-b0b5-55c3f718cf7d | checkpoint | 5.6 - Cut to Fill Zones
9569e63f-28e1-5489-b73e-5f5c4e645bf1 | note | Reference - Section 204.06 g)
1b921c92-29ea-5e2f-93ca-40032d6630ef | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A/B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A/B material.
00d88832-413a-56b1-8b52-ed17c471c374 | note | Method - Site Inspection
b47118e3-e7ae-57cb-aba1-0b64bc2a04af | note | Frequency - Each lot
92139080-67f0-5504-8763-3947b6105cb0 | note | Category - IP
3720c37f-ad89-5641-a5a8-22bdd2e9348f | note | Responsibility - SE/Site Supervisor
6eecb523-d677-5eb3-a333-f63ef44d2642 | note | Verifying Documents - Sign ITP
e858e123-63db-53f1-9f3e-2d63ac942501 | date | Date Completed:
08397a0f-5971-4477-b193-bd0a652c8c4a | checkpoint | 5.7 - Proof Roll
80b8fd6e-60da-511f-a93a-5ae95bea3f82 | note | Reference - Section 173
4e74c48c-d2f9-5ffb-9b5f-1741517465fd | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
2c3f852f-2796-5f4d-9792-5057cd792a4e | note | Method - Visual inspection
5604c166-1012-5541-b521-cf13ec37711d | note | Frequency - Each lot
9199ba2f-59ae-5308-ac98-5181208ad6fd | note | Category - HP
45a56bbf-5264-5ae8-a266-3bc496cfcc2c | note | Responsibility - Site Engineer/Superintendent
29e0ff93-4ca2-52b4-8ee2-4bb84cd6a3a2 | note | Verifying Documents - This ITP
a0a0f91f-1f97-5c84-a688-e22cc4df3978 | date | Date Completed:
d618f530-8ca4-477d-8cc3-b150c0b61ba0 | signoff | AUTHORITY HOLDPOINT
dedb3cac-a58f-482f-87c2-4d4daeabb176 | checkpoint | 5.8 - Compaction Testing
1bf7c7b1-adaa-5c29-81fa-cc2ab459005b | note | Reference - Table 204.131
3dbf4ce0-93eb-5436-8ec1-403e64cf0ad9 | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
e162db90-ad48-5849-a86a-4c3b7ffb0bd4 | note | ○ Scale B: Characteristic Density Ratio 98%.
1b946f3e-486e-5c64-a3b5-226d6013376d | note | ○ Attach: Compaction Test Result:
2d75fd2a-d190-548b-b728-cdb177d746d3 | note | Method - Document Review
e626005d-3486-5c51-8411-122743d8647d | note | Frequency - Each lot
bdb1d54c-1647-5430-9c88-91840c1f47c7 | note | Category - IP
5e7df62e-9efa-5a89-a36c-1797f8be4cf1 | note | Responsibility - PE/SE
326e0513-2ff5-5c9a-b9e9-9a1cda4d0046 | note | Verifying Documents - Test Records, Lot Register
5737c462-377e-5d00-83dc-ff2e69a6e97c | date | Date Completed:
f58d806c-8bde-4afd-8b1e-1e76fe3833cd | section | 6. Post Construction Activities
ab99ecd0-5d53-4762-8cd9-bd3f3334a891 | checkpoint | 6.1 - Post Compaction Material Property Testing
a49cb4d4-69bd-5149-9e36-9e71326d8671 | note | Reference - Table 204,041, Table 204.141 Section 204.14 a) or b)
4534444f-2aee-56db-9a51-c5aa811e56f6 | note | Acceptance Criteria - Material Properties:
ad2121cd-03be-5841-accf-cf01640d7b54 | note | — CBR ≥ 2% and Swell ≤ 1.5%
54c5e00d-4360-5381-b193-01ee98d0d42d | note | — Max Permeability = 5X10-9 m/s
cca5c107-76f8-56c5-9e1b-9a2387342a70 | note | ○ Grading:
5f1c65a6-9d57-5223-a4f2-dc6c220ba600 | note | — 75.0mm 100%
767c7ed0-0f23-558d-a6e1-cb6dfa9f7d47 | note | — 4.75mm 40-80%
b9a408e5-5627-50c3-95c8-ad2ebae63975 | note | — 0.075mm 10-40%
a7611230-78b9-5466-83a7-1b12c0522164 | note | — Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
66ca715a-646a-5f68-9db2-381e956bad3a | note | ○ Scale B:
e26cd8ff-2941-5fc4-97f7-9f2ffad8510c | note | — 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
c6fddaa7-8684-5b4f-8102-9d4ce217dc82 | note | — Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
bc01d941-4079-5068-a9a4-ed3c3b4bcd5b | note | ○ Attach: Post compaction test results:
6960e8d4-2662-5c9a-b6f8-71cfc87ea05d | note | Method - Review Document
3fe130f2-f10c-527a-b839-7e56b0394a15 | note | Frequency - Refer to Section 204
6350efcb-8cf8-5525-ba41-e9cc1f11474b | note | Category - IP
ed5277d0-1f52-541e-b4ff-0a32f90c02df | note | Responsibility - PE/SE
bad861d0-5a58-534a-a247-b4b2be9c74e2 | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
411931ac-b3fe-53e8-87d8-fc1ac05d0c1e | date | Date Completed:
48c908a8-7f0d-483b-b8d8-c06b85fbbc71 | checkpoint | 6.2 - Survey Conformance
6528bc45-6b10-5109-a88e-914f8af3d0d0 | note | Reference - VicRoads 204.03f,g and h
3fa0afc6-8d64-5788-b4cb-7fe6c5eb1aaa | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
df839e69-cdd1-53c9-81cd-aea5d3d5c8ec | note | ○ Level tolerances (Scale B):
d4d2917d-d745-5fad-b5b5-dd917ea344b8 | note | — Range x = +5, -25mm
834ecddd-7c72-5a65-a1bf-4b11cd5c1584 | note | — Max S = 15 mm
05101f7a-7f8f-509d-8a92-784e587905c2 | note | — 40 measurements per lot
45dbc9d9-8a0b-52c6-80a2-ac9a28b1c1af | note | Method - Review Document
43e5fe43-6b5a-5f11-b5a3-cc933cc0f26c | note | Frequency - Each lot
52cced5a-ed75-528f-be07-c9c49c5aa762 | note | Category - SCP
86a9bd21-7c1e-50bd-80d1-f7ea0c6afbc5 | note | Responsibility - SE/Surveyor
f72d79e1-64f0-5768-82ff-edea2fc810ca | note | Verifying Documents - Sign ITP, Attach Survey Report
3b83e103-f17a-510e-971c-f68078898021 | date | Date Completed:
eb6b4722-f431-4e1a-8203-609d79ee74eb | checkpoint | Final Inspection
a09e3277-61ba-5686-a69a-ba0800160f83 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
aa4ef702-2b3b-5298-8059-750634d81433 | textbox | Name:
535afe58-6077-5d01-988d-f16c6714a6c5 | textbox | Position:
b45c7731-7fac-50de-af79-ee6bc4986f69 | textbox | Date Completed:
cf4ef08e-5e2b-47a6-87c6-7481c11859c1 | signoff | Sign ITP
9b5d3812-7d1a-4e07-b48a-aaa24516f45a | checklist | ITP-227-CIV-Ferris-Kerb & Channel (Supply and Install) Rev 0 | itp | ITP-227-CIV-Ferris-Kerb & Channel (Supply and Install) | 5052ff9d-b20e-4ba5-a18a-8b7c93b259d1
19e270c0-cb94-4d45-af36-24b1e35e55c9 | section | 1. Referenced Documentation
e6b350e5-1d1a-4478-9c33-c34d8b147c54 | checkpoint-no-value | Referenced Documentation
3e0a5031-b434-549e-97c0-be0ea6b0cf66 | note | Document Title: ITP-227-CIV-Ferris-Kerb and Channel (Supply and Install)
327ef5ff-0262-5de5-a8c7-0b4b8661b5b5 | note | ITP Description: Ferris-Kerb and Channel (Supply and Install)
d7beba6e-1da1-5709-8fe6-1e24dcbb1cc3 | note | Discipline (e.g. CIV/STR/RAIL): 227-CIV
06eb4c1f-98e3-5d1a-bb34-39a27dd4d7cd | note | Revision Number: 0
07da6883-42f0-55dc-80aa-ba2a08a87d6c | note | Revision Date: 23/01/2025
e63a8b4d-7a15-56be-84b6-2070d676832f | note | ITP created by: Kamel ALSHOBAKI
4f4dfb8a-3f28-5f19-904a-e48207fede32 | note | ITP approved for use by: Pradeep Talasila
d75cd20e-1a11-5ac7-9d30-6079162e1d8a | note | 1.1 - Non Dependent
4330bd7f-4b1f-5288-8879-1cd1e2fea379 | note | Reference - VicRoads Section
3f2609ab-1380-5f62-b26d-e7a2c0c7606d | note | ○ 703 (August 2021)
50654fc4-6be7-5f11-b9e1-f276a9a0b16b | note | ○ VR SD2001
3590b75f-2ef3-586a-b309-2aa4159d9a87 | note | ○ VR SD2102
58909279-021e-5f77-8f76-e05df29a13ff | note | ○ AS 2876
92324ace-2a16-5eef-8b84-fafea3d59164 | note | ○ AS1379
f573439b-e7c1-4596-8452-1d1e1da2c8e6 | section | 2. Preliminary - Materials
c8f7eb0b-ca62-42c5-9d38-2bccdb34a405 | checkpoint | 2.2 - Mix design
784e39bf-e240-533f-a99f-5ab87536a221 | note | Reference - Section 703.05, 703.06, 703.07
23c8f380-3c5e-57af-be4a-a301f6ff1fd4 | note | Acceptance Criteria - Approved VR mix design to be used.
b7754d05-38ce-5976-964b-8f10789fdc57 | note | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
17988ed7-9c6d-5614-aa82-bfe4b77363f8 | note | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
dbb2a1a2-1a9d-5cb7-ab27-f5addcccf942 | note | ○ Attach: TeamBinder Material Approval Ref No.
6d0de6b5-899c-538d-afb7-a7f1fe7b9165 | note | Method - Verify, Document Review
c08efdd9-f913-5f26-bfdd-c3929d075d27 | note | Frequency - Prior to commencing any activity
d9578739-6741-545a-ad52-b6f6c003dc25 | note | Category - HP
ad31b2d3-8350-5f77-a8b3-3d9e4b992171 | note | Responsibility - Nominated Authority
29fd1b38-95d9-561c-b2ec-a345decdb0b3 | note | Verifying Documents - Conqa HP Release
67096bd3-8b38-550b-ae41-d902288a208a | date | Date Completed:
a0ae1357-c75c-4aa6-9ade-158a041f68c7 | signoff | AUTHORITY HOLDPOINT
2719a63e-b1bf-493c-97d5-c50a3e20831f | checkpoint | 2.3 - Bedding Material
06c4f750-6f51-574e-ba0f-d5e82a4e5b68 | note | Reference - Section 703.21 IFC Drawings
175050d5-d5b0-5e39-9693-c71170d77565 | note | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
4d8ac858-5ce6-55c9-bd60-fa6030528ae1 | note | ○ Attach: TeamBinder Material Approval Ref No.
cd722431-4b36-51cc-812a-9d446bbcf7ca | note | Method - Verify, Document Review
6bbe06b4-b827-5ada-bc79-bb136d573a9f | note | Frequency - Prior to commencing any activity
2d445620-9823-5917-b53a-f0eee4cbf4c8 | note | Category - HP
c772bec1-f22d-5030-8818-ea2c235a1e0c | note | Responsibility - Nominated Authority
8edd0d70-75b6-59c0-9787-7f5ec340e4f1 | note | Verifying Documents - Conqa HP Release
b0bbb60c-4f7d-55c6-82f3-2750677b697e | date | Date Completed:
ad63c6dc-e5ad-4066-b174-a7e592972875 | signoff | AUTHORITY HOLDPOINT
b35d972f-5b41-4571-b6a8-12a0bef510c9 | checkpoint | 2.4 - Curing Compound
e7361666-beb4-5b96-bc6c-84536f597e9b | note | Reference - Section 703.10
a7011487-ba99-5de5-b961-9c30810ef558 | note | Acceptance Criteria - Curing compound shall comply with AS3799
1b6e4595-1717-50f8-af58-cfe58d3b36a1 | note | ○ Attach: TeamBinder Material Approval Ref No.
311f016b-12fa-58cc-9c19-c33f280e406f | note | Method - Verify
f540f97f-3c25-5511-ae4d-1653861d6dd9 | note | Frequency - Prior to commencing any activity
7e0bb16c-493c-5209-b80e-51955cf28153 | note | Category - HP
3266aa9f-c1e8-5f8c-893c-c78e34d58389 | note | Responsibility - Nominated Authority
8540f64d-45ed-5145-8986-794cb7c5d33f | note | Verifying Documents - Conqa HP Release
d199de46-8441-59dc-8729-4bcaa45e42ee | date | Date Completed:
7aa1cc23-47de-43a3-b706-2c2493cc30ba | signoff | AUTHORITY HOLDPOINT
ffcb1083-3855-4115-be26-633787e8520b | section | 3. Preliminary - Documentation
18c6772c-bef5-493d-8e15-cbc20ce6f2b7 | checkpoint | 3.1 - Check for correct documentation
f08898c7-2e50-5cd9-8475-34679e0facb2 | note | Reference - IFC Drawings
e32d0661-e846-59b6-824b-b857c7e909f8 | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
aa13a859-17a3-563f-8408-521f1c9ec25e | note | – Using the correct and complete set of drawings
4ee8bb63-ae8b-5e20-a44d-b5e8229a4adb | note | – All drawings are the latest version
18a7c5d1-96a5-5479-82e9-796f7fd5bd77 | note | Method - Visual inspection
cc5b9d72-8e94-516b-8134-a706d0b14f96 | note | Frequency - Prior to commencing any activity
f499426e-45f3-5154-9ec9-99d79a3bf28a | note | Category - HP*
f8b58858-559a-5bf9-a239-72f4892718db | note | Responsibility - SE/Site Supervisor
5b90a2b6-4217-5bf0-8ac9-84e15cd09f58 | note | Verifying Documents - ITP Signed
3ae87ecc-19e4-56e1-be67-06ba63e73c38 | date | Date Completed:
f081c9bd-0287-423e-ad47-a3b94b04148e | checkpoint | Lot Map
d7180ef9-57fc-5f27-998d-843f4f85f3cc | note | Reference - MRPA Lot Management Procedure
579ecd8e-93c6-54f1-b500-e25264a67c1a | note | Acceptance Criteria - Upload a Marked up drawing which indicates the Location of this Lot:
a25a0060-c5b4-55a6-88c0-23ecc1a7c368 | note | ○ Attach: Lot Map
9ea50cc3-d045-58f0-870d-f479e73d3c9c | note | Method - Document Review
f44ff8e7-8645-5427-bb8b-d5e94f467fda | note | Frequency - For Each Lot
6581afe4-fe30-5893-ba38-e98d32f2e4f7 | note | Category - HP*
e33a7fee-37e7-55f5-b92b-26bee38237f8 | note | Responsibility - SE/PE
201e7019-0abb-5d7d-afba-bef675a31f42 | note | Verifying Documents - Lot Map
ccbc401f-77d1-583f-9b8f-f2fa6475247a | date | Date Completed:
82095e27-1dd1-41dd-98b2-9b3645a14ad4 | section | 4. Pre-construction / Pre-installation Activities
0ae3c881-b1b3-4d02-ad26-71159512dfd9 | checkpoint | 4.1 - Setting out
dd320e6e-f891-5e93-b5f1-cffa6292880c | note | Reference - Section 703.17 IFC Drawings
c53018e4-544a-55de-91d6-61994634d43e | note | Acceptance Criteria - Set out work in accordance with IFC Drawings.
789b46d6-4563-5b3e-a689-7cdf13c50367 | note | ○ The superintendent will review and confirm set out.
cedf7da2-54d6-597d-9ce2-74ab291e2622 | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
3a70d09a-c806-5fe9-a480-5a673ea4fe3e | note | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
3833e348-13cb-5190-9087-7e742824e1b4 | note | Method - Verify
9dc4d596-776d-558b-93d2-03251092db91 | note | Frequency - Prior to start
174388e7-5a35-53fb-b53f-f696910f99bd | note | Category - HP
5e173dc4-1307-587c-9158-a44cc6f2997b | note | Responsibility - Surveyor/Nominated Authority
6ac7209b-984b-530e-bc12-66dd7f4de6e1 | note | Verifying Documents - Conqa HP Release
25d21716-1a66-58b9-9102-705688c6cd64 | date | Date Completed:
1b987d97-6243-4575-b7bb-d41cccda42fb | signoff | AUTHORITY HOLDPOINT
1d9b4b4a-a81b-4149-b282-111112d3aa5c | checkpoint | 4.2 - Temporary drainage provisions
49ddb9ab-02cc-50eb-8468-953250cfe873 | note | Reference - Section 703.18, CEMP
4e401666-a0c9-5f1e-86ef-39fe142e1834 | note | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
6325c5ad-c747-5a36-b1f5-ce1eab7d50a8 | note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
c9cc9217-6da2-5bcf-88ff-11d8b4bca56a | note | ○ Attach: relevant written approval from relevant stakeholder.
7074c32c-a148-5cca-beb1-858247d8ff65 | note | Method - Visual inspection, Document Review
2b85b532-b8f8-518d-967d-c2a639e31c33 | note | Frequency - Prior to start (where required)
17a363a6-160f-51fd-83f0-a47d3828959a | note | Category - HP*
08a828cd-a79a-55d8-8a51-50858dd4ac35 | note | Responsibility - SE/PE/Site Supervisor
6fa9e615-d6be-5bfa-8997-2ccff6400aa3 | note | Verifying Documents - ITP Signed
fea07976-f50c-5f51-8a96-5dbc9e839450 | date | Date Completed:
c6115ca8-d8d3-40d2-9b06-722cec1185bb | section | 5. Construction / Installation Activities
e60e79f5-4807-40d1-be44-fec5f583e90a | checkpoint | 5.1 - Bedding
916e3333-11d4-5136-9e13-39d113c6a5b8 | note | Reference - Section 703.21
1ad617bd-1257-5da1-ba65-721d04835fc6 | note | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm.
3a52da18-7e2d-5916-bb1d-15dbc6f61d5b | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
bfd9f2ba-9228-5283-9f7f-5652b1a800fc | note | Method - Visual inspection
656abf73-6f85-53d0-8871-ea172d4cecb1 | note | Frequency - Each lot
b0ed6d64-c649-5260-b2fd-0a2b78f9f37e | note | Category - WP
94a3fe97-ce99-564a-a575-afee01a87fb8 | note | Responsibility - SE/Site Supervisor
0fd5ba5f-8801-5252-a873-950f394dd44c | note | Verifying Documents - ITP Signed
65643170-d39d-53b7-a7e5-656febfe466a | date | Date Completed:
04a1963b-0f24-496e-9371-dec1a264a003 | checkpoint | 5.2 - Formwork
9ead5182-6779-5b8d-8a44-d2e7bfc751d4 | note | Reference - Section 703.12 AS3610
aa378169-c8b0-5fd2-99ae-eecb5eb153dd | note | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
42628e13-3aae-5e1d-acae-9203d049c1fb | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
3c7b4a5a-421d-527e-8222-8bef8927d7dc | note | Method - Visual inspection
111fc329-a132-52b2-a1b2-7b5eb20ba02e | note | Frequency - Each lot
0df1ac8e-3cba-5a94-9b56-0a6038e23e77 | note | Category - WP
b112c5c6-56a1-5fa3-83cf-e5650a1a4803 | note | Responsibility - SE/Site Supervisor
c385edb5-3230-5e92-9e24-07e59c2d734e | note | Verifying Documents - ITP Signed
9ab1ab81-47a0-5930-94c2-e468b1416792 | date | Date Completed:
dde12457-a9da-4be1-8862-7e97778e8388 | checkpoint | 5.3 - Pre Pour Check
591304c8-e9e5-5fd8-a6b3-aa81d6bd4b5a | note | Reference - Section 703.09, Section 703.2, Section 610.17 (a,b,c)
d1b86e3f-5531-5186-bef7-4d70e7adee9a | note | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface .
e3949edc-1554-5aad-80e4-35d1357b3c79 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
a19033c1-eaf6-536e-908c-0972b444c79b | note | ○ Attach: Pre-pour Inspection Record
7e3fdab3-1bed-567f-afef-ad23f99855ac | note | Method - Verify
c5670c76-8a7f-565a-a82c-2f8371696146 | note | Frequency - Each lot
bf78fa0f-1794-562e-9501-eef1c0e13c38 | note | Category - HP*
245fc535-0821-518a-bcfe-94baaa96c4fd | note | Responsibility - SE/Nominated Authority
c175876b-51f3-5c04-a9cd-5468d7a4cd3f | note | Verifying Documents - ITP Signed
82034ab9-59d8-5077-8a29-c194ac08c2dc | date | Date Completed:
5272244d-35eb-4687-bbdc-71b57fc3b505 | checkpoint | 5.4 - Concrete placement
f0096218-7e09-554d-86ca-926acabc540d | note | Reference - Section 703.08, Section 703.23
804cb44e-6411-5fec-a5eb-f4ecac533e9e | note | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
37f77f80-9b22-5080-beaa-cd105607fbc9 | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
d98e834a-5141-5ab9-bc15-613b2e7a9d79 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
c426a58d-ef5b-56bf-8bc6-bff1ca42ee24 | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
59a669ba-ac58-5dcb-9cc1-4fa44837a49f | note | ○ Attach: Concrete Pour Records
a76b5734-2651-5344-b8ea-efe97653c2a6 | note | Method - Site inspection
39b16373-30bd-51f8-9daf-d1e20525eba8 | note | Frequency - Each lot
73b2a6b1-4757-54bb-9398-68571cbb5bbc | note | Category - IP
37815f49-eed3-5c3d-9316-60b8117528bc | note | Responsibility - SE
78b56617-c8d9-532c-a965-6663d8fad512 | note | Verifying Documents - ITP Signed
df758e99-08d6-5a06-9f0e-730744336714 | date | Date Completed:
d70fdae4-ed0d-4863-aaed-b18ece782a05 | checkpoint | 5.5 - Transitions
5d203917-5b1b-509b-87a1-a0b53f48511d | note | Reference - Section 703.24
6f3100ee-719c-5665-b26f-ed1371a437a9 | note | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
de121c23-bafd-5a16-9f20-2d3a9ea60de4 | note | Method - Site inspection
b87d1cff-046e-5dac-b0b1-3a2b62f99077 | note | Frequency - Each lot
a6a4f804-4ff2-55bc-a51f-aa9739fdb963 | note | Category - IP
35a6018c-df4f-5cfe-9fa0-334d4ef03b09 | note | Responsibility - SE
14baa172-790c-5aac-8dad-38ef6bdbbbff | note | Verifying Documents - ITP Signed
31384909-edd1-57a3-b2a5-424eb54351d8 | date | Date Completed:
3b3b2a3c-2ce7-42b2-b446-d1bf550ba83a | checkpoint | 5.6 - Surface Finish
8b575630-3826-5270-bfe3-113a9f631ac2 | note | Reference - Section 703.25
5bef37ca-5b52-5879-a67e-b4e16684d0db | note | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
1ea4e7c4-43b6-5e98-8fd7-037632ebf525 | note | ○ Renderings shall be applied within 30 minutes of extrusion.
6892d8e3-3a59-58af-8d64-be96953733d5 | note | ○ Concrete to have a neat appearance and uniform colour.
e5dc4765-18af-54aa-ac49-50507a76b5c6 | note | ○ Class 3 finish required for external surfaces.
5fa980b2-0691-59c2-a6f4-d92f78c04ba4 | note | ○ Class 4 finish required for permanently hidden surfaces.
612b13d2-9294-5326-8021-b942aa27cd48 | note | Method - Visual inspection
f77951d0-555e-54a2-aa45-40eb21c2014f | note | Frequency - Each lot
4fa57ebc-72c3-522b-adf3-48ab40140094 | note | Category - IP
73fa738f-7d8e-5df4-b853-59225f4951c3 | note | Responsibility - SE/ Site Supervisor
c9d145f8-ad68-578b-afb7-821b63a8b6ad | note | Verifying Documents - ITP Signed
ab776645-4c3b-5c02-956a-0d775ae836d3 | date | Date Completed:
d33d66ce-da50-4a97-a6e3-7406173a0517 | checkpoint | 5.7 - Formwork Stripping
e22203b2-40a8-5b48-9f63-a61824234032 | note | Reference - Section 703.12 AS3610
24a04ad8-a6d8-5ded-9712-1aa7da02a908 | note | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
a3868117-5cd5-5767-9968-5cbe97fbb022 | note | – External faces 2 days
099e1aea-e3b3-5eb3-8b9f-33ed8ade1c08 | note | – Permanently hidden faces 1 day
3dc70f20-df4d-59a3-ac27-e7aa34f9351b | note | Method - Visual inspection
2acfa548-6185-5037-bba0-8eb6c7e3534e | note | Frequency - Each lot
8af2c1db-02f9-5371-a0a5-f0904c0581c9 | note | Category - HP*
65183fad-923f-579a-8ea2-a5a89c27ee7e | note | Responsibility - SE/ Site Supervisor
9d9d8e47-3f7d-5fc3-843f-38c416747f15 | note | Verifying Documents - ITP Signed
d3c8cad0-3591-5645-a601-06773d46d82c | date | Date Completed:
ca7ecfca-e7b1-4951-a3de-e824d57b0de8 | checkpoint | 5.8 - Tolerance
2dc7447f-8af8-5539-9623-4bc453d837b1 | note | Reference - Section 703.15
e44d528b-f19c-5af3-986c-6f4a4309a2bd | note | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
93c60677-8255-5280-a39e-b442d2305c0a | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
1ccb7f9b-b28d-5d0a-b4ef-e13990a6463c | note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
54517dfa-0f37-5717-8e93-bc9800a4e9bc | note | ○ Attach: Post-pour Inspection Records
44ffa194-a9fb-5b2d-87d9-4dab0ba663a7 | note | Method - Verify
22022d47-8896-583c-8fe4-ebb78bbf52dd | note | Frequency - Each lot
99d344b0-aae9-593d-ae58-429f2d4c5f93 | note | Category - IP
dc2e7d56-2e6b-5758-a996-1b87e2415cec | note | Responsibility - SE/Surveyor
65750a08-2335-5c82-bb72-b03275aeb597 | note | Verifying Documents - ITP Signed
abf3878e-e0d4-5bd0-b718-39423e3b49b6 | date | Date Completed:
754e5927-70d7-4089-a224-11324bda8eec | checkpoint | 5.9 - Curing
c04087f1-38a5-5a82-ab65-f3db1ea96ecd | note | Reference - Section 703.10
02edc628-14f0-5ecf-aec3-37d531316ee8 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
6c408969-eba3-5ffc-ab1d-1873a2f6e706 | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
f4ec1203-dbc9-58b2-b9be-f12915bf5ebf | note | Method - Visual inspection
47c37aa3-8737-50ef-8477-2e931ab212b3 | note | Frequency - Each lot
e622fae7-40e3-5204-bfeb-430f69ab9c29 | note | Category - IP
726bcf67-2165-5190-a8b7-7581174840f5 | note | Responsibility - SE/Site Supervisor
21221f08-e167-56a5-93c4-4558b789e2e6 | note | Verifying Documents - ITP Signed
8e65b11d-69e3-51a8-9150-6b41833bae05 | date | Date Completed:
da8eb5d8-eca1-47b9-83fb-fc6c40e0b04f | checkpoint | 5.10 - Joints
b70ede06-9a5f-5c5e-b3de-ea37a61c4722 | note | Reference - Section 703.26
b4759870-25f6-5f82-b96a-b40d7c87ca08 | note | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
83d316e7-441b-560c-9c47-71c51ed2c38c | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
cc085fed-604e-5260-b40d-b7c202779b20 | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
11cd0c5c-6de4-5974-a4da-710ea852d6ce | note | Method - Verify
87550dea-5c55-5048-8990-927e56d10a91 | note | Frequency - Each joint
e91f6ba4-1a2b-5883-870a-35def2984ff0 | note | Category - IP
4757126c-f81d-541c-b1d8-e4781f2e6981 | note | Responsibility - SE / Site Supervisor
c4ab6843-b903-510d-90bb-a1b2f08d89be | note | Verifying Documents - ITP Signed
daf163fb-85ca-5894-9d03-6425c39e454e | date | Date Completed:
d5a0000a-e41d-4e65-bdb7-062cf0fdc39d | checkpoint | 5.11 - Protection of Concrete
b9518ef2-2e46-5a0c-a919-e9e26cba4a63 | note | Reference - Section 703.27
14ca9abe-bf85-5e64-ac3f-8ad0499bf62a | note | Acceptance Criteria - All concrete shall be protected from damage from early loading.
05d72d52-417b-5847-abbf-3b1f2309f3fd | note | Method - Visual inspection
3cde988f-319f-5636-9929-72da1cc478d8 | note | Frequency - Each lot
b9095944-88d3-594a-b3df-ca3e5c5f92ad | note | Category - IP
f0138bdf-3380-54f6-93a7-e2d05b08e172 | note | Responsibility - SE
05407808-6ff0-5549-8dc8-010089055680 | note | Verifying Documents - ITP Signed
b122ab9d-da22-5aa4-9c4a-4d48ba1d1cab | date | Date Completed:
ea724ab9-2827-4b3b-a522-e7b3970fd3d4 | section | 6. Post-construction / Post-installation Activities
901030bd-3652-48cd-9d61-9a41e8269b22 | checkpoint | 6.1 - Backfilling
277bff85-dac2-5f09-a590-5aa761afe6bd | note | Reference - Section 703.29
7737bd76-56cd-5978-8613-a87b8b0bbc7d | note | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
0ca5c0f2-56a4-5403-b64c-b42cfc365af0 | note | Method - Verify
4fa8ceae-2d5d-503b-8943-750fbd21d5ba | note | Frequency - Each lot
edb48d33-b7b6-530e-a975-9670239ca21b | note | Category - IP
9942ed56-a9d3-5d72-9575-e3fc54d2f2a8 | note | Responsibility - SE
7ad02e27-a514-5672-8009-c1efd1525972 | note | Verifying Documents - ITP Signed
dc08d476-50b8-543e-b787-c7e4d1c9e177 | date | Date Completed:
444251a0-7945-49fe-8b01-210e4afb356a | checkpoint | 6.2 - Cracking of Concrete
189ee0ec-6643-563b-acdd-0a65b5a0bbe8 | note | Reference - Section 703.30
de7d85ee-a761-50db-936d-b4d99886acf3 | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
c735c3de-34e8-5d87-97da-0060fae15d00 | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
e78b09fa-f0bd-5f7b-9720-bda364634268 | note | ○ Attach: Pot-pour Inspection Record
e2b44217-5231-5979-a92b-47e5989a539a | note | Method - Visual inspection
2aca5f50-6442-5f2b-8a53-4967e660422f | note | Frequency - Each lot
b8512be9-2e21-5021-9fbb-2ad565d8e6e7 | note | Category - IP
b456a435-7c18-55e2-a21f-f82543009ecc | note | Responsibility - SE
ee947d2a-9622-5691-ac33-d07ec3157c8f | note | Verifying Documents - ITP Signed
2d7206a0-56db-56c0-8a9c-a1750702a73b | date | Date Completed:
086adf4b-0ee1-4ae0-bad7-1057bff4a1bb | checkpoint | 6.3 - Survey Conformance
c6fed5f9-729e-57c0-b538-95986117d982 | note | Reference - Section 703.15
e2e5c2d6-a5c6-5d7d-b612-8f8da9c728e2 | note | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
ee27751d-34b8-5af2-8219-8ecd724f0a19 | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
3824af15-a1c0-528b-b180-9d0e166f76b5 | note | Method - Document Review
7dda6c02-61d4-569c-982a-25adc81c3e04 | note | Frequency - Completion of each lot
2a03005f-4764-5e70-9450-d2fe32f056c2 | note | Category - WP
48ae3f62-df56-5d93-856b-4a5d3c8405db | note | Responsibility - Project Engineer/ Surveyor
cde7314c-c402-507f-8dd0-e6215fab6372 | note | Verifying Documents - As-built survey records
f6f1cdde-adf6-52e9-b8a6-c36046f14c37 | date | Date Completed:
3d085f28-c444-43a8-bad7-4e8d826f5a5d | checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
8dc6f711-ff8d-5ec2-84e0-b384dd57c08f | note | Reference - MRPA Quality Management Plan
14539acd-9f64-5519-9d47-af4487623582 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
5e82713b-9ef4-545d-803e-d8cb14339844 | note | Method - Document Review
0297573f-bc43-5278-82b5-6eb413e3c3a6 | note | Frequency - Once, prior to closure of this lot / element / Work area
102aca85-7e01-527e-ab55-9ccb09fd4610 | note | Category - HP*
c3ca593b-2c4c-58b4-9038-8d1397ea3fd5 | note | Responsibility - SE/PE/SPE
2ad364a3-4932-5ad0-b5dc-9a6735e3bf8c | note | Verifying Documents - This ITP
ea3e6017-0ac9-57d3-b345-6aaacad02e6c | date | Date Completed:
b3df7fad-c03a-45fb-a0d0-3e1fafdfba13 | checkpoint | Final Inspection
8382baaa-cbc3-5b56-baf4-b12072407fa2 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
91a8fe3b-62c0-5591-8b58-811bfd9e570f | textbox | Name:
3d24ed5a-2803-54c5-8757-9a1d29052e65 | textbox | Position:
6280f2c2-34e8-59bb-bbec-d17bd6039cf5 | textbox | Date Completed:
a7b5231e-cfd0-4a6c-9794-eb945526008b | signoff | Sign ITP
d7c626e3-6615-457b-8b55-94808ed0dca9 | checklist | ITP-228-CIV-Ferris-Unbound Flexible Pavement Construction Rev 0 | itp | ITP-228-CIV-Ferris-Unbound Flexible Pavement Construction | 2cd2a132-f641-4356-9e85-070b4efac011
5bfd761d-e679-48fc-a563-a56b4271472d | section | 1. Referenced Documentation
1b0d2d3a-33dc-423e-812b-f8fe9e8dd8d7 | checkpoint-no-value | Referenced Documentation
94bc5b0d-42d0-5f59-881f-f79ad938fef9 | note | Document Title: ITP-228-CIV-Ferris-Unbound Flexible Pavement
689dcba7-ad7a-5f9d-aa57-55db24a0f8a4 | note | ITP Description: Ferris-Unbound Flexible Pavement
1bb5ac89-cebd-5738-b83f-63bd647d58da | note | Discipline (e.g. CIV/STR/RAIL): 228-CIV
97911c5a-9746-5000-9f3f-02b229f5ee73 | note | Revision Number: 0
cba6deca-4a07-5044-b180-40f44c94b923 | note | Revision Date: 23/01/2025
5ee7d73b-cb62-5418-a8d7-533a1d057766 | note | ITP created by: Kamel ALSHOBAKI
edebbe4c-c307-534a-b063-24b39f688943 | note | ITP approved for use by: Pradeep Talasila
f3affd18-d32c-5133-a9b2-17be7726fbba | note | 1.1 - Non Dependent
bba5105a-a9c7-586a-af33-93495dfaabc9 | note | Reference - Reference Documents: IFC Drawings
8115ad43-4315-57a5-9d75-c68e07e7f49a | note | 1.2 - Non Dependent
b1094e60-a078-5dd5-98b4-b8ffafbf3ac3 | note | Reference - VicRoads Section 173 (10/9/2008)
4c953396-56b4-5bba-b80d-c0f431852e62 | note | ○ VicRoads Section 304 (13/8/13)
87cf478b-4c6e-5bf9-b543-82bc3d5e0816 | note | ○ VicRoads Section 801 (19/07/18)
128ea6db-3c0c-5d71-a63d-a0c7331bfa16 | note | ○ VicRoads Section 812 (13/07/16)
91c0c057-0f57-470a-ad96-4fc293eb91c1 | section | 2. Preliminaries-Materials
f77fd82d-431b-44c5-8ac1-1f9eaf200c70 | checkpoint | 2.1 - Crushed Rock Mix Design
75213f5f-8a79-5c9b-83d6-03008c8e9945 | note | Reference - Section 304.03, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
b17b8e85-dbfd-51fb-af6d-679b7281f7f7 | note | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
c1612dbc-4734-561a-8ba8-659c749a0576 | textbox | Enter: Teambinder Material Approval number
e423bf8b-2597-51be-bb19-04f12aad0a1c | note | Method - Document Review
c64c129f-0ab3-50f6-baa3-ff051b39f791 | note | Frequency - Material conformance as per Table 812.121
cc4b160d-a38f-516b-8237-27794d33f81c | note | Category - HP
508ec507-0b19-5347-bd8b-10b79ec43f07 | note | Responsibility - NA
046aa2bf-95e0-5305-9e13-26082b183db8 | note | Verifying Documents - TeamBinder Material Approval Number
dc733069-5629-5467-8b68-b894613ab847 | date | Date Completed:
c12e70e9-3ce1-4778-b836-76777082a4b6 | signoff | AUTHORITY HOLDPOINT
d660c1fb-14d9-4084-ad99-5defac412f7f | section | 3. Preliminaries-Documentation
7768206d-5a59-4834-a3c1-e4c4135192c5 | checkpoint | 3.1 - Subgrade Preparation
315d8dbe-5b32-5ffd-9858-d606fb435da5 | note | Reference - 304.04
d9b8ec59-f654-56d4-bf45-15c4c14cd598 | note | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
c3646f6c-eff2-5153-9b1c-d74fcd662599 | textbox | Reference: Subgrade Preparation/Type fill Lot Number:
f3f8978f-24c0-58b6-835a-c8aed8d67e48 | note | Method - Document Review
bc0a11aa-00b7-596d-bcca-dea54e8ea566 | note | Frequency - Each Lot
a1f36ebf-3ac6-509a-b693-96722ccbc9b6 | note | Category - HP*
e0365043-5c90-5bd8-b6e9-987ed454cab2 | note | Responsibility - PE
49dac1f3-dba4-5d4c-8d95-2190cadf8dd3 | note | Verifying Documents - Underlying layer Lot number
e898e6d8-356c-5714-b597-81859caf0933 | date | Date Completed:
1e559946-16bc-4159-a6e7-7ccedee10bd5 | checkpoint | 3.2 - Select Scale
b1899fc2-f31b-5f66-bc99-3e475d4f624b | note | Reference - Project Requirement Specifications, IFC Drawings
2deed4fb-8f89-5b6a-a3f6-592345896c76 | note | Acceptance Criteria - Specify site specific scale:
ae1c44dc-6ea4-55e4-818d-ac79f96be917 | textbox | Enter: Site Specific Scale (A, B or C)
15cd363d-8a4e-59f3-a2ad-ecd9a78fd6da | note | Method - Document Review
d48ba17f-ead6-59f3-92d3-08b656c9c3a2 | note | Frequency - Prior to Commencement, Each lot
267925c1-b1f4-57e3-afe9-4b06a00006b9 | note | Category - HP*
89f64940-6a4e-59f6-8f0a-4b65fc532147 | note | Responsibility - PE
c5ee92c3-1e5b-5469-a846-5553281404a1 | note | Verifying Documents - Sign ITP
f15df170-fb48-5cf2-95fa-81156398ab75 | date | Date Completed:
2a9dcc84-97c8-4744-8349-9e71633f33d5 | section | 4. Pre-construction / Pre-installation Activities
b26b6169-6e48-46c2-8d70-0b469c93d54d | checkpoint | 4.1 - Survey Set-out and Lot size
f69e5a7b-3479-56c1-93d5-7be934bdf1be | note | Reference - IFC Drawings Section 304.06
dc2f7b3a-9232-5af7-b49d-f6f182ec28ef | note | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
8a22c8ce-192b-513f-ad81-a1fc79478b24 | note | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
adc6005e-8ae4-5fae-af26-f5f6fe53ce84 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
18be6c55-f04d-558a-a62a-634454343fc9 | note | Method - Survey, Document Review, Measure
74f6944b-84f0-5eec-ac66-6ead7cddf29a | note | Frequency - Each lot
b1f8b17b-5ca9-5abf-ba70-eded40550905 | note | Category - IP
7e0f2076-bfb4-51a1-ba6b-c467ae559d2d | note | Responsibility - Surveyor, SE
4783aa25-595d-54c8-b97a-6f0f6cf3c1ac | note | Verifying Documents - Sign ITP
8e9adb31-906e-51ae-abb7-9669220741d9 | date | Date Completed:
feabd607-1b8c-491b-882f-77373c67cf06 | section | 5. Construction / Installation Activities
e08fec53-bf58-4294-a6c8-252571bc00f0 | checkpoint | 5.1 - Crushed Rock Delivery Dockets
5a292608-e4ef-5ef8-80d2-dd61516cda68 | note | Reference - 304.04
35ed3350-2585-5dc6-a4d4-dada3811ad12 | note | Acceptance Criteria - A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
949b941d-39bf-5ba3-ba25-cf6d5a0d3fde | note | ○ ATTACH: Delivery Docket(s)
ead006bb-441e-5e7d-becb-e1d6334ca157 | note | Method - Document Review
be575e29-c880-591f-a655-374215c4dc52 | note | Frequency - Each Lot
bc5432e8-be12-5c96-98aa-bf68b4de48aa | note | Category - IP
fa1695b2-7bb6-5773-a512-27585f300e2c | note | Responsibility - SE
56fc4da8-85b3-55b9-a548-fb8fce4e55d6 | note | Verifying Documents - Attached Docket, Sign ITP
8fe49fd3-ef9e-5324-9366-75077c202222 | date | Date Completed:
eabb05ab-eba6-4307-9ba6-158c60e1b6d1 | checkpoint | 5.2 - Placement of Material
04873d40-9622-5ce8-a477-010dc17698ae | note | Reference - Section 304.03, Section 304.06, Section 304.08
e6a97fb3-52da-5784-9c75-0c6567d3542e | note | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
fe96639c-cf27-5071-995f-a4157213e7ce | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
a106ca00-f511-57fd-91a9-c4c7d0b2edf7 | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
d27b71d5-8abb-5c94-a7c1-5fa6477a0275 | note | ○ At no location shall water pond on the surface of any pavement layer.
dd038a50-968f-586d-9d1b-208678a06323 | note | Method - Visual and Measure
7e8e6d75-8d9e-5bbd-8b64-72949c72ff83 | note | Frequency - Each lot
eda66243-9228-5160-874d-61dbaf752f35 | note | Category - IP
36795587-a8c8-568a-94f3-4b4fa9d0382e | note | Responsibility - SE/Site Supervisor
e377123c-6942-5878-823f-85bd7d6e852f | note | Verifying Documents - Sign ITP
94e02bca-19b5-57fd-8cef-91f2c1afcf93 | date | Date Completed:
343c6401-bdb7-4414-8dd1-507f210b8d99 | checkpoint | 5.3 - Construction - Jointing
40e62f26-733d-5500-810c-bdd3d3c37fc1 | note | Reference - Section 304.07
8c1e437e-6175-5cfb-916c-9f4b0d579209 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
0ca3865f-241d-5430-bb7f-223399602d83 | note | (a) material shall be spread in such a manner as to minimize the number of joints;
c364d6e4-70d2-533a-84bd-ed13f23db362 | note | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
749eaa10-c029-52df-ae60-9ed931c2ca8d | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
9140aee5-ffa3-537a-8259-3552bc99a397 | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
80138c86-4a6a-5ad4-8fe4-e97f50a8332a | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
acbc2888-1780-577b-93ea-88b931f1c533 | note | Method - Visual and Measure
2ff587ad-af2a-524b-b2cf-12354dbe73fb | note | Frequency - Each lot
2153ca57-f620-5bc5-bd22-b0915cf6e05b | note | Category - IP
f96a4b9a-fbe6-53cc-8a0e-02fe11f73749 | note | Responsibility - SE/Site Supervisor
e58e85d5-a093-5c94-92ca-2f68ccefaf81 | note | Verifying Documents - Sign ITP
e902f320-c2f1-5e63-b280-c00a41f96109 | date | Date Completed:
a76dff69-ca1e-481e-8d32-b37c77ae462e | checkpoint | 5.4 - Compaction test (Frequency)
c0e2f461-8af4-5044-aeae-4c944058c170 | note | Reference - 304 .11 (b)
e5790790-a9cb-5ce5-a2c5-cb073cfcbbd7 | note | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
a445a973-eafb-5e1f-b5b6-fcb268c023e5 | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
1b214994-16cb-5d17-b860-f15c489c8bf6 | note | ○ Scales A and B: 6 samples
cb3546f3-75f4-50d3-94c1-09691dd65c03 | note | ○ Scale C: 3 Samples
39ccae25-41ed-5746-8292-b70a1e37fdc5 | note | ○ Pass: Tested
9e9758e4-b7cd-5f9b-b3bb-2bb39d88bd6d | note | ○ NA: Not Tested
4e5fc303-534a-5819-bd6e-67d77bdd72cc | note | Method - Visual
6c931f38-db18-5f2b-bd0f-4e02dd8a953c | note | Frequency - Each Lot Where applicxable
f8e7fbae-3d19-5dfd-80fb-bc9a65ae3942 | note | Category - IP
e1183df7-6510-5e4d-aefc-8d01f1cfc575 | note | Responsibility - SE
7c5377c7-ed12-5e1f-a948-3d17f0e2a1bd | note | Verifying Documents - Sign ITP
89fd469f-6ea1-5c22-810a-62b4ed36a085 | date | Date Completed:
147226a5-0ce6-4375-b863-b1fe147330d4 | checkpoint | 5.5 - Post Compaction Materials Testing (Frequency)
d24384ea-1e3a-503e-b9f8-6e0be93e6fc2 | note | Reference - 304.11 (c)
68c51254-2d05-5dfa-979f-f09f20e30ff4 | note | Acceptance Criteria - SCALE A:
d096f024-7788-509d-97b9-b109eb3448bc | note | — The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
4c156ccf-1038-514d-ade3-583cba9a18ad | note | ○ Compaction:
6b3733b4-73a2-523f-af36-f6fc0f9ee25a | note | — Lower Subbase: none
66e02c6b-3499-5861-86ed-884a0de24bde | note | — Upper Subbase: 1 in 4
50288837-eadb-5241-a8a2-606656278b37 | note | — Base: 1 in 2
0a102269-9705-5733-a431-3a34fbfb0da8 | note | ○ PI:
c8d02f49-12c9-5ec2-ac4e-39048ae5b595 | note | — Upper Subbase and Lower Base: 1 (two samples) in 8
b4c569bb-0d5b-5163-a0be-a2c07ee88613 | note | — Upper Base: 1 (two samples) in 4
f837d325-ecc6-57fa-b152-c71ee8d65799 | note | ○ SCALE B:
df1bd44c-8272-5275-9824-6908f97b6838 | note | — the first lot of each pavement course shall be tested for post-compaction grading and PI.
e18a7d10-e24b-56ac-8548-123ddcb38426 | note | ○ SCALE C:
ea3dacde-ce23-5b8b-b497-aee2083b27d4 | note | — Post compaction grading and PI testing is not required (CHOOSE NA)
7961f5fd-ed6d-5676-822b-da7f8e63ed93 | note | Method - Visual
60da7249-6c45-513f-8bb7-15ce6de8e76d | note | Frequency - Each Lot Where applicxable
38e50a92-dab8-5ee9-9faa-f0fbb9217ce4 | note | Category - IP
e4efcf57-fa85-5f34-9465-70731dbcb83e | note | Responsibility - SE
76257f2b-a1b6-577e-9a87-2bc7ca9bf38e | note | Verifying Documents - Sign ITP
3a429e8b-21a4-55bb-a3e5-07194d45d688 | date | Date Completed:
c8b18319-1879-4b35-b27a-54fb9c5854c5 | checkpoint | 5.6 - Proof Roll
62e93ccd-b9f8-5ab4-acf7-2bcb9c596d17 | note | Reference - Section 304.08
cb004e86-b271-5f48-a901-bbfba3fa5100 | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
408fe42b-14fb-57ca-bb0a-e9095a675782 | note | Method - Visual
03fae410-03d8-580e-8af5-d41382682cbc | note | Frequency - Each lot
53b04dce-fa1d-598e-982e-a44d990892d7 | note | Category - HP
4c974696-fa2b-5078-8146-86ff10fe7fd6 | note | Responsibility - Nominated Authority
af8d7e9f-6dac-5866-bbc5-cddb39008e07 | note | Verifying Documents - Sign ITP
76a2fa3b-dc3f-577b-846e-707834a044ed | date | Date Completed:
097a83ed-e89f-4eb3-884f-3d71671710c9 | signoff | AUTHORITY HOLDPOINT
bbb27a1d-f482-4e95-abd7-1f9830e89f43 | checkpoint | 5.7 - Protection of compacted layer
d45281fd-7a89-594b-be22-e84a34551114 | note | Reference - Section 304.09
a224a19d-2c29-5cf9-b302-a9edbda99d7d | note | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
4125456f-1896-50f6-bcf7-bd08b67b62d0 | note | Method - Visual
9e788ebe-a320-523c-9cdf-753421ba5ade | note | Frequency - Each lot
c95f4bca-f2d8-5ea3-8ca5-d2811302213f | note | Category - IP
3ded5804-a6b9-5dc8-b191-c909f17625fe | note | Responsibility - SE/Site Supervisor
4c2c1ab3-785a-5b96-b740-84ebe23c91f9 | note | Verifying Documents - Sign ITP
c816bdf0-17ce-5955-95b6-2648f215b41b | date | Date Completed:
13687ab9-63bc-4304-a9d5-2bc395cfda5e | section | 6. Post-construction / Post-installation Activities
06041a83-3cb9-4d24-a4ac-bcd94a70549b | checkpoint | 6.1 - Compaction Testing (results)
00c21baa-88a2-512a-83ed-ba3d2ddeef2e | note | Reference - Section 173, Section 304.08 Table 304.081
c4276ebe-98b5-5753-b1d1-38481e957c79 | note | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
7ef32f03-8de6-5051-a9b7-690e17c2751c | note | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
457cda31-a8aa-538b-ad2b-c1d46d970126 | note | ○ Scale B:
131d2e52-64ab-525b-9747-c3f5714c68b2 | note | — Subbase Layer CDR ≥ 97%
2160d0b0-7924-53f8-830b-39a225f3a487 | note | — Base Layer CDR ≥ 98%
5a346e27-101c-5a9b-800d-aa36676c080b | note | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
de173051-7d83-57c5-9ea3-568dc4060ffe | note | ○ Scale C:
da337d53-5056-59bc-a8d8-3a9159b45656 | note | — Mean Value of Density Ratio (3 tests):
8789b060-e518-52eb-9edd-ee179b7ad640 | note | — Subbase Layers >98%
c23d88a0-1d7f-517e-b989-852ec9ea3e74 | note | — Base Layers >100%
4fb94da8-46fc-5f34-b8f0-1b66ac0935c0 | note | ○ ATTACH: Compaction Test Results
38d6a0ec-61b9-5618-b413-9365350ec004 | note | Method - Document Review
9e39ceae-fd15-5ff4-b57e-adc70d16581d | note | Frequency - Each Lot Where applicxable
584e3ef9-5bc4-5d2e-92ab-eb77044cf4b3 | note | Category - IP
e38bcd4d-19f0-5b31-ab67-e6e540b123bf | note | Responsibility - PE
3167d71a-950a-5a37-9eb8-5a8d4ed10f15 | note | Verifying Documents - Compaction Test Rersults
ff5d816e-f074-52e9-91a5-c86a291229a9 | date | Date Completed:
3839de14-bc2f-4007-88eb-4ccb9b571bcb | checkpoint | 6.2 - Post Compaction Materials Testing (Results)
d9e06317-a020-5cf3-ab80-f849e7d83ae9 | note | Reference - Section 304.10, Section 304.11, RC 500.02
c1649cc3-dd86-5ee0-a78d-168c21ebc394 | note | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
f96af24a-f5fc-5751-aa91-4c00adf7d3f7 | note | ○ 20mm Class 3:
f944c00e-07fe-5f5e-9a80-44c8138b1ae2 | note | Grading
d8c616ee-60bd-5c0c-9462-9523af2796a4 | note | — 26.5mm 100%
b194d89c-56ab-5560-b190-42348e0891cd | note | — 19.0mm 95-100%
f908994e-bd3f-5c1d-8c9b-0f2d14c5d0ba | note | — 13.2mm 75-95%
f6f2cfe0-75fc-576f-9831-7ab453959ba8 | note | — 9.5mm 60-90%
6a576cf2-3194-5778-b933-6206729a5dc9 | note | — 4.75mm 42-76%
6623f1cd-b187-5185-ba67-cb417a62abf8 | note | — 2.36mm 28-61%
8d83c353-6e4c-527d-9ee5-3fc1705ace13 | note | — 0.425mm 14-29%
757cec31-04ee-534e-9ccf-9e52a5fe2437 | note | — 0.075mm 6-14%
619e900d-6979-560e-82d8-54581ee42854 | note | — PI between 0 to 10
cc9e2b25-abb0-5dea-999d-e4abedbb20cd | note | ○ 20mm Class 4:
b59a0edb-0d60-5bf7-a74b-e3eb8bc22718 | note | Grading
bd1ba9c7-51fc-5cc2-9edb-0f84a91da6ec | note | — 26.5mm 100%
b27288ef-b095-525d-b8b3-fe439d45f930 | note | — 4.75mm 42-76%
0161b132-c906-58c3-b73d-7e8156e98669 | note | — 0.425mm 10-28%
a70167f9-e77f-596d-a3ff-a47581376c01 | note | — 0.075mm 2-14%
bfd7686f-46be-5ea4-945f-1a886ddea741 | note | — PI between 0 to 20
156e8da2-b9a0-5651-a48b-1e9324892d37 | note | — PI x % passing 0.425 mm sieve (max) 450
37bc043d-ab5f-5860-837f-5e9d79a2058f | note | ○ Scale C: Post compaction material testing is not required (Choose NA)
b537814f-86d9-5f47-843c-57609bdfd2c1 | note | Method - Document Review
314aaf67-f477-5cd3-98b1-8b7ba41ea3d7 | note | Frequency - Each Lot Where applicable
8e9bd916-9ac4-535c-8e62-89cfe1a3c86d | note | Category - IP
bc4b6629-16ab-56a8-9562-25cc70669e5a | note | Responsibility - PE
2f4277d9-0772-544f-a5f6-1c83adf86849 | note | Verifying Documents - Compaction Test Rersults
4383289f-c446-510e-9d5a-f7e4b244e9e9 | date | Date Completed:
4da4ba49-828d-4024-8c31-f7a7dacc9d98 | checkpoint | 6.3 - Survey As-Built - Surface Level
7c525a37-b52e-5b4e-ba85-f0f4456b4e12 | note | Reference - IFC Drawings Section 304.06 Table 304.061, Table 304.062
b1577c2d-b9bb-504d-b439-0f08680f3cdd | note | Acceptance Criteria - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
5bdf6947-3aee-5a01-9972-e9de23030e26 | note | ○ Subbase course shall be not < the specified thickness by more than 15 mm.
f6825c7f-e220-5213-b97c-fdb067547bf9 | note | ○ Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
05e26699-997e-5b6c-8d9d-7416d5fe01ce | note | ○ The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
5268abd3-07cc-54c8-ba82-52069ceb612d | note | ○ Scale B: A minimum of 40 measurements per lot
2be1e9b4-af26-5969-9a0a-60f5f062e9ea | note | ○ Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
d96a2b91-8711-519e-acee-8d6aa6b54d1b | note | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
089aa683-6bf6-5356-86a3-adec535e91d1 | note | ○ Scale C:
c1854501-16bc-5049-a89b-100dad0271d0 | note | — Lower Subbase (mm) +15/ -25
3a8e5630-2d41-5fec-9be7-9ccebd10fdb2 | note | — Upper Subbase (mm) +10/ -25
0eb68a02-39f3-58a3-9214-614f76249551 | note | — Base (mm) +/-15
1c078be5-fe14-554e-bfbd-1521d8ec091c | note | Method - Document Review
4cc1f079-298f-58e4-bd57-853d20a4a8e1 | note | Frequency - Each lot
98856719-1917-5c75-b42d-98d210651731 | note | Category - IP
cf644941-db80-5138-82b5-523766a3aee1 | note | Responsibility - PE/Surveyor
6161b39b-692d-5a8f-9f33-5bd4161bdd9d | note | Verifying Documents - Survey Conformance Report
c3bb2fee-d6d8-5c62-a64a-ff23d0a03c56 | date | Date Completed:
c41f856c-c653-4393-8d02-546e3e2ec1fd | checkpoint | Final Inspection
3579465c-829d-592b-92ed-4db38d71b497 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
bc914a30-1db0-5d7c-81cd-b1ee3ca35cf6 | textbox | Name:
0306f38f-4489-5220-8117-0752b5c535db | textbox | Position:
1b4a7755-377d-572a-ba4d-47f935f73336 | textbox | Date Completed:
507a9363-4a43-48b5-8046-429d8d47f5d8 | signoff | Sign ITP
af89f4c3-3bf5-42db-88cd-c88434827b51 | checklist | ITP-229-CIV-Ferris-Subsoil Drainage Rev 0 | itp | ITP-229-CIV-Ferris-Subsoil Drainage | ff3eb146-057d-4906-9fdc-155ca2f326a1
d62bbbb8-0fa3-450c-841e-267f69a5bedd | section | 1. Referenced Documentation
ffee9dcd-f8c5-4a82-b527-220749c871ce | checkpoint-no-value | Referenced Documentation
3bbe4216-5463-5721-b0bc-b06ce0d4ee54 | note | Document Title: ITP-229-CIV-Ferris-Subsoil Drainage
71303997-0df8-5e80-b15f-61da4472281b | note | ITP Description: Ferris-Subsoil Drainage
71101d52-4ded-5a05-ac26-cc35b2482bf7 | note | Discipline (e.g. CIV/STR/RAIL): 229-CIV
e4fb8a42-dc84-5b28-a913-6aa11a4c08f9 | note | Revision Number: 0
fac9a7bc-cf02-5e4f-8df3-5f9778f76f5c | note | Revision Date: 23/01/2025
1d011472-b0d9-5c62-b232-c00475db276f | note | ITP created by: Kamel ALSHOBAKI
8e47b507-416b-522e-a1aa-e3e847e35b39 | note | ITP approved for use by: Pradeep Talasila
abdbf87d-7384-57bd-a427-9029feca5c14 | note | 1.1 - Non Dependent
91ed0788-23f1-5429-8918-dd8aa270ca30 | note | Reference - VicRoads Section 702 (May '19)
599f5658-109b-4d29-959f-6697cfe29ec2 | section | 2. Preliminaries-Material
fe1b822b-e36c-4ba1-bdad-bb40daeb81db | checkpoint | 2.1 - Pipes
d8706b1d-d4bc-511d-ac7c-e93b0cb7655f | note | Reference - IFC Drawings VR 702.04
288e93cd-7961-5946-8ee3-12618a12677d | note | Acceptance Criteria - All subsurface drainage shall be Category 1, 100mm DIA Class 1000 Perforated Plastic Pipe. Perforations shall be max 1.5mm and minimum length of 150mm per sqm
4f52d0d2-b1b4-5dd7-bb04-3c8e93800e08 | textbox | Reference: Material approval in Teambinder:
5ea63642-2a0a-5b8e-a00e-79d10b13661a | note | Method - Verify, Document Review
64d0b35f-69cd-567e-9397-29b6f3362549 | note | Frequency - When applicable
b8347c6f-cdfd-5982-ac3a-6c0e50859dc2 | note | Category - HP
4f533b7c-d0ad-5235-8fe2-a81c390cad57 | note | Responsibility - PE/Nominated Authority
50ab5b33-8571-5498-8397-078d44501b83 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
4344fe12-c972-565d-908c-aa011e81ee70 | date | Date Completed:
fe5ba36c-de34-4a55-b332-01fced39d4b8 | signoff | AUTHORITY HOLDPOINT
6f11c502-202a-4762-81c6-a4754f6d71c0 | checkpoint | 2.2 - Granular material: Filter Sand
a46c4578-e51c-5627-9e18-0dfb86a862fb | note | Reference - IFC Drawings VR 702.05
c8b0f087-8ffe-5bbd-98ab-9cc87f3a2386 | note | Acceptance Criteria - Filter sand to be Grade A4 and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
055d5b10-2b76-588b-9686-73eaa2aaebf3 | textbox | Reference: Material approval in Teambinder:
15df3fad-4915-5ec0-ae53-cfc20b1830b2 | note | Method - Verify, Document Review
384b61f1-9475-5540-a366-8e8070c52979 | note | Frequency - When applicable
4cad7a40-08bd-559a-a100-b6de0893c00f | note | Category - HP
fc1e99d0-3d01-5e80-8206-00c48cf6d4fc | note | Responsibility - PE/Nominated Authority
43f3e6fe-be8d-573b-a170-6b3787a98d81 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
82cefd1b-46c3-5135-9c5e-2a5e114bb0e3 | date | Date Completed:
cae44efa-e431-4a16-b069-5677fd7c0465 | signoff | AUTHORITY HOLDPOINT
33a86448-0680-4e32-bd1f-5b8c17e73c60 | checkpoint | 2.3 - Granular Material: No Fines Concrete
61ef3d9b-c6df-5c16-bc36-6e82ef260be3 | note | Reference - IFC Drawings VR 702.05 (e)
7eb5154f-7955-57b8-ac13-ca73a0e69d58 | note | Acceptance Criteria - No Fines Concrete: Shall comply with 702.05 e)
cd3c24da-f8e2-5612-a8f6-ca3116a3d56d | textbox | Reference: Material approval in Teambinder:
dcc48873-48a5-5268-8462-944b937db48e | note | Method - Verify, Document Review
048b7121-a2ae-5699-abb0-1d8234c034c9 | note | Frequency - When applicable
1d4d724d-3cfa-5693-a31e-4afbcf939b42 | note | Category - HP
d79f3ad8-3378-5b40-af6f-92e615d43916 | note | Responsibility - PE/Nominated Authority
baf40432-92f0-5f2a-a626-02b712bfe68d | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
68badb88-1801-58e7-a6c9-bf8b5231fa92 | date | Date Completed:
3472d57d-1fa9-4275-bcae-608c6002ea64 | signoff | AUTHORITY HOLDPOINT
6845b6a2-41e3-4fb4-85a8-05527e41700d | checkpoint | 2.4 - Geo textile
319dc623-aef7-53de-a2d4-01eaec7ffc5f | note | Reference - IFC Drawings VR 702.06
6a2e6e57-35fb-59a6-be8c-75c2c4726690 | note | Acceptance Criteria - Geotextiles: Shall comply with table 702.061
12ae6353-46e9-537f-9b77-5e71c9766afd | textbox | Reference: Material approval in Teambinder:
4e2bc262-857a-508c-885a-070435a559fc | note | Method - Verify, Document Review
1234df39-4f7b-5fa4-a2c6-186d4de6bfd9 | note | Frequency - When applicable
d1981d18-dd88-5c02-b10e-63fe7f714754 | note | Category - HP
c1c303ac-58a2-568b-8ead-134af52e2278 | note | Responsibility - PE/Nominated Authority
2522cf04-c3f8-59cd-91ff-5243fd6a9d19 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
091b32e6-a4e1-5e38-b76c-6d05f818c32b | date | Date Completed:
3e9bd49b-0517-4605-abc2-9d85388892db | signoff | AUTHORITY HOLDPOINT
24d4d759-4975-46f3-9153-5384174238ba | checkpoint | 2.5 - SSD Pits, Pit Lids, Flushout Risers
4ba65a36-4a8a-5bdf-a591-3c98aa413a70 | note | Reference - IFC Drawings Section 702.04, 702.05 & 702.06
fdf6640d-1ff8-57ac-a566-0fb7426eacf4 | note | Acceptance Criteria - Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
46d32aee-720e-5460-80a3-64bfd467f29c | note | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
fb6fba39-7042-52e7-85d9-1ce284d8acba | note | ○ Flushout risers: As per SD 1631
b58260eb-32cc-5562-9e43-565001906452 | textbox | Reference: Material approval in Teambinder:
db5e882e-9e00-52a9-99b4-1f489ab96ad1 | note | Method - Verify, Document Review
274d7399-cd2a-5158-9a72-9936940d94e9 | note | Frequency - When applicable
fc2b453d-24d1-5286-a3ce-54c85057bd2f | note | Category - HP
058c39c1-59b7-5996-a0ef-6f9a27b36d67 | note | Responsibility - PE/Nominated Authority
e1aba871-b6bf-515c-ad06-c5b61c9dd1cf | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
03a092ad-16cb-5215-b027-41e760d80c24 | date | Date Completed:
92a49235-efed-427c-8ff2-d91cf533e1a3 | signoff | AUTHORITY HOLDPOINT
ba0b9345-6242-424d-80ed-ba129d3d5931 | section | 3. Pre-construction / Pre-installation Activities
ecb00963-b2eb-4a74-8ce9-0a4827773a22 | checkpoint | 3.1 - Survey Set Out
b2390052-16cd-5c6e-9fe0-cefdb526438f | note | Reference - Section 702.03
3e3d51ee-22fe-5412-88a9-7a3292ec2224 | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
e5368ada-0ae7-5429-aebd-b149671804dd | note | Method - Visual inspection
953b14e2-4ed0-5d60-96f8-371e5a6c7d15 | note | Frequency - Each Lot
a7d8ac66-2551-5914-85bb-d8f6c0268bab | note | Category - HP*
e48bad0f-f63d-5780-b525-869eb7db266f | note | Responsibility - SE/Site Supervisor
3153698e-5a8f-5515-bf59-33be680c33de | note | Verifying Documents - This ITP
c4a63891-3ebc-571a-92af-7dc7d96c21bb | date | Date Completed:
ddfbf719-3f07-4b93-a44b-d48955aaaae3 | section | 4. Pre-construction / Pre-installation Activities
b9bfa2a8-9d4a-4f11-b669-d7b9f0d49e47 | checkpoint | 4.1 - Survey Set Out
78bfeab6-5fc8-5330-8409-973050325981 | note | Reference - IFC Drawings Section 702.03
45a51bb4-e8e9-559b-8128-859bc0a8a9f1 | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
2092e0a3-eb68-53cc-80fa-0ce3bf335ce2 | note | Method - Visual inspection
d2fda7a1-4cae-527a-b8c4-d9ff0d292313 | note | Frequency - Each Lot
a91d9049-7509-55dc-aa7c-fe3451c0bb8f | note | Category - IP
f5b21723-92b7-5b5a-9176-521012954d01 | note | Responsibility - SE/Site Supervisor, Surveyor
e372fe10-6ec2-52d3-a207-2ad07f9c65a6 | note | Verifying Documents - This ITP Signed-off
b7f07661-9a1f-5ef6-b924-1284c88e5494 | date | Date Completed:
a8be2d9c-f314-4c6b-ae76-bb2fb7718700 | section | 5. Construction / Installation Activities
746f604a-d848-431f-ba9b-4a2806719f4d | checkpoint | 5.1 - Trench Excavation
fd3a5db9-82c1-54d1-ad5b-ee33bdae8e16 | note | Reference - IFC Drawings Section 702.08
56ce388c-dbe4-5b1f-8f66-987651104ac0 | note | Acceptance Criteria - The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
de3fa237-5303-52c9-84e4-514c809bafbd | note | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
d8830f83-e293-5893-b943-11aa9dde88c1 | note | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
0c37b651-1db9-54e2-8eb0-2174ad30f84e | note | ○ Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile.
6146ab02-2737-5325-b086-5e544f130249 | note | Method - Visual Inspection
85bbe902-56dc-5d6a-acda-2ca54b9ec5cf | note | Frequency - Each lot
609b6851-78db-5eaf-af55-e0927fc5f513 | note | Category - IP
0bbeb2ef-dc06-520a-8f83-ae9814367bff | note | Responsibility - SE
95242939-e61f-50c0-9c8d-9c8ced24efcc | note | Verifying Documents - This ITP
48342e2c-82d5-563e-8335-947c9237d2ef | date | Date Completed:
9f02f0dd-6402-4176-b732-976ad7a2287d | checkpoint | 5.2 - Trench Excavation
112c459b-9bdb-5916-bff3-b20b3318c57b | note | Reference - Section 702.08
aa0d68ce-74aa-58e6-be76-9b969286f640 | note | Acceptance Criteria - The base of the trench shall be inspected to verify compliance with the requirements in VR 702.08 prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection.
bdee55c4-67a4-51f7-b861-aa697abef6bd | note | Method - Visual Inspection
af445870-acaf-5a1e-abf0-d36fae05ab2e | note | Frequency - Each lot
863f7bf9-c8c8-5658-aba3-27f452a2e3e6 | note | Category - HP
50911c64-6a7d-566e-8b34-94b4479b8d98 | note | Responsibility - SE/Nominated Authority
5debe6f7-50c3-5fc4-a835-2ce626a75cbb | note | Verifying Documents - Nominated Authorith sign off ThisLine
2aae0828-14c0-5d05-a510-8007325c3b08 | date | Date Completed:
683261b2-7888-4db3-b8ac-ebfceb5c967a | signoff | AUTHORITY HOLDPOINT
4c4787d2-de5a-4a90-bd8c-7468a6a77e36 | checkpoint | 5.3 - Placement of bedding
7a51099c-a100-5224-adc7-93742a7c43ca | note | Reference - Section 702.09 c)
9c8180e6-b493-5764-af33-3bd4e813dd3b | note | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
af230465-5f3f-5f70-b287-f357e6bb0c25 | note | Method - Visual inspection
cfca8217-9785-57bb-9ec6-c9e367d6b3cd | note | Frequency - Each lot
2b0500aa-54cc-54a6-b828-b54620f66422 | note | Category - IP
3a5df60b-c092-52ec-9a06-969fdf6b4899 | note | Responsibility - SE/Site Supervisor
3583b800-0e2a-5324-952a-0625feda00ee | note | Verifying Documents - This ITP
f33a91dd-0301-54e4-a583-e29471c9739f | date | Date Completed:
09f1b20b-8683-4a75-8852-0bd9b820de62 | checkpoint | 5.4 - Traficable Pavements
b5803197-6eac-508d-b379-93ef2badb52a | note | Reference - IFC Drawings SD 1601, EDCM 201
b08785c5-f6af-5f93-a10e-d48df9283d5d | note | Acceptance Criteria - Choose pass when applicable
ebbb273e-b8e0-56ee-87f6-045c509a5b12 | note | ○ All Subsurface drains located within trafficed pavement shall be Type 2 with no fines concrete filter with filter fabric wrapped around the trench in accordance with SD 1601 and MCC202B
dd4f01bf-a249-58c6-a2b8-e0970a216c6d | note | Method - Visual inspection
bc262f01-e064-5999-80bb-5ea3e2f4f229 | note | Frequency - Each lot
9e16bba4-2ee1-5fdf-a090-ffa99d693667 | note | Category - IP
51f011c7-0166-5332-bd1e-5e2f46c3eda8 | note | Responsibility - SE/Site Supervisor
9f91aab1-c1d2-563c-8173-815e7910f85f | note | Verifying Documents - This ITP
69062753-d197-5125-b793-89bea2abfeef | date | Date Completed:
fb42edb4-3ed1-4ece-acfb-c8d97138a13d | checkpoint | 5.5 - Outside trafficable pavement
1528eee9-23e1-5060-a8dc-3ae2410c36ad | note | Reference - IFC Drawings SD 1601, EDCM 201
12910347-2999-5b07-98c8-34e613dcf090 | note | Acceptance Criteria - Choose pass when applicable pavement drains outside trafficable pavement shall be type 3 with grade A4 Sandfilter and Geotextile wrapped around the pipe with minimum 150mm lapping length
5405a44a-2cc8-5190-9e33-b0bc5f5317e7 | note | Method - Visual inspection
75c617dd-0d4f-56b4-b4ef-79d994453ab2 | note | Frequency - Each lot
1032269d-6213-590c-a380-fdc07c481d3c | note | Category - IP
2c2ca5fb-148d-5515-ae21-7370e470c8b2 | note | Responsibility - SE/Site Supervisor
7f055432-9a03-5f4f-82d0-56898d0a89d2 | note | Verifying Documents - This ITP
2177e799-7e79-556a-ba18-26ce00281c05 | date | Date Completed:
b0420eb4-c2f6-4220-9f08-5ad9373e1036 | checkpoint | 5.6 - Pipe and Geotextile Installation (if required)
6e08f3e7-d660-5826-b2f3-d70144fe1e58 | note | Reference - Section 702.03, 702.09
a648f164-e991-501e-89df-8069fb1ee27c | note | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding.
8cfde8ce-8b7c-5965-888a-672f8ece598e | note | ○ Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped (Mininmum 150mm lap)
6cbcf3df-284d-5462-a0a3-b05404078aee | note | Method - Visual inspection
b487c0cd-adad-5d11-b477-7e9871cacd0e | note | Frequency - Each lot
9e4f9302-37f4-5b29-ba7e-b87acbb240dd | note | Category - IP
bc0c5a95-61cf-50cb-b0f1-08b85c1927d3 | note | Responsibility - SE/Site Supervisor
eb7225f6-3654-54a8-8706-284857d78e9b | note | Verifying Documents - This ITP
265f287e-dec5-5f84-8bad-d0611103805b | date | Date Completed:
3848e9ab-134b-4b40-804f-63c3eae82c68 | checkpoint | 5.7 - Backfill Installation (Granular Filter Material)
86703a2a-af67-5f6b-91bd-de6021981985 | note | Reference - Section 702.09 (g)
cad385a3-e367-58be-860e-2d31d33f28a8 | note | Acceptance Criteria - Material shall be placed moist and compacted in layers not exceeding 300mm.
0cb8187c-50b8-5fc1-a77e-980543422781 | note | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
23fe0fb8-9ddf-5c05-a7fe-ab20ddfb5c38 | note | Method - Visual, Doc. Review
f282fda3-c506-5796-b9c5-7ac455d4222d | note | Frequency - Each lot
9d6a0ad9-e423-5a45-9a07-4b7962e31605 | note | Category - HP
67b7bf7a-100f-55e0-9d10-31b69bedf819 | note | Responsibility - SE, Nominated Authority
3cfdc29c-905f-559a-92e6-9165f0f8f4b3 | note | Verifying Documents - Nominated Authorith sign off This Line
84263c3c-af66-56c0-b2eb-56fbb5b00ebd | date | Date Completed:
abf33565-390c-4ab0-a3da-b0cd05823f02 | signoff | AUTHORITY HOLDPOINT
9001b2ab-281d-4286-a9de-267724aed994 | checkpoint | 5.8 - Backfill Installation (No Fines)
1fdbd77e-f3ab-514c-ad0b-4666fef5a408 | note | Reference - Section 702.09 (g)
dd6ce415-f4fb-5ebe-a1dc-6e08ade74c8a | note | Acceptance Criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
3ac9aa6b-9a50-5169-aa98-58a28c7c56e0 | note | ○ ATTACH: No Fines Delivery Dockets
e8a8aec8-0fe6-5611-8df3-8d7b0b89f90b | note | Method - Visual
9d1429ee-3551-5844-9f19-a7679c4d76d5 | note | Frequency - Each lot
da34b816-4f6c-545b-9e2c-a7691c722e46 | note | Category - HP
4fef4466-e183-599e-bed7-27b68a4f65b9 | note | Responsibility - SE, Nominated Authority
eafb1d34-9bf5-59f2-b9e2-3ebab356f29c | note | Verifying Documents - Nominated Authorith sign off This Line
decf15ca-3c85-5a81-b116-15cb9af515b8 | date | Date Completed:
9a06f139-3b63-4b13-b036-4d4764fc34e1 | signoff | AUTHORITY HOLDPOINT
514da10e-d659-4d09-971d-d5ec154dd406 | checkpoint | 5.9 - Install Pits and Flushouts
4278d120-2dc1-5659-8f88-ffd9d01d4928 | note | Reference - Section 702.10
71889f63-7bab-5f31-bdaa-ba9aad16d435 | note | Acceptance Criteria - Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
541bf296-b7e6-52f6-9a16-37d00b6298b3 | note | Method - Visual
783cb14b-df25-577c-ad27-e3a5484ec89d | note | Frequency - Each lot
ab4b0393-7eed-572f-9f6c-1fd27669cdad | note | Category - WP
ecea2807-6765-527b-8d72-766329efd72c | note | Responsibility - SE/Site Supervisor
6123e466-1405-534a-911d-cbcfb176a88a | note | Verifying Documents - This ITP
a555d096-254a-5103-b894-f08cd067c2c4 | date | Date Completed:
1ad69f89-a809-42d9-b65b-f6dfef13e726 | checkpoint | 5.10 - Marker Points
ead987df-bd25-5d0e-8e9b-06bac0f17d4e | note | Reference - Section 702.11
75383053-be38-569c-82b0-4a2264cad07a | note | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
2c48ef5b-faee-57a6-98f2-de2f1f5f3ede | note | Method - Visual
a77c60d9-d268-531f-ac70-0aeeee2ff719 | note | Frequency - Each outlet
494c31ed-0c1f-559c-aa25-fb3be53a36b7 | note | Category - IP
ce769859-b2bc-5b94-bcb6-f6b45a9539f3 | note | Responsibility - SE/Site Supervisor
1181eb14-20f1-571e-80f4-77f9636f9026 | note | Verifying Documents - This ITP
7daa2cc1-2683-5e1b-99b7-e78140042597 | date | Date Completed:
3dc0f925-d75b-475f-9a59-48fa37c4f615 | section | 6. Post-construction / Post-installation Activities
71000a1f-fc00-453e-a026-1516be621030 | checkpoint | 6.1 - As Built Information
9a173a9f-a6a0-516b-9624-99747bcaa8dd | note | Reference - Section 702.03
125a381f-0429-5b2f-af1d-4e483bd916d7 | note | Acceptance Criteria - The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
d73b0c26-33f0-5dc3-9635-bf43e6e52dc1 | note | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
dd6ab7a1-bb5e-5c6e-9f74-c659555ab6f8 | note | Method - Document Review
65a20cb5-e7f8-527d-94dc-a18744d7c013 | note | Frequency - Each lot
4aff6612-6b70-58f6-a31e-69e3f307dda7 | note | Category - IP
506e3f48-15de-5dde-b6b1-2c04b442a644 | note | Responsibility - Surveyor, SE/PE/SPE
bbb0504d-33a0-58d6-9f6d-f7b6ab575dbc | note | Verifying Documents - Attach Survey Conformance Report
eb63ecb9-764e-5ee8-8f0a-f552945f917e | date | Date Completed:
3269e488-5822-4a6c-8781-a8fc3540b2a7 | checkpoint | 6.2 - Flushing
72c86832-e86b-5cef-8b03-2e3d0e6c1c4c | note | Reference - Section 702.09 (h)
24fcde0a-2da9-5299-8254-39829482c1f2 | note | Acceptance Criteria - Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
811824f2-bb4b-5e64-9eef-1e47d7dc4ef5 | note | Method - Record Review
555c254a-39d8-507f-bf25-fb93b7cd8526 | note | Frequency - Each lot
106e9ae2-0479-52c4-b724-b2b2d662d10d | note | Category - HP
55f4bac4-5368-51cf-a46b-aae5b12af122 | note | Responsibility - SE, Nominated Authority
ad47b3b2-c5d9-5a91-bc6c-e714791ae0c8 | note | Verifying Documents - Nominated Authorith sign off This Line
afb5ac1c-4a9a-5077-a780-33faf07071b4 | date | Date Completed:
78ea2f38-1e8c-4dab-a6be-8e93878c472f | signoff | AUTHORITY HOLDPOINT
d4146fdd-2703-4882-a1e5-4e709b8873ee | checkpoint | 6.3 - CCTV
95babddb-9e74-537d-9c5a-902129c61335 | note | Reference - Section 702.09 (g)
b45b80e2-dafa-54b7-b487-d4a656c10dd0 | note | Acceptance Criteria - Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
e3e74e10-4db6-597a-ad62-00595458c639 | note | Method - Record Review
e4cf91f5-4a41-5d04-9219-10e798b8ae03 | note | Frequency - Each lot
9aeba76f-c0ad-5e18-9975-1ea41c827962 | note | Category - HP
ca84987f-37dd-52dc-98dd-8ce24e886aaa | note | Responsibility - SE, Nominated Authority
f681eaea-45bb-56cc-93fe-b36fcae23acf | note | Verifying Documents - Nominated Authorith sign off This Line
73aaf7e8-51f1-5f97-8e69-db338d5c3a63 | date | Date Completed:
5944eea1-d76b-4568-aedb-b8a45d480d02 | signoff | AUTHORITY HOLDPOINT
2788e9d3-b9f6-48d5-956d-36b71070ec9c | checkpoint | Final Inspection
78a917ea-f522-57a9-a927-95f38f4b597b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9da750df-0e95-5578-9015-78279ca25d3e | textbox | Name:
e02ad69f-db30-5e4b-b603-3802f7d1add9 | textbox | Position:
777765ee-aeb6-5a0d-97cd-480ef9782b62 | textbox | Date Completed:
8fb4c302-fe53-47c0-a063-76cda9ea9f19 | signoff | Sign ITP
a4ffc4e2-d159-40f8-9776-82f47c0686cc | checklist | ITP-230-CIV-Ferris-Stormwater Drainage Supply & Installation Rev 0 | itp | ITP-230-CIV-Ferris-Stormwater Drainage Supply & Installation | 551122e4-70a4-4bf6-bc79-3e66e5d7a20c
c1458f5d-8f08-420a-9285-1f6ba4423c73 | section | 1. Referenced Documentation
220090b8-116c-42cf-ad50-e57e76245948 | checkpoint-no-value | Referenced Documentation
ccfce74e-f68f-5676-8b4c-40613f22bbea | note | Document Title: ITP-230-CIV-Ferris-Stormwater Drainage Supply & Installation
c8444932-17b6-5939-8c7a-95234c88043e | note | ITP Description: Stormwater Drainage Supply & Installation
a0427d61-2f46-5164-8802-5422a1d4f05e | note | Discipline (e.g. CIV/STR/RAIL): Ferris-CIV
fa74261b-d028-52b0-ba86-a608fa3ddabd | note | Revision Number: 0
05405eea-c70b-5cf3-9067-655fe6a8f0e4 | note | Revision Date: 23/01/2025
344887af-c9f7-5c2a-839e-45042c4d933a | note | ITP created by: Kamel ALSHOBAKI
947903f2-7dcc-5ca5-8d5d-7560d3905131 | note | ITP approved for use by: Pradeep Talasila
1d3f91fb-3e67-541c-82f9-d5ffd116fdf1 | note | 1.1 - Non Dependent
82529233-1540-5060-a6db-dd8b5516a4b2 | note | Reference - VicRoads Section 701 (May 2020)
e48d3d4e-37c2-52e4-a3a9-04ef4070b609 | note | 1.2 - Non Dependent
0821ea2b-9705-5346-bc76-9d1fb654054b | note | Reference - VicRoads Section 705 (June 2021)
f6c82e23-67f5-561c-ba2d-4476b2b413ba | note | 1.3 - Non Dependent
71d6970a-b27d-51fe-a5c0-268da18e3a83 | note | Reference - IFC Drawings
e3dce7d9-6668-5f18-b190-b1c39d60e4ce | note | 1.4 - Non Dependent
0febfdc2-14b4-5802-864a-565736279823 | note | Reference - CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
48c506a0-4fc6-4d3e-973e-fc1b93b49038 | section | 2. Preliminaries-Materials
cce3a0e7-0856-4e58-8528-46e735456ea9 | checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
470e0936-56e1-5175-9da4-cef6c756f18c | note | Reference - VR Section 701.04, VR Section 701.05, VR Section 701.09
ba91699d-38af-526a-838e-078853ab75d5 | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and VR Sections 701.05 & 701.09
9af38dd8-484b-5730-a7af-8257a09d4405 | note | ○ Precast reinforced concrete box culverts shall comply with the requirements of VR Section 701.04
8ebee7f7-4bbc-5e81-9fed-0d9d2006d85b | note | ○ Rubber ring joints shall comply with the requirements of AS 1646
8679f7ed-5e02-505b-8554-68c093755d2f | textbox | Enter: Teambinder Material Approval number
bd40449e-b6e7-5198-a83c-c3d06eefca13 | note | Method - Document Review
ef26ff40-d94f-5ab6-8df1-6a98a2cc0e13 | note | Frequency - Each lot
b3355a87-679c-5645-a4b9-6b03b0ea98ee | note | Category - HP
759a1f18-1ac1-5106-aee7-8b409365a6e4 | note | Responsibility - Nominated Authority
a27e808f-8c8c-57d2-bfb9-a59578b679e3 | note | Verifying Documents - ConQa HP Release
b9801965-0716-56a4-a113-e902c98d848e | date | Date Completed:
102835fd-4a5b-4247-8dce-ff511a6a976f | signoff | AUTHORITY HOLDPOINT
62933d01-6665-4355-87f1-e4115e7ec986 | checkpoint | 2.2 - Drainage Flexible Pipes
43d2098d-f47d-5887-9c5d-4a2a7e70697f | note | Reference - Section 701.08
d5ff89f8-4494-5342-a4d4-f9a71fa9b9bd | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
de30c4fa-a9a4-598d-94ec-bac7f6596c2d | textbox | Enter: Teambinder Material Approval number
c2cb2fd9-82e2-5bdb-bf72-e36bf65b3a20 | note | Method - Document Review
0434435e-812a-57c9-9083-fa31a46427b9 | note | Frequency - Each lot
08be0792-5c00-53ba-922f-e63d5d3a1756 | note | Category - HP
6fdfac13-14ad-5fe4-9dda-98d858aa2c11 | note | Responsibility - Nominated Authority
8e4cca4d-da05-5564-a158-b18952dab20a | note | Verifying Documents - Teambinder Material Approval
189260a9-2a0e-57f2-9769-3d5359d71a5b | date | Date Completed:
20b7c56c-6325-4531-8ce7-47014d3e0c27 | signoff | AUTHORITY HOLDPOINT
50575fda-09ef-462e-adc4-9e2f2faab41d | checkpoint | 2.2 - Precast Drainage Pit
198128c6-7062-57e5-8f80-37ef128047f8 | note | Reference - VR Section 705.07, VR Section 705.04, VR Section 705.09
651a7a5a-86e8-5aa6-86ad-411106da4d79 | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with VR Section 705.07 & 705.09
0b773400-b93f-5610-bf32-ba33c2896cbc | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of VR Section 705.04. Concrete grades shall comply with Table 705.041
10bc1542-0e8e-5393-87cb-b3da77700288 | textbox | Enter: Teambinder Material Approval number
b94b60b5-aa9e-556b-a04b-4d46c9d29942 | note | Method - Document Review
bf3cfed3-7a5e-59b8-a8d9-ac063f7ab3f7 | note | Frequency - Each lot
dfe86fc9-7f3c-5c6d-bdd6-43d3942f3f6f | note | Category - HP
cf97c5ed-3a79-57dc-9e41-bba3e9d2ac54 | note | Responsibility - Nominated Authority
f24f0835-5b3c-5413-a192-863ba7bda9e9 | note | Verifying Documents - ConQa HP Release
0d6fc806-36e3-5e95-bbbe-989c9c521098 | date | Date Completed:
4a944266-5af0-43b5-93c2-60d46519ea87 | signoff | AUTHORITY HOLDPOINT
7fa2fa6e-7f28-4189-a3fb-f4066bb0fea9 | checkpoint | 2.3 - Cast in Place Drainage Pit
39c22bdb-b157-5b22-8a17-bd362aec8746 | note | Reference - VR Section 705.06 IFC Drawings
9a891a7d-2b99-5239-b159-6cf10e941eb6 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of VR Section 705.06 and at the locations and to the dimensions shown on the drawings.
9b4383af-af2d-5d30-8eef-19c6ca3efef2 | note | Method - Document Review
e240781b-5531-5da4-9230-bc57774595fc | note | Frequency - Each lot
7722055b-ab8d-5cce-9a91-8b72c8835e35 | note | Category - HP
3671213e-cea5-5a47-a28a-528e04362a08 | note | Responsibility - Nominated Authority
47bef8c9-73d1-5543-9401-d4c71feaa63e | note | Verifying Documents - ConQa HP Release
6d53071f-adc4-591e-a4a6-a09e7993ac6d | date | Date Completed:
84fbd892-9039-42de-809a-fae173b6ae41 | signoff | AUTHORITY HOLDPOINT
4e3c9b3e-fabb-4b34-87c3-ed30e47b6d81 | checkpoint | 2.4 - Drainage Pit - Step Irons
f5db679e-e602-5e4f-ab29-216f40ff6335 | note | Reference - VR Section 705.04, VR Section 705.12
dae4db1e-1655-5f09-a3ff-40ee396b77e5 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
4bc60850-8f40-53c9-83d8-90071e055035 | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with VR Section 705.12
2ad73898-bb84-5630-979d-1afb0bffa2c6 | textbox | Enter: Teambinder Material Approval number
992ab594-3129-53d2-9265-dce93b10171c | note | Method - Document Review
fa447817-78f0-51ce-b88c-ba2aeb876614 | note | Frequency - Each lot
502c8fbb-919c-50f5-a3bf-fc47a92272e6 | note | Category - HP
17ffca41-a4fa-5ba3-91f1-83fc001e5c22 | note | Responsibility - Nominated Authority
335b257a-4b80-55b1-a421-f1cb2dca27b9 | note | Verifying Documents - ConQa HP Release
1536e889-ed6f-5ddd-8447-aba87c8766e6 | date | Date Completed:
e3b15165-5247-4e5a-9c92-0899af7ee35d | signoff | AUTHORITY HOLDPOINT
cf680f23-93d3-4520-bc69-5945c1fbf0f8 | checkpoint | 2.5 - Drainage Bedding Material
27c848c0-4e9d-586a-a23e-4c9be1a7de44 | note | Reference - VR Section 701.09
64d539fb-3aa5-50a4-9673-83157d9f1b71 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
9d253069-e17e-5c9b-a308-7c941e3df9e7 | textbox | Enter: Teambinder Material Approval number
7fd1cd6f-fe05-5af1-b011-0f236bee7db9 | note | Method - Document Review
a9c16fd7-75e4-5a04-9271-3579f6278632 | note | Frequency - Each lot
826cf96b-20b8-5044-9abd-f1fd17b44dc2 | note | Category - HP
05a76894-1ff7-5ec5-bcc6-418ff29d2458 | note | Responsibility - Nominated Authority
969afbcf-46c3-5c27-a36a-267d58d18604 | note | Verifying Documents - ConQa HP Release
93626551-690b-5239-8b9f-de5bb0301f70 | date | Date Completed:
b36f8881-cbcb-4819-bb7b-895b94e5a1d0 | signoff | AUTHORITY HOLDPOINT
190fe515-9daa-4bca-a7bb-dd002e49f33c | checkpoint | 2.6 - Drainage Backfill Material
7295a1de-ba9e-5142-acdb-dee674aff65d | note | Reference - VR Section 701.09, VR Section 701.19
27073973-59bd-535b-b155-91ec7ef320d8 | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
1d343d55-64c8-5890-b802-7d72f102da4f | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19
5e1ea76f-c5e7-5629-9045-cf78c7f36bb2 | textbox | Enter: Teambinder Material Approval number
e8b54f35-d1cf-5068-a58d-b2d7ac3180dc | note | Method - Document Review
daa30693-9119-5bdc-9ba7-fa3e6dd2a5cf | note | Frequency - Each lot
f7194fb1-4511-53dc-8324-56bec54ca8d1 | note | Category - HP
d5744249-d17b-527b-a624-c6dadda7ef78 | note | Responsibility - Nominated Authority
5a8ea354-9b1c-55da-aabb-b69544404b1f | note | Verifying Documents - ConQa HP Release
26800e36-485f-5ff5-9e6b-719378d5a431 | date | Date Completed:
adfbaf56-f0b5-4096-bc66-4820ce40add4 | signoff | AUTHORITY HOLDPOINT
758f5daa-195d-49dd-8bf3-738640947661 | section | 3. Preliminaries-Documents
6c0b045d-a762-4b58-918f-06014187c44b | checkpoint | 3.1 - Subcontractor ITP (where required)
68419f85-a30b-5a0f-848d-b2ebfbb8c572 | note | Reference - Subcontractor ITP
20595ae8-a911-56ea-8ef6-a19ea7ae573c | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
02db9a94-09e1-5197-b88c-c9cc05b19668 | note | ○ Attach: Approved Subcontractor ITP
0320e519-06cf-5e6d-b461-13b4bbb18baf | note | Method - Document Review
2af16b77-a7f1-5253-a5a0-ef7ea29d175e | note | Frequency - Each Lot
abb56578-f483-53f3-bd83-b473bcdfa23a | note | Category - HP
1c48dc3d-983a-56e4-9bcd-b8155c92e1d5 | note | Responsibility - Nominated Authority
8ae0667e-feca-503c-aff5-694f451936d6 | note | Verifying Documents - ConQa HP Release
94c7aa07-89fd-566c-b6f6-ed07ddf8ef4e | date | Date Completed:
1ca5fe47-d888-4ca2-8d55-6ea3e08c8cfe | signoff | AUTHORITY HOLDPOINT
cc5f3e68-74c7-4f27-b0eb-3aa36bf9e06d | section | 4. Pre-Construction Activities
54fb33f4-b3e0-437f-8ed4-1d489df74be1 | checkpoint | 4.1 - Survey Set Out - Pits & Pipes
57a9932f-9866-55c0-a74d-e669e25643a8 | note | Reference - IFC Drawings VR Section 701.10
0d9558eb-0213-569b-949e-9d122e45ce9f | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
ea4ca6e3-f528-5862-850a-7b11dad93985 | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
056c3a7c-ad6e-5686-aef8-3086f8b742eb | note | Method - Survey
55d9c549-fd09-538a-b793-720ae4f425f3 | note | Frequency - Each Lot
9e7df4df-32d9-574d-a63d-cc4e5d18e76d | note | Category - HP*
42b42011-811a-5efd-b922-a5a2c77e24dd | note | Responsibility - PE
4b440c77-4d96-5b6e-8a83-1faa5e8dc5b9 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
234e80a1-36fb-5547-b761-5b5d60a0cc37 | date | Date Completed:
02c93c40-0f0c-4d67-8f5e-af4add9967b1 | section | 5. Construction / Installation Activities
48a6c48b-4293-42de-8104-eb460747f76e | checkpoint | 5.1 - Pits - Excavation
5e90185c-f791-5c5d-a308-b284e01edeeb | note | Reference - IFC Drawings VR Section 705.05
749671b8-d2c2-5608-97f8-eb5544a4ceb8 | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
c0c37d1e-08a8-5537-a029-5a06af918330 | note | Method - Visual inspection, Measure
8b9eb036-f9c7-5016-b9c3-ee89983a0ef9 | note | Frequency - Each Lot
9f8ad79e-4d87-524f-82e7-60cec2041001 | note | Category - IP
28bde88f-ac73-51e4-80c0-d447878bfd53 | note | Responsibility - SE
25bdf1e5-fcf9-5829-b0b1-7ab285c381f3 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
9c036b9b-55cd-5eec-98ef-648a170d4580 | date | Date Completed:
28edc8f2-58fd-4799-934c-152e1be3cd27 | checkpoint | 5.2 - Pits - Placement of Bedding Material
d25fa03f-2c19-5ea6-b490-944ed93079e3 | note | Reference - IFC Drawings VR Section 705.05
d905836b-66bd-5701-ab0f-77c8f3decf9a | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
6f2c1337-d2b9-5e09-9781-927c293e4a11 | note | ○ > 80mm for clay foundations
61d60df6-4b06-5a41-b2c3-310ea5fc0d1e | note | ○ > 150mm for rock foundations
8e8a66a3-9d7e-5c08-93ee-1dfbe7f6fd7d | note | Method - Visual inspection, Measure
dc3124df-7802-570b-8657-80647192b037 | note | Frequency - Each Lot
7f719ab6-19d9-5d63-a589-e6ac2a90947f | note | Category - IP
5405809a-1642-5693-b625-22c0be3ead66 | note | Responsibility - SE
f59cdc52-3a0f-57e1-b179-dc2a42e5a4b5 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
dd035bed-2a83-5ba2-9c57-514f9d7f4307 | date | Date Completed:
527d338f-fb04-413b-9d0d-d263ebfceb89 | checkpoint | 5.3 - Pits - Bedding Testing
19a11e68-33cb-5a96-b1f0-b65995e89fb7 | note | Reference - IFC Drawings VR Section 701.20
10353034-158d-5f82-bf3e-533fa7c509ce | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
3eb60bd2-2116-55d6-b944-caf4e0ba03fe | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
900ce843-ff50-51b5-8f5d-b1ac923e7c55 | note | Method - Compaction Test
407650d4-dc79-5997-ad41-43e7bb7759ca | note | Frequency - Each Lot
fd586cb3-6a66-5c6b-954d-02992696405d | note | Category - IP
c7433226-5737-5064-abd7-e7294adc0753 | note | Responsibility - SE
7d4b1f1b-4e25-5ced-b8bf-cd5c828efff2 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
1e0e6727-447b-5aaf-adea-56f537e9207f | date | Date Completed:
626b9bb4-60fb-4375-84c2-558fa376362e | checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
18b80367-4064-5b92-bf16-32809f044074 | note | Reference - IFC Drawings VR Section 701.10
64162453-df07-5ae4-a3dd-76666c9834f8 | note | Acceptance Criteria - Survey pick-up to verify:
f7161d18-2f90-5308-a4b6-19ed6bf8ba47 | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
244268c7-09aa-52de-ab17-f169da2b4ca8 | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
cbb26e14-b435-54ea-9bf5-24aa0e2e51a8 | note | Method - Visual inspection, Measure
13757fa2-4718-5d5f-b27e-ed7430c86b03 | note | Frequency - Each Lot
2599bdab-97c6-5696-a008-ff971efe9115 | note | Category - IP
c9a63140-37e7-5a9c-8900-c6e6635a7612 | note | Responsibility - SE
6cf9e8ba-a9e4-5f47-8d55-f223c2b7b240 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
f1b14f80-6cae-5b47-91d5-7580ad4572f5 | date | Date Completed:
24d9945a-7a7a-412f-a1b8-2a79c1ae1956 | checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
10af61bf-0496-5efe-9f75-54271204d530 | note | Reference - IFC Drawings VR Section 705.06, VR Section 610, VR Section 611
af8bad3b-eb87-50e1-91dc-6fe9bc75e693 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of VR Section 610 and 611.
726a8757-ae7d-5e2a-9fbf-b6ef046f0353 | note | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
98b43e85-620e-5824-86ea-1f1d903c3b1e | note | Method - Survey, Measure
8e4e36e8-18e2-5b5e-ae23-885de2c579f6 | note | Frequency - Each Lot
4c87b2e7-fcbd-5b5f-b8da-7f14b04f4203 | note | Category - IP
090efc70-9b7f-5dbc-9ec5-71cb04aaff39 | note | Responsibility - SE
18ec0563-5187-54d7-b895-2f8092d584ab | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
45e7eb85-fe84-50cb-820e-0d9d0dd5f391 | date | Date Completed:
6130c857-e771-4907-8b49-0aa4a97bb973 | checkpoint | 5.6 - Pits - Jointing & Drainage Connections
a0963b5c-f0b0-5d5a-a41e-ce69b9ae467d | note | Reference - VR Section 705.11
81c63451-e478-589a-be60-017f6f64919b | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with VR Section 705.11.
50b75ee4-a25e-5381-8474-18dacfa1c036 | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
942acbaf-a738-52a3-aa8d-6839f6f55642 | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
24b48428-d970-5791-94a1-1a0edd0ff8cc | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
69c4c994-7966-5c03-bb97-512b4f179721 | note | Method - Visual inspection, Measure
c9bac6ed-8744-5b02-9da7-3e89357836b7 | note | Frequency - Each Lot
92c900c4-ad03-5c9e-aa3b-47ce24a8c6b5 | note | Category - IP
10efc7e5-a0d6-514d-936e-c58ffc0c2ef1 | note | Responsibility - SE
8bde8bc6-9330-57fd-8306-bd8b065f6171 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
9cf92292-0b90-52a6-a9ee-c7f13ce5ffe6 | date | Date Completed:
dab69464-66f7-4920-affc-80de87af300e | checkpoint | 5.7 - Pits - Shaping of Floor
09d27d42-ebd0-541e-91f3-0ecae227302b | note | Reference - VR Section 705.13
40dc880e-53b4-5631-8c9c-8794a1e05598 | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with VR Section 705.13.
02fdba74-d99b-523a-a78a-aed07a0441fb | note | Method - Visual inspection, Measure
1c7f1902-e821-5653-83c2-25674dbf10af | note | Frequency - Each Lot
f5084a58-4d35-5a13-b986-dafef672646e | note | Category - IP
1b96ecc1-8043-5726-81c3-dbd6ee2e06e1 | note | Responsibility - SE
bcc9992d-92d2-51ed-91c1-55d3c8509624 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
e191083c-7a6e-59c8-9697-999747918bbc | date | Date Completed:
baa851a2-5a69-40ee-ab98-d70ac409b99c | checkpoint | 5.8 - Pits - Step Irons
3eacaf58-b0f6-5247-b89e-a4e4b57c39ca | note | Reference - IFC Drawings VR Section 705.12
ea65d037-0eb5-588c-85b5-ba2040abcb8c | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
a65269b2-6486-54ab-9e88-8075475159e1 | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
e952a302-0b0e-5f3d-8cac-5724fe815c71 | note | Method - Visual inspection, Measure
f4014870-4a26-5958-a8c3-3141ccaa207f | note | Frequency - Each Lot
c49ec835-0e5f-573a-8912-5eead91273de | note | Category - IP
5b94c668-57c0-56b0-95c3-916d6d2a7b42 | note | Responsibility - SE
d07061de-b43b-5a3f-8a19-8715435dd053 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
cb4d53f9-4926-5259-a637-fc085991073c | date | Date Completed:
a7c324a4-7c69-4926-a5bc-e35530d07388 | checkpoint | 5.9 - Pits - Fitting of Covers
ba9750f3-34bd-5f30-88f6-67108824ef97 | note | Reference - IFC Drawings VR Section 705.17
d74af244-c310-546b-8b78-cc221883cd62 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
47f6e3db-916a-532a-96dc-90602a6f3c0f | note | ○ Height shall be within 10mm of the design level.
c62bd232-8dbf-546e-ba56-ff2dad11797d | note | Method - Visual inspection, Measure
4914efa6-7149-571d-a8a2-8326662546ff | note | Frequency - Each Lot
de59d8af-5afa-5de6-9b9e-15cb8fc32045 | note | Category - IP
81434496-7ed4-5894-b285-5cb2b5e8a730 | note | Responsibility - SE
2218561e-50fd-5934-8918-b3b60f92a44b | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
cdb56f2b-087f-56b3-9378-19d5e33a7f83 | date | Date Completed:
675130e3-7072-42c7-9dcf-1e3a0dd51a37 | checkpoint | 5.10 - Pits - Pit Lids
d486f89c-6dfd-5110-800d-b362f9088ea3 | note | Reference - IFC Drawings
bc59230c-516c-589d-b64f-b949b49ff70a | note | Acceptance Criteria - All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
2e6ca747-c502-52f2-8031-fa7c739b7d2a | note | Method - Visual inspection
3b5dd9c6-a4dd-5caa-8b17-c2764c695f25 | note | Frequency - Each Lot
b814bf99-0a95-562f-9a67-9e173a023fcc | note | Category - IP
56ede307-82af-5e51-8cfa-b5f9f71e9515 | note | Responsibility - SE
ce0ae12c-3a0e-569c-ac8f-a6cfed8d088f | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
a2d12075-21ac-5f4c-9f65-428fc1eb7cb3 | date | Date Completed:
eaeecdf5-f1b3-497c-b38e-8a8d8b8c6429 | checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
af5d29c0-ff8b-57c6-ab4e-1089ce76591e | note | Reference - VR Section 705.18
b195c757-5cac-5c9a-a399-2f21c1dd1d3b | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
18eb44b7-3e98-55af-ad8c-08dfdcac12d4 | note | Method - Visual inspection, Measure
67925a1f-c2dd-57de-8c77-98df32211af0 | note | Frequency - Each Lot
cbc8753a-6391-5805-b024-aefe22940728 | note | Category - IP
60268fb8-6df1-5558-a8fd-22d744b6af89 | note | Responsibility - SE
f01be20d-728a-5814-b6bd-8919c57e0ff8 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
95ad74b0-fc36-50cf-9b66-8452e1b8b032 | date | Date Completed:
bd8ff0d2-5f1f-44e2-be3d-c18829da14f0 | checkpoint | 5.12 - Pipes - Trench Excavation
0e5a6652-5f20-5c52-9bc2-24cfb4ad84ad | note | Reference - IFC Drawings VR Section 701.15
3b641820-fccf-5446-bffb-3f6cd24be7b0 | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
27a45233-81f4-58e0-805d-d2fb2bc81322 | note | ○ > 300mm, < 600mm for RCP
2e620c6b-7dbb-5c2c-95f4-739c082a5908 | note | ○ > 150mm for Flexible Pipe
b8a3bdfc-dcc0-5337-b74f-c3cf01d60a64 | note | — The base of the trench shall be compacted to refusal using mechanical plant.
cbacb612-298e-52ac-a354-2c950f4cc9fe | note | Method - Visual inspection, Measure
8951f87e-36f5-5029-a795-7dd3371a59d7 | note | Frequency - Each Lot
90525523-5dbb-52ed-b610-aaffa1bf3e33 | note | Category - IP
dd6c3d67-db2c-5649-b9a3-be3242e6c931 | note | Responsibility - SE
ae2b04a4-71e1-5cb9-b7f3-d57e9ffea835 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
ec797a46-8a96-5d9a-a6b8-382821b3d2d8 | date | Date Completed:
4b034458-e38c-4425-b003-5ea7a4938ff9 | checkpoint | 5.13 - Pipes - Bedding Placement
64b62072-ec3a-55cb-a223-399b61757316 | note | Reference - IFC Drawings VR Section 701.16
7a3225a8-445d-5e34-8f48-9dd0e292f507 | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
de60335c-3bce-5328-81d8-850403ed54b8 | note | ○ > 100mm where D<1500mm
f56c14ee-7246-584a-9d70-95d29b77e785 | note | ○ > 200mmwhwere D≥1500mm
2907b09b-9388-5f1f-97bd-424b98ceb4ca | note | — Bedding material shall be placed and compacted in layers <150mm loose thickness
016d7f2f-c8d4-55d1-9ef4-82e1c2bcabae | note | Method - Visual inspection, Measure
5ba12217-b93c-5dbf-88dd-bac3e6facca5 | note | Frequency - Each Lot
ba72b709-d4eb-58d9-bba8-6f54956346a7 | note | Category - IP
9fc6646d-6ac6-537e-85ca-1c10fbd0de1a | note | Responsibility - SE
a74f94d9-8544-5629-ae7e-e9b7b255292e | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
b3db2330-cbdf-5157-9cba-b1f8406c3486 | date | Date Completed:
982735d0-0df8-4537-82e6-9dfd1324f459 | checkpoint | 5.14 - Pipes - Bedding Testting
06e9d871-1211-58e6-a8e1-63a33553d9c1 | note | Reference - IFC Drawings VR Section 701.20
312d113f-f7f6-5068-a87c-acbc71b6af3c | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
d0fe262c-ab2d-59b1-94b9-a08deebad505 | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
ae15d648-f572-5f2b-a22f-36e1d4bb16cb | note | Method - Compaction Test
ce338965-18d8-5418-81f6-606512d62497 | note | Frequency - Each Lot
730c7399-5866-566b-8542-3feac1078cc9 | note | Category - IP
725cbac5-6011-5959-95a4-4c8b1678d5b2 | note | Responsibility - SE
2308354d-0d96-5d91-abf9-d0267dbd12d3 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
2153d31d-625a-5b9b-af47-fa12b404076f | date | Date Completed:
07eab39e-55d4-4c2e-ac45-baa4175e4cbe | checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
9f99b6a2-829b-5819-9480-f5ff7c79f808 | note | Reference - IFC Drawings VR Section 701.17, VR Section 701.20
0b759aaf-74ce-5d7f-842d-122b21d71c84 | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
f5c5c6af-de65-5285-9398-f952da893981 | note | ○ Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
2404d5b7-9fea-5219-b6dd-fdcbaafb92df | note | ○ Gaps between spigot and socket are in accordance with the manufacturers specifications
67811088-f98e-54c4-ae3b-2bf3fbee22c0 | note | ○ The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
5d806d36-ff45-5efd-8e5f-820c5cbb502d | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
2f2920db-f0d7-53b2-913f-173cf4c25167 | note | ○ The spacing for multiple row culverts shall be as shown in Table 701.171
4251f9e4-a3ac-5d2d-92d0-44b9ac263946 | note | Method - Visual inspection, Measure
85b25263-0f23-56e3-bac1-e6b546773b71 | note | Frequency - Each Lot
b9e32d5b-55f6-5970-b9cc-827fc276088c | note | Category - IP
544cae08-6fe5-5dee-8882-6264a164cac9 | note | Responsibility - SE
362c72e8-8e45-5c87-9316-5fc3fd424b1a | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
4f720238-419a-5811-8056-17da86416e18 | date | Date Completed:
e4fdd2ab-fc98-4a57-b35d-c4d4cf618694 | checkpoint | 5.16 - Pipes - Lifting Holes
2146302a-067c-5fdc-8760-36385eaf2ba8 | note | Reference - VR Section 701.18
8c9fdfab-717b-59ac-960a-5ea048c54a8c | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
d314049b-fec4-5cd7-b412-c1ec4278a5a5 | note | Method - Visual inspection
2a601e40-61ea-56cb-93a0-399fb93227fe | note | Frequency - Each Lot
9e35cc51-18c2-59c4-8730-4e726e876e61 | note | Category - IP
e853f010-2735-5500-bf73-dd2079b367a2 | note | Responsibility - SE
d3a7585a-9534-5904-abd5-9d8f44f0d30d | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
8f291058-9e2d-5440-8094-777448324f15 | date | Date Completed:
172f98be-1b9d-4b82-b443-8e081fda0055 | checkpoint | 5.17 - Pipes - As-built survey pick-up
c13372ad-fb37-5a19-8d46-25ba5f90952b | note | Reference - IFC Drawings VR Section 710.10
3aef12f6-ca9a-5e5d-a742-c75fb3f2ee02 | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
a5802c09-dec2-5a91-99f7-34f3244a31ab | note | – Offset pits to kerb +/- 20mm
29dc9106-68a2-5fea-9ffd-b0d9fc418690 | note | – Plan location pits not adjacent to kerb +/- 100mm
8d4ce209-7830-56c5-8fef-d0a4dd76d7ad | note | – Invert level of pipes at pits +/- 50mm
d56c57b1-908d-50f2-9ee1-40e0c13e3eae | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
5ac11493-8edd-59c7-859a-dc150dc9c1b1 | note | Method - Survey
c50c0fa8-3ccd-51b2-9507-0460e3ff7afc | note | Frequency - Each Lot
c36d2801-927a-5f55-b750-a91a3a6caf77 | note | Category - IP
5d87dbc1-71cc-5cb1-b63c-97ce8ff5152c | note | Responsibility - SE
a50f35d2-bf06-50e2-8805-77a8edbc792a | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
7072f28a-30e8-5dcc-9cbb-f4ab85548a2c | date | Date Completed:
1bfc055f-8ce1-4a0a-8c83-b9e455187bb0 | checkpoint | 5.18 - Pipes - Backfill Placement
cdbf58a3-2f81-5a2e-bc6f-ec8a7d47ba72 | note | Reference - IFC Drawings VR Section 701.16
16631132-ae01-5645-a403-f22ff4699aa1 | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
958109ff-9b96-54aa-8ff4-7bdda2e42324 | note | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
daf99899-4183-58c0-8bb3-5746025a8d92 | note | Method - Visual inspection, Measure
e2966eb0-7e43-53b0-9963-94a345b9eafd | note | Frequency - Each Lot
c528dd5e-4ca3-500e-a0e7-5673c017ae47 | note | Category - IP
3f345548-70fd-5230-a772-4a559dea009b | note | Responsibility - SE
f1b8b7be-0bc7-57a1-afc2-35883cd2b57e | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
7a16d966-68ba-5b02-a06c-da830f597673 | date | Date Completed:
1dba4fc6-11ea-4550-b456-12dace036dad | checkpoint | 5.19 - Pipes - Backfill Testing
ad031c38-6a70-5752-951c-62104381be3f | note | Reference - IFC Drawings VR Section 701.20, VR Section 701.29
a9e659d8-872c-506c-8f50-342d297b9047 | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
39390773-95b4-511c-a6cc-864aecc69df3 | note | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
ee4668a6-8641-53db-9ff8-9781287d82b0 | note | Method - Visual inspection
35ffc3ad-0320-5f94-ac85-6b50fb104773 | note | Frequency - Each Lot
63aab8d6-7590-50a5-9ee3-dd940b0f6629 | note | Category - HP*
29880db9-dff1-5a34-aa7e-16b17853e08d | note | Responsibility - PE
6309a45e-7828-530f-8c50-653ed5edc331 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
04ac9d4a-46ad-51b2-a35c-61c493d03b2d | date | Date Completed:
9cc87885-713a-4118-938b-646daed89143 | section | 6. Post-construction / Post-installation Activities
f9a41ac0-8d6b-4c4a-baa7-c29399992acc | checkpoint | 6.1 - Flushing & CCTV
3c4da116-c8d3-5891-b7fd-ab267b06c5e2 | note | Reference - VR Section 701.28, VR Section 701.30
5ea28935-7fae-5197-a86e-f93158864d66 | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
6dcbf382-43c9-520b-952e-896ff45f8868 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
0adb5997-ebb8-5349-91c1-78aeb95c907f | note | ○ Attach: Flushing Record, CCTV Reports
e128e27e-dd57-59d4-9ab0-99b2f93bd270 | note | Method - Record Review
81fc2ef8-b455-5a25-a310-f46c08a37f34 | note | Frequency - Each lot
e79418b2-3585-5e6f-9839-a5a5593eb210 | note | Category - HP
c588bc0d-da30-5d42-a392-d877cd964bc8 | note | Responsibility - Nominated Authority
5cf70f4b-f059-54f6-97eb-193320fee8da | note | Verifying Documents - ConQA HP Release, Flushing Record, CCTV Reports
d10c7084-911f-5b64-96a6-618a83356adb | date | Date Completed:
e5ed1d81-7fbf-4f91-9477-baf2cb43a1b1 | signoff | AUTHORITY HOLDPOINT
8751d992-b4ef-439f-97c4-21113c325338 | checkpoint | 6.2 - As Built Survey
c5de9a05-7d9a-5a0a-be4a-fa265ea09d1d | note | Reference - VR Section 701.10
270e778c-a5bc-5ea3-b595-ce457783f4e4 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10
3665d1d0-22dd-5e98-a585-6d78db2d5872 | note | ○ Attach: As-Built Survey Conformance
4f5261e2-0f1d-5c1b-b854-622bebfc9f9a | note | Method - Document Review
fd27154d-1cfe-585a-9dce-6c5ff6ea293d | note | Frequency - Each lot
2a6da622-ec42-5a8f-aedf-37d20072f4f4 | note | Category - IP
26fe221d-e4fb-5b6c-9804-88450fed179f | note | Responsibility - SE
6eb1da31-3447-57ef-8829-643a0bd4e98f | note | Verifying Documents - ConQA HP Release, As Built Survey Report
5f695a52-2d2b-580d-b758-880566298bf5 | date | Date Completed:
ede930f7-7235-479c-b2d2-440557540de5 | checkpoint | 6.3 - Repairs to Damaged Pipes
e6c08bcb-6f34-5e01-9967-24a576039b5b | note | Reference - VR Section 701.31
134de21a-dcf0-52a3-b3e4-b0dbe0b20cf4 | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
8983f845-d611-51c8-913d-87329370bda5 | note | — cracks wider than 0.5 mm
f7d88140-2755-53a9-aa2a-08298fd7cac6 | note | — spalling of concrete
04cb9f23-b71d-51c6-ae10-cdaab543df1b | note | — exposed reinforcement
b7990621-2cf1-542a-a9aa-979b5394df64 | note | — joints that are not fully engaged.
9e9c1ce5-ab67-5757-a660-7550ce6307c2 | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
071d5ae7-56fc-5910-aead-084dbed5f284 | note | — longitudinal cracks greater than 2 mm
bca0d54c-51c2-5fae-9a65-d4b99c32ce3f | note | — circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked VR Sections exceeding 3 mm
2aee65da-910e-5af1-a532-e335913e4943 | note | — circumferential cracks around part of the circumference with width greater than 4 mm
e9608df1-cdbf-500f-83b2-501c00479521 | note | — penetrations with area greater than 400 mm2
12339def-49d0-598d-8022-e65ca61d1ea3 | note | — pipe joints that are separated.
45cadd91-1ef1-580a-89a6-f0ecb98c404a | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
7cb7338a-4275-576e-86d9-93aa695d191d | note | — hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
a64ea455-387a-5f06-8299-923a63f72166 | note | — fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
bbf2a39c-7e81-52db-88b1-3240a8d9d32d | note | — spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of VR Section 689.
3a96e46b-e346-59fc-9674-2dc300490cf2 | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
f6e65d57-8e4a-57c6-86f6-ab5dd30824e8 | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
b436a538-3cb5-531e-92c2-9b08a22931ec | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
c17719d4-fd84-5eb2-88d4-5359db326d13 | note | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
c248198e-0953-5965-bae4-41ab4af49ebf | note | Frequency - Each lot
93295d0d-9665-5e54-a243-7892c2ea6147 | note | Category - HP
58c27da4-6646-55a0-8552-cdbf972118dc | note | Responsibility - Nominated Authority
f0d11e9e-a11c-51c6-b765-3243257a5534 | note | Verifying Documents - ConQA HP Release, Approved Repair Procedure, Post Repair CCTV Report
9eade41e-475c-53a9-b896-132113b0e51e | date | Date Completed:
6ee0f28b-f311-4db0-9c85-938fd3418aea | signoff | AUTHORITY HOLDPOINT
7f0787b1-a044-41b0-84e9-f6b954caca8e | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
f9b044c7-6b74-5e9c-b2a7-1e4899313ce7 | note | Reference - MRPA Quality Management Plan
b111e9da-6e57-5d40-ab31-162ff0f3c517 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
e412e432-ce53-55e7-85a3-8d19013a6a61 | note | Method - Document Review
7e347ea8-ae7d-5eb5-84fa-912512e490f4 | note | Frequency - Once, prior to closure of this lot / element / Work area
15c7e608-fbf3-59af-8749-fb429be08716 | note | Category - HP*
106a79b3-296a-5fbd-a3b3-6408f366f468 | note | Responsibility - PE
73ddb569-94c3-5dec-adcc-fa701ab0f511 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
ceaf3904-485a-5441-85b0-d7eea7a4721c | date | Date Completed:
df1945a3-519b-4c39-b79e-4002cb32c4b8 | checkpoint | Final Inspection
612d7a1d-bc26-5320-bffb-c7dfe2fb72d0 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
1dc4e762-7bd0-5a63-86e1-f5db305feb51 | textbox | Name:
896e1b4f-8c17-5237-b3c4-c98465efc585 | textbox | Position:
35b679e8-cead-562d-b744-e4c0e65f592f | textbox | Date Completed:
e9338047-24cb-466a-b3d2-4c220042645c | signoff | Sign ITP
| checklist | ITP-231-CIV-FRMS-Type A Fill - Road Rev 0 | itp | ITP-231-CIV-FRMS-Type A Fill - Road | 36d68765-6c1b-49e6-9d9f-ba1899663467
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
b4cf90d3-4ef4-5500-8308-ba8a6088b631 | note | Document Title: ITP-231-CIV-FRMS- Type A Fill - Road (Supply and Install)
c02769f1-0de3-5186-8660-a492346b8cef | note | ITP Description: Type A Fill - Road (Supply and Install)
41e82946-a9fd-53c6-9465-1ac69a648bec | note | Discipline (e.g. CIV/STR/RAIL): 231-CIV-FRMS-
9eaa99cc-b1b6-525b-829a-8e863fc28c39 | note | Revision Number: 0
69bb6bb8-ba74-54a7-8ba0-e234cdb3385a | note | Revision Date: 28/10/2024
aeee9bc6-1d47-586f-867b-f9029e36568e | note | ITP created by: Cedric Guico
1d2cb22d-cfeb-53a5-9b3d-e3db0a5435ce | note | ITP approved for use by: Pradeep Tisala
2bdd7751-7a85-5970-9799-d81ea84f8afe | note | 1.01 - Non Dependent
20cdafa7-ab70-5679-9de3-217b925bf637 | note | Reference - IFC Drawings
a2ef19fc-60a2-5160-8d81-12d5fea2b9ed | note | ○ VicRoads Standard Section 176 (Sept 2008)
ec2118d3-d4df-5d9e-8b35-ce621dbc6ef1 | note | ○ VicRoads Section
9177e861-ee6b-5030-9e72-2485a8fa54af | note | ○ 204 (Dec 2015)
8b7e21f7-b531-5cf6-8bcf-85205f551f3c | note | ○ Code of Practice RC500.20
c358de88-2b5a-5da9-8b7c-ac4ca4a50005 | note | ○ Code of Practice RC500.5
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Material Conformance
97d33fde-be6a-5ddb-a787-9d68a1eb3387 | note | Reference - Section 204.04 b) Table 204.041 IFC Drawings
47aa3f38-4adf-59d3-ac78-5e03bdc3fc19 | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
b8bd69c4-761d-5032-b18b-cf7abd33e80a | note | ○ Assigned CBR≥8%
ddd12352-171e-541c-a101-4c8151cbb95c | note | ○ Swell ≤ 1.5%
c0bfaadb-5f86-5406-ba1b-e596dab99c2b | note | ○ Permeability ≤ 5X10-9 m/s
cbff4a32-d49c-51c1-986b-eaa45966754e | note | ○ Grading:
64e3d265-a9ff-5223-b49d-60f3254d65a1 | note | — 75.0mm 100%
67fbed68-6e1c-5dc2-a06f-cc59a72b380a | note | — 4.75mm 40-80%
632bb070-36d9-5cb1-a949-a0b624c14fa2 | note | — 0.075mm 10-40%
09f793e1-4cdf-5f4f-abc2-ebb22254cbd0 | textbox | Reference: Material approval in Teambinder:
0e4d8d0e-e6a3-558b-9121-c6ca1e3e4293 | note | Method - Document Review
ef7d2fb0-a49e-5d35-bc3c-b91d21dfe747 | note | Frequency - Once, for each material type
022b49bf-8132-571b-b7d1-43c238b154d4 | note | Category - HP
cdea62a1-0f45-5576-a2dc-0ccc7c616114 | note | Responsibility - SE/Nominated Authority
f73b8e7a-dc9d-5f7f-bbb5-f9b68bb1cb7d | note | Verifying Documents - Supplier Material Conformance Certificate
ffcf06e4-247f-5c7b-973c-8026fb54010d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documentations
| checkpoint | 3.1 - Pre-Commencement of Fill Works
d0052291-b446-5bd7-b53f-1ed86933aadc | note | Reference - Section 204.10 (b)
4dc4d39f-c8e7-5fe5-a423-c8247846e84e | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
284b7b9a-b8a9-576d-94d0-39388cd71a27 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
2254a28c-48a3-5c3d-be20-e9586a9f9c7c | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
88696e81-2283-570a-bc1f-c89e0071566f | textbox | Reference: Subgrade Preparation Lot Number:
71e86f21-53bf-5470-8ec6-355f228f1ad9 | note | Method - Visual Inspection
0dccba75-84a5-5d82-aa2c-feed1fb223ca | note | Frequency - Prior to commencement of fill works
460b6207-eb75-59d5-b5c8-74bbe4ee49c5 | note | Category - HP
d7fa1318-2d93-52f9-9f24-d656edb65150 | note | Responsibility -
0c5a3ea5-6d51-5e9c-a2a4-915b69890451 | note | Verifying Documents -
6e3ca31d-a125-5b33-bec7-7bfb30467009 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set Out
2111c622-165a-5208-a69a-6744fd60c784 | note | Reference - Design Drawings
11fa4729-5026-5a75-9fba-ca2b025f50c8 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
eb39f693-477e-59ec-978c-e95ede250ec8 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
a8834ac8-9d67-54a2-a765-fc34ee132b0c | note | Method - Visual Inspection
e3c1bfcf-0a01-5ff5-be9e-0e1f9186a1f6 | note | Frequency - Each lot prior to commencement
184eb843-d49f-51ec-9b3e-23d3a2f9298e | note | Category - HP*
3a967ead-72e6-5faa-a8e1-4832d809417c | note | Responsibility - PE
890f0ad3-935d-5716-82cc-d9433bdfafbe | note | Verifying Documents - Signed ITP, Lot Map
e274067d-9cc0-521a-96be-9763637ea8e5 | date | Date Completed:
| section | 5. Type A Fill/Verge Activities
| checkpoint | 5.1 - Placing of Fill
dd07bbcb-3197-5f7d-9044-7717b8440bf8 | note | Reference - Section 204.10
63bcb50a-2124-5687-b757-08e87f62fbac | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
0ac8a7dd-f30e-569f-9617-4e43f2137394 | note | Method - Visual
e7e64a82-5166-5869-b09a-ef677262e73b | note | Frequency - Each Lot
0de16e73-6364-5aef-b16a-388b167787b3 | note | Category - WP
bd7891a5-f5c6-515a-a81d-eef3602c0fab | note | Responsibility - SE/Site Supervisor
ca25b959-7750-5807-b3f4-85828d897801 | note | Verifying Documents - Sign ITP
2ffad2fa-ac47-503e-9e4f-d56415cdf259 | date | Date Completed:
| checkpoint | 5.2 - Test Roll
0f8c6213-c8f7-5f50-acdb-fe7c27f3bd21 | note | Reference - Section 173.03, Section 204.12
2b6688be-6cb4-5fa6-911e-afcba2c2c0e9 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
669fde16-2f8c-50a7-a558-b5f677839ca0 | note | Method - Test Roll as per 173.03
d167c7fe-d8d3-5635-9619-b84bdc8e92f8 | note | Frequency - Each Lot/Layer
b155294c-1c66-5222-8fe9-dabb3fed60f4 | note | Category - HP
69030d80-ee3d-5662-bd39-8f219c3b18a8 | note | Responsibility - SE/Nominated Authority
170d8260-a7bf-55dd-9633-f143832d7428 | note | Verifying Documents - Sign ITP
da6ab2f6-b80a-5ea8-bc34-7a5fcc591cc7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Compaction Testing
58c9e270-b024-52ea-ad81-aa975c73f79d | note | Reference - Table 204.131, Section 204.14 c) Table 204.142
4f72f2aa-f52b-5a11-bc0b-b8986b398dbd | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
c985de56-e650-548a-b40e-b41c09129a8f | note | ○ Standard Compactive Effort
51529567-5c28-5008-a16e-b7c79305dae0 | note | — For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
7131e2bd-1c58-5329-b3a5-b46bfd9baeb2 | note | — For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
b4857039-e420-5d6a-a269-18b23fdc8f44 | note | ○ Compaction and Moisture content
26e62e44-2e05-5aaf-aaf3-bdfa51fc45eb | note | — Scale B: Standard Compaction 98%.
e3052ed7-2b19-5520-a00d-10ea6a78b9b5 | note | ○ Lot size - the leser of one day's production or 5,000sqm
ba52c1b0-ed1b-50b3-9744-18e510adb373 | note | ○ ATTACH: COMPACTION TEST RESULTS
23b9c822-7a01-5413-9dd2-8c5abee72d4a | note | Method - Review Document
3f0838ba-3d5d-523d-ae40-b0bcec5f7d71 | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
1c435dfc-0250-5690-9a8c-61a810da0f34 | note | Category - IP
e4eeb7e5-1cc8-50be-a642-865199d3967d | note | Responsibility - SE/Site Supervisor
17defbaf-8347-5529-a3b0-4a84d5552ae3 | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
7d87af61-6c4e-5018-8743-498981a239da | date | Date Completed:
| checkpoint | 5.4 - Preparation of final surface
e6697215-be1d-5dbb-9a4c-b2c905e492a3 | note | Reference - Section 204.15, 204.03 (g)
3ddf9f31-734e-5366-b15d-fd915c00e843 | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
ea17f7b8-4b18-5b33-9d2c-3d273ac5e732 | note | Method - Measure
c1b88c6a-1eda-5164-8073-35905e798c9a | note | Frequency - Top layer
2991a479-a11e-5342-9756-ec5b1b823e70 | note | Category - IP
d1f0ea0c-7f89-529d-96de-bdab73f811b4 | note | Responsibility -
5ff934b6-b2a6-5d4f-a2aa-6e352d8a634a | note | Verifying Documents - Signed ITP
bdddab9b-e9f5-5c3e-a9a4-be24b17d4082 | date | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Post Compaction Material Property Testing
ce54d093-b5f5-545f-89c7-af0443e64544 | note | Reference - Table 204,041, Table 204.141 Section 204.14 a) or b)
eb568dea-68b2-5f63-875f-16384c70e53c | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
5fdddfcb-79ef-550d-9572-a8c005497460 | note | — CBR ≥ 3% and Swell ≤ 1.5%
5c17f14e-2ca7-5ab3-af90-c0b5a80dd94b | note | — Max Permeability = 5X10-9 m/s
d0afa4ee-b89a-5fbf-b8ca-ae4f907638ab | note | ○ Grading:
59464fac-9794-5968-9dde-03e8cb3cf2ad | note | — 75.0mm 100%
06a8d303-3a9c-5fed-84e8-5a6f5515b9f0 | note | — 4.75mm 40-80%
047fc7b6-2c9c-5825-a84a-8f9c348ef5c3 | note | — 0.075mm 10-40%
1a36ef48-ebd7-530d-8beb-60e2d0a3f170 | note | — Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
0ce9f84d-f276-5bc5-bc08-6ae2878b85cc | note | ○ Scale B:
4ea0bfe1-c8a7-5ba6-905a-ccf85d4e9f22 | note | — 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
1872e97c-121b-55a5-ae7a-c59a433684c8 | note | — Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
b6aae5de-b429-5a34-8d13-af3ba70d3dd4 | note | ○ Attach: Post compaction test results:
c6faaa0d-9ce8-5e49-98ec-9a6e52292281 | note | Method - Review Document
c294274f-ac8b-552b-85a7-ddf1a12be31f | note | Frequency - Refer to Section 204
e72aa4d9-386e-5da3-989f-d469ee4744d1 | note | Category - IP
32569d7a-75fc-5d11-8275-dfa0448f6a53 | note | Responsibility - SE/Site Supervisor
638b194e-6318-5a20-99c5-e8b8de269e00 | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
4c922ded-3324-5d57-9d9f-8ea2e686c36a | date | Date Completed:
| checkpoint | 6.2 - Survey Conformance
3ec4b5c0-2e0d-5b7c-9b78-30521ae2f361 | note | Reference - VicRoads 204.03f,g and h
e549d43c-283a-5fe3-8ff1-bb092a41e985 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
36ff8bdd-e881-528b-bdf6-0b0b87fe22c1 | note | ○ Level tolerances Scale A:
9d2196b8-e898-5b74-9aa9-387fae4a9ef8 | note | — Range x = +5, -15mm
0ce8c6b9-e97f-57df-9d3c-a60b44700e87 | note | — Max S = 12 mm
28d5d968-9d42-5fce-9133-b5ca4c0454cb | note | — 80 measurements per lot
b7457a65-cff1-59ff-8f06-b8f0ad75eb50 | note | ○ Level tolerances Scale B:
329877c5-b45f-53cf-a0a9-7de5f3486436 | note | — Range x = +5, -25mm
0fabef7e-4e6e-5292-992c-756158d516f0 | note | — Max S = 15 mm
45eea8ef-e32d-597e-97c5-0fc67869b15c | note | — 40 measurements per lot
c34da6a8-510d-5d51-8e62-c0804af20c9a | note | ○ Level tolerances Scale C:
f8d1440d-7aea-5c9d-bcf0-c68806ecbb07 | note | — Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
db6b78fe-d4e7-5fdf-978f-6cc9dd45b78d | note | Method - Document Review
f4e84c94-43f0-5a4c-8d84-cbb06261038c | note | Frequency - Top of Type A/Verge
c4e7206e-0819-5fae-8fb3-10937e2893ea | note | Category - IP
5e438e75-5414-5f91-a040-6a3020ca87a2 | note | Responsibility - Surveyor, SE/PE/SPE
ece6792e-e242-553e-8e48-eea4dbb0fc75 | note | Verifying Documents - This ITP, Survey Conformance Report
fa14a14e-35af-5ca4-8e8e-cef09eeddbd2 | date | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
c981c651-47fd-5432-97a4-7e95144bea6d | note | Reference - MRPA Quality Management Plan
7f98cade-1af9-5a95-8117-ad12ad71c210 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
66319302-c261-5065-9d46-79a91cc4625b | note | Method - Document Review
a0b0337b-3dc6-5e72-9043-b0c89720e483 | note | Frequency - Once, prior to closure of this lot / element / Work area
8d9f9571-6160-5314-879b-188c408561be | note | Category - HP*
325d98a1-0135-5735-8757-e344a52dc22d | note | Responsibility - SE/PE/SPE
ee7e4011-2e77-5a6f-9151-9765ebf044c1 | note | Verifying Documents - This ITP
4ae921f7-8512-5276-9143-c8bee6a35ea6 | date | Date Completed:
| checkpoint | Final Inspection
fa4aa1e9-fca3-51d8-96e8-f1e0389a3e29 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2c56bb32-5256-582b-ad88-7191ad89b9bc | textbox | Name:
85f8c840-b769-5243-9e6b-fab02b680723 | textbox | Position:
7292dc9e-1c14-5c5d-ba80-16a4f5ec2c9a | textbox | Date Completed:
| signoff | Sign ITP
3f043095-2677-4535-a3b1-a1d502f4fccd | checklist | ITP-234-RAIL-Ferris-ITP Track Removal & Construction Rev 1 | itp | ITP-234-RAIL-Ferris-ITP Track Removal & Construction | c35dff7a-70b1-4eb0-a5d6-8286a8c6a7d6
7b17ff0c-fcbe-4487-8d16-065cb8ff53a1 | section | 1. Referenced Documentation
6fcd8fd2-a9bd-40b2-8a56-799325d64041 | checkpoint-no-value | Referenced Documentation
17a5f63a-0d59-5804-aa09-53ba6f561fd8 | note | Document Title: ITP-234-Rail-Track Removal & Construction
a7fdfb62-26af-5e39-84a6-cbcaea9a8d1b | note | ITP Description: Track Removal & Construction
ca18d297-d4e6-5510-9247-cc6a70bc0891 | note | Discipline (e.g. CIV/STR/RAIL): 234-Rail
3a1ea297-2cae-5ee4-aaa8-01f3024f17c5 | note | Revision Number: 1
375cdc3e-4ba1-53f5-8f6e-1b4f08da2f76 | note | Revision Date: 22/10/2024
c644fe27-af92-5007-8946-991651747482 | note | ITP created by: Jake Argentaro
a53f5cb9-3c06-5b42-8769-245d5a0eec78 | note | 1.01 - Non Dependent
6fea73b4-c1f3-5f55-9cf9-f3075c150fe8 | note | Reference - Ferris Road Track & Civil IFC Drawing Set MRP-DPK-103-00-CPW-0060, MRP-DPK-103-00-CPW-0063
9f3355d3-8447-5ae6-9a7d-b8145a8249ff | note | 1.02 - Non Dependent
b7c3366c-eeb3-5f12-86bc-d6c0fc84f1c8 | note | Reference - NIST-2654 Ballast
a3d68af5-16b8-5b95-95a5-a989f4ee2d50 | note | 1.03 - Non Dependent
2445e212-a9a3-57da-852b-54543550d884 | note | Reference - NIST-2651 Sleepers and Fastenings
427169e7-c1e4-539e-8182-ef29dc179e9e | note | 1.04 - Non Dependent
69610329-fa2f-5c41-a562-ac12d53be84f | note | Reference - NIST-2650 Rail Use Laying and Adjustment
e8d8d3e7-5fb5-52c6-a9fb-c323ae4d8f15 | note | 1.05 - Non Dependent
6aa0944c-c036-5e7b-b938-c536ef541fb9 | note | Reference - NIST-2630 Track Construction
ad348c0d-4c7a-52a2-81bb-13e01803fc48 | note | 1.06 - Non Dependent
4e055cbf-ecd8-5a66-bd0a-be3fef68cd62 | note | Reference - NIST-2706 Track Geometry
8c0aa477-041b-5a39-9a21-fdb8d7526e15 | note | 1.07 - Non Dependent
2ee2fc13-c46e-5a44-8c81-3513fd02b577 | note | Reference - NIST-2659 Earthworks and Drainage
b525ffb4-8ae5-5f8f-b633-e5774d3361e2 | note | 1.08 - Non Dependent
03104d11-c390-5cc2-877c-ac1720e7e547 | note | Reference - NIST-2618 Track Design
65b46f22-eb32-5bd2-88ff-13d2551465bb | note | 1.09 - Non Dependent
52fcba43-da58-543c-9d82-4c7d9ac3c7f3 | note | Reference - NIFO-2650.5 Aluminothermic Weld Record
066fbf2b-e495-5270-86f1-dcd558935db3 | note | 1.10 - Non Dependent
661006d2-f9f9-55c9-b557-1b08dfa441ce | note | Reference - NIFO-2690.3 Certificate of Track for Operation
22e39aec-6444-4f27-a0c8-fbdd5aa5f78e | section | 2. Preliminaries
b20f0266-1318-4007-b3d9-dccdd3cae199 | checkpoint | 2.01 - Obtain and submit Material Certificate of Compliance for Track Materials;
f76fd7c2-70a2-5a6c-9d9d-c6131c704879 | note | – Track Rail
bb70ade2-52e9-5933-bc29-40a0b826717e | note | – Track Sleepers
b8b0564d-f6e6-5bf7-a810-af17333bf335 | note | – Track Jewellery
6de01d94-c631-5759-bb57-67802255d8bb | note | – Geofabric
79a5dace-635f-5f2d-ae56-4a0dcba6c380 | note | – Ballast Matting
c95215e9-778a-551e-b928-619cd043f7a8 | note | – Ballast 60mm Aggregate
aeb0e23b-7f07-5953-898b-d27be0bab7a1 | note | – Welding Kits
691d216f-142a-5194-a799-55dea45901af | note | – Welding Crucibles
e203f048-70db-5a7d-99b9-25f530c73191 | note | Reference - IFC Drawing(s), Track Constrction Site Mudmap, Bill of Materials
fe6c4161-6809-5e20-b74f-6267c0007aa8 | note | Acceptance Criteria - Units to be free from damage, total and types of units for full set validated No signs of discoloration
138e14a4-f97e-56c6-8c6d-a0e65647aa22 | note | ○ Attach: Manufactuer Cetificates of Compliance
5d24978a-f88b-51f6-a3cd-d8731ea046cb | note | Method - Review Document
0b151a46-5d48-5440-9ba6-470ce500de53 | note | Frequency - Once
f5a081ec-b7fc-51b7-a518-02f9b0c2e38b | note | Category - HP
f0b81ecf-414e-551f-97fd-275e1fcca7bb | note | Responsibility - Site/Project Engineer
ba02584d-b86d-5f1c-8c40-dde77e8376f8 | note | Verifying Documents - ConQA Hold Point Release
6fc908e1-f10c-5781-8026-dd7c26640451 | date | Date Completed:
28ec26de-3bee-4081-be12-1cabcf167ee2 | signoff | AUTHORITY HOLDPOINT
c5e61da2-de40-4f8f-82ed-4fce2eca6b40 | checkpoint | 2.02 - Submit Welding Procedure/welding qualification welders Record
fc76bf5a-9eda-58bb-8635-037337f30daa | note | Reference - NIST-2650 Rail, AS 1085.20 Welding Rail Steels
c15457c6-934c-58da-8407-bd59c71a7c14 | note | Acceptance Criteria - Qualified personnel & welding accordance with manufacturers specs.
c1dd9cbc-3b3b-5e41-b8f7-d9facdb6b47f | note | Method - Review Document
416502d8-c821-5225-ac5f-de7e53964658 | note | Frequency - Once
39700b9d-3fc0-58b4-9a60-224476399c92 | note | Category - HP
67dc9916-84b9-505c-8df8-ee30f23ba919 | note | Responsibility - Site/Project Engineer
ffc62353-1009-52e9-a58b-af23460dd0fc | note | Verifying Documents - ConQA Hold Point Release
481a98b4-55cb-5840-a879-8e674d9aff15 | date | Date Completed:
a897e3d4-2c21-490b-9c4e-e7a3db125c2e | signoff | AUTHORITY HOLDPOINT
cf6573c8-aee3-4105-9f0b-5020c119bb66 | checkpoint | 2.03 - Inspect supplied items upon delivery
438df81f-3489-5270-9777-01050c1d6f7f | note | Reference - Bill of Materials
0d44f53d-e079-5976-80ab-8c2693effbc4 | note | Acceptance Criteria - No damage or debris on components
2f9dd9bf-162d-5d33-862d-d91d484ec98e | note | ○ Validate total number and type of components matches drawing
f9eaa26e-af71-59b5-a6df-9e7408ef9835 | note | ○ Attach: Photos on site;
05f2af86-c359-576c-a621-6c8247307eec | note | – Track Rail
ba40a1aa-0d67-5e35-9652-fc27f8749d4e | note | – Track Sleepers
a3322dc7-517c-59c2-a922-2ec63bf8c31e | note | – Track Jewellery
fa070f24-d849-59a0-86f0-dfa56ddc928d | note | – Geofabric
a17225ff-9058-56f0-a7cd-0925d99d2de4 | note | – Ballast 53mm Aggregate
326aa831-cdf4-57a9-946a-11283b73a2a1 | note | – Welding Kits
48b089b6-a1c7-5d1e-83c9-3048cde4ae0e | note | – Welding Crucibles
513446d4-7c4e-5f13-a8b2-fedb923500c7 | note | Method - Visual, Measure
5253ea5f-79d0-52ac-b05d-a9ea3d69a350 | note | Frequency - Per delivery
55c1c16c-8c6a-5185-837e-822e052d2d0a | note | Category - IP
30a4624a-970b-5707-85f5-c3362f3360ee | note | Responsibility - Site/Project Engineer
a2b43818-c730-52ff-8fb0-df8767335b44 | note | Verifying Documents - Material Inspection Report
dc2ef0f0-dfd1-5f1e-8bac-7f453b2ef811 | date | Date Completed:
341356f3-cfb1-4fe6-af52-79a10929b104 | checkpoint | 2.04 - Confirm extent of track removal required for civil works
5a136d20-32c4-501e-ac22-2fc0d341be56 | note | Reference - IFC Drawing(s), Track Constrction Site Mudmap
862ee407-c35a-5b74-b2ec-62f0fd5852e9 | note | Acceptance Criteria - Extent of civil works and subsequent track removal to be confirmed in conjunction with MRPA civil team, limits of removal to be marked up on site
321ecc5b-dcbe-580d-8974-d69bff4de800 | note | ○ Pre-removal survey of existing track alignment
c9c0ca51-312a-5da4-a776-0e9d45ef765a | note | Method - Visual, Measure
d06c9cdd-52a7-58ab-8153-8a1a7b228b03 | note | Frequency - Once
c70a2767-1899-5d31-aa65-511a3b88ee25 | note | Category - IP
27b6157d-01dd-5696-b6e6-ab9f3590c9d9 | note | Responsibility - Site/Project Engineer
6ff46dcd-a013-58a3-bc77-efd27f14e09a | note | Verifying Documents - This ITP
1734c7d4-1049-5021-983c-eabf1015ae27 | date | Date Completed:
bc8c39cb-1511-447e-9b6c-cce5018a90d3 | section | 3. Construction / Installation Activities
a1dc810b-25a2-4e65-a724-936e80ea985f | checkpoint | 3.01 - Deconstruct and remove track componends, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction
aa1e7394-95f4-5028-a57a-fa469ab2ff30 | note | Reference - IFC Drawing(s), Track Constrction Site Mudmap
af0a2d64-7498-5170-9609-ebe57ff9e97c | note | Acceptance Criteria - Track structure to be removed to the designated limits as identified.
ee1df8c5-56ca-501a-9c4a-1593c071475e | note | ○ Visual confirmation of removal on site
0c3cbe89-a3f0-544c-92de-854b8ea5968d | note | Method - Visual, Measure
056e4c0c-ccc5-5d92-9866-e4de71e512fc | note | Frequency - Once
272a9fb6-b482-575d-992c-b3e39b57b8e3 | note | Category - IP
c1b0f700-a4c9-543f-98ac-3a5e43edda1a | note | Responsibility - Track Supervisor, Site/Project Engineer
e225b1de-d734-5553-821c-aece59bcada6 | note | Verifying Documents - This ITP
b9715218-9ef3-5a72-af2c-e587288c88f3 | date | Date Completed:
8b0a8711-a27c-46b4-95c2-e1094a72a4d3 | checkpoint | 3.02 - Earthworks completed and site handed over from Civil Contractor
1e505d9b-c954-5cba-916d-41e94068d6dc | note | Reference - NIST-2659 Earthworks and Drainage
fdf0ca0a-9f03-5279-aea7-b7fb63d804e6 | note | Acceptance Criteria - Confirmation of completion of underlying ITP(s)
f18db6f7-dffa-58c6-b966-6181967d7ae8 | textbox | Underlying ITP reference:
49e4b70b-232f-5df6-ac22-b0d64acaabd4 | note | ○ Applicable: Stage 2 - Track Construction
4aad1c13-f140-5cc1-a3dc-da6f66cde184 | note | Method - Visual, Measure
0381f801-11cb-56f9-8f0f-ec526f3afce4 | note | Frequency - Once
a024b44d-05da-55a4-9980-eaa4e11ece96 | note | Category - IP
4280d3c3-b68a-5c21-9357-d5c6c056e00d | note | Responsibility - Track Supervisor, Site/Project Engineer
c90d871e-b7d8-5cf7-acba-f27e13eda503 | note | Verifying Documents - This ITP
e984618d-c786-58bb-87b9-3bce4e67a318 | date | Date Completed:
a97743a3-49e1-40c2-aae8-dbe384b4abb4 | checkpoint | 3.03 - Installlation of Bottom Ballast
88064ab7-1384-5187-8c5d-c0d1b5dcafd7 | note | Reference - NIST-2654 Ballast
71eb6e5e-a5e6-5372-a4ca-56e9f68d2ba1 | note | Acceptance Criteria - Overal Minimum 300mm bottom ballast depth
9ae863c9-2a53-5e36-899a-7ae8c26a8af0 | note | ○ Ballast to be placed in 150mm max layers. Layers to be compacted with 10 tonne smooth drum vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compated using a vibratory compaction plate
3d361beb-a91f-5bd4-8c7c-5f9c46bff007 | note | ○ Bottom Ballast to be left 20mm below final design level
62c08b44-0be6-5683-9233-14de0571ac63 | note | ○ Tolerance: Under sleeper -0mm/+25mm.
bcb1a0b7-8ed0-5d4b-86dc-fe125e453d75 | note | ○ Attach Site Photo: Installed Bottom Ballast Layer
d6dabb63-69eb-57d4-a291-6c0cdfbf108e | note | ○ Applicable: Stage 2 - Track Construction
20d132c0-1316-590c-af8b-551b2ed2175d | note | Method - Visual, Measure
a7629fd9-7566-524b-82c5-bdf5f15d55e1 | note | Frequency - Once
48c94753-0bdb-5bd6-abbc-ef374de50f2d | note | Category - IP
79294b72-0e8d-5132-8d91-31d64bf161e8 | note | Responsibility - Track Surveyor, Track Supervisor, Site/Project Engineer
435a436b-4f05-5eb6-a274-fe3c8ba4e23a | note | Verifying Documents - This ITP
28320485-ecfe-58e4-b12f-cca6c449b02f | date | Date Completed:
df51f0d2-7a64-4dba-9feb-1090bf7d5660 | checkpoint | 3.04 - Laying of Sleepers
d70cc812-c6d2-5536-ab61-28df6788c1a9 | note | Reference - NIST-2651 Sleepers and Fastenings
7a2ffc5a-93f8-537a-a6ff-2a15b3d188af | note | Acceptance Criteria - Sleepers square at nominal 685mm +/-25mm for open track
51266f40-07d8-57e1-9023-dc2d06ae5aa0 | note | ○ Attach Site Photo:
820b37c2-c438-5691-b9f3-9b05cf0eca35 | note | – Laid Sleepers
0142b1b8-bc95-5173-9e25-633ce1011921 | note | – Sleeper Spacing Measurement
467e075d-8482-5853-8a1a-4422a41b8664 | note | Method - Visual, Measure
7b278671-9630-5730-a934-a4f0283d747e | note | Frequency - Once
33d4cc4f-044c-508d-8e3b-6482ddb6f29b | note | Category - IP
61fd7add-4418-5da2-b42f-d80dc10c9225 | note | Responsibility - Track Supervisor, Site/Project Engineer
7faaf70c-d80a-5183-af00-7dda1e0bb183 | note | Verifying Documents - This ITP
5a728278-59f1-593a-bbef-c8bfa203d944 | date | Date Completed:
82336199-11a6-4dd8-afee-0d902a796ebb | checkpoint | 3.05 - Rail & Fastening Installation
9b5806cf-1471-5b80-b134-a990c5607ade | note | Reference - NIST-2650 Rail, NIST-2651 Sleepers and Fastenings
dacb3d6b-d6bd-5b44-bc18-669239ca9a2b | note | Acceptance Criteria - All rail sitting within Sleeper footing with correct sleeper insulators, rail ends positioned the midpoint of sleeper bays +/-50mm, no rail ends to be located within 3m of existing track welds, rail fastenings installed
4a67dcd9-f69d-5336-bee1-dcd7ff2eae09 | note | ○ New Rail lengths installed to be as per approved Ferris Road Rail Weld Plan
ccdd4781-d069-5482-9a80-d898b5b95ef4 | note | ○ Gauge of track to be checked upon installation of fastenings
cdec2ec1-ffc2-5cc8-bfe7-112a3f2d80f8 | note | ○ Gauge +4mm/-3mm
52d5cbdf-d03a-58be-8d8f-a8ce3388c83e | note | ○ Gauge Variation over 2m 4mm
006dce59-f2c8-5e3e-91b9-c189eee52e9b | note | ○ Attach Site Photo:
a7bbebb1-048e-54df-820c-4beaa7a26a3c | note | – Laid rail
b3a1f40f-8f1e-54d1-ac62-16a4c4adcc06 | note | – Rail joint to exisiting weld measurement
7a7e4ad7-3ce7-5609-bd42-f68f7b0e3738 | note | – Rail joint between sleeper bay measurements
df3822ce-cd6d-50ef-b424-19419662efb1 | note | Method - Visual, Measure
a804c1f2-2242-5c84-a527-34168d1e8701 | note | Frequency - Once
71f02aa5-0996-5d40-bbe9-c0a373a02072 | note | Category - IP
f57ca4c9-1bbc-55af-8eaa-8f5704aa4b4e | note | Responsibility - Track Supervisor, Site/Project Engineer
85e81fb9-5fd6-591a-83af-59ea882f6c6f | note | Verifying Documents - This ITP
afa60355-74e1-562b-b94c-2a23f91f9db5 | date | Date Completed:
960c6b39-324b-4a0f-ad91-7e5f35dc9ea9 | checkpoint | 3.06 - Track Tamping
d5f51db8-5722-5d74-af6c-217aec9c6b0e | note | Reference - NIST-2630 Track Construction, NIST-2706 Track Geometry
1080e4e0-21e7-550a-bf2e-f68671ee4cf3 | note | Acceptance Criteria - Tamping Ensures Track Geometry Tolerances are not breached (dimentions are in mm);
90aef726-fe61-55ec-a8ca-e2b71ef3f0c7 | note | ○ Line (10m Chord) +/-5mm
954b0eb1-3b51-5dcb-9827-bf755ffc6a7d | note | ○ Twist (3.5m Chord) +/-5mm
983348e2-94ed-591f-a9d2-489afbc4dfbe | note | ○ Twist 10m (Chord) +/-10mm
f86d39c3-fbad-56c9-ba02-2f5da0bb0099 | note | ○ Cant +/-5mm
9ab33c75-1be7-5843-9af0-9e6df6a7b6b8 | note | ○ Top (10m Chord) +/-5mm
daa9d0b3-dbb1-55e3-b4f5-bc2e0131301c | note | ○ Alignment +/-20mm
a59f432d-b32a-50da-b276-8ad1271e3ed3 | note | ○ Survey measurment of RL of top of rail head
4628cfac-afc2-5bd1-b71b-1db06b2a6a4b | note | ○ A minimum horizontal clearance of 3.0m from track centreline to structure.
e32d3d18-1a22-5ded-80ce-448d000c578e | note | ○ Attach;
fc92d169-1b66-5c3e-b23f-76bb72866757 | note | – Tamping Geometry Recording
44de8d2b-a593-5818-9918-02551e790d1b | note | – Survey RL measuring sheet
0e8191de-ece5-5b5f-8bc7-537edd581b4b | note | ○ Attach Site Photos:
e50e98a8-dfe7-5fce-8830-fbe6a8aa62e4 | note | – Tamping Activity
5bd58f70-e0b9-5244-8a78-c2c355a53723 | note | – Structual Offset Measurement
26020b3b-a123-5799-ab44-a30c54cb0c7d | note | Method - Visual, Measure
f6a9788f-85ff-52d0-8efa-8aa7ca2bea70 | note | Frequency - Once
1f67de70-2a5f-523c-8b9e-53f3b24121a4 | note | Category - HP
c0a3fe6f-8592-5b3a-b64a-8855c7c59b03 | note | Responsibility - Track Surveyor, Track Supervisor, Site/Project Engineer
6786ca34-56e1-56e7-b20c-0ff897952eb6 | note | Verifying Documents - This ITP
575b3ac9-e95d-57aa-91d1-f723860ff495 | date | Date Completed:
9fd3c966-a475-4e72-a836-4bfc6923878e | signoff | AUTHORITY HOLDPOINT
054f0540-52d7-4566-bd87-7f1e7aef687a | checkpoint | 3.07 - Regualting and Ballast Profile
1e638d54-4158-5991-b07b-6f4be2a95c04 | note | Reference - NIST-2630 Track Construction, NIST-2706 Track Geometry
1e441607-88a4-5ce3-8fb5-3b9b46c3a011 | note | Acceptance Criteria - Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter
ca578f6f-f3d6-559d-b7ad-bc77638aa708 | note | ○ No Ballast to be on top surface of sleepers or aorund rail Fastenings
f8b31e69-5cac-578e-b520-e96f1a02c06d | note | ○ Attach Site Photos:
d5d9b1dd-2006-50a0-a516-bd4176a95f4a | note | – Ballast Shoulder Measurement
6a18e226-e581-58ae-a091-8c268235b5f9 | note | – Rubber Panels free of ballast materials
2e1a2b9a-19f6-5864-9944-465fbabcba0b | note | Method - Visual, Measure
ffd0b14f-3caa-5d27-b5c4-efd290b0e2ed | note | Frequency - Once
08d801ab-9d23-5138-aa5e-48ead472bcd9 | note | Category - IP
1be67c62-c38e-565e-b413-52900874c58f | note | Responsibility - Track Supervisor, Site/Project Engineer
f62e5888-2381-5c4c-a161-135d4166a90a | note | Verifying Documents - This ITP
2a7f9b0a-7c61-55cd-8d17-d154f959b389 | date | Date Completed:
2c047fd0-e5fd-47e6-b931-9877c9c151d7 | checkpoint | 3.08 - Aluminothermic Welding
12a37549-94f8-5312-8458-6704cfbf99a2 | note | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
f10d65d9-5f9d-5887-a1bf-b8065cccf5b7 | note | Acceptance Criteria - Welds to be lined and finished to alignment standard
4f80ece0-cf3c-586c-900c-4bb2f1c66515 | note | ○ Tolerance:
24d8af1a-12fb-573a-8d1c-9d203ce844f3 | note | – Gauge Face +1.0/-0.5mm
203961a1-675c-5adc-9a36-cb522cdc3bbd | note | – Running Face +0.6/-0.0mm
d988704c-f798-5cb9-9b6e-578bbd466966 | note | ○ Verify Aluminothermic welding carried out in accordance with AS1085.20
9a5b61ac-703b-537b-9429-05cd3a1ea043 | note | ○ Aluminothermic Weld Return Form to be completed
8d0e6513-76ce-5550-b1ec-45bc20179b3e | note | ○ Attach
88d26dac-7ef6-593f-b198-80372a313dc3 | note | – Aluminothermic Weld Return Form
76446464-f5c4-5725-9cdb-51e00f29397c | note | ○ Attach Site Photos:
0ebee534-75de-5588-a32b-41f8033389f9 | note | – Welding Aligning
90722b74-d814-5881-b213-d54724c441e9 | note | – Welding Process
7622586d-f94c-5d02-90d7-8b06ff01f038 | note | Method - Visual, Measure
a3872ece-23d6-5b3e-adf8-d5eed017523d | note | Frequency - Each Weld
7d45389f-e008-59c7-b494-f80c577d3086 | note | Category - IP
d3f3363f-7f85-5ab7-9e80-1509b10d8ded | note | Responsibility - Track Welder, Track Supervisor, Site/Project Engineer
eb8d35df-e477-5b4b-b0f9-54b52fc6491b | note | Verifying Documents - This ITP
a24dac46-6b5d-5c2c-97be-008a0d108196 | date | Date Completed:
a3c7f8df-0c73-4375-a746-ee0cce736663 | checkpoint | 3.09 - Track Stressing
85414535-3ae6-504a-acaa-6f6a6b0c2fa9 | note | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
de687921-2a59-587d-a738-714672592d66 | note | Acceptance Criteria - Stressing Rail in line with V/Line Rail Welding Process
5014354b-56a1-577c-abad-e2f6eed68d5b | note | ○ Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
c0b7ea59-d457-5c82-87b9-dc979b9e76cb | note | ○ Complete track stressing in 330m module or otherwise as noted on approved track stressing plan
c877c5cd-8f21-5942-b651-d6a17a6fc463 | note | ○ Reference Marks recorded pre and post tensing of rail
16b5b68f-6a7a-5431-a19e-f83509c211dd | note | ○ Aluminothermic Weld Return Form to be completed
47229535-9d0c-5a1d-957b-10d23f661ef4 | note | ○ Attach
d2ad4983-5d92-5538-9f2d-bbba3cf205ac | note | – Aluminothermic Weld Return Form
acaee5ae-dcfe-5ff9-9ef2-804946994999 | note | ○ Attach Site Photos:
6e4869aa-5b32-5cd4-99b5-d34d27ac4fd1 | note | – Stressing Activity
e8dfeebf-80ff-5662-9f7d-216a6b5aee57 | note | – Under Rail Roller Spacing
acf4ec52-cd96-5d7b-9c70-46b1c37ae2fc | note | – Before/After Reference Mark Measurments
b171b0b4-3a7f-509d-929b-0d19568621c8 | note | Method - Visual, Measure
4da3012c-17b8-58ea-a006-761f0f4c8f33 | note | Frequency - Each Restress module
b1292ba7-a74b-5802-9552-49768e1c9fa3 | note | Category - IP
476caa99-e907-5f30-9e56-6a671ba998db | note | Responsibility - Track Welder, Track Supervisor, Site/Project Engineer
4c081846-2177-5e08-9ee1-cf12cb5d33bd | note | Verifying Documents - This ITP
9e4dd50f-4f7a-5035-9313-843ba3536e16 | date | Date Completed:
e51008e8-0058-4035-a9a0-47f7463cbeae | checkpoint | 3.10 - Weld Ultrasonic Testing
1b5f7b64-e514-5f19-90e4-726b706bc5a7 | note | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
218b2bbb-411e-5cd1-987e-e80447c97f0e | note | Acceptance Criteria - Ultrasonic testing to be carried out in accordance with NIST-2650 Rail
83d3ed2b-94e9-5370-8942-d369e2749508 | note | ○ The cross section of the area of the head and web shall be completely scanned;
99d7a55d-f7cb-5571-befc-22e31d27b750 | note | – The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
81622894-1e55-577a-82f3-3f740f2898d4 | note | – Welds shall be scanned to both directions.
71168a01-044a-5473-9a4c-09ff4a314e8a | note | ○ No classified internal defects found
e8c85939-c7ba-59f4-96f3-43687342f061 | note | ○ Final weld geometry to be assessed
117214ea-a800-5847-8808-eedb4c3bff00 | note | ○ Tolerance:
9d9db7e6-cb74-5874-b586-62e033a20134 | note | – Gauge Face +1.0/-0.5mm
bee5cb72-0672-5c74-a9c3-e3b12fca1214 | note | – Running Face +0.6/-0.0mm
82bd6481-d019-5550-8cab-168d4ca445fc | note | ○ Aluminothermic Weld Return Form to be completed
9882acba-329a-5a4e-86ff-e9c192b553f6 | note | ○ Attach
9357bd68-6832-5724-ac21-0045b43ad7c2 | note | – Aluminothermic Weld Return Form
5d4b2484-bb1c-574c-975d-55cb3398548f | note | – Aluminothermic Weld Test Report
58ac1b7f-a27e-51cc-b16b-f620c5bbf7f6 | note | ○ Attach Site Photos:
b0db5d53-0dcb-5887-aa26-5c135439d975 | note | – Welding Aligning
f0d1ebf5-92d5-557c-bb01-6a919da288a2 | note | – Welding Process
33a6a8a7-a6b3-5908-a618-1130a0be61cc | note | Method - Visual, Measure, Test
96a6eb38-560c-5266-ae19-e5080bc5fe6c | note | Frequency - Each Weld
8d3a7535-57a5-5536-97f7-82e616ced6d2 | note | Category - HP
7dfaa03b-f6ac-572f-a3e3-61a7964a5e62 | note | Responsibility - Weld Tester, Track Supervisor, Site/Project Engineer
909ece79-3692-5299-b1e4-0eabb706aa1a | note | Verifying Documents - This ITP
841b6029-df42-5afd-a6d3-f64babc7bab5 | date | Date Completed:
7086fc54-8854-4629-a580-9cf37a11fb2f | signoff | AUTHORITY HOLDPOINT
c86eb3f8-b191-495d-aecb-de726df3a5f2 | checkpoint | 3.11 - Installation of Guard Rail & Guard Rail Nose
94377d48-4385-522a-ac18-580ebf20064c | note | Reference - IFC Drawing(s), NIST-2650 Rail
ec88853a-0e06-550a-a804-b3a199929fef | note | Acceptance Criteria - Install guard rail and guard rail nose as per IFC design
9f5f091b-ab7b-5c9f-8371-1ecce92aeaba | note | ○ Guardrail to be installed with alternating fastening pattern
41871324-d1e6-52db-aee1-9bdf179b53ee | note | ○ Guardrail to be isntalled at lengths of either 13.7m, 19.9m or 27.5m, joints to be gap adjusted and plate & bolted upon completion
054bff4f-df9d-5df9-939b-3c7280e8f70a | note | ○ Attach Site Photo:
30a92980-53d6-5ab9-8a0e-4359d0942915 | note | – Guard rail installed
e1acf82d-e4dc-54a5-b9a2-b6cf373af3cf | note | – Guard rail nose installed
1b0ae0a1-e5fe-5bc1-aa7d-fa5fc17dd6cf | note | Method - Visual, Measure, Test
98ddc68e-9338-5f08-9495-c2aeab0efe85 | note | Frequency - Once
7f28c8a2-feea-555b-8980-57abf869906f | note | Category - HP
2438dded-965f-5405-81c6-526e8ae8a4ce | note | Responsibility - Track Supervisor, Site/Project Engineer
26517010-1563-522b-a047-2e5c08677b07 | note | Verifying Documents - This ITP
22b5e759-5ef2-54f4-af5b-3b6c990ba7ca | date | Date Completed:
19a4b9d1-af89-459f-8cfe-cf37a2bf2401 | signoff | AUTHORITY HOLDPOINT
e91a6a53-011c-4dc9-b4ef-f1a2156c3284 | section | 4. Post-construction / Post-installation Activities
408266eb-6d4b-4338-b850-161b4dc44c57 | checkpoint | 4.01 - As-built Survey
0607e5f9-5439-5bdf-8c32-5a615e599ba6 | note | Reference - IFC Drawing(s)
e5b6a061-707d-59aa-a075-fd0ba88d728e | note | Acceptance Criteria - Survey activities undertaken to validate correct construction
d122f316-0c04-5779-a314-c735c4b9bc16 | note | ○ Attach:
866df5a5-678a-5d74-bf06-911c263d0e65 | note | – Survey Report
65f09069-409c-5923-9e37-c5b5ec8620c7 | note | – Engineering Asset From
f7ad8339-3044-5f4b-b308-d6062f7e0645 | note | Method - Survey, Document Review
ef84ed39-2559-5cfe-91a5-36db8f502196 | note | Frequency - Once
62e10818-0082-5e18-948f-3f7fd8db10ff | note | Category - IP
aaaebeca-eaee-52d6-be13-a56ed7369fa4 | note | Responsibility - Track Surveyor, Site/Project Engineer
32b4e050-12cc-5b5d-b34d-2ed2a564708b | note | Verifying Documents - This ITP
d0968761-b563-5aed-8229-4f78632efd06 | date | Date Completed:
db89547f-d88e-416a-8036-2845832b4891 | checkpoint | 4.02 - Track Certification
88970b56-d626-5700-aee2-176aeae6dc73 | note | Reference - NIFO-2690.3 Certificate of Track for Operation
bad01eeb-e301-582f-a539-7e52b1e5c39c | note | Acceptance Criteria - Attach:
de4f61f3-a362-52f7-9c2f-1cd3fc140f60 | note | – Track Geometry Conformance Certificate
6d336b26-40cd-56ad-a3ad-299450be7e15 | note | – Track System and Component
2089ac30-b456-5047-893d-d30e230830d5 | note | ○ Attach Site Photos:
25443785-fef4-5470-afe3-8c445fcc98b0 | note | – Before/After Photo of worksite
925de8ed-2383-5f2d-87bb-4da09e89da71 | note | Method - Visual, Measure, Doument Reivew
c13ab590-7040-5fdd-8f12-8dd9a9b76225 | note | Frequency - Once when all occupation works complete
00b721eb-8151-51ed-880d-8a32545f483e | note | Category - HP
37547553-0e11-584b-95d5-2de19d863278 | note | Responsibility - Track Certifier, Site/Project Engineer
2f69da8b-bd0a-57c3-8cfe-2aa50c38485a | note | Verifying Documents - ConQA Hold Point Release
ec0be400-622b-5969-88a6-d6b008c3af54 | date | Date Completed:
2991c8be-cc1c-4ef3-b210-cbf6cc48698a | signoff | AUTHORITY HOLDPOINT
5bf28eaa-f677-4d6c-baeb-071bf1bc3fae | checkpoint | Final Inspection
fd7a6cce-89b4-5f6f-abea-5a8c85485674 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
41327a68-4683-56b6-af54-f33e1e85c39a | textbox | Name:
29706c66-5254-593e-99a3-8129a0b47f53 | textbox | Position:
97eb8f9b-6bb8-550b-800c-b02f33e2b735 | textbox | Date Completed:
aa2985ce-8f4f-432c-a4fe-dc592f1e4065 | signoff | Sign ITP
0c40e999-067b-459a-840c-186dfe916e7a | checklist | ITP-240-CIV-Ferris-Under track crossing - Ausnet Gas and Telstra Rev 0 | itp | ITP-240-CIV-Ferris-Under track crossing - Ausnet Gas and Telstra | ec7d87cf-fc6a-4d2c-8171-3a4d1c40ddae
9ec67a72-98bb-479a-b7db-1d189552be46 | section | 1. Referenced Documentation
685216f6-8935-470f-af55-763cb210804e | checkpoint-no-value | Referenced Documentation
7090e209-2d6a-5d97-a4bb-a4948e584f21 | note | Document Title: ITP-240-CIV-Ferris-Under track crossing - Ausnet Gas and Telstra
abd81861-4567-51f2-938a-27c21c7822e0 | note | ITP Description: Under track crossing - Ausnet Gas and Telstra
cce5b5fb-2e76-5bd5-aac2-994ca30f8046 | note | Discipline (e.g. CIV/STR/RAIL): 240-CIV
0b82eaa2-e8f2-5a2d-a505-cd776dff16df | note | Revision Number: 0
5f663a16-4504-51fd-bc7f-c32f927bcd19 | note | Revision Date: 4/02/2025
ebc0a0c0-d55a-57ea-91f8-ad9d921d54ae | note | ITP created by: Joanthan Kogan
f5ef5671-5ecb-5d45-84c0-e63eac8f147e | note | ITP approved for use by: Pradeep Talasila
72842eb8-8113-5b4d-b106-156228f23ca8 | note | 1.01 - Non Dependent
5fafe724-a9da-5df1-af64-5720b87ba110 | note | Reference - AS 4799-2000 Installation of underground utility services ad pipelines within railway boundaries
ae454a50-fcc1-545f-adc8-a0a2a0ba0f19 | note | 1.02 - Non Dependent
2f6357e5-cd6a-516b-ac73-101fa59a6026 | note | Reference - D/17/62901 Design Requirements & Guidelines - Civil Works on, under or over VicTrack Land
7491bd6a-9a7b-5889-8c74-f25b2787df1f | note | 1.03 - Non Dependent
33ec1f6e-f06d-52ec-9eb8-5f8b2072bc5f | note | Reference - NIST 012.2 - Specification for Signalling Supply, Construction and Installation (V/Line)
e1663b8a-a383-5a00-8d4f-cbfbc56bb1ef | note | 1.04 - Non Dependent
38bbad47-69bc-5d7e-ad48-c53dcfe6a8df | note | Reference - AS 4142 Fibre Ropes, installed and anchored in the pit
ff4a6867-42ae-5482-9d60-25a60ca0c768 | note | 1.05 - Non Dependent
ff92ea96-36c4-5b23-8bc2-9716bb38d6fa | note | Reference - NIST 012.2.1 - Standard for Construction of Cable Route and Signalling Civil Works (V/Line)
c0dc24a9-63a2-520b-8823-6e7c38ce259a | note | 1.06 - Non Dependent
5f4e6aea-57e1-515d-b6f3-22790bd8c437 | note | Reference - NIST-2706 - Inspection and Assessment Track Geometry (V/Line)
71bdc860-d7b1-596c-9bab-c75f5f150303 | note | 1.07 - Non Dependent
3b635cf1-de13-5a92-acd2-0e49cb70d46d | note | Reference - VRIOGS 012.2.1. Settlement Monitoring during construction
bde3595a-326d-509c-9d16-66ec48ea80f3 | note | 1.08 - Non Dependent
17698a44-9b0d-5083-a0d9-c2903a00cd4c | note | Reference - VICTRACK STANDARD TS-SP-013 installation of the encasing pipe
1603f5f1-79e9-4c4b-955b-afcfe2db19e9 | section | 2. Preliminaries
3bc0d022-0ecf-42df-8722-36ddc52a32b3 | checkpoint | 2.01 - Materials - Gas Jacking Pipe
c48e205c-414f-50fc-a0b9-44a2cc95f231 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
ed4db007-7afd-5fa4-a0cd-6b18a95f4401 | note | Acceptance Criteria - Confirm that the GRP pipes delivered to site meet the Pipe Specifications:
71621b9d-9a2a-5f18-867a-8a0f44262a23 | note | — Internal Dia: 389mm
bdacd56d-c71c-58ea-bf63-70ceff297510 | note | — Outside Dia: 427mm
5f3d9e76-d6f0-51e7-aa7a-f61f07c2bab3 | note | — Material: GRP Pipe
64e83414-9ecb-52c3-8d06-0ef5611da798 | note | ○ Specification & Grade: DM427 SN100,000 N/m²­­
243726c7-c58d-54e7-ba0e-083d97ce0e3e | note | — Wall Thickness: 19mm
74657397-3e36-5186-b949-544ee925caf1 | note | — Maximum Working Pressure: N/A
c6ff4191-265b-53b1-af61-48ab28cd9529 | note | — Joint Type: Stainless Steel Collar with EPDM Seal
58cd5a5a-7130-5443-a310-2e2c8d08b36f | note | — Pipe Coating: N/A
7489028b-ecd9-5f1b-8d89-139988b85671 | note | — Cathodic Protection: N/A
bb40fb62-eae8-5b45-9cde-06dc282c3333 | note | Method - Document Review
6aa24a0d-ed69-563a-8c9b-fd00496783b4 | note | Frequency - Prior to Commencement
f11aee15-97c9-5e9d-8c74-d55b863e2278 | note | Category - HP
43c07f18-ec9d-5b29-b106-f8c71324cec3 | note | Responsibility - SE
d9392d8d-9544-5256-94b4-9413e367cf6d | note | Verifying Documents - Material Compliance Certificate
f6d6890a-288f-58bd-bf80-b90ef9db25ad | date | Date Completed:
115574fc-0bd5-4185-a2c2-74b5eef1ed5b | signoff | AUTHORITY HOLDPOINT
5f1d9fcc-c3e3-47eb-bf69-161f1277f2dc | checkpoint | 2.02 - Materials - Comms Jacking Pipe
879db6e7-ee18-5acb-a4e1-df8407d6c7bb | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0203
1e6e565e-6e1f-514c-bd52-30f56245d37f | note | Acceptance Criteria - Confirm that the GRP pipes delivered to site meet the Pipe Specifications:
593dfa77-d57b-561e-a3a9-82889d4e6d06 | note | — Internal Dia: 389mm
cf173a30-6525-53f9-acce-b57ddab270e1 | note | — Outside Dia: 427mm
63b23ff1-d8d4-5e1b-870d-9b9518d46e45 | note | — Material: GRP Pipe
e0dd0388-02c9-517c-9c4e-c90fb7a2473e | note | ○ Specification & Grade: DM427 SN100,000 N/m²­­
493544c2-6b0f-53a9-96db-435a542a1948 | note | — Wall Thickness: 19mm
da194ff4-ccf7-508d-849a-a076795a549f | note | — Joint Type: Stainless Steel Collar with EPDM Seal
cd61a245-6a7b-5e2a-9135-ef176fafadb7 | note | — Pipe Coating: No Coating
928790e7-ede1-5427-abc1-f05c4f2a2ae4 | note | — Electrically Continuous: N/A
165b4810-1640-56f2-8cec-8630ee7944c6 | note | — Cathodic Protection: N/A
0f3384eb-bc69-5453-926c-580df71f7ed5 | note | Method - Document Review
65b66ffa-ab10-569e-a5c7-38004baaed0b | note | Frequency - Prior to Commencement
2423e292-722e-5835-8e07-f83b024582cf | note | Category - HP
b98e91de-67e7-5b0f-8b56-e39838434b09 | note | Responsibility - SE
b5dd03d6-88c1-5402-8187-c7af9e816fbb | note | Verifying Documents - Material Compliance Certificate
b8779216-5920-5910-8afa-0326d2cc19b4 | date | Date Completed:
cd606d18-9226-4066-971a-55bd7a146c8e | signoff | AUTHORITY HOLDPOINT
ae4e9094-ce5f-4aed-b1ae-d9cdde4c568d | checkpoint | 2.03 - Materials - Draw ropes
f51af56c-f063-559c-bb51-e779d7da5c11 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002
ab64f1a7-3010-5ef6-8f64-b87955ff1e48 | note | Acceptance Criteria - All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
8947bef6-777c-5366-a67b-4fb33e4cecd6 | note | Method - Document review/ Visual
73877361-e0b8-50f3-97ab-b98c6f1b8d7a | note | Frequency - Prior to commencement
5e6b2f81-ee29-5839-a78a-0e56aed20d8e | note | Category - HP
c37fdf6a-3473-5c64-83ce-b2c255a06766 | note | Responsibility - PE/SE
8b8f549b-647a-5415-a59d-47abb77b0821 | note | Verifying Documents - Material compliance certificate
21ac63a3-8b9b-5728-a8e2-3762ccefa825 | date | Date Completed:
b4b8b140-60da-4a9a-bf27-266229b096e4 | signoff | AUTHORITY HOLDPOINT
1e76014d-1afa-4f9f-b1d9-86670413e345 | checkpoint | 2.04 - Materials - Comms Carrier conduits
a8376a12-aed6-58ad-b692-faca127bc1d1 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0203
76bda481-d50d-5a62-af94-634474ba384e | note | Acceptance Criteria - Conduit fittings shall be the same type and material as the conduit.
8706a9fe-d28e-5e11-9715-a6dc308718e8 | note | ○ Comms conduits to be:
4f398130-f734-5c8c-b75b-31d4114502f9 | note | — Internal Dia: 93.3mm
7f97b882-065d-5698-b699-bac67ca6a327 | note | — Outside Dia: 110.5mm
83240bad-07e5-590d-a53c-2e40fc69b43d | note | — Material: White PE100 Branded "TELSTRA"
d6ef63fe-fa3a-5d04-8c04-82552a50e8a3 | note | ○ Specification & Grade: OD110 PE100 SDR13
af248380-2d09-5b70-956a-25a05d68957c | note | — Wall Thickness: 8.6mm
3e31fffd-c6fa-548e-8013-2e9f88a6c09d | note | — Joint Type: Butt weld
b7cde180-e700-5dc4-a172-0c49a628a9e8 | note | — Pipe Coating: N/A
4f11fe49-e3cf-501d-9be6-0704a7310193 | note | — Cathodic Protection: N/A
11d0d19a-3cee-5d97-be03-12d7fa31c0ae | note | Method - Document review/ Visual
a2afca55-18fb-5fa9-b6c5-9b74eb2f9692 | note | Frequency - Prior to commencement
3f757bb1-a5f8-51cf-b443-90fce23ebe71 | note | Category - HP
5e98ccc6-42dc-510e-b344-5e6b2f7c0f5b | note | Responsibility - SE/PE/SPE
5da83596-7b7d-5be0-bbf8-cc969a5907db | note | Verifying Documents - This ITP/ Material compliance certificate.
39942658-c891-5510-8cd6-494cbb7ea17a | date | Date Completed:
231bb9c6-b418-4b9d-90a9-50641071901a | signoff | AUTHORITY HOLDPOINT
6cbd055d-0e47-4a06-9141-72a02af53b24 | checkpoint | 2.05 - Materials - Gas Encasing pipe
bfe13b5a-df11-5c81-9d19-59884503dfe2 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
72110ce2-ebe4-5a0b-8022-89b227d958af | note | Acceptance Criteria - Confirm that the Gas Encasing pipes delivered to site meet the Pipe Specifications:
e8d3a333-193b-5e7c-8318-d74d0e86921a | note | — Internal Dia: 256mm
536f4c86-08a3-539e-a085-8815f083f12e | note | — Outside Dia: 315mm
2a251416-a305-5087-a7a3-0ff111594982 | note | — Material: Polyethylene
0248926a-b343-52c9-a747-562be8eceb23 | note | ○ Specification & Grade: DN315 PE100 SDR11
85e9ca81-9ced-585b-85e8-4330b8977695 | note | — Wall Thickness: 28.6mm
41d4edd1-097b-5321-b130-38cf2c00ac4a | note | — Maximum Working Pressure: 700kPa
5d933db5-29df-5856-a507-d06124d6362a | note | — Joint Type: Burtt Weld
c3825c83-a70e-5a8f-a7f1-8f653145c30b | note | — Pipe Coating: No Coating
b3eb19c3-6d04-5687-8cfd-61bb9cc19a97 | note | — Electrically Continuous: N/A
c31c6384-d963-5821-94a1-7285344028a6 | note | — Cathodic Protection: N/A
944db182-964d-567d-ade4-99e2ab66c6d5 | note | Method - Document review/ Visual
6673a5fe-711c-51bf-afa1-ceb569e831c4 | note | Frequency - Prior to commencement
d20406dc-cc82-5c19-a861-65c89080d0b5 | note | Category - HP
8c5b18d7-9f84-5f4a-a321-9f10c308d3a7 | note | Responsibility - SE/PE/SPE
1a0e06a5-f1b9-5a28-a11e-893d5c0c7386 | note | Verifying Documents - This ITP/ Material compliance certificate.
4a19f27e-e57c-51cb-8e0a-0cf53a66e983 | date | Date Completed:
8026ecd0-efe6-4a6b-9526-d7a160a92eb3 | signoff | AUTHORITY HOLDPOINT
34eea79b-7027-416e-a933-508b820b3578 | checkpoint | 2.06 - Materials - Gas Carrying pipe
efc78249-be2b-588a-8a95-03a26a5f25bf | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
008f2ec7-6475-51fd-bca6-358aacf6aab5 | note | Acceptance Criteria - Confirm that the Gas Carrier pipes delivered to site meet the Pipe Specifications:
1ebadd9c-ef2e-568b-b42a-bf0b5324f508 | note | — Internal Dia: 145mm
3f2820be-c9ab-5ba6-8e87-40031cafe56b | note | — Outside Dia: 180mm
6b99801f-d517-5145-84f5-d6fda8faf054 | note | — Material: Polyethyene
35613f24-f3a8-5826-962b-0e2b50165729 | note | ○ Specification & Grade: DN180 PE100 SDR11
92a6204a-b639-5d4e-9734-0faac897fae1 | note | — Wall Thickness: 16.4mm
293980ff-7981-540c-9540-9fd7c69846af | note | — Maximimum Working Pressure: 700kPa
68b542c4-c857-523b-991e-909b089f9b97 | note | ○ Joint Type: Burtt Weld
7cb34291-59e5-588e-933e-50ffcf14f749 | note | — Pipe Coating: No Coating
3494c557-794a-5e89-ae76-415eeb534266 | note | — Electrically Condinuous: N/A
28a36b80-a5f8-59ff-aa2a-a182efb82fce | note | — Cathodic Protection: N/A
01bc89c7-c237-5f80-ba72-a8a49398f997 | note | Method - Document review/ Visual
f2af3a07-6e69-564d-9600-2b066757bdf4 | note | Frequency - Prior to commencement
131ae206-3ad1-525b-b33b-cc65a6951fc6 | note | Category - HP
cf75a342-c0a7-55ad-9e22-5ab331a87a5c | note | Responsibility - SE/PE/SPE
4e42d6aa-ff74-5d8f-8a3c-421a1d7bd9d4 | note | Verifying Documents - This ITP/ Material compliance certificate.
66386190-7321-5a50-a4ee-c44d2fb60b33 | date | Date Completed:
99554717-8b51-49da-aaac-17541622f8ac | signoff | AUTHORITY HOLDPOINT
69b87636-ad9a-4bfd-b45c-81c2025b3f85 | checkpoint | 2.07 - Materials - Grout
d8d6c465-8b84-5ac1-ab5b-956fc8a1b0ff | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
ae59eefd-782e-56a1-808a-38ec259cb9ff | note | Acceptance Criteria - Diameter of bored hole to jacking pipe shall not exceed diameter of encasing by more than 50mm. annulus to be grouted with an approve controlled low strength material (CLSM) of minimum 2MPa strength material
f6875379-1cca-50c4-9786-6d79f3f6de02 | note | Method - Document Review
66b33d0f-aeac-5a25-9f39-3f4ee9043a2d | note | Frequency - Prior to Commencement
f76ed94b-4b2a-5b1c-924a-9f35e601203a | note | Category - HP*
f4c1e92a-97ca-547f-b2f5-2bc90759f64c | note | Responsibility - SE
35356bb6-cda8-51c6-b2de-d1b6ea77bb24 | note | Verifying Documents - Material Compliance Certificate and TDS
1feceb36-3d31-5d9f-ab20-04c1013ecfff | date | Date Completed:
f32be13d-83cb-47a3-b353-7c6b9fbb6fbf | checkpoint | 2.08 - Marker Post and Marker Plate
f67973a3-0162-519b-b9dc-8fc459acd506 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203, AS4799-2000 cl 3.10
5629a3df-b085-5970-b9e5-1f88be9caf35 | note | Acceptance Criteria - Be of non-combustible material for the marker plates and of at least fire-resistant material for the pole.
9287c8ca-7f9d-56ae-96b8-f0dc36ed391c | note | Method - Document Review
a39be917-115e-5058-9ec1-02ae07339e19 | note | Frequency - Prior to Commencement
4021e267-f544-5bef-bb0c-ea5adda4aa1c | note | Category - WP
ecaa248a-ab4e-5a49-8abc-f4cbf56fe0ab | note | Responsibility - SE
0a1b3b72-21c1-54a1-8924-73bf41794ab7 | note | Verifying Documents - Material Compliance Certificate
7273c7c3-eb2f-525e-b673-ffa6de03a1e0 | date | Date Completed:
5fcea3bc-11a1-4e4a-b61e-34e4ff3c1b7d | checkpoint | 2.09 - Poly Welding Qualification (if applicable)
1c230bf0-7cb2-5cad-adcd-dbdb8c5ac93e | note | Reference - IFC Drawings
a4cf8899-debc-5b47-ad1f-39f5ad2c975c | note | Acceptance Criteria - HDPE welder qualifications to be supplied
0cc79b0b-e74a-5491-8f6e-350556bc40cf | note | Method - Document Review
fd478ef5-fb9d-5116-9db7-9b584dbf6785 | note | Frequency - Prior to Commencement
74a46efb-e3ef-596e-bf7a-d02f85add3aa | note | Category - WP
2f1aa2f4-0ef5-5e13-ba58-108643841aa2 | note | Responsibility - SE
2211ca68-b924-5a3c-a9e8-230a2fd700aa | note | Verifying Documents - Welding Certificate
f2cf57a4-81d0-5c16-bfd0-7047406f72e9 | date | Date Completed:
fa290789-e346-4c40-9b4e-4402fad6f400 | section | 3. Pre-construction Activities
c19fba44-a079-435e-b912-920f86a287ed | checkpoint | 3.01 - Survey Set-out
2e42ac70-37d7-54c6-944c-e47bc9021ce1 | note | Reference - IFC Drawings: MRP-DPK-103-00-CUT-0065, MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
86ff6123-62b2-5619-9ba9-b09b428007ce | note | Acceptance Criteria - Set out line and level of drilling works.
f9f195b5-e5a4-5bda-8c04-d96e3fc77129 | note | ○ Survey to mark out existing services.
588a3535-231a-5bf6-869f-8457767cb9ac | note | ○ Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
a986526a-f680-59ae-baa9-dd260fde5ad6 | note | ○ GFRP must achieve a min. 1200mm vertical clearance to tracks and minimum 800mm to surface level. Check FSL of track and ground.
0ae6ebe1-7988-52c2-9261-eef224737946 | note | Method - Measure, Visual
61d70257-9183-5ae4-8819-adb38f067d3d | note | Frequency - Each element
55b15e64-0399-55b0-9f85-f3dada773ade | note | Category - IP
981474e3-91be-5727-abd9-4eee87fd5523 | note | Responsibility - Surveyor, SE/PE/SPE
e4e6c590-b77d-5d09-ae89-7c9baeb91323 | note | Verifying Documents - This ITP
57444901-fe6b-5eef-bd09-52b9bdb0a032 | date | Date Completed:
0c7977be-1473-45c0-978d-e6a4c2b0e190 | section | 4. Construction Activities
b98ebc44-1cde-4d0d-864a-54657f7a88fd | checkpoint | 4.01 - Drill rig set out
0235e862-dd8a-5868-87f4-a5db40e3c82f | note | Reference - NA
40aa23cd-76d7-58c8-9f0f-6dbf6bdc410d | note | Acceptance Criteria - Location as per current Drill shot plans
7965147c-7be5-5ed8-82fa-136c47af4c1a | note | Method - Visual
d5700400-9782-5e68-be21-2c7dd1bad3e3 | note | Frequency - Prior to commencement
3a6ed27c-335b-5040-a59d-ae4bb9b5c856 | note | Category - VP
5b599b34-99e6-5758-9a4e-59bac00af387 | note | Responsibility - SE
a3245dbf-696b-5121-86a3-7cfc4912b398 | note | Verifying Documents - This ITP
789beff2-e72b-5f48-be01-65feab1535a3 | date | Date Completed:
d62a319e-cf94-40c9-b589-cb491a5d8391 | checkpoint | 4.02 - Ground Conditions
e81c42ce-4159-53eb-a4a2-d497fb3bd8af | note | Reference - IFC Design Report
bb9510f5-7ce5-5f73-820b-dda7f2bc9e98 | note | Acceptance Criteria - Assumed ground conditions are as per site geotechnical report.
d0b8c99c-ea11-594d-8246-c2fb63be7e01 | note | ○ Geotech Engineer to be immediately notified if the excavations encounter different materials than expected
18f93609-0ff8-577b-826a-be182acc872f | note | Method - Visual
46d7bd1f-d002-503a-82a1-b071a37c180d | note | Frequency - Each lot
c3440667-3ae1-55aa-953c-c9c5268c822b | note | Category - IP
3cfd42fd-55eb-528c-9f80-e6dd22f28b5b | note | Responsibility - SE/Site Supervisor
5e9e4d59-4505-5786-ae03-f70c97042e6c | note | Verifying Documents - Photos, Sign ITP
8e2e269e-afba-5739-8305-7ca8d87e4b4e | date | Date Completed:
871f486b-a262-4bbb-82df-2a7a8a84bced | checkpoint | 4.03 - Pilot Hole Drilling
ef7d51bc-188c-5eae-88a2-64502b1fa268 | note | Reference - IFC Drawings & SAP
a53a64ee-f6f4-5555-820d-bc092d0c2e60 | note | Acceptance Criteria - Pilot hole to be drilled and fully supported at all times.
891183a0-eb77-58e2-8668-e11a75ca13b5 | note | Method - Visual
02551687-f3b8-5ebd-b4ee-205546f685e5 | note | Frequency - Each lot
4c2c529f-ca00-5416-a609-d920209169ad | note | Category - IP
214137dd-6e5a-5995-afea-7e12573cc621 | note | Responsibility - SE/Site Supervisor
75259b71-d860-5fba-8748-b7587b80d700 | note | Verifying Documents - Sign ITP
e4e893ff-a2ec-5884-a6db-b35bb8bf24f1 | date | Date Completed:
ac7d6171-a4b1-42d0-a77c-2fbd42125e2f | checkpoint | 4.04 - Pipe Jacking Monitoring
b847fef1-ff6f-5fdf-afe2-c88536dca334 | note | Reference - IFC Drawings & SAP
61ac1638-4613-54ca-83db-e8acf0b84d7b | note | Acceptance Criteria - Inclination and path to be monitored as per design alignment.
c3ce40e8-d485-5a72-9af9-f061a7ede038 | note | ○ Ensure bore hole blockage and fluid losses are detected and addressed by:
6587b960-cbf3-5981-aba9-03d98bd64ac7 | note | ○ Monitoring drilling fluid volumes, monitoring annular pressureand monitoring cutting returns.
e1cc81f9-2b31-5af5-b302-a9e40add1d98 | note | Method - Measure
c4c93bac-cb10-58fd-9e99-e2d14a21479e | note | Frequency - Continuously through installation
0cb7c8b5-c42f-57c3-9d60-aa6633be422b | note | Category - WP
fc3151a6-04ed-5a68-b5c0-61e41dcefc29 | note | Responsibility - SE/Site Supervisor
f7f17a99-e971-516d-9e0a-a72989ceb297 | note | Verifying Documents - Sign ITP
0ea38cdd-df53-5a70-a640-28859b2ac3fa | date | Date Completed:
55f81a22-f4fd-4cc3-b9c9-a05ef597000b | checkpoint | 4.05 - Jacking Pipe installation
662b743f-80fc-5239-bdb7-74784e1ec5bb | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203, D/17/62901
b4ae9e82-0872-552a-9b43-11532c757def | note | Acceptance Criteria - DN427 GRP Jacking Pipe to be reamed, then immediately followed by pipe being pulled through. Bore should remain supported at all times.
3336d1ef-5bce-5095-8ae2-9451be82d5f4 | note | ○ Diameter of bore is not to exceed diameter of pipe by more than 50mm.
e7171fe3-e008-5988-a004-10b8b8de3b7a | note | ○ Pipes to be installed in straight sections with no excessive bending in the pipes
fde98351-660c-599e-be8b-818c03cf2547 | note | Method - Visual and Measure
982824c8-94e1-5e1e-b9b8-d605af7a0daf | note | Frequency - Each lot
e12ff3da-a5f1-5c05-b8fb-c72a84e50833 | note | Category - IP
d340c156-bafe-50d4-aedf-1df6bc530da7 | note | Responsibility - SE/Site Supervisor
9f4f0ae4-eca3-56a8-b096-c553c4908583 | note | Verifying Documents - Sign ITP
33ecb7fe-8ba2-50a4-8a0c-967a90009e2d | date | Date Completed:
f992adbe-8cb1-45af-8080-71da5b22f6d1 | checkpoint | 4.06 - ULX1 - Gas Encasing Pipe Installation
c1513785-a0a9-5e72-9d90-ba6deb0b38e1 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
392c7245-0dbb-5ba0-9e03-e2a3d9f6604e | note | Acceptance Criteria - Install thininsulators @ 1000mm centres between Encasing pipe and Jacking pipe to ensure centralisation
4020fd39-86f8-5e5d-91c6-31f324b9f97c | note | Method - Visual
f8629e6f-1bbd-5c30-aa1d-cbc9c2f3f04f | note | Frequency - All Pipe
b4d1e5b1-2231-5969-9799-9251315a298c | note | Category - VP
d26c87e7-18eb-54e3-8cdc-fe12dc7798ca | note | Responsibility - SE
9d60e9a7-6ea0-5282-9552-e47791b47356 | note | Verifying Documents - Sign ITP.
20c0719b-9278-52ba-86b9-d966addacabc | date | Date Completed:
4112a6e1-c54d-4d43-83d6-7cea8561067b | checkpoint | 4.07 - ULX1 - Gas Carrier Pipe Installation
a430972b-2863-5196-871a-4096694e6083 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
32514224-c80a-5b94-8bfe-62778fddaffb | note | Acceptance Criteria - Min depth as per IFC drawings.
71b0614e-ca25-51cf-b01e-945d79c6ae99 | note | ○ Install thininsulators @ 1000mm centres between Encasing pipe and carrier pipe to ensure centralisation
2294a341-77e9-5709-83d4-49a37bba5933 | note | Method - Visual
43882b98-1c42-5e62-817a-392bdeb47057 | note | Frequency - All Pipe
206a1ac3-3f89-5b4f-9f05-a91fdeb301ce | note | Category - VP
3b58d40a-e900-57a6-b8d8-7c598cc3ed45 | note | Responsibility - SE
4baf258c-311f-5b9e-94a7-392da859a632 | note | Verifying Documents - Sign ITP.
429d998c-1413-5500-a500-a6c5521e2191 | date | Date Completed:
8a957817-6846-46e5-8d73-5bb62256e057 | checkpoint | 4.08 - ULX2 - Conduit Installation and Trace Wire
c313c9a1-faa6-5e47-b6da-ef1d70de4a1c | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0203
9d27ffaf-d872-5a29-adda-8922e1d4203e | note | Acceptance Criteria - Min depth as per IFC drawings.
653cdc60-83b9-59e1-894b-33e764ace988 | note | ○ All bored communications conduits shall include the installation of stainless steel 3mm trace wire.
62bca84d-8a56-58d6-a6d3-2b98b5b97cbd | note | Method - Visual
beec80bc-2666-535c-b8fe-d8c7910a1195 | note | Frequency - All Pipe
50f8f6ae-8d31-5bfd-9c14-ba0c0440c4a5 | note | Category - VP
17cdd888-02c6-5867-b458-59b7ef8d72ef | note | Responsibility - SE
74346641-bb94-5a2e-babc-ec6a3fa3be01 | note | Verifying Documents - Sign ITP.
5ca04c27-7cdb-564f-b62e-398663007d95 | date | Date Completed:
a436be1d-f08f-48c2-9dfc-fd22746e19eb | checkpoint | 4.09 - Track Monitoring and Ground Settlement
7ce4a1dc-ddda-5d9d-a173-99fce92c05ff | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002, MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
67430561-d138-5a0a-94ff-2d71fb3b6919 | note | ○ NIST-2706
8add79e6-955c-50a9-a8e9-5217f0dd5896 | note | ○ MRP-000-MRPA-PLN-XPM-0055
42f87696-db25-5c47-a51c-a9c485b88f42 | note | Acceptance Criteria - Both tracks are to be monitored at 2m intervals either side of the centreline of the under bore for 10m either side of the bore centreline, with additional tilt sensors at 5m intervals up to 20m either side of the bore centreline.
b488806f-4873-5b71-be15-4ba42f94bac7 | note | ○ Settlement to be monitored with the escalation matrix on the monitoring plan to be followed. <5mm = no action. 5 to 9mm = notify v/line for inspection. 10 to 14mm = stop works and rectify. >14mm = halt train operations.
db4aa07a-9342-51cb-a430-0cdf4a15d66c | note | Method - Measure and Visual
3da51a22-9f24-5928-87f6-d10e4a0f2639 | note | Frequency - Continuously through installation
ea354ba9-75e2-5593-bca8-e9d1550d3c35 | note | Category - IP
94709ab3-79fd-5fe9-bedb-85075ac40db1 | note | Responsibility - SE/Site Supervisor/Survey
a95dc8aa-473b-52db-9a59-84df5bd3a752 | note | Verifying Documents - Sign ITP
d2d4edfa-7031-580d-9cf4-b069819980a5 | date | Date Completed:
fed36038-a28d-444c-866c-d8037671fc90 | checkpoint | 4.10 - Conduit Welding
8fb6be23-fa66-5b4d-b51f-372a4e4699af | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
84a30b49-5dc7-542f-86b0-5a6e65df3978 | note | Acceptance Criteria - Joints are to be butt welded.
ea963599-f7ba-5a7a-811f-f546f4941d11 | note | ○ Weld map to be supplied and identify unique joint numbers.
627bf2ab-6ea7-5afa-a668-a58e02ac10da | note | ○ Butt Welding records to be supplied.
d536d142-b859-5db5-b05d-0937f5d90989 | note | Method - Record and Review
945e782a-64a5-5532-a6af-9eb383c4baa2 | note | Frequency - All Joints
718cbf5e-402d-588d-9753-f1ed6d023978 | note | Category - IP
5beb1304-91f4-57de-915d-1f598a1a5e82 | note | Responsibility - SE/Site Supervisor/Survey
f7795835-5549-59e5-b8ca-120a5228c8f3 | note | Verifying Documents - Sign ITP, Butt Welding Records
06d8b5d2-33cc-5162-94b1-a59cfbff083c | date | Date Completed:
4515b6be-d1d3-4e7a-8f92-2f5f2e602a95 | checkpoint | 4.11 - Vent Pipe Installation for ULX1 Gas
3c95d7c5-8916-5e67-a4b1-fe352f8d7093 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
a2908692-02f6-524c-b595-d3c8b3da6631 | note | Acceptance Criteria - DN50 PE Gas Ven to be installed by Asset owner (Downer) a minimum of 3m away from rail assets
0742f1dd-57e7-5ce4-8800-7bcb0dba7d13 | note | Method - Record and Review
5a6bd358-f9db-5162-94ab-3bafed674f2c | note | Frequency - All Pipe
7c0f8122-6dcb-5caa-97ff-d6eabf353d80 | note | Category - HP*
6d6ea4af-de17-5b1b-87ce-bcf23eacfb85 | note | Responsibility - SE/SPE
63cef8f1-3981-5077-b357-871e7af8f5e2 | note | Verifying Documents - Sign ITP
18adce3f-ff2a-5372-b3db-5072000f763f | date | Date Completed:
fa772c06-d9cc-4355-9d5f-bbd3d37aa7fe | checkpoint | 4.12 - Grouting
13f37c6b-e569-5346-95df-a3cd10d92f22 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
24c52f1b-fc7b-5e88-a7c3-e90c0d070de9 | note | Acceptance Criteria - Diameter of bored hole to jacking pipe shall not exceed diameter of encasing by more than 50mm. annulus to be grouted with an approve controlled low strength material (CLSM) of minimum 2MPa strength material
2e14f2fd-c29d-5f97-955a-9f59ab9de214 | note | Method - Review
aba393a7-bb02-56bd-9dda-c13afb96abed | note | Frequency - Each lot
c25fb45d-ea0a-56e7-b222-f96de80b7398 | note | Category - IP
c7c0a3e3-a9c2-570d-8a69-05a5148cb3dd | note | Responsibility - SE/Site Supervisor
6df48572-fb14-55d3-92d3-4d505ccc94ec | note | Verifying Documents - Sign ITP
1536e8df-e053-593a-8080-bfafe46af089 | date | Date Completed:
4c3e8215-ff43-4f21-ba2f-6575d3ffad0d | checkpoint | 4.13 - Draw rope
0ee4ccc3-99a5-5dcb-9f12-1d0c9eef10d5 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002
91b26510-df2f-50b7-9390-2beffa19fb8b | note | Acceptance Criteria - The draw rope shall be continuous for the complete length of the conduit run.
c28afdeb-230e-5611-8bce-f7938f19a096 | note | ○ All draw ropes must be continuous between pits and have 2m slack in the pit.
1e43b804-86fd-53cc-b2a2-bd0014fb7c24 | note | ○ Draw ropes to be restrained in each pit to prevent them from being inadvertently pulled into the conduits
2e1d0d3e-6514-59ee-b201-e89b43e254fa | note | Method - Visual
015559e1-d64b-58d2-9223-458fbbb8323d | note | Frequency - All Pipe
4cf0c673-a510-5bc9-9794-3102505215b3 | note | Category - VP
6a5b8a00-f35a-5bab-a3d0-90acca53b9ac | note | Responsibility - SE
bb6ae419-5209-562a-bc8a-51765a6f233e | note | Verifying Documents - Sign ITP.
9b6a3108-4da8-5585-88fc-c1bad9d385e3 | date | Date Completed:
ca960845-40d9-4082-9f0a-e1b5cb25b2c0 | checkpoint | 4.14 - Mandrelling
fecaaab6-4459-5587-812c-605bd3872b49 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002
31aee3bf-6724-5973-be49-8a9fa84060cf | note | Acceptance Criteria - Plug with 90% of the pipe diameter to be pulled through each conduit to ensure the conduit hasn't been compressed.
bfd7589a-4a0c-5cd2-ade9-fc506d72bed4 | note | Method - Record and Review
5d776272-73a3-5760-b648-643c51fcabce | note | Frequency - All Pipe
d1e9ff85-9f5f-5614-aef0-53156bbff7a3 | note | Category - HP*
e1fa9c66-57be-5b50-8124-939c509e2585 | note | Responsibility - SE/SPE
b8e6a24b-7fe9-5455-81c1-75c30371642a | note | Verifying Documents - Sign ITP
63784f15-71b6-5088-ad05-04ecc2e03c5c | date | Date Completed:
06f8e0df-b695-4490-adb6-9e74302a990d | checkpoint | 4.15 - Tracer Wire
a5aa2666-1fcd-5a46-a1d2-7cd83048fc48 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002
23eccefe-2b26-5a2d-bee9-2c75f1b6b410 | note | Acceptance Criteria - All bored communication conduits shall include the installation of a stainless steel trace wire of 3mm diameter.
7ef3f9da-9dac-5e1c-9d69-2e53ed1d8a05 | note | Method - Record and Review
eeae155d-6cdb-53a8-9784-db67769f22f7 | note | Frequency - All Pipe
497b6842-65f1-590f-ac8b-b900d550fb97 | note | Category - HP*
85995889-8436-5aa1-b7c2-e02601fd834c | note | Responsibility - SE/SPE
c43ec950-a854-5637-9bb1-be3f4884eea0 | note | Verifying Documents - Sign ITP
e032e011-20f2-5759-b566-915523ed341b | date | Date Completed:
7fc90178-31ab-464c-9b6c-19d6b289db4e | checkpoint | 4.16 - Pipe Completion
5f6b2bfc-245e-5de4-baae-3e94eb17df90 | note | Reference - IFC Drawings
9ba26092-564d-5dcd-bd04-cb3155e20a20 | note | Acceptance Criteria - End of encasing pipe to be sealed at each end as per IFC drawings
02b3f7c9-ceed-5d58-8c5e-20cb6b7eaf77 | note | Method - Review
96e98c64-75db-5c70-a041-8f8fa066c33f | note | Frequency - Each end of pipe
8dffb93e-a27a-5bf6-8cd8-e0b2469345f2 | note | Category - IP
e531150a-ec31-5847-aa38-fdb3009962f2 | note | Responsibility - SE/Site Supervisor
d6bbaddb-84e1-5765-95af-5ef7001cefb6 | note | Verifying Documents - Delivery dockets, Sign ITP
130f1cf9-a9c1-5a58-8e39-d67036b7d7f5 | date | Date Completed:
c7405d59-1c30-46f4-8313-33076f3ff1ba | checkpoint | 4.17 - Reinstatement
5b611a52-9a93-569c-8b1d-1bad575d7e19 | note | Reference - IFC Drawings
f49f7aba-2f8d-5e1f-8d30-0b413da6b6ba | note | Acceptance Criteria - Entry pits, exit pits and trenches to be backfilled using approved fine crushed rock material. Backfill material shall be compacted to the same density as adjacent material or as specified.
b0667202-ed3f-5738-b298-40736e59d3c3 | note | Method - Review
7520baf4-9c97-514d-b23d-f56b507aefd9 | note | Frequency - Each lot
a8159e17-adcb-5b80-a690-f77171984a4e | note | Category - IP
e0d93d47-04ef-52c1-856c-21627d3c5ded | note | Responsibility - SE/Site Supervisor, VicTrack
d5576fb2-3a50-5a30-8294-12db6e5b9561 | note | Verifying Documents - Sign ITP
1ee9b078-1545-5db3-8135-d845ca2604a2 | date | Date Completed:
e8c6989e-4235-4287-9827-bd35b100b9e2 | checkpoint | 4.18 - Marker Post Installation
7ac31c1c-e065-56af-9514-daaea8dd5280 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203, AS4799-2000
d0a8c54d-41a3-502e-8584-2df23b83acd9 | note | Acceptance Criteria - Marker posts to be installed at every 200m intervals, any change in direction and at the entry and exit points of VicTrack property.
abb19644-835e-54a2-8438-6b63c81a1eec | note | ○ Marker Posts to be placed facing the rail tracks within VicTrack property
28983b33-a5b5-528a-b10b-69ef172f0874 | note | ○ 50mm x 8mm Galvanised Steel Plate Welded to 50mm Ø Galvanised Post with as Capped top protruding to the air and flatted end in concrete
c2696a3c-8fc7-5087-8bcb-d612e8236dd5 | note | ○ Marker plate riveted to post with 8mm insulated aluminium rivets.
157c90b2-694c-556c-a111-56aff3d78c1f | note | ○ Post to be extend 500mm in ground and be concreted in a 300mm Ø footing, concrete to extend out of ground
0cae94d8-638b-5303-a4aa-57b56f510722 | note | Method - Review
79e89079-6d6d-5ad0-ad1b-4bab38ea1b73 | note | Frequency - Entry and Exit Points
38c5fdd8-c0d5-5949-bd6e-e5dad829a933 | note | Category - IP
b04a8aca-6466-5a03-8cc9-aa225135e6e1 | note | Responsibility - SE/Site Supervisor
02316bc8-8182-5994-b2d6-b213c39bd3fb | note | Verifying Documents - Sign ITP, Delivery Dockets
455aa703-2cf9-5c2d-879b-73080cce041c | date | Date Completed:
09be45db-2a9f-471c-aaba-af3718aa5e6b | section | 5. Post-construction Activities
d54c6d4d-b299-420e-9c32-f00553d0a18f | checkpoint | 5.01 - As-built Survey
91c4d1c4-6ea0-5076-ae6c-401c14815df8 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
ec4f2448-4171-569e-b1e3-55f3a001a447 | note | Acceptance Criteria - Survey as built report to be compiled.
4a937e28-015f-56f9-8199-72973b4096a9 | note | ○ Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
fc68d918-f5a5-5186-952a-fb42d3dba1c1 | note | ○ Sleeve must achieve a min. 2000mm vertical clearance to tracks.
daf8a076-ef86-5dad-bd1b-082e5149bb96 | note | Method - Document Review
ba6b4dc6-b8b7-5c93-a5d6-8d7ac8fa578f | note | Frequency - Each element
a445d29a-28aa-5222-848e-e24e2146b83e | note | Category - IP
62aafee4-6942-5a95-bba2-972a65a614a8 | note | Responsibility - Surveyor, SE/PE/SPE
5862d78e-094f-53cf-b622-251af329d452 | note | Verifying Documents - Survey As Report
b62c76ff-259c-58da-8ae9-f262b0e54ab2 | date | Date Completed:
fbb2247a-1684-4952-a17d-1d5d4b6d441e | checkpoint | 5.02 - Track Inspection and Maintenance
362f28ad-9ea0-5f6e-aa12-72521d8beb6b | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002, MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
c56b4072-dddd-596b-ac81-d1b628415540 | note | ○ NIST-2706
ce3572a2-7091-5378-bc06-da6368035acb | note | ○ MRP-000-MRPA-PLN-XPM-0055
0a1da398-ba6b-5432-925a-70ff16e3e586 | note | Acceptance Criteria - Once works are completed, survey to confirm settlement of the track and ground are within the predicted design settlement values.
898effa2-4b87-51c0-9dbf-7d1c9c9249ff | note | ○ Not > 15mm
d02a616d-f672-5b10-bc63-264c5af5e075 | note | ○ To be provided to V/Line prior track hand back.
b629abcb-8d92-59b2-9327-0c93204ccd2a | note | ○ Where track has been disturbed beyond the tolerances, realignment and/or maintenance is required by a qualified sub-contractor.
422a062c-55d2-5cc5-941e-cb1fb6360486 | note | ○ Attach: Track Inspection & Maintenance plan
194b4774-be6f-594b-ad06-3f477e8b3bb2 | note | ○ Attach: Track Measuring Sheet
348e9581-74dc-51b9-8ad8-d8d64223fb3e | note | Method - Document Review
591f8269-8d07-527c-aad0-d682ce98ba31 | note | Frequency - Each element, Where applicable,
2f469c64-c94c-525c-ae10-dd3ee34a3c5e | note | Category - IP
9c088c4b-5f4e-5c10-919c-3a0a6123a79c | note | Responsibility - Surveyor, SE/PE/SPE
42a0ec5b-bea5-5bcf-ba7c-0254687ed951 | note | Verifying Documents - Survey As Built Report
f3adba56-86e5-5ad4-bdf2-a0ea4c1ba28e | date | Date Completed:
17a887d4-aae1-4414-b432-e5507f5cfb9f | checkpoint | 5.03 - Red-line / As-constructed IFC Drawings
7dac1486-465d-539e-89ba-fa0649977b91 | note | Reference - MRPA Quality Management Plan
88e58a79-77d3-5df8-9992-83c0ccfd6f2c | note | Acceptance Criteria - All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
40a4a7e7-4e34-5c7e-8647-45412ffb2672 | note | Method - Document Review
2d0a4c9b-b16d-5cb6-a3ae-32dce1832a08 | note | Frequency - Once, after construction of the design package
db45fe64-42fe-5c0f-a2f4-835fc9da35f9 | note | Category - WP
37f4bdc7-7667-53a4-94dd-857a7c66175f | note | Responsibility - SE/PE/SPE
e03cdc51-e5a2-5492-912f-4378c0190159 | note | Verifying Documents - Red Line Drawing Pack
8d3fdabd-a515-5a2d-bddd-86bffd39ea63 | date | Date Completed:
de2b1fa7-5372-47d4-8278-af1dd35eb86e | checkpoint | Final Inspection
ac4c7329-6028-591d-a25d-39038c16e6ec | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
662989da-65f3-5ae5-b7e6-e8b9d6c596c8 | textbox | Name:
863595d3-c687-5a88-bc52-b6f82ae18111 | textbox | Position:
0ca63c3b-eaeb-5126-90e9-f44f278458af | textbox | Date Completed:
35417162-075e-4b87-91c3-67622999185f | signoff | Sign ITP
43092937-2b7a-404d-a998-2f3127e6ff3e | checklist | ITP-242-CIV-FRMS-Stormwater Drainage-Pipes Supply & Installation (CCTV) Rev 0 | itp | ITP-242-CIV-FRMS-Stormwater Drainage-Pipes Supply & Installation (CCTV) | cf608dc6-ead3-4a49-a530-48e9f94d3256
7581c8ec-02da-4910-94b9-a553e772a8af | section | 1. Referenced Documentation
97a79493-94fd-4b3e-bc5b-04583e15caec | checkpoint-no-value | Referenced Documentation
b2bad124-0d86-570a-8bc4-589dcfd401d2 | note | Document Title: ITP-242-CIV-FRMS-Stormwater Drainage-Pipe Supply & Installation (CCTV)
9e1661c3-d5c7-52a9-b51d-5a48081722df | note | ITP Description: Stormwater Drainage - Pipe Supply & Installation (CCTV)
0306865b-cf06-56ef-aa88-50775d92ece3 | note | Discipline (e.g. CIV/STR/RAIL): Ferris-CIV
a922d9d9-43cd-591d-bf60-e060fdeedc81 | note | Revision Number: 0
9aca6c59-b0d2-5d1e-932a-670a10ab462c | note | Revision Date: 27/02/2025
87ebbdb3-82c4-585a-8567-53c7515870e5 | note | ITP created by: Kamel Alshobaki
a693ae13-7179-57c3-aa12-13030c2f093b | note | ITP approved for use by: Sandy Escalona
bd304a99-53ce-5118-a29f-fd6fa96c1a9b | note | 1.1 - Non Dependent
09813e2a-daff-5238-b8c7-4503a13aef70 | note | Reference - VicRoads Section 701 (May 2020), VicRoads Section 705 (June 2023), IFC Drawings
73dc2fd4-9c0d-477e-a595-403e3efd157c | section | 2. Preliminaries-Materials
9527f8df-4f6c-441b-926c-ba1ae96fa646 | checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
1c94413a-cd63-507e-8779-d067bc11672f | note | Reference - VR Cl 701.04, VR Cl 701.05, VR Cl 701.09
ebeba305-f032-5a3e-90e3-158447c0f2f7 | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and VR Sections 701.05 & 701.09
41244360-dd74-5f47-8c43-330cf5d54ec7 | note | ○ Precast reinforced concrete box culverts shall comply with the requirements of VR Section 701.04
97ee68cb-105c-5461-bb18-0db820e4243a | note | ○ Rubber ring joints shall comply with the requirements of AS 1646
5a540e41-2807-58cb-b801-905be764e268 | textbox | Enter: Teambinder Material Approval number
ea4fc245-8e92-552f-b640-8fc2b75aeb96 | note | ○ Attach: pipes delivery docket
18860954-c813-52ba-a7ef-da29736333bf | note | Method - Document Review
6803c54f-63b9-5423-a540-1d5effb255c0 | note | Frequency - Prior to Commencement
e72914b0-d53c-51ba-866c-96f85b405d6c | note | Category - HP*
9057c4a4-2428-5407-9672-86c8500ac8f3 | note | Responsibility - PE/SE
3b5b2111-5ab5-5d57-b41a-ac9aef2ee1d6 | note | Verifying Documents - Teambinder Material Approval Number, Pipes Delivery Dockets
59f18f23-aab6-5c21-bfb1-a33368dceafc | date | Date Completed:
07186493-8508-4ef2-89b8-1dacd105c0c3 | checkpoint | 2.2 - Drainage Flexible Pipes
f93d1feb-65a1-5eee-8039-1f8afdbc7cf1 | note | Reference - Section Cl 701.08
a4d8e23e-3e74-57e5-98e5-c9ae90fc4b3f | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
57011122-8797-5e90-9f62-deedd06866bf | textbox | Enter: Teambinder Material Approval number
fff923d5-7483-58a6-9416-8e0c75235a7d | note | ○ Attach: pipes delivery docket
214735aa-7b7d-573c-9228-7e08b8136b9a | note | Method - Document Review
f3944dd0-4387-5be0-b28b-f53a7d6caf73 | note | Frequency - Prior to Commencement
8bd92ca3-9cd3-5eb3-9210-147e7f37f7d9 | note | Category - HP*
ab29dfa0-9bc7-5b4b-88ee-555e7f2d483c | note | Responsibility - PE/SE
5332ce71-6412-55f6-8950-a357322b4d3b | note | Verifying Documents - Teambinder Material Approval Number, Pipes Delivery Dockets
dc7035e7-06e7-5bbd-84b2-bdf299d34754 | date | Date Completed:
150385db-519b-443e-a897-cb7ae1daa0be | checkpoint | 2.5 - Drainage Bedding Material
7e89b9a1-9590-55ae-b6bc-1fae74e6c142 | note | Reference - VR Cl 701.09
b8cd7032-eaf2-54fd-bb8b-abab0907d622 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
978316ff-2c9f-5423-85ee-bbab860b6372 | textbox | Enter: Teambinder Material Approval number
ca9329aa-b060-5174-acc1-543bcacda99b | note | ○ Attach: bedding material delivery docket
4c06f92b-0ffb-5451-ae94-2b285556e118 | note | Method - Document Review
80c7cf66-bad1-55f0-a51d-bcdca82137b6 | note | Frequency - Prior to Commencement
35676737-3223-5a6c-b585-c6af7aa7aecb | note | Category - HP*
afc6c7db-248d-589d-be17-a9d17be9481c | note | Responsibility - PE/SE
96ba572e-5f24-5a00-9b1b-06e783b1d088 | note | Verifying Documents - Teambinder Material Approval Number, Material Delivery Dockets
f936247c-12e6-5720-b618-22ccd5500b9d | date | Date Completed:
0609428e-c520-4a98-b9a6-22e059ddc33b | checkpoint | 2.6 - Drainage Backfill Material
2964d1ea-e862-58c1-b4b2-f593e0392fdc | note | Reference - VR Cl 701.09, VR Cl 701.19
6d73e428-2b79-5411-b335-675541d1a5ae | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
010d4201-85ee-54b8-b2f6-3752a99ff145 | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19
639798f1-b5ec-5fd9-9f5d-6d89bae718c1 | textbox | Enter: Teambinder Material Approval number
ac40d008-61ce-54e9-8c3f-0a8bf8433bf4 | note | ○ Attach: backfill material delivery docket
a8d0e51b-1efb-57d6-a3fa-b9c24b50be88 | note | Method - Document Review
9d35195b-59a3-5221-98b2-ff19bfe78e66 | note | Frequency - Prior to Commencement
22713e65-8245-5489-a8a5-3604b67af18d | note | Category - HP*
c8ffdfbe-fa30-5e4f-912e-8a018650e020 | note | Responsibility - PE/SE
e9e95e62-9433-5ed1-a4c8-e42083b78ee5 | note | Verifying Documents - Teambinder Material Approval Number, Material Delivery Dockets
2fd872e7-e725-5c43-be24-ba22ce623552 | date | Date Completed:
bbc07197-cc1e-49b0-8ca6-fec5e8fa59b7 | section | 4. Pre-Construction Activities
91a6e63d-7d69-4161-beff-3b913fac99a0 | checkpoint | 4.1 - Survey Set Out - Pits & Pipes
55c8a636-b339-527c-8a29-ffef592020a0 | note | Reference - IFC Drawings VR Section 701.10
0ded5e2c-e9c5-5490-9f07-1e207551bf07 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
38dd4ce3-9303-5d25-896c-52ede033537d | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
e14d783a-98c6-5d77-9edd-e2625d529ee0 | note | Method - Survey
6512259e-73fa-51b0-8ce8-9bc04ab0190b | note | Frequency - Each Lot
fbd24d2b-5547-5393-bb07-6cad7eae5946 | note | Category - HP*
0bdb636e-7e0b-5f4f-a5b5-f820f59d0a61 | note | Responsibility - SE/PE
a49f745b-3f61-58f7-ae75-0def793a9f3a | note | Verifying Documents - This ITP
c48bfce9-f0c9-57d3-b5c6-81baf72f6c6f | date | Date Completed:
57f4a3fa-8c5b-44c9-88d9-599bd99acbff | section | 5. Construction / Installation Activities
aab0be52-aed6-4a6a-9c39-e9cc42a17bed | checkpoint | 5.12 - Pipes - Trench Excavation
b458a6ea-ecfb-5c0c-a3c4-e2ccc8019255 | note | Reference - IFC Drawings VR Section 701.15
419cd0e5-be87-5222-8504-51df10bd59b3 | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
6ccae899-0032-55eb-a708-a8af7831189e | note | ○ > 300mm, < 600mm for RCP
aa938209-d050-5249-898e-e0df5490df89 | note | ○ > 150mm for Flexible Pipe
ed6ef863-fb66-52b3-a640-ffc25a586ea4 | note | — The base of the trench shall be compacted to refusal using mechanical plant.
85622e76-1f74-505b-9ee4-a08ea04c3ce5 | note | Method - Visual inspection, Measure
6b46fde5-b095-509d-a59a-c3dd09bb8346 | note | Frequency - Each Lot
71f3a393-62f9-51ea-bad7-e0d794be8dd5 | note | Category - IP
2d0dd505-3df9-5288-9acd-01b8694a688f | note | Responsibility - SE
cda62f91-3051-547b-b4f3-1ee560c29530 | note | Verifying Documents - This ITP
d96ea54d-46b3-51d6-9789-4fc8d9ad94b4 | date | Date Completed:
71f47218-b879-43d6-b67e-469047642202 | checkpoint | 5.13 - Pipes - Bedding Placement and compaction
0132c4e3-6bd4-5ac4-9af3-0c4799f406d6 | note | Reference - IFC Drawings VR Cl 701.16, VR Cl 701.20(a)
6bc108a5-2c7a-5458-ae24-8987fe059a54 | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
41300f2b-0f19-5693-b8b3-705a31e6af11 | note | ○ > 100mm where D<1500mm
897e0c0b-aef1-5d9e-a472-6b2caa40f92e | note | ○ > 200mmwhwere D≥1500mm
a4b575bd-7837-5f83-994e-8cf2e233ff21 | note | — Bedding material shall be placed and compacted in layers <150mm loose thickness
d48a05cb-70cd-59fa-8e12-0c0d62c40bfd | note | — Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
bb6ea1ae-7d27-51cc-8c7c-498d0035355a | note | Method - Visual inspection, Measure
69a99ecc-8ffa-5092-9836-16b7df67abf6 | note | Frequency - Each Lot
1e41f3de-0704-5162-9e8c-d4f03c021eb1 | note | Category - IP
1997e3e9-63dc-5a7d-8911-fdbf54ecd08a | note | Responsibility - SE
2358f385-1979-5bf7-a633-6031527a5e7d | note | Verifying Documents - This ITP
f77b2739-e561-575d-af49-f3c0eeab940a | date | Date Completed:
b5eac23d-36a7-4a71-b3ad-55b63e03f9af | checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
3e2a1adc-c2fc-545c-b090-e52c4c8b82c9 | note | Reference - IFC Drawings VR Cl 701.17, VR Cl 701.20
0e413cae-ec99-5188-9397-b695854ca885 | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
767c9dc1-0f09-5786-8810-784171430017 | note | ○ Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
dd70ecd7-e955-5ef2-afde-b3b16bb453eb | note | ○ Gaps between spigot and socket are in accordance with the manufacturers specifications
96875811-f10e-5ea3-b907-a800d413fd0e | note | ○ The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
c60148ee-6b76-54a0-af9b-a9bed0c26ed7 | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
9084bb26-2a57-51f5-81c6-bef01a60aee6 | note | ○ The spacing for multiple row culverts shall be as shown in Table 701.171
4b526094-79b8-5251-9f60-087fdbb61e08 | note | Method - Visual inspection, Measure
c5721109-1b1f-548d-90bf-72babe079d54 | note | Frequency - Each Lot
8d9b64e9-8fce-5587-83e3-7a23c67d2a7c | note | Category - IP
af1a3b1c-b01b-5f52-a7cc-33d73e8b988a | note | Responsibility - SE
e84eb0c0-b8a9-5699-95a3-8cd576ddd2d6 | note | Verifying Documents - Ferris Rd - IFC Drawings
da4e531e-20e5-555b-80a9-16a44bd2502a | date | Date Completed:
37e93e4e-f329-4d6a-ba37-e7580dc41972 | checkpoint | 5.16 - Pipes - Placement of Pipe - Flexible Pipe
a0ab7fbe-e3bb-5b97-80a1-ce8bf1aa00fc | note | Reference - IFC Drawings VR Cl 701.22
f8195e1f-2cb4-5fc7-9a4b-37f16cd391d3 | note | Acceptance Criteria - All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
6c192a77-69f1-5a3f-a0d5-9afbe9a67e00 | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
f824685b-367c-5c8b-bb17-be782a3b008b | note | Method - Visual inspection
07bf551e-0465-55a3-92d3-37ce8480ff22 | note | Frequency - Each Lot
11ea270b-0f98-5b4a-8aab-cfb664daf92f | note | Category - IP
53b4ac58-be06-531e-b4d8-985a7e776fbb | note | Responsibility - SE
5622aa9d-5b5a-559f-a1ae-e1c1ccee665e | note | Verifying Documents - This ITP
428defe2-e32a-585c-89f9-db75489593f4 | date | Date Completed:
cdbe5c2f-6a73-48c8-9a00-fc4bdefab76c | checkpoint | 5.17 - Pipes - Lifting Holes
733ebc34-7324-542e-98cb-5ffc6b87e086 | note | Reference - VR Cl 701.18
56477181-5de6-50fb-8e59-e8ae33e06d8e | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
c03e8c69-cf4b-528c-b87e-2cc78c3b5699 | note | Method - Visual inspection
ad3a24cc-2e09-5ffa-bb28-2bd9611cd28b | note | Frequency - Each Lot
6305a7d5-df9d-5c4c-8538-550ab20d45b7 | note | Category - IP
62582de4-b3e1-5679-bfe7-6784db8293f8 | note | Responsibility - SE
0be33e67-e4ab-52a3-80af-8d05f5477088 | note | Verifying Documents - This ITP
1fed0fc5-ae8a-58dd-97ef-26703b4d6938 | date | Date Completed:
482b2fe6-4cfb-4c4c-9e95-4a74d3064202 | checkpoint | 5.18 - Pipes - As-built survey pick-up
fc12bd94-08c3-52a5-b98e-dd00caf51b7c | note | Reference - IFC Drawings VR Cl 710.10
0ae8aa1b-1b89-5667-b840-41c440427af0 | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
761544a6-8e93-5fa4-bebe-6553565bf27f | note | ○ Offset pits to kerb +/- 20mm
7a759f37-3d43-56fb-828a-8ab68093debc | note | ○ Plan location pits not adjacent to kerb +/- 100mm
ebeda83d-d388-5bf2-a63c-176cac7fad3c | note | ○ Invert level of pipes at pits +/- 50mm
561e22ef-b37d-5734-ae68-ec6a72fc0f2f | note | ○ departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
d8bba40b-1a18-57e8-9fb2-08d5b33b554f | note | Method - Survey
a1f199ce-dd50-5210-82cf-d0ea00940801 | note | Frequency - Each Lot
ae16dee8-e499-5b8e-ad0b-727bf276800e | note | Category - IP
b997f77c-248d-5aec-8308-1eca3e3cc75d | note | Responsibility - SE
ef02e42c-3417-587b-90b9-abf1e3db23b2 | note | Verifying Documents - This ITP
714b896a-0de0-5949-bde0-3b5a02609e23 | date | Date Completed:
65058507-0d68-4afa-a4f9-eaa57b3d6626 | checkpoint | 5.19 - Pipes - Backfill Placement
37628c45-a934-5475-9203-3d2b95777f14 | note | Reference - IFC Drawings VR Cl 701.16
352c0c17-336a-51b2-9dc7-7b2a919fc97a | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
85364b9b-48ff-5b61-9c73-e873e7f17deb | note | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
7c177bb6-6bff-53eb-8716-f091c9f0afa0 | note | Method - Visual inspection, Measure
0232a9fd-887c-55a7-b16c-cb2c677e520b | note | Frequency - Each Lot
adc62d62-7a5f-5740-bf43-903f361301d6 | note | Category - IP
4b19fd1b-1775-560b-94bb-8fed5fd4de80 | note | Responsibility - SE
f246dd7a-33fd-5e18-afac-560dbf725955 | note | Verifying Documents - This ITP
5ae87172-0281-5dc4-ad71-1cfd84974244 | date | Date Completed:
20f6ad5d-9061-4df5-8009-459d0f17b47d | checkpoint | 5.2 - Pipes - Backfill Testing
965fa55b-29bd-5df6-b444-248a4396213d | note | Reference - IFC Drawings VR Cl 701.20, VR Cl 701.29
3baf9053-5641-5ed9-bae3-014c327287d5 | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
f0de95f7-6964-5739-9915-e795b0331803 | note | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
a452b51a-d423-51ef-88cd-38625bf9287b | note | Method - Visual inspection
97917e51-75ae-5722-9795-d9574086d1a6 | note | Frequency - Each Lot
ef70d902-013c-5ee5-857d-e2348d3c959e | note | Category - HP*
3a965b14-556b-5d3b-886b-a6c520e81ebb | note | Responsibility - PE
42ab1f1b-07fc-5d68-b779-1ba168ce8ed8 | note | Verifying Documents - This ITP
75fa0e6f-3287-54ce-b19a-21156fd0b587 | date | Date Completed:
dfa134e0-5162-4e37-ab5e-dedbc7c377f8 | section | 6. Post-construction / Post-installation Activities
49a2e6a4-d47e-4b45-ab2e-1a1dd6ebf540 | checkpoint | 6.1 - Flushing & CCTV
89766feb-8aad-5015-b873-9bbb5f851928 | note | Reference - VR Cl 701.28, VR Cl 701.30
c7935fef-a41c-55cb-991a-8c2b654a3fb9 | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
ec35586a-4195-5adf-81f5-8bfbe05bb881 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
c0cd57c5-d015-59be-9164-1b2955f353e2 | note | ○ Attach: Flushing Record, CCTV Reports
51683d5b-9243-5467-969d-0993c4474599 | note | Method - Record Review
eb3544fb-dc69-5b54-b7bc-e1ec787c9ad3 | note | Frequency - Each lot
17f475f0-fc0c-5378-b749-ed0e885ce2ee | note | Category - HP
c305a9ca-5f6a-50ee-9cfa-2cb27bc44780 | note | Responsibility - SE/PE
db0a568b-71e1-5062-a7d2-00bef4f1dbe0 | note | Verifying Documents - ConQA HP Release, Flushing Record, CCTV Reports
ad87bc85-8b3e-54a5-94b1-1ea1ab9a82c6 | date | Date Completed:
caa40d04-0fd7-4424-b2c7-35da0f03f578 | signoff | AUTHORITY HOLDPOINT
a67a9313-40e6-4ea7-8adf-3f14e4497284 | checkpoint | 6.2 - Compaction and Moisture content tests
c5113816-d3c9-5c15-94de-5e8d0211be72 | note | Reference - VicRoads, Cl 701.20
220e2305-0bf0-599a-8872-ba629d9b6935 | note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
ef36cd92-018c-5ae1-918d-590a01e0a2ab | note | ○ ATTACH: Compaction and Moisture content test results
be75e38e-c626-5c17-996f-2b82bee3a5e3 | note | Method - Document Review
74d6a308-6382-512c-b851-5f1b707aabb2 | note | Frequency - Each Lot
8e34c836-bb7f-573b-b44a-0d278e3f4ee6 | note | Category - IP
5a0a18c3-77a4-5ae9-b0d4-2c6ed23d9b7e | note | Responsibility - SE/PE
1f3e3044-83ed-51c2-af1e-0a76e2cc6dd3 | note | Verifying Documents - Test Results
a23e8029-d814-5b88-a4a7-ebd9e07bff15 | date | Date Completed:
57cd4151-3ef5-4a0d-b022-f717f2165049 | checkpoint | 6.3 - As Built Survey
ea0e4cdc-7b79-5f77-b021-f31b3d587092 | note | Reference - VR Cl 701.10
c8c9804d-925f-5cd7-814f-50aa54676ed7 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10
b396ba54-fffc-57c3-9cef-f22a64ffb054 | note | ○ Attach: As-Built Survey Conformance
e0f9289d-ae70-5bda-bf2c-8f39d9836a12 | note | Method - Document Review
4328013e-8867-5b5d-ae33-86a139249cd6 | note | Frequency - Each lot
e293b548-f5e9-5d56-b1ea-94618410e43c | note | Category - IP
ec694551-ddfa-569a-a6de-f56dd26819d9 | note | Responsibility - SE
f0b4f71b-610f-5a63-bb06-21f00b4d35b5 | note | Verifying Documents - ConQA HP Release, As Built Survey Report
526b1104-5688-508e-8099-5f70f86942dd | date | Date Completed:
4f13b4d2-3847-45d8-b569-50fb22892c58 | checkpoint | 6.4 - Repairs to Damaged Pipes
37e5af02-b19d-5830-8d18-cb38b0ee3d13 | note | Reference - VR Cl 701.31
8dae66f4-8595-554e-84ab-193a1b24c0c0 | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
5d280daf-2910-54d8-bda6-ec53d1880de9 | note | — cracks wider than 0.5 mm
5dcd806c-8979-589e-aec9-39a908b44f42 | note | — spalling of concrete
cfcd0bf0-32b2-5e15-b872-d98995e675e6 | note | — exposed reinforcement
9f53a995-337b-50ec-bf5a-a59247c14741 | note | — joints that are not fully engaged.
4bc17e69-ee36-5b4c-a53e-2e39305cd135 | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
fc05f128-bc3e-5bd2-9f32-cb91b0c9c884 | note | — longitudinal cracks greater than 2 mm
fd36c274-bd63-543e-8f42-332805c68799 | note | — circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked VR Sections exceeding 3 mm
5d7decc5-e39b-5d92-bfc7-490d2333910b | note | — circumferential cracks around part of the circumference with width greater than 4 mm
dbb8ac30-beed-596a-aba1-7daf1cb35de2 | note | — penetrations with area greater than 400 mm2
6b720546-786a-5049-8b53-9462eb668cd5 | note | — pipe joints that are separated.
13a2bac8-12ab-5b3a-bc60-73e56b3c9782 | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
1a794105-b4a6-5f86-ac1d-f7a5a7958bdb | note | — hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
4e3bddd3-7509-5e7d-922a-e99319fb83fe | note | — fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
8d223ec0-10af-5ec3-8a53-933379bc90f2 | note | — spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of VR Section 689.
586d9578-cac1-529d-9513-3b18067bf5f6 | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
26022542-85dc-5e78-8f83-01d444e7fe52 | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
68d962ce-7f35-5d7f-9fc9-3c2a15dc77dd | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
7f978741-bbdd-53f2-bdb4-350c2881d60c | note | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
a093ecb4-4437-53f9-a74b-5f8964150adb | note | Frequency - Each lot
04841da3-4e3f-5543-bb2b-26ba654e27b6 | note | Category - HP
80f7f653-2811-5405-b09f-29323f987a5c | note | Responsibility - Nominated Authority
2fbbbf92-e9e3-5289-9347-038d894cdc9c | note | Verifying Documents - ConQA HP Release, Approved Repair Procedure, Post Repair CCTV Report
4479a175-d47d-5da8-8717-1d89f03f1bca | date | Date Completed:
6c3c65db-9bf5-49f0-945d-0d2244922c9e | signoff | AUTHORITY HOLDPOINT
07e7e3f7-98ff-4e0d-8b40-15483e6f81d5 | checkpoint | 6.5 - Non-conformance Report (NCR) Closure
8b0a81e4-f7ce-59d3-8e23-da46cd492e32 | note | Reference - MRPA Quality Management Plan
12d7f5a6-f1a7-50c6-8f0a-dd5f36f4b4f1 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
5390ddd9-7344-54a9-9d59-c5801ffa9e5a | textbox | Enter: TeamBinder NCR number (if applicable)
89f42375-dcfe-5888-a1fc-f054b93409c3 | note | Method - Document Review
53e927d6-693c-5790-bb73-48b5a32f5571 | note | Frequency - Once, prior to closure of this lot / element / Work area
fde9c862-1d59-5311-a043-381bf2b3037b | note | Category - HP*
e2da1fec-44aa-5ee4-a9f4-57613e88b45b | note | Responsibility - PE
82b33e0a-5cce-54d7-ab28-28f983157a65 | note | Verifying Documents - This ITP
bff9ce9c-ce1e-563e-9308-5845f9ef3347 | date | Date Completed:
2215297e-1d3b-4571-9c2c-1bbb412705eb | checkpoint | Final Inspection
89c65d47-d5d0-5660-870a-ebef1183e3a4 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2ef27598-6cd0-5750-97ce-9519ac5ec416 | textbox | Name:
1ee387a3-9523-5b0d-897f-72d11e241e76 | textbox | Position:
2fa526b5-a95e-5386-9722-2e6ffc2518b5 | textbox | Date Completed:
170b44d8-6010-4340-8641-b2c76c1fe9eb | signoff | Sign ITP
8520561a-555c-4792-94c1-e6d844c5d68b | checklist | ITP-243-CIV-FRMS-Stormwater Drainage-Pit & Covers Supply & Installation Rev 0 | itp | ITP-243-CIV-FRMS-Stormwater Drainage-Pit & Covers Supply & Installation | 2ddad472-4dcd-4618-a552-88fa6fbaa488
ede3fb35-6966-4f90-b3da-7d1fae4615d6 | section | 1. Referenced Documentation
9a0c52ce-d533-4a0b-9287-987a0f67bb5d | checkpoint-no-value | Referenced Documentation
74b31601-d7a0-5132-b047-82cce977a2b4 | note | Document Title: ITP-243-CIV-FRMS-Stormwater Drainage-Pit & Covers Supply & Installation
135f494c-8825-5bd8-b541-a9cb0753bc02 | note | ITP Description: Stormwater Drainage Pit & Cover Installation
5c026432-12f3-5da1-b580-100949bb7c1b | note | Discipline (e.g. CIV/STR/RAIL): Ferris-CIV
748e5ca7-f0ca-5f43-adb2-ecb2d188a2ad | note | Revision Number: 0
90461164-c6b7-5583-acb5-c1c23d016b08 | note | Revision Date: 27/02/2025
21ccb917-084e-5b0e-b886-e827996fe3ac | note | ITP created by: Kamel ALSHOBAKI
1f9fd696-d136-5a9c-89f9-26f2650236a3 | note | ITP approved for use by: Sandy Escalona
a5b2a9e4-9381-55ad-9fe1-f8fea13c0a76 | note | 1.1 - Non Dependent
655d1876-4853-56dc-a81a-feb990c846d2 | note | Reference - VicRoads Section 701 (May 2020)
94d8f7f5-cea8-5511-8764-ca63f13aa263 | note | ○ VicRoads Section 705 (June 2023)
b6324b4d-90ec-57a3-af1a-4226b55c8842 | note | ○ IFC Drawings
4f0a6fba-9b90-5da3-a593-4d64dfa4d791 | note | ○ CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
140e2e48-3138-4d09-a6c8-9d4befa4b6cd | section | 2. Preliminaries-Materials
212191b6-0e58-4c59-ac32-1cdd79a37fa4 | checkpoint | 2.2 - Precast Drainage Pit
17887801-f373-5d62-9d4f-4cdf54e901fb | note | Reference - VR Cl 705.04, VR Cl 705.07, VR Cl 705.09
891dc4ca-6f24-5a7a-84e1-d7f1e593f5f2 | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with VR Section 705, BTN 033, Section 610 and 611.
0e14b709-7c6c-592d-8fe0-8547c6541243 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of VR Section 705.04 610. Concrete grades shall comply with Table 705.041
c5bed86c-111c-57a4-a01f-0fa1fda02a08 | textbox | Enter: Teambinder Material Approval number
c242d807-f714-52b8-b061-cdee949c5de4 | note | ○ Attach: precast drainage pit delivery docket
3e4f50ba-d4d0-5ff1-8f2f-611557e5f84a | note | Method - Document Review
9e57a769-515c-5c58-be03-115a422037e8 | note | Frequency - Prior to Commencement
a1a3cc82-2335-538c-9526-b8b2e35fe6c6 | note | Category - HP*
80f5dc07-7fde-5bda-b0ea-ecf243941682 | note | Responsibility - PE/SE
b41fe640-3f42-5db4-9eb3-e7f30598d2a8 | note | Verifying Documents - Teambinder Material Approval, Precast drainage pit delivery docket
86259c62-9214-5e91-b943-98d4db742b29 | date | Date Completed:
d74d051f-63f3-42c4-8e0d-ce8a24910289 | checkpoint | 2.5 - Drainage Pit - Step Irons
b8011209-6de6-5c72-8d19-c05108fa488e | note | Reference - VR Cl 705.04, VR Cl 705.12
aa40543e-0b25-56bd-b487-fc1dbd11e3a1 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
2bea4459-eb58-5d1a-8904-d32207e65c60 | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with VR Section 705 and AS 1657.
41320fd7-eda9-5766-846c-e95948f448f2 | textbox | Enter: Teambinder Material Approval number
713beb71-5288-5e68-90c0-c0d9af3bf655 | note | ○ Attach: step irons delivery docket
9bd33fbd-cf26-59b8-b86c-dba91fd5ffac | note | Method - Document Review
10950149-45ce-52bd-9689-86b535386a5c | note | Frequency - Prior to Commencement
9df71360-151c-5bfe-af8a-3743b7b05ec9 | note | Category - HP*
8216d1b6-9ef8-5275-b1d8-3d9d0c17046a | note | Responsibility - PE/SE
298eebb1-3fa0-59df-b849-44198af29147 | note | Verifying Documents - Teambinder Material Approval Number, Step irons delivery docket
58eac3d3-fdb1-5533-8724-2f3af7069fcb | date | Date Completed:
2c954ca5-85c9-4dcf-9c7a-e57cc27872d1 | checkpoint | 2.6 - Drainage Bedding Material
90f99e58-b147-5802-906d-2ef0dbdd5c95 | note | Reference - VR Cl 701.09
1f08aa0c-9a77-55b1-b1f1-9260f0ef4b46 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
4e266e6d-cbbc-5080-b875-5dc6f39372e5 | textbox | Enter: Teambinder Material Approval number
c22f6b5a-8cd9-51c2-b143-e4431038897f | note | ○ Attach: bedding material delivery docket
f91f215a-7c9e-566b-bf56-1493ae43a981 | note | Method - Document Review
d91ded18-b079-552e-952d-15f42c8e6ba9 | note | Frequency - Prior to Commencement
32e2d1f3-5bee-5cd3-a79d-71c87d1abcd0 | note | Category - HP*
1e6e5b97-cd28-5b9a-a88d-98b072bb4300 | note | Responsibility - PE/SE
963fef66-a7cc-534f-98a2-5e3d173b46ea | note | Verifying Documents - Teambinder Material Approval, Bedding Material delivery docket
918f10c5-a9dc-5c86-ba82-cd686e96a9ea | date | Date Completed:
8c611c6a-8415-477e-8205-afeda4da96fd | checkpoint | 2.7 - Drainage Backfill Material
a466865c-f0f4-5f86-a611-852796fbfa6e | note | Reference - VR Cl 701.09, VR Cl 701.19
b764a71e-8083-56b3-b46b-58b00b9ccc2b | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
dad74492-e9de-50cc-8a1a-566b2beec7d1 | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19
5ac74f2f-7d70-5060-acdf-ac6614ee6e47 | textbox | Enter: Teambinder Material Approval number
c0c6859a-44d7-5529-b13b-7c4db9b8a7b5 | note | ○ Attach: backfill material delivery docket
223d5caa-f03f-5c3f-94d8-66cebf975747 | note | Method - Document Review
c566dee3-2c5a-59d2-a8d4-5f98f426546f | note | Frequency - Prior to Commencement
2f584b9e-774f-5e43-a451-39135c8b4e12 | note | Category - HP*
fedd831c-0963-56db-ab48-f9866188b9da | note | Responsibility - PE/SE
5a8668d8-ab2f-5fc9-b18d-b59934162641 | note | Verifying Documents - Teambinder Material Approval, Backfill Material delivery docket
a2a8d0ef-b611-5066-a03c-979634d0edd2 | date | Date Completed:
c637385c-7d8c-495d-a44b-621460548ca3 | section | 3. Pre-Construction Activities
be6f0d8e-b7cb-42c1-b0d0-1ef6659a1c43 | checkpoint | 3.1 - Survey Set Out - Pits
8207d7fb-9aec-5970-acd8-a5f39b32e7da | note | Reference - IFC Drawings VR Cl 701.10
8cf8b9b4-b660-52e3-ac74-2df7f5c1e453 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
4134f0f1-2214-548f-bb5f-6569e19d7bff | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
98187bf3-6cd1-5800-88af-609866046098 | note | Method - Survey
141d4cf0-455a-5cb4-b6f8-3dbb1a27521b | note | Frequency - Each Lot
03b064e5-48fb-5457-8719-d8cd77798f6c | note | Category - IP
77343bd2-86a4-596c-b1f2-0120b0995c62 | note | Responsibility - PE
cf56e4af-3da0-5901-9c5f-4a62a7962d74 | note | Verifying Documents - This ITP
8ea2cfcd-76f1-53b8-b5b0-75041d2c80d2 | date | Date Completed:
6d9408fa-8e20-4587-8b90-7bbe226e09a9 | section | 4. Construction / Installation Activities
a7c6e7b0-9644-48d9-8926-3d85d31c404e | checkpoint | 4.1 - Pits - Excavation
dae92a84-594a-5abd-94f2-2d5566821821 | note | Reference - IFC Drawings VR Cl 705.05
5e82061b-61ba-5ccf-b45a-5e4cdf086bb0 | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
2bf694d2-2adc-5a77-b87d-e16600c64f97 | note | Method - Visual inspection, Measure
fb60f38c-bfe7-516d-8e07-274f4ce88a61 | note | Frequency - Each Lot
993f80c4-9624-5806-975f-5cb1831f7cc6 | note | Category - IP
901c9057-5e53-5806-8fdc-cf06a0a9a0d0 | note | Responsibility - SE
0c93428e-8fdb-5828-bf6f-a4c8b934d057 | note | Verifying Documents - This ITP
1fff109f-8d94-5cee-9b1a-e4f60eb76764 | date | Date Completed:
4c3ac13d-39e8-42e3-98f0-9a04a26f0c81 | checkpoint | 4.2 - Pits - Placement of Bedding Material
bef1e165-f5bb-5331-8fb2-0c18b0e6135b | note | Reference - IFC Drawings VR Cl 705.05
a6ec6523-7c3f-539d-81e3-75a98f9180b1 | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
d618680f-b2b8-570a-b75f-bb53eee87412 | note | ○ > 80mm for clay foundations
410607c2-98e6-50a5-bf3e-f260a5510746 | note | ○ > 150mm for rock foundations
4f364fb4-0f7f-530a-a06f-b1021cc96d4f | note | Method - Visual inspection, Measure
8aa104e7-914a-569e-b0c3-a3cf079771ef | note | Frequency - Each Lot
2f6ad88d-bf93-5150-b301-afb3b288ce92 | note | Category - IP
5c3bfd4d-c51a-5105-92b2-83a243e657d0 | note | Responsibility - SE
fa9beff7-257a-593b-8f6c-b5d5fbb0a874 | note | Verifying Documents - This ITP
37f6c8ad-722e-5e18-a7cb-d95a58eb216d | date | Date Completed:
dc94c6b7-104d-40bb-93e8-656c2e7f2fe3 | checkpoint | 4.3 - Pits - Bedding Testing
07986812-3a92-5546-b93f-db8d5766473f | note | Reference - IFC Drawings VR Cl 701.20
77655029-b5a3-5481-907a-6f2634c7fa11 | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three.
f7475491-92ad-516b-b579-1704d5d1c491 | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material (Swell ≥ 2.5%) shall be mantained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
12a52ee4-0693-5354-98d2-a8bcb7c76138 | note | Method - Compaction Test
556d8c39-5ab4-50f4-abd3-f747c128f407 | note | Frequency - Each Lot
00efbf78-abf6-5878-85b3-0882a97196f8 | note | Category - IP
4b54d070-199f-5d18-8278-530c01720356 | note | Responsibility - SE
6ff5553f-b001-5ed8-ad8e-632018bc8426 | note | Verifying Documents - This ITP
92719d20-3e6c-53ee-a6af-e71ed6262f15 | date | Date Completed:
afb5d259-f903-48dd-80e7-e28af1f78ed9 | checkpoint | 4.4 - Pits - Placement of Precast Drainage Pit
71d9784a-5394-565f-a4cf-0ec354b466a5 | note | Reference - IFC Drawings VR Cl 701.10
a7babfa8-a0c8-5bfe-9b6f-811a1a13a4c4 | note | Acceptance Criteria - Survey pick-up to verify:
7dadc736-56f6-5959-abf2-bceacbba658f | note | ○ Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
2269fbf9-487f-5b3b-bf43-11bea17a0c70 | note | ○ Offset of entry pits required to match lines of kerbs or barriers ±20 mm
5db161ca-0822-5dba-ae21-1aca2b8c5014 | note | Method - Visual inspection, Measure
5f153a82-bddb-5dfe-8e28-2d5c05746b9f | note | Frequency - Each Lot
071c6275-b411-516c-90fa-71836e1777a0 | note | Category - IP
2019dcf1-8532-5f5a-802b-6ca06d66f229 | note | Responsibility - SE
7ea03568-9e66-5b92-a766-af31da8ffec8 | note | Verifying Documents - This ITP
062860db-ddde-5d91-a387-7e6e02eb45ae | date | Date Completed:
c6a69718-716f-4c8b-99b6-0f840f7cdaa7 | checkpoint | 4.5 - Pits - Jointing & Drainage Connections
0e78588b-2407-5ba4-86f8-3749c03c2740 | note | Reference - VR Cl 705.11, VR Cl 705.15
7b425cac-0bae-5904-b2b4-a638770c12d1 | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with VR Section 705.11.
b5e661b7-5621-5dfd-a33f-e8520ad103f2 | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
983ce284-a4df-559b-bc1d-af07973cd4c9 | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
de96d864-3f2d-59d4-8599-8ecacc7d7e26 | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
dfee28ea-02c3-52b9-9f3a-9985b3f592b0 | note | Method - Visual inspection, Measure
ab0d86df-ff14-568a-863a-9a8d1d73509f | note | Frequency - Each Lot
fe4dddd8-b502-5d36-88ce-76f87c5a61c0 | note | Category - IP
7a83c008-17b9-5b48-bead-eeb222d867e2 | note | Responsibility - SE
c297678a-f4cb-579e-809a-0befabfedbe9 | note | Verifying Documents - This ITP
17936af8-e044-568d-861a-88fde773a7a7 | date | Date Completed:
c240e44b-7009-4ba5-afc5-52e8ccb21317 | checkpoint | 4.6 - Pits - Shaping of Floor
f19317dc-51ff-50f5-9a25-ad2c35a3527a | note | Reference - VR Cl 705.13
7be55e3b-017c-5775-b888-b442f5d779c7 | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with VR Clause 610.33
fdbef760-5fc2-59ac-a643-64683a312efc | note | Method - Visual inspection, Measure
c57af704-4584-55e3-b348-43b6665b8000 | note | Frequency - Each Lot
1f3fa2aa-a1e6-5fc5-879d-237209d168fc | note | Category - IP
b611eb48-ba51-5045-81d6-124036aea4fc | note | Responsibility - SE
f00622be-9a18-5efd-b8dd-7c00d807728d | note | Verifying Documents - This ITP
c99ce628-c162-5db9-866c-e95f47ab57ab | date | Date Completed:
7b19ab5c-c384-4408-aafd-4596ca230665 | checkpoint | 4.7 - Pits - Step Irons
fed47166-88d3-57dd-99a4-6b474a12890c | note | Reference - IFC Drawings VR Cl 705.12
e6e8f6c6-a734-5754-b5ab-e6d41bc1d631 | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with VR Section 705 and AS 1657. Ladder rungs shall be located directly below the opening in the cover and set into a wall which has no openings, or beside an opening, or accross a corner of a pit. Step rungs do not come within 50mm of the top of the riser. Ladder rungs shall have circular or rounded edges.
e890b294-0c20-5aaa-ac19-ccfe35211dea | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
484a1026-ec2f-5204-aa96-ed53ff0ec066 | note | Method - Visual inspection, Measure
82b8c64a-fd23-5c47-9162-2782364ea99a | note | Frequency - Each Lot
873f79e4-8f1c-5558-b3c0-839be7e9141e | note | Category - IP
c35f8bdd-280d-56a7-93e7-cce1374a0f14 | note | Responsibility - SE
2371e924-2373-5504-9b80-7cb92ed7c950 | note | Verifying Documents - This ITP
989bfb68-b1e7-5b24-87b0-46c5255407ba | date | Date Completed:
276ea893-2378-4c2d-8de9-d1c0cb63eacb | checkpoint | 4.8 - Pits - Fitting of Covers
4b35181c-3c59-5115-aee1-832ade01c06e | note | Reference - IFC Drawings VR Cl 705.17
0b163fce-a863-5f59-b7e8-d2cb0ad1a6b6 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
b54183bd-85cf-551a-a89e-1706c017e103 | note | ○ Height shall be within 10mm of the design level and the line of the cover shall be within 10mm of the design kerb line.
f74e7001-1299-5d37-a7b3-b272ef8b3128 | note | Method - Visual inspection, Measure
395478da-7846-5916-97e8-23282178fbc0 | note | Frequency - Each Lot
5311ce6a-b01e-50a7-bf20-b69f51d1aae7 | note | Category - IP
8f35a0fd-b934-5a4c-84c2-58255b5c121d | note | Responsibility - SE
ce7a0dfa-c38e-5590-b158-c73d678ac92e | note | Verifying Documents - This ITP
abcbd535-24ee-53b3-82c2-dfeaaa0deb1c | date | Date Completed:
4502eb9c-1a63-494f-a0c2-476c101f2209 | checkpoint | 4.9 - Pits - Backfilling Around Drainage Pits
9bc28ce5-9ddd-5efc-a54f-c136c8a0b6b9 | note | Reference - VR Cl 705.18
8005de66-d09c-54f7-8219-9db0206eb1bb | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
7000e190-db33-5c90-b353-5b0fa9a9cd80 | note | Method - Visual inspection, Measure
87187dbb-4b2f-537d-9003-78a1de10b304 | note | Frequency - Each Lot
e540d030-4d4e-5f5f-a04b-6bb560efab2d | note | Category - IP
ca0db318-47ee-5ce3-b9a3-02b4aa4abdd6 | note | Responsibility - SE
91a8a1b0-b573-5146-8f50-3dcbf8880fc9 | note | Verifying Documents - This ITP
2b68e953-381d-5f61-a4b5-b8374bc93dcd | date | Date Completed:
60652fb5-868f-4f57-b274-cb26e6055eae | section | 5. Post-construction / Post-installation Activities
de2bf341-7ede-4692-ba3a-fe4f9f596672 | checkpoint | 5.1 - As Built Survey
5f4caf1a-5de9-58ca-a400-52405477bbb8 | note | Reference - VR Section 701.10
e72e3330-b6c2-5923-8e65-88695dfa57bd | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10
0b0824e0-cc5f-5994-96ac-f63f431b19a1 | note | ○ Attach: As-Built Survey Conformance
88c65183-e5f6-5af4-8d64-d8447c4ed30a | note | Method - Document Review
977b7b2b-5384-562b-b566-7859832a6705 | note | Frequency - Each lot
e7e6f2fd-c6d5-56e6-bc61-c9de75863015 | note | Category - IP
2708d654-2893-5e82-b72c-e77f49c3e2be | note | Responsibility - SE
cddbd329-2481-5a92-bef8-151f5d1069e8 | note | Verifying Documents - As-Built Survey Report
c2b29596-9a63-5b99-b777-9816752e74a9 | date | Date Completed:
3e411f5d-8842-4251-bf5d-b51da4ee82bc | checkpoint | 5.2 - Compaction and Moisture content tests
a6ca3161-a157-5d1f-a4ec-7d4396e8e932 | note | Reference - VR Cl 701.20
ce5aada7-e5d6-5fbd-a58f-3978d25ea559 | note | Acceptance Criteria - Bedding and backfill shall be placed and compacted in layers not exceeding 150mm loose thickness. Bedding and backfill shall be assessed for compaction and or moisture in lots (3 tests per lot). A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
e2b44f91-0101-5081-9989-2fee71fc0096 | note | ○ ATTACH: Compaction and Moisture content test results:
58e2b2ce-ea92-5972-834a-57a7b780a61f | note | Method - Document Review
7394dc1d-569a-5bc8-bc01-9b9f7a11baa2 | note | Frequency - Each Lot
54a35276-bb73-5a53-9798-c6057a7ff008 | note | Category - IP
7643ecd3-ad09-5e0f-ba80-8907819b4a98 | note | Responsibility - SE/PE
5a0cb60b-b91e-5b95-983b-51a22b5a432e | note | Verifying Documents - Test Results
88e6bbe3-4e73-5bad-ba17-4704090676fd | date | Date Completed:
cf77e68e-b70e-43f8-8dc8-adaf160e9135 | checkpoint | 5.3 - Repairs to Damaged pits
82b217d4-930a-50c7-96df-e535438b3394 | note | Reference - VR Section 705.16
a8bc4b3a-6ff4-5e41-abfc-2dee26c4580c | note | Acceptance Criteria - The method of repair of minor surface imperfections including porous spots, shallow honeycombing, rough areas and blow holes not conforming to the class of surface finish as specified in clause 705.14.
744d6d50-e480-5d43-b60a-4c5897c8f6d4 | note | ○ The cementitious patch repair of other concrete defects shall be in accordance with Section 689.
14ce5f16-f45c-5f51-981a-c1293b5fda13 | note | ○ Epoxy materials shall not be used for the patch repair of concrete.
25888de6-e2f6-5de1-bbdf-74ca91ee7de0 | note | ○ The exposed surface of the repaired area shall be similar in texture and colour to the surrounding concrete.
61d83d7f-0a94-5431-9373-f49bddfb3f33 | note | Method - Document Review for Repair Procedure, Visual Inspection
88bc1cb4-1380-5602-a001-a51868e96691 | note | Frequency - Each lot
77ccf374-b08e-54ca-b01f-f62777d871ff | note | Category - HP*
cd19ac73-e6f7-56a5-a3fe-75cdcb14a041 | note | Responsibility - SE/PE
2ad04291-62c1-527e-82d6-b27cabc8c825 | note | Verifying Documents - ConQA HP Release, Approved Repair Procedure
9e2abce3-78ed-5f4e-b90b-0c82e5699254 | date | Date Completed:
a438eb99-fc49-4c6b-a7c3-9222adabf1b0 | checkpoint | 5.4 - Non-conformance Report (NCR) Closure
718d1d40-b67a-56b1-b9ea-cd743dd4490c | note | Reference - MRPA Quality Management Plan
1b586730-620a-5212-a11f-7d8a6793a5e1 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
69e86029-a6cf-5c9d-990d-a439c9a9fc8f | textbox | Enter: TeamBinder NCR number (if applicable)
69bd00b9-9c17-5030-963c-318d769ac3f0 | note | Method - Document Review
8f84b2e1-0124-5fe8-9147-61ef6e423655 | note | Frequency - Once, prior to closure of this lot / element / Work area
56688b0c-03cb-51e6-bd58-5f6750ea4475 | note | Category - HP*
b3c4e05b-5687-5b76-ae06-73c35674b184 | note | Responsibility - PE
2a9cd7cc-9200-5f59-881a-18d6c7561065 | note | Verifying Documents - This ITP
7f30fd34-54b2-526d-9422-0323c7d53beb | date | Date Completed:
8b71f96e-a2f3-4479-8b11-cc773e787308 | checkpoint | Final Inspection
124809f1-43b0-5647-a5e3-f99fddd0a0cf | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
01c28a24-8cf1-5217-a79e-6e557e259be3 | textbox | Name:
de23e9ab-f2d3-55b3-b272-dd4d4a7baa7b | textbox | Position:
a19a5347-d708-5a5b-b7f4-a932ed443d01 | textbox | Date Completed:
26dc68f8-d1f2-4268-b490-a7cf98dfbbd7 | signoff | Sign ITP
c92e5470-33e8-4947-8002-c279a3cecbb5 | checklist | ITP-246-CIV-FRMS-Supply & Installaton of Street Lighting (Vic Road) Rev 0 | itp | ITP-246-CIV-FRMS-Supply & Installaton of Street Lighting (Vic Road) | 7a150e2a-5bb4-40ef-a2fd-f00202af8da0
18c49056-bf87-44f6-a47e-d4f102f5136d | section | 1. Referenced Documentation
63d2bc5d-ed9a-4971-b6a7-55944c2b8285 | checkpoint-no-value | Referenced Documentation
ba1621e6-16a5-5d9f-82c6-08aa386cd8f7 | note | Document Title: ITP-246-CIV-Supply & Installaton of Street Lighting(Vic Road)
d889a601-febd-5098-bdd3-83fc56af572a | note | ITP Description: Supply & Installaton of Street Lighting(Vic Road)
32a50669-0d1b-5a3b-88a5-1fa176b1d335 | note | Discipline (e.g. CIV/STR/RAIL): 246-CIV
19fa8879-d01f-56ee-9de3-fb67634317d0 | note | Revision Number: 0
b9aeae28-c180-5037-9ab0-51ac68dd6a22 | note | Revision Date: 25/03/2025
967ed0ba-4a2b-5433-bf50-745c7ea57cf4 | note | ITP created by: Kamel Alshobaki
f5592489-7d21-55bc-b8f4-99d9b8348d84 | note | ITP approved for use by: Pradeep Talasila
ea3bd6a9-6ad9-5056-9051-ceb623a456c2 | note | 1.1 - Non Dependent
8f416353-576b-5c0a-9eba-30294e4182f7 | note | Reference - VicRoads Section 731 June 2017
2e624a00-ad7e-535b-9aec-00a37a914612 | note | 1.2 - Non Dependent
259f797b-3d17-541b-b2f5-8519f3234c90 | note | Reference - VicRoads Section 733 April 2019
eb127ece-bf30-42d8-aa9e-acd0e02f4f80 | section | 2. Preliminaries
30214adb-c432-4755-ae68-1b6938a86b1e | checkpoint | 2.1 - Obtain and review manufacturer documentations for the supply of materials
e53759e8-ea0f-56dd-9dcc-52f1a5fe5861 | note | Reference - Vic road 733.02 AS/NZS 2053, AS/NZS 1345
8eb7c312-6d82-5715-bece-3052d5cb06ea | note | ○ Vic road 731.02 AS/NZS 3000
422229fd-e943-52f3-a956-94950eca00d7 | note | ○ Vic road 630.07 AS 1627.1, AS 1627.4, AS/NZS 1554.1, AS 1214
b1bbe64e-927f-53f5-8540-a3c9ea04eab3 | note | Acceptance Criteria - Materials comply with Vicroad Section 733.02,731.11, 630.07 and relevant specifications.
18fe11fb-465b-52c6-9589-6f8b717f00d0 | note | ○ All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
74c9fc5f-1a4d-5113-9385-087a2118849e | textbox | Enter: Teambinder Material Approval number
92226b43-23e8-5340-b982-8bbe3682b601 | note | Method - Document Review
370f9ca4-c772-5efd-977f-e353a1e5490b | note | Frequency - Per Source
e5b6a0c4-01ca-54b4-b83e-745c9c5a6636 | note | Category - HP*
fa580efb-8373-5274-8831-884e06fd8d49 | note | Responsibility - Nominated Authority
c1b2f6b1-a7e9-5864-ac41-bfc86c855e94 | note | Verifying Documents - ConQA Hold Point Release
2003650d-40e1-5aa7-9cb3-fc26c64a00d4 | date | Date Completed:
7fc6499c-ffec-4967-b755-2d22e3d64248 | checkpoint | 2.2 - Inspect supplied items upon delivery
e9c14218-07f4-5610-9d82-9136ebbf40b1 | note | Reference - QMP
9877c23b-a7f5-567b-9594-91df56ce09b3 | note | Acceptance Criteria - Supplied items are to correct spec, class, size and undamaged
a3a12657-00f9-5511-8810-de04a8ad456f | note | Method - Visual /Site Inspection & Document Review
9fd9f673-f11e-5642-8d59-7836095fe491 | note | Frequency - Per Delivery
9ea6dc24-a149-52dd-9a2f-2990a4163fe7 | note | Category - IP
bc6fdcff-40f6-5b9c-a3c6-7e86eb5eb060 | note | Responsibility - SE/PE/SPE
35aa084f-640d-5ce8-9232-5a00b462457f | note | Verifying Documents - Material Inspection Report
7cb34ba5-e4db-591c-8d68-305c6f58d768 | date | Date Completed:
8ff2f2e2-68a6-4fe2-b07f-0a07c9105ccb | section | 3. Conduit Pit Installation
df8fdcf6-90dc-43f3-b823-c9b1b4d5dd18 | checkpoint | 3.1 - Conduit & pit installation
ce67b44b-2e4b-5ad9-bbaf-24c1b8cd567b | note | Reference - Vic road section 733 April 2019
a9efabcf-78da-583e-982d-a16b53b383b6 | note | Acceptance Criteria - This Item will be completed under the checklist conduit & pit Installation (Road)
ff925896-73ba-539c-8547-fed1b3d6cb18 | note | Method - Document Review
aacbdddf-e46b-5d37-928e-2d92299a4531 | note | Frequency - Per Lot
b8f5c5d6-e016-521c-b124-4557120d51bb | note | Category - IP
2be7a104-299e-5f8f-9a03-d6be5871d533 | note | Responsibility - SE/PE/SPE
d43ae9ef-c1a6-5cf9-a6be-76017570d3cc | note | Verifying Documents - This ITP
43dbb760-86f8-533a-807b-c9fa45b48fed | date | Date Completed:
3cdfbcf5-7c20-4ef3-aab1-72117dc0a7eb | section | 4. Foundation
b2faf3ad-9ff0-4c26-88e8-babe0130a607 | checkpoint | 4.1 - Prepare the plinth foundation(Excavation & levels)
29d7c39a-debb-546e-975e-2bcecf39a9a9 | note | Reference - VicRoads Standard Drawings IFC
43c86328-7078-5626-8fcf-35a06e78c3e4 | note | Acceptance Criteria - Check levels conform to relevant drawing depending on type of pole to be installed.
7b3fdbc8-0a0f-58b2-a965-d2c543242b0d | note | Method - Visual, Survey
b1bedb9c-d48e-55e9-af5f-e84fc83c6599 | note | Frequency - Per Lot
dba537d9-bc29-5461-91bb-623af8ece939 | note | Category - IP
6012b4b6-6da7-5daa-bf0d-32054a94cf2e | note | Responsibility - SE/PE/SPE
adaf8fd5-f1ed-5972-be8e-0ce15b503458 | note | Verifying Documents - This ITP
a7576002-06d5-5949-b505-457c810db92c | date | Date Completed:
76c2ffd6-ce9d-427c-979f-2b2bfc79ac4d | checkpoint | 4.2 - Installation Street lighting pole bases
675c4b3f-be14-529a-bf73-b0b51c6c363c | note | Reference - VicRoads Standard Cl731.11
65636672-29eb-5362-aa3a-8b9ca420c268 | note | ○ VicRoads Standard Cl731.6
fe5c694e-9d84-507c-bbfd-807b43ca5908 | note | ○ VicRoads Spec Cl733.6
ade0a2e4-ff17-57aa-affc-7cc51328f15f | note | Acceptance Criteria - Pits located 1 metre in advance of, and 1 metre off the line of the pole and in accordance to TC-1210,TC 1220 & TC-1230. A two(2)meter of spare length of each cable shall be left coiled in each pit.
9023411a-ab49-5487-bfc1-7b919a1111e1 | note | ○ The slip plane of a slip base pole is to be located 75mm ± 25mm above the surrounding finished surface level
8ee06280-c568-5b15-9e57-1a3d41008dec | note | ○ All poles/luminaries to be individually earthed to the earth cable in the pit
95765835-c377-59fd-aeb3-a43afe3655ed | note | Method - Visual /Site Inspection & Document Review
9909ef4a-a8b4-5981-81c7-73cda09bcb6d | note | Frequency - Per Lot
b59dccbf-04ad-57a9-8c76-0f2e6910a1b6 | note | Category - IP
76fb0056-44d3-5d6b-8a7f-b01ec42cbb3b | note | Responsibility - SE/PE/SPE
070ac958-831a-5323-91a5-0f6d57497aba | note | Verifying Documents - This ITP
b4ce112e-6e80-50f2-ba92-dd34770f7fe0 | date | Date Completed:
66e2aff1-6848-45b4-84f1-696a1606050a | checkpoint | 4.3 - Installation of frangible poles (Slip base and Impact Absorbing)
4c9935f1-0620-5631-ad9d-714dc3b16f8a | note | Reference - VicRoads Specs. Cl 731.06b
f064030a-6f15-567d-a3ff-5e5a1334d253 | note | ○ Requirements
69138f05-2dcc-52b4-91ea-73ac94bd1274 | note | — TC-1065
f1014ae3-ca32-5c8b-a8cc-408e00b8c6fa | note | — TC-1066
d48cf5f1-d56a-5b2b-8aaa-feeecfda6eee | note | — TC-1072
f2f32db1-177f-5df3-b843-7b7cf7f4f2ae | note | — TC-1071
235ee4c1-ec97-581c-8c07-8d89c56ddab5 | note | ○ TCS014 Supply of Frangible street lighting poles
88407556-eadb-565c-bdf0-18d0e889e7cd | note | Acceptance Criteria - The slip plane of a slip base pole is to be located 75mm ± 25mm above the surrounding finished surface level as per VicRoads Standard Drawing TC-1072
a19030b5-f361-5a67-b29b-67ffd7204961 | note | ○ The holding down bolts and nuts on the flange are to be slackened of one at a time and re-tightened using a torque wrench to 40Mn for Main nut (Half Nut) and 90Nm for Lock nut (Full Nut)
80be1ad7-8418-5093-a4f4-b67efab2739a | note | ○ Record torque of each Slip Base pole in report
a7c99da3-be5c-5130-bf91-1e5ca69523d9 | note | ○ Locking nuts to be installed on all hold down bolts
554390c9-758f-5343-9406-2250353b7e9e | note | ○ Lock nuts to be installed on Slip base as per VicRoads Drawing TC-1065: Slip base pole assembly, Ground set mounted and VicRoads Drawing TC-1064a: Impact Absorbing
ff804a2f-e52b-5582-a647-00d18c5c163b | note | Method - Visual /Site Inspection & Document Review
a7b246ac-a124-5724-b56d-6e51c131daff | note | Frequency - Per Lot
f70d7961-aa7b-576a-838c-930f4098f668 | note | Category - IP
a635015c-3e43-5bed-b9cf-e07ba1a06ca3 | note | Responsibility - SE/PE/SPE
7f725fbe-e368-5fec-a18e-f99e595c9147 | note | Verifying Documents - This ITP
c2389e06-73de-54f2-a02e-b37daf961862 | date | Date Completed:
65453db2-eaad-4bfb-8c31-d825ab7bc2b1 | checkpoint | 4.4 - Erection of Street lighting columns
9ddd445e-c24e-50d1-9c10-1ed5686013b7 | note | Reference - VicRoads Standard Drawing TC-1068
bb7f3160-44ba-599c-95d6-7397361859a8 | note | Acceptance Criteria - Installed on rigid columns as per VicRoads Standard Drawing TC-1068: Rigid Street Lighting Pole
b2b1d978-786c-5aa4-ac06-992272cf0bcd | note | Method - Visual /Site Inspection & Document Review
90fcf4b0-c5c3-5bc8-a3af-27d3fc6b6ac2 | note | Frequency - Per Lot
89b00c72-12c0-56be-86ec-e45adf36d539 | note | Category - IP
1d798826-10f6-5aa8-a00a-ca0c1a7ef9ab | note | Responsibility - SE/PE/SPE
ca643f98-aa60-5930-8614-731b0d1e0619 | note | Verifying Documents - This ITP
c72c55a0-8d8d-5338-a6a5-03d2cdb9f2a4 | date | Date Completed:
5537245c-c359-4d9e-a843-25c448dd5951 | checkpoint | 4.5 - Assembly of outreaches and luminaires
2aa0ea2d-3d37-5199-b992-24aa5925412c | note | Reference - VicRoads Specs. Table 731.061
3c77bbbb-cfd3-505f-9920-56a69cd1dad4 | note | ○ Requirements TCS065
0bb28449-5c91-525b-bb59-280cb4e90b5d | note | Acceptance Criteria - Outreach bracket to be installed to the pole spigot using the clamping bolt assemble
a6d99e7e-4cd2-5035-bf79-929773af2a53 | note | ○ Bracket and luminaire to align at right angles to vehicle path on road
5c12050d-42fa-51c0-8f0a-36c1576b2d51 | note | ○ Luminaire orientation to comply with Table 731.061 from VicRoads Standard, Section 731 - Road Lighting Installation
7d06b1f6-b4b1-5011-a312-c4b7bad38605 | note | ○ Luminaires to conform to TCS 065 - Supply of LED Road Lighting Luminaires
e81976a6-eb74-5bb9-98f1-3b3d244f2f67 | note | ○ Luminaires shall be supplied with the PE cell bypassed or deactivated
88e812e4-c34f-52ce-a8c1-d6d247814001 | note | Method -
bb984953-7449-536d-ac65-123144d675d0 | note | Frequency - Per Lot
58e0ee38-9486-5b7d-a66a-8b49629cdd90 | note | Category - IP
1209ffa3-9449-5666-a100-b9ed82c16f0c | note | Responsibility - SE/PE/SPE
4bf7894c-2f22-5bd6-ba6f-fa4f005f4aba | note | Verifying Documents - This ITP
b37e9081-c32a-5b07-85bf-441857ca8362 | date | Date Completed:
06891a58-72eb-4f71-a42f-1076ad5d9bb5 | checkpoint | 4.6 - Installation of lighting distribution cabinet
273063cd-f34a-5851-b09b-c6a1cf165fdc | note | Reference - VicRoads Specs Cl.731.11 IFC Drawing
71574f5a-ee01-5ec3-a73a-cbfe9a565220 | note | Acceptance Criteria - The lighting distribution cabinets shall be supplied and installed in accordance with VicRoads Specification TCS 043 - Specification for Distribution Box for Road Lighting Power Supply.
d4e7a523-62a9-5857-a11c-e7153a76a4ba | note | ○ The foundation of the distribution cabinet shall be installed as specified in VicRoads Standard Drawing TC-1062.
c780b607-c4da-57b1-b60e-dd18f901816e | note | ○ Distribution cabinets shall be located not less than 5 metres from any carriageway and where possible beyond the clear zone for the particular road. For any distribution cabinet within the clear zone, the Contractor shall provide traffic barriers to protect the distribution
cf04ec0b-47b0-5f0f-b499-c75b47750ec8 | note | Method - Visual
41a2a25d-f107-50a9-b323-88cec923d0b8 | note | Frequency - Per lot
96eb1405-8502-5ce9-94b3-eac5e874a5d2 | note | Category - IP
e9f12887-5d56-50a9-b3f7-8b51736a098b | note | Responsibility - SE/PE/SPE
ed5431b2-2105-5a77-9882-0ca130667347 | note | Verifying Documents - This ITP
9e72b142-8971-56ce-ae53-60070409bddb | date | Date Completed:
941797e5-7488-4194-8d50-5c1a42b41f21 | checkpoint | 4.7 - Installation of cabling
c43cb06d-ea32-5333-a276-1056407eaabd | note | Reference - VicRoads Specs. Cl.731.11
538fae7a-2cb3-5931-abd2-66a8547bd0bf | note | Acceptance Criteria - All electrical cabling to be in accordance with the requirements of AS/NZS 3000: (Australian/New Zealand Wiring Rules)
5e35ca9b-27ff-56b6-89e4-0e4738b82038 | note | ○ Each pole to be cables from the pole circuit breaker
6760a72d-a8df-5e5f-ba30-205e804c5f77 | note | ○ All electrical cable joints to be water proof
f6e1930f-ab7d-551c-9188-e34fcf8b8324 | note | ○ JUP, JUMA or slip base pole: Cable to be supported by nylon cord or steel catenary. Cable to be attached the support wire with cable ties, no less then intervals of 4m
e5536c01-2d42-58a4-968d-a8ff54c67829 | note | ○ IA pole: Cable to be supplied through flexible conduit fitted inside the pole from cable termination access door to pole spigot.
5438e479-af9c-50e3-ab44-416e2a295aa5 | note | ○ Cable for trunk electricity supply from “point of supply” to distribution box to be not less than 16mm square 4 core, three phase copper XPLE cable
600fe2bf-dae9-55f6-8f30-467205943ea3 | note | Method - Visual & Document Review
71183de5-bd1a-5161-8281-a957df08015c | note | Frequency - Per Lot
4406e474-3999-51c7-b430-91b9afba5c84 | note | Category - IP
29072762-657d-5a21-8adf-1a135e874b37 | note | Responsibility - SE/PE/SPE
553c51a0-21d1-5d5e-9dc5-3f956541217f | note | Verifying Documents - Test Certificate, This ITP
63c66762-a423-572d-9c30-952000646a0a | date | Date Completed:
5d4671de-330b-4ced-b287-fe04a915a424 | checkpoint | 4.8 - Labelling of Assets
c1541079-70b5-509e-82fb-b0517e84f2aa | note | Reference - VicRoads Specs. Cl.731.12
07710747-9500-5a47-943b-14fcde8dc2e0 | note | Acceptance Criteria - Labels fixed to poles as per VicRoads Section 731.12
d1243843-6e8a-56be-a1cc-f56ede3678ea | note | Method - Visual /Site Inspection & Document Review
66a2b7aa-54db-592b-810b-251cdc24400c | note | Frequency - Per Lot
cedef795-c3f2-5840-9c23-7678d2f351a8 | note | Category - IP
b80ed199-034f-521a-ac52-da647af0d1d1 | note | Responsibility - SE/PE/SPE
d2bd28ca-3cfd-5cee-b6bf-f5236c94fba0 | note | Verifying Documents - This ITP
bee94a0f-c1c5-544f-8dfa-c1e3132090a9 | date | Date Completed:
5ae1ac78-8821-42cb-a8b4-245c3bf4b2b8 | section | 5. Completion
60582385-5640-4113-865e-d108c4c30a41 | checkpoint | 5.1 - Commissioning & testing(if Applicable)
ca60e5bd-777c-56c8-881d-511363ed0ab2 | note | Reference - VicRoads Specs. Cl.731.16a & c
5b18cce5-4eba-57c5-b577-520e32f3215e | note | Acceptance Criteria - Upon final acceptance, the Contractor shall switch on the lighting installation at the distribution cabinet in automatic mode, and record the time, date and meter reading for contractual, warranty and power supply purposes and supply this record to the Superintendent within 48 hours
fec76ee7-a506-5ab4-98e3-656957ed610b | note | Method - Commissioning & testing
43892e17-4ed0-5a0a-a43c-51ef596e3ec4 | note | Frequency - Upon completion of each section
c68b5215-5a27-5d6b-8524-572716b7c58d | note | Category - HP*
930d4f86-9289-55a2-b2cb-9be54306e30f | note | Responsibility - SE/PE/SPE, Services Engineer
78a68b0f-ba4d-5ce0-9fa5-e88a8c4561ce | note | Verifying Documents - ConQA Hold Point Release
2d1fb885-585e-5b3d-913e-bbe8048431a6 | date | Date Completed:
04271ed9-4f9b-46b5-9fc3-ab110c9d0fb2 | checkpoint | 5.2 - As-Constructed Plans
14eeea4a-3600-5b57-b62b-1c64211782c4 | note | Reference - VicRoads Specs. Cl.731.16d
2bf85186-0489-51ee-847d-b72494018fbe | note | Acceptance Criteria - The Contractor shall supply to the Superintendent two copies of ‘As-Constructed’ plans along with a USB drive or other approved storage medium containing the CADD drawing files, and the same shall be supplied by the Contractor to the local distribution company if appropriate.
7b28ffb7-07a1-58d5-9666-0edf5bf9b40b | note | Method - Document Review
8d7d48ba-2b56-5db9-8b56-4c4a3ec22d6b | note | Frequency - Upon completion/ Work area
a3b43d45-91a7-597c-8130-9ca70ed5fb22 | note | Category - AP
fe292ffa-195c-554f-8fef-3fad8e2b5c46 | note | Responsibility - SE/PE/SPE
edb85f40-abb9-5821-b6bc-bf0408ca3475 | note | Verifying Documents - ConQA Hold Point Release
ed6e3361-a8b9-5e67-8606-979cbd5b67ab | date | Date Completed:
1c6049d8-5d90-46b3-86e1-ccd7bd1914de | checkpoint | 5.3 - Non-conformance Report (NCR) Closure
ea37ca8a-4a37-55e2-b84b-c063da2454c5 | note | Reference - MRPA Quality Management Plan
95c2774d-4de1-5f3b-9864-0eaa60783e7e | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
54597edd-665e-5d96-aef9-9a87ff5545d9 | note | Method - Document Review
29580f64-8ec6-5200-a515-a59a0674c431 | note | Frequency - Once, prior to closure of this lot / element / Work area
2cf51c38-a522-5adf-9164-de0ecf58f8b8 | note | Category - HP*
f8cd1078-5078-505c-97a8-84ca689175f2 | note | Responsibility - SE/PE/SPE
f50b2a9b-f2eb-5908-89e2-ceadd2a3e473 | note | Verifying Documents - This ITP
364023d3-44c2-53f5-a3a5-c4bf8bcfb903 | date | Date Completed:
e3197bdf-ede4-4a81-9385-51f46af97d72 | checkpoint | Final Inspection
ef000ccf-24d9-583b-87e9-28a63f11e84d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5e7f6b8a-0848-525f-8e3e-b391e619c23e | textbox | Name:
ecd06840-c0de-5fe5-aa12-412c6b42d12a | textbox | Position:
9f1b62a2-fdd3-5beb-b6ee-a03049617c54 | textbox | Date Completed:
72f10bfe-566d-446a-9a6d-8a307d4deb1e | signoff | Sign ITP
dd5fb8ef-5729-439e-bf5d-330373c591ed | checklist | ITP-247-CIV-FRMS-Traffic Signals - Commission (Supply and Install) Rev 0 | itp | ITP-247-CIV-FRMS-Traffic Signals - Commission (Supply and Install) | f967406d-0dc9-45ed-a10e-bd3c7762b7e7
7786d2cd-dc93-4024-a9f9-597738cb17f4 | section | 1. Referenced Documentation
f3074cad-ac51-4714-9e21-8ed4c99ca9bd | checkpoint-no-value | Referenced Documentation
476b5fb9-2ca9-5312-b9b2-11aceb3bd4d7 | note | Document Title: ITP-247-CIV Traffic Signals - Commission (Supply and Install)
02f86e4b-99d9-5529-b609-607295d31f75 | note | ITP Description: Traffic Signals - Commission (Supply and Install)
b9a37b9a-8b2a-5c1b-9b3c-e432c745a07f | note | Discipline (e.g. CIV/STR/RAIL): 247-CIV
0f859ebc-a5b5-5328-95dd-2eb0a4a2d4b0 | note | Revision Number: 0
b3da4f85-e358-575b-9982-ee7817299606 | note | Revision Date: 28/03/2025
035b338e-aede-597e-83f1-b2a2e9addeb5 | note | ITP created by: Kamel Alshobaki
1d018c11-20fa-5a9c-b90f-f77ecf91c6f9 | note | ITP approved for use by: Pradeep Talasila
496a0435-3125-58bc-a21d-e8afac903a05 | note | 1.1 - Non Dependent
8f0833a5-1638-58e7-b128-c0fa808c121e | note | Reference - VicRoads Section 730 October 2013
8af7041c-ef7c-5e6d-a5c7-8e072e35c3ef | note | 1.2 - Non Dependent
f42f8e03-a22e-5ad4-8d35-7204142c5540 | note | Reference - AS3000
401a52ea-074c-4c37-96db-229e648eb5b8 | section | 2. Signalling Electrical System
d3c8a3bb-0a5b-4d0b-af94-f088f6f87b7b | checkpoint | 2.1 - Point of Supply
716f6a7b-d56d-5c38-a1eb-8943d2e4b8d5 | note | Reference - Section 730.14 (a), SD TC-1207
087347d6-a62b-59e2-b870-e8807a2630ad | note | Acceptance Criteria - The Contractor shall arrange for the installation of the point of supply with the local power distribution company, at the location approved at the pre-installation meeting
6be3a0db-b0dd-54e9-8646-303838112b9e | note | ○ The point of supply shall be installed in accordance with SD TC-1206 and arranged with the local power distribution company to meet the specific requirements.
724f4386-35fd-57d7-917c-4a0f2d9825d1 | note | Method - Review
03faf906-aeab-5c20-be12-142521e8ba06 | note | Frequency - Per item
d836f641-4853-5059-86cb-75c6b27f29da | note | Category - IP
f53758c5-b8c8-5c40-8cf2-094b1cc2ebf2 | note | Responsibility - SE/Supervisor
14c4c971-a57e-5a56-8ea0-9a39e657a303 | note | Verifying Documents - This ITP
ac3a37fe-f4b5-58ba-b66e-60e911e92995 | date | Date Completed:
92cba62f-03da-4708-af01-218644453cea | checkpoint | 2.2 - Communications Line
d32f9986-bad9-51f3-b358-7cc98ab26e4f | note | Reference - Section 730.14 (b), SD TC-1207
e8089913-fcfb-50fb-9cca-6c76b9065c33 | note | Acceptance Criteria - A communications conduit along with a two pair telecommunications cable is to be installed from the signal controller to the nearest sutable communication supplier's pit as per SD TC-1207
c6dc0d43-311a-5e03-900e-c57737a33579 | note | Method - Visual
ea24952b-8ca5-51d9-a104-872b8bf84cd5 | note | Frequency - Per item
d368c42e-0141-578a-bfa9-13970d9e6b3f | note | Category - IP
9845d2b9-e95b-5db2-a66c-ab37335cc998 | note | Responsibility - SE/Supervisor
ba72c349-37bd-5e5d-a03f-e2d2f66e445f | note | Verifying Documents - This ITP
6af8c951-0dac-589d-a22c-149f3314654b | date | Date Completed:
a31ef9a6-87f6-4bf5-9534-72db0cbd9736 | checkpoint | 2.3 - Cable Installation
8c39dc6a-e751-5f76-8cfb-e4bfeb403e93 | note | Reference - Section 730.14 (c)
822eee70-9137-56ad-9f0c-3aa81b9f6993 | note | Acceptance Criteria - Site cabling is to be completed in accordance with Section 730.14 (c), ensuring all cables are installed with no damage to sheathing and insulation, restrained at the point of termination (top of pedestal and MA/JUP access points) to ensure minimal stress on terminations, as well as sufficient cable provided to reach 1.5m above the signal controller base
33768cd0-4b91-51f8-ab10-73dad59b8f79 | note | Method - Visual
26e067d2-5517-535a-829b-be720a9d6363 | note | Frequency - Per cable
06ef4cf4-04f2-582d-b31a-b1ebf52e95fb | note | Category - IP
6fdda770-f48f-5957-9c46-8031c8a2a674 | note | Responsibility - SE/Supervisor
260f284e-2be8-5492-a62d-7bea34694df5 | note | Verifying Documents - This ITP
600e55c4-1e76-5922-a309-ca30cb84c009 | date | Date Completed:
9505429e-48c3-408a-8b2b-c0d41ccf80b8 | checkpoint | 2.4 - Cable Sizes and Wiring
a1d3749a-04f9-5568-ad54-d442124bcd71 | note | Reference - Section 730.14 (d)
b934af9b-75c0-5473-904d-7c5357449a44 | note | Acceptance Criteria - 51 core cable is to be used at intersection traffic signals and its sequencial assemblies. 29 (dual carriageway) or 19 (single carriageway) core cable is to be used at pedestrian operated signals and its sequencial assemblies
5c4f0ea6-b75f-511f-bad9-4a777d11f856 | note | Method - Visual
94c64aa8-a12f-5aac-ad90-2a93d195106e | note | Frequency - Per cable
2c8cccbd-885a-5a64-8563-a21bfcde58e3 | note | Category - IP
dee1552f-a866-52c7-a66e-c780163d6cea | note | Responsibility - SE/Supervisor
f5385b93-e4ed-5085-aa77-cfed000ec6ab | note | Verifying Documents - This ITP
b2f18709-4fba-51e3-b114-ef0ee6f07bb6 | date | Date Completed:
c0540bd1-87c4-4875-9c50-b2798734819e | checkpoint | 2.5 - Pedestrian push button terminations
81724f62-f303-50de-a3aa-e53c8ff3fa8c | note | Reference - Section 730.14 (e) Table 730.141
0ad78798-0f99-5841-906e-8afda9de5964 | note | Acceptance Criteria - Pedestrian push button detectors are to be connected by 5 core cable and terminated at the required locations.
45549edc-7390-50a2-b826-7c18f8b8177a | note | Method - Visual
cfefdeca-49dd-5f09-920c-ec4ba78f0718 | note | Frequency - Per cable
4e8f4cad-e69b-502d-bc0d-954390f1b14e | note | Category - IP
04d4522f-0976-521d-aba4-c1e7eb27bd31 | note | Responsibility - SE/Supervisor
c9c46c4e-39a3-52bf-b19e-e6d1bb4527f8 | note | Verifying Documents - This ITP
94a91393-e01d-5db0-858f-38e0e57e05fa | date | Date Completed:
9e0132eb-8907-4aee-97da-4931745f7924 | checkpoint | 2.6 - Connecting of traffic signal controller
878335a3-1a7a-555b-8878-5864ad06c45a | note | Reference - Section 730.14 (f)
fd01f5db-bf30-518c-93a2-96a30382a8a3 | note | Acceptance Criteria - Contractor shall install a 3 core supply cable in a 50mm conduit between the supply point and signal controller base. 1.5m of supply cable shall be coiled in the pit closest to the controller base.
0e296785-c0ac-57ee-97a1-13827f27b6a6 | note | Method - Visual
29d5647c-228e-5147-a153-879b01f4f1fd | note | Frequency - Per cable
4faafb8e-3cf1-53c2-a79a-ceadd57971f5 | note | Category - IP
2514999e-09f6-5f4c-af93-7c9c718ba982 | note | Responsibility - SE/Supervisor
fe095af5-3c03-58a8-ab13-217986933fb8 | note | Verifying Documents - This ITP
f7567897-061b-5eec-8739-e83c32d995f3 | date | Date Completed:
5b8bb768-11c6-4ecb-b445-c4a39c186070 | checkpoint | 2.7 - Testing of Electrical Works
74c3253a-c0a2-529f-ba1b-29b07426a61c | note | Reference - Section 730.14 (l), AS3000 Cl 8.3.3
33aeaa61-db48-5434-9a1a-f842b648ba16 | note | Acceptance Criteria - The following tests are to be carried out prior to the installation of lanterns and hardware:
6c060ffd-d7c5-5b41-b2b7-1a4c699ae776 | note | — continuity of all active, neutral and ELV conductors as well as earthing system.
31bcd23d-3e69-526b-989b-52d5d6a9b232 | note | ○ Attach: Electrical Test Report
ff9ce397-9520-5e70-8f7d-e184b12fe84c | note | ○ Following the installation of all lanterns and hardware, the Contractor shall carry out a flash test.
5bed596b-3759-5e4a-ae9b-0d8ee1bb0233 | note | Method - Records
5db33fb2-1b80-56dc-a8de-6e97eabe52c7 | note | Frequency - Per installation
5c9e14f5-9634-5554-a2f2-6161787a7372 | note | Category - HP*
e18c6ec6-9dd6-5551-8ece-7dbaa7386046 | note | Responsibility - SE/Supervisor
8c027bbb-f772-5703-ae39-28a9d4803561 | note | Verifying Documents - Electrical Test Report
245cdb9b-7691-5b87-9c91-45cce5e7121c | date | Date Completed:
60815520-91e6-4de6-8588-1a292df6f43d | section | 3. Detector Loop Installation
459197ab-fc0e-47fa-9ed7-5ac0f3610330 | checkpoint | 3.1 - Cutting of detector loops
4c778cf9-5c0d-52c6-99aa-c123e3dedded | note | Reference - Section 730.14 (j), VicRoads TCS 054
e386bb04-0947-58a5-9272-0c237717ec8d | note | Acceptance Criteria - Detector loops are to be cut as per the locations shown on the design drawings to the TCS 054 specification.
eb38dfae-a472-5ba7-bc5e-9cf6f5f7e6fc | note | Method - Visual
d14ac714-d4fa-533f-982a-689979619dcf | note | Frequency - Per loop
4431a35a-ba1c-54c8-aed6-aa2da22a1c53 | note | Category - IP
4346d10f-0db6-5243-9a6a-d9af8a881f2e | note | Responsibility - SE/Supervisor
8915a25e-3011-5296-ba22-1ebfa40e0f00 | note | Verifying Documents - This ITP
dc639f4b-6fee-50d4-ad81-9ac3f699eea1 | date | Date Completed:
ac5f5787-289b-4cc6-9e86-8fd4e5caa9cd | checkpoint | 3.2 - Installation of detector feeder cables
d2b3e08e-9793-513e-a865-21ca0c30a051 | note | Reference - Section 730.14 (g), SD TC-1300
84be0c18-80d7-50e8-9ec3-240240aa8f22 | note | Acceptance Criteria - Detector feeder cables are to be installed to connect detector loops to the traffic signal controller. Installation is as follows:
8228e338-4c86-54ff-aa25-d814c4cd0451 | note | ○ Install 1 cable per loop and each cable pair shall be clearly and durably marked at both ends to enable positive identification
4ed2d0e3-8048-51ab-a1a0-1329a9f4fafd | note | ○ Connection of the detector loop cables to the detector feeder cables by soldering
8e14be44-4739-5922-b388-db3bc98a73a8 | note | ○ 4 wires for each loop (as per SD TC-1300) shall be tied together in a knot close to the conduit end
3fdfd2bd-0897-5817-a0da-8d2ebfebafec | note | ○ Terminations (joined or unjoined) shall be seperately insulated and sealed against the ingress of moisture with heat shrink
56436780-2eff-562b-bbba-a0861ac93541 | note | ○ Detector cables to have sufficient length to allow 1.5m to be coiled in the pit and 1.5m to reach the top of the controller base
0a519929-f696-57dc-aa85-771ea250251a | note | ○ Cable diagram shall be provided once complete and visible to the controller installation contractor detailing the loop cable/feeder cable connections.
643971c3-e8e4-5c8f-88e8-7e404a108f9f | note | Method - Visual
68690748-fbf9-599f-87d6-fb797339b020 | note | Frequency - Per loop
db383d7c-223f-5576-ae7a-8303eaa1294c | note | Category - IP
38699ee4-66b5-5d12-91ef-f918eeebf8c8 | note | Responsibility - SE/Supervisor
d3f79c17-0ff3-5304-b803-20c870daeed2 | note | Verifying Documents - Sign ITP
ea210598-974e-5581-8730-62ccb2ab0555 | date | Date Completed:
c09e41b3-5b3b-444e-83a5-d9f89d1b5d70 | checkpoint | 3.3 - Cabling of Large Sites
538d50e3-d708-5cb7-844c-e61d6b3a17c0 | note | Reference - Section 730.14 (i)
5dd96c3d-e278-5a92-864b-3e67b3f7b010 | note | Acceptance Criteria - For large signal installations where the standard allocation of cores as specified in SD TC-1204 cannot readily be adopted, MRPA shall draw up a proposed cabling scheme for approval.
484ba14f-eacd-58de-9a07-d158fec3abdf | note | ○ Attach: Proposed Cabling Scheme Checklst
af3efd8a-c92b-59a0-abb8-25244e02c6d4 | note | Method - Records
810e272b-e69c-5719-b9b4-f4a43e13807c | note | Frequency - Per installation
4dff0e9d-e1a8-551d-a8d5-c60b422bf492 | note | Category - HP*
897b12e8-7818-5502-8c60-14fb1784c746 | note | Responsibility - SE/PE, NA
40054e5c-dd87-5e8c-9ae2-d4aef46a7d63 | note | Verifying Documents - Attach Proposed Cabling Scheme Checklist
3eae386a-c122-5bcd-be57-ee2a80875e24 | date | Date Completed:
401d6de7-b324-4f07-b62c-f4e3d71b3648 | section | 4. Pre-Commissioning
e236e3c8-80cc-4230-9478-1f99138b232d | checkpoint | 4.1 - Pre-Commisioning Site Inspection
e63f2059-2722-5b70-8ee8-68235fe2ac78 | note | Reference - Section 730.16 (a)
2a570319-a56e-5a31-a564-45e3acc9dfb3 | note | Acceptance Criteria - Inspection to be carried out between the relevant parties upon completion of the installation works.
1d3526d8-e92b-52dd-a914-7af762201d22 | note | ○ The Contractor is to notify NA and VR of the inspection.
d69dd369-2aec-5f16-aa38-d204975ed63c | note | Method - Records
514cd1a1-b60f-5aa5-b7fe-6869b0d86307 | note | Frequency - Per installation
37464533-8c3b-58fa-ba81-11670d2919d2 | note | Category - IP
09ce5914-7d40-500c-8b1f-780557a53da7 | note | Responsibility - P/E, NA, Supervisor, VR
c6b49c42-7fe4-51cd-80a0-93d328936079 | note | Verifying Documents - Attach Pre-Commissioning Installation Report
8fbd8561-cfb5-51f4-ba1e-63c1155841be | date | Date Completed:
4c85ed22-8a75-45b6-89fc-1b3d92df3cae | checkpoint | 4.2 - Provision of power
4344c56b-1e8d-5200-8d69-e22944625be9 | note | Reference - Section 730.16 (b)
47c4038e-e66d-55c0-b0fc-671c57624489 | note | Acceptance Criteria - Obtain connection of mains supply by submitting all necessary paperwork and payment of fees.
38cc1cf1-0857-5d88-920e-d8edaedfac06 | note | Method - Records
f551c1b8-4d90-5e6c-9ce6-8a5be72d47de | note | Frequency - Per installation
8411573a-8e7c-5688-be01-7f10fd2032db | note | Category - IP
3014c7e6-edb9-5a4b-a7b4-5c16557486a4 | note | Responsibility - PE, Supervisor
acad5d97-e5aa-55d1-a227-f50f69343f00 | note | Verifying Documents - Sign ITP
9adf46c1-7e32-5040-aed5-f8d159985b46 | date | Date Completed:
fd2f2317-13cc-48ec-8462-0255825951bb | checkpoint | 4.3 - Traffic Controller Installation
dfda7abf-589d-5554-9ddc-a9a22029c65b | note | Reference - Section 730.16 (c)
d493dac5-5693-5191-bbb1-1811598e2d95 | note | Acceptance Criteria - Contractor to notify VR when the site is completed, tested and ready for the traffic signal controller to be installed.
9414cb91-5328-5970-b2e5-4688ea72d42c | note | ○ Traffic signal controller to be installed by controller supplier or authorised representative.
5e9d57ca-4d19-5ac6-9977-b9de79a1990e | note | ○ Contractor shall arrange issuing the Certificate of Electrical Safety and the necessary paperwork to obtain connection.
6aa2d9e7-d84d-5f48-b027-ec0495ee4202 | note | Method - Records
09f5d4f4-cd9d-5496-9e71-1bbdaa62211c | note | Frequency - Per installation
6eb0444a-747a-570a-9b5a-2da2c25a34bb | note | Category - IP
72227423-6642-5871-953b-f723c2b49df6 | note | Responsibility - PE, Supervisor
37ab27af-8ed6-5c04-a4e9-0c290bdb4a58 | note | Verifying Documents - Attached Certificate of Electrical Safety
a16f543d-9e95-5369-aec8-51e028bc9b44 | date | Date Completed:
033ae11a-0190-4533-beee-13cd03cf140d | section | 5. Completion of Site Works and Commissioning
7faa8f7a-c8d5-4f1e-9196-d0c63fe008c3 | checkpoint | 5.1 - Switch-On
2854dc18-af95-5a55-b0d0-9c148f53a0d4 | note | Reference - Section 730.17 (a)
a4f8a570-9187-56ea-9894-7b5ed97ee4fe | note | Acceptance Criteria - Prior to switching the signals on, a 'flash test' of the installation shall be carried out to ensure that each lantern is connected to the correct cable core. The flash test shall be witnessed by the Nominated Authority and VR and confirmed as acceptable.
9ff99456-4f4a-5345-a985-2fa1c0c8a985 | note | ○ The controller supplier is to record the relevant details required for the Electrical Test Report.
6e428a3a-eefd-576e-bd42-6645e2d765dd | note | Method - Review
a2a310eb-01a0-5723-9493-b0668417b87b | note | Frequency - Per lantern
1b3dc3d0-a641-5137-bcb9-8a066ce90953 | note | Category - HP*
922df3e6-22a6-56e3-8596-4143e1c4250d | note | Responsibility - PE, NA, VR, Supervisor
f4cb7a22-9976-5fb2-b99c-7714373f47b3 | note | Verifying Documents - Attach Electrical Test Report
406e4a3c-3d12-5e40-ad20-13d244108baa | date | Date Completed:
5918d9e5-948a-4916-9d2b-3a5968e195f4 | checkpoint | 5.2 - Removal of redundant hardware
88bb95db-6b03-5652-a6bb-43b43b72cdbf | note | Reference - Section 730.17 (b)
e234f90f-a5ff-5dd4-96b1-b955e3a5a3d4 | note | Acceptance Criteria - All redundant components of hardware and equipment shall be removed unless specified on the design drawings.
026d581b-2ce8-5273-b931-77a29dc32ecd | note | Method - Visual
267450ae-0c5f-5bc1-be56-273c15533a4e | note | Frequency - Per installation
8158bad8-45a5-5ec5-b0a9-d724e026dfc8 | note | Category - IP
4675b959-4cb3-5849-a247-8fc51044de93 | note | Responsibility - SE/Supervisor
1148307e-1971-506e-a14f-579eb5d627c1 | note | Verifying Documents -
4825450b-b3eb-51a0-8494-61b65a571d42 | date | Date Completed:
ec19d033-dfaf-48e1-9e21-515702689236 | section | 6. Post-construction / Post-installation Activities
f5d6cede-a830-4131-b035-67be8ebdcbe0 | checkpoint | 6.1 - Survey as-built
0deec2fe-7a0d-5a8b-b900-b809e0f28ac3 | note | Reference - IFC Drawings
96b17a8a-5e33-5b2a-90bd-75d10bb2a2ca | note | Acceptance Criteria - Survey to As Built Traffic Signalling works.
355c5bcb-ee6e-50c3-9b68-3ad5fa995dda | note | ○ As Constructed Traffic Signal plan to be submitted to Vic Roads.
b51230d1-1fc6-51cb-bd7c-3a49296cd6fe | note | Method - Document Review
4869c9d2-584e-545a-bea3-0a72c83e1ed0 | note | Frequency - Each element
7a0f7651-c7f9-55c2-9264-c2a16a751b43 | note | Category - IP
829d4ed1-2d85-53ba-a9cb-dfd3b7f75668 | note | Responsibility - SE/Surveyor
70bcaeb9-bdb8-5151-969a-ea3f7f908e63 | note | Verifying Documents - Attach As Constructed Traffic Signal plan
e9a8edd0-9b4d-58b0-a749-c4eb795f2243 | date | Date Completed:
f904ab53-fb74-4138-8bf4-0438e786a3b8 | checkpoint | Final Inspection
963f0b49-37e6-5f2b-8276-7f216f1b4f81 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d9303bda-4ebf-57f9-90c1-20a705dc9d03 | textbox | Name:
8d19e3aa-4fa9-513d-a218-42be7fc4697a | textbox | Position:
eae8e37d-8673-5fd4-96c2-0600d486172c | textbox | Date Completed:
579e75c3-0d5a-444e-bd0f-d9c71cf7803f | signoff | Sign ITP