## Sheet1
1 | Permits CHAR(AMP) Services (1) | H | Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | Prior to any construction commencing | Document Review | Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | Permit attached or permit number noted. | 1 - Permits CHAR(AMP) Services (1) | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | FREQUENCY: Prior to any construction commencing | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | RECORDS: Permit attached or permit number noted. | 1 - Permits CHAR(AMP) Services (1)
1 | Permits CHAR(AMP) Services (2) | H | Locate and mark out all existing services | Prior to any construction commencing | - | B4u dig procedure - follow utility protocols and GPR Report | B4u dig plans CHAR(AMP) GPR report attached | 1 - Permits CHAR(AMP) Services (2) | ACTION (Hold, Monitor, Witness): H | DETAIL: Locate and mark out all existing services | FREQUENCY: Prior to any construction commencing | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): - | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols and GPR Report | RECORDS: B4u dig plans CHAR(AMP) GPR report attached | ACTION (Hold, Monitor, Witness): H
2 | Pre-Construction Sign Offs | H | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | 2 - Pre-Construction Sign Offs | ACTION (Hold, Monitor, Witness): H | DETAIL: Sub-Contract and Supplier Agreements | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed | RECORDS: Subcontract and Supplier Agreements | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
3 | Design | H | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT if not issued to IFC. | Drawing Register. | 3 - Design | ACTION (Hold, Monitor, Witness): H | DETAIL: Design is approved and Drawings are of the latest revision. | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT if not issued to IFC. | RECORDS: Drawing Register. | FREQUENCY: Prior to any construction commencing
4 | Survey Setout | H | Setout Pipe Alignment and Service Locations with inlet CHAR(AMP) outlet points and inverts as required to construct to design | Prior to commencement. | Survey | As per IFC Drawings and design AutoCAD file. | Survey Receipt. | 4 - Survey Setout | ACTION (Hold, Monitor, Witness): H | DETAIL: Setout Pipe Alignment and Service Locations with inlet CHAR(AMP) outlet points and inverts as required to construct to design | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey | CONFORMANCE CRITERIA: As per IFC Drawings and design AutoCAD file. | RECORDS: Survey Receipt. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
5 | Pipe and Manhole Material Compliance | H | Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards | Prior to commencement. | Document Review, Visual Inspection | Pipe shall be Check for freshly formed pipes and return if required 1).Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall and street catchpit be in accordance with TDM Standards | Manufacturers Data Sheets, Delivery Dockets | 5 - Pipe and Manhole Material Compliance | ACTION (Hold, Monitor, Witness): H | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection | CONFORMANCE CRITERIA: Pipe shall be Check for freshly formed pipes and return if required 1).Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall and street catchpit be in accordance with TDM Standards | RECORDS: Manufacturers Data Sheets, Delivery Dockets | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
6 | Locate Existing Services by Hand Digging / Hydro Vac | H | Ensure all services conflicting with the line of trench have been exposed by hand digging. | Prior to commencement. | Potholing / Survey | All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services. | As-built Drawings. Doc. Review | 6 - Locate Existing Services by Hand Digging / Hydro Vac | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging. | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services. | RECORDS: As-built Drawings. Doc. Review | RECORDS: Permit attached or permit number noted.
7 | Trenching CHAR(AMP) Excavation (1) | H | Excavation methodology | Daily | Prestart review | The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016) | Prestart RCP | 7 - Trenching CHAR(AMP) Excavation (1) | ACTION (Hold, Monitor, Witness): H | DETAIL: Excavation methodology | FREQUENCY: Daily | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016) | RECORDS: Prestart RCP | 1 - Permits CHAR(AMP) Services (2)
7 | Trenching CHAR(AMP) Excavation (2) | M | Trench Profile - Width | Daily / as trenching takes place. Different depth methodology | Visual Inspection, Excavation methodology | Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing | Construction Photos | 7 - Trenching CHAR(AMP) Excavation (2) | ACTION (Hold, Monitor, Witness): M | DETAIL: Trench Profile - Width | FREQUENCY: Daily / as trenching takes place. Different depth methodology | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing | RECORDS: Construction Photos | ACTION (Hold, Monitor, Witness): H
7 | Trenching CHAR(AMP) Excavation (3) | W | Trench Profile - Depth | Daily / as trenching takes place. | Visual Inspection, Measurement | Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings | FH Drainage Line Record / Construction Photos | 7 - Trenching CHAR(AMP) Excavation (3) | ACTION (Hold, Monitor, Witness): W | DETAIL: Trench Profile - Depth | FREQUENCY: Daily / as trenching takes place. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings | RECORDS: FH Drainage Line Record / Construction Photos | DETAIL: Locate and mark out all existing services
7 | Trenching CHAR(AMP) Excavation (4) | M | Trench Base | Every 10m | Scalar testing | Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2. | Test reports / Construction Photos | 7 - Trenching CHAR(AMP) Excavation (4) | ACTION (Hold, Monitor, Witness): M | DETAIL: Trench Base | FREQUENCY: Every 10m | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Scalar testing | CONFORMANCE CRITERIA: Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2. | RECORDS: Test reports / Construction Photos | FREQUENCY: Prior to any construction commencing
8 | Bedding for Concrete Pipe Laying CHAR(AMP) Manhole CHAR(AMP) Cesspit | W | Placing and compaction of Bedding Material. | Inspected continuously during placing and compaction of Bedding Material. | Visual Inspection | Bedding CHAR(AMP) Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725 | FH Drainage Line Record / Construction Photos | 8 - Bedding for Concrete Pipe Laying CHAR(AMP) Manhole CHAR(AMP) Cesspit | ACTION (Hold, Monitor, Witness): W | DETAIL: Placing and compaction of Bedding Material. | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection | CONFORMANCE CRITERIA: Bedding CHAR(AMP) Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725 | RECORDS: FH Drainage Line Record / Construction Photos | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): -
9 | Pipe Position Tolerance | M | - | At any point of pipe | - | Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design. | FH Drainage Line Record, Survey Data. | 9 - Pipe Position Tolerance | ACTION (Hold, Monitor, Witness): M | DETAIL: - | FREQUENCY: At any point of pipe | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): - | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design. | RECORDS: FH Drainage Line Record, Survey Data. | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols and GPR Report
10 | Trench Backfill - Placing CHAR(AMP) Compacting | M | Placing and compacting of Trench Backfill Material | Throughout Trench Backfilling operation. | Visual Inspection | Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm ATAP40 for subbase/basecourse. | Construction Photos | 10 - Trench Backfill - Placing CHAR(AMP) Compacting | ACTION (Hold, Monitor, Witness): M | DETAIL: Placing and compacting of Trench Backfill Material | FREQUENCY: Throughout Trench Backfilling operation. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm ATAP40 for subbase/basecourse. | RECORDS: Construction Photos | RECORDS: B4u dig plans CHAR(AMP) GPR report attached
13 | Subsoil Material Compliance (1) | H | Ensure Subsoil Drainage pipe complies with TDM RD010 | Upon delivery to site | Ensure delivery docket matches materials delivered | 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock | Delivery docket | 13 - Subsoil Material Compliance (1) | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD010 | FREQUENCY: Upon delivery to site | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock | RECORDS: Delivery docket | 2 - Pre-Construction Sign Offs
13 | Subsoil Material Compliance (2) | H | Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate | - | Visual inspection | Ensure clean drainage aggregate - F2 Sand | Delivery docket | 13 - Subsoil Material Compliance (2) | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate | FREQUENCY: - | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Sand | RECORDS: Delivery docket | ACTION (Hold, Monitor, Witness): H
14 | Trenching (1) | H | Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade | 10m intervals | Visual inspection and measurement | Record levels of base of trench on dip sheet. | Photo / subsoil log | 14 - Trenching (1) | ACTION (Hold, Monitor, Witness): H | DETAIL: Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade | FREQUENCY: 10m intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet. | RECORDS: Photo / subsoil log | DETAIL: Sub-Contract and Supplier Agreements
14 | Trenching (2) | H | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | 10m intervals | Visual inspection and measurement | Ensure trench line and levels match the design drawings | Photo / subsoil log | 14 - Trenching (2) | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | FREQUENCY: 10m intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings | RECORDS: Photo / subsoil log | FREQUENCY: Prior to commencement.
15 | Bedding, pipe installation and Backfill (1) | W | Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench. | 10m intervals | Visual inspection | Record levels of top of bedding on dip sheet | Photo / subsoil log | 15 - Bedding, pipe installation and Backfill (1) | ACTION (Hold, Monitor, Witness): W | DETAIL: Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench. | FREQUENCY: 10m intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet | RECORDS: Photo / subsoil log | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
15 | Bedding, pipe installation and Backfill (2) | W | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | 10m intervals | Visual inspection | Consistency with Subsoil Details | Photos | 15 - Bedding, pipe installation and Backfill (2) | ACTION (Hold, Monitor, Witness): W | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | FREQUENCY: 10m intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Consistency with Subsoil Details | RECORDS: Photos | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
15 | Bedding, pipe installation and Backfill (3) | W | Backfill by tipping AP20 as bedding CHAR(AMP) ATAP40 as pavement structure into the trench | - | Visual inspection | Ensure good coverage | Photos | 15 - Bedding, pipe installation and Backfill (3) | ACTION (Hold, Monitor, Witness): W | DETAIL: Backfill by tipping AP20 as bedding CHAR(AMP) ATAP40 as pavement structure into the trench | FREQUENCY: - | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Ensure good coverage | RECORDS: Photos | RECORDS: Subcontract and Supplier Agreements
16 | Catchpit Connection (1) | W | Ensure minimum entry point 150mm above soffit of outlet stormwater pipe | As required | Visual inspection | Consistency with Subsoil Details | Photo | 16 - Catchpit Connection (1) | ACTION (Hold, Monitor, Witness): W | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe | FREQUENCY: As required | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Consistency with Subsoil Details | RECORDS: Photo | 3 - Design
16 | Catchpit Connection (2) | W | Perforate Catchpit and epoxy grout pipe from inside to completely seal connection. | As required | Visual inspection | Consistency with Subsoil Details | Photos | 16 - Catchpit Connection (2) | ACTION (Hold, Monitor, Witness): W | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection. | FREQUENCY: As required | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Consistency with Subsoil Details | RECORDS: Photos | ACTION (Hold, Monitor, Witness): H
17 | As-Built Drawings | W | Red pen marked-up As-Builts of every 'Issued for Construction' | Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure. | Drawings / Visual Inspection | As Built and GIS Data | Redline As-Built Drawings, scanned as .pdf files. | 17 - As-Built Drawings | ACTION (Hold, Monitor, Witness): W | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction' | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection | CONFORMANCE CRITERIA: As Built and GIS Data | RECORDS: Redline As-Built Drawings, scanned as .pdf files. | DETAIL: Design is approved and Drawings are of the latest revision.
FREQUENCY: Prior to commencement.
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT if not issued to IFC.
RECORDS: Drawing Register.
4 - Survey Setout
ACTION (Hold, Monitor, Witness): H
DETAIL: Setout Pipe Alignment and Service Locations with inlet CHAR(AMP) outlet points and inverts as required to construct to design
FREQUENCY: Prior to commencement.
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
CONFORMANCE CRITERIA: As per IFC Drawings and design AutoCAD file.
RECORDS: Survey Receipt.
5 - Pipe and Manhole Material Compliance
ACTION (Hold, Monitor, Witness): H
DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards
FREQUENCY: Prior to commencement.
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
CONFORMANCE CRITERIA: Pipe shall be Check for freshly formed pipes and return if required 1).Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall and street catchpit be in accordance with TDM Standards
RECORDS: Manufacturers Data Sheets, Delivery Dockets
6 - Locate Existing Services by Hand Digging / Hydro Vac
ACTION (Hold, Monitor, Witness): H
DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
FREQUENCY: Prior to commencement.
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
RECORDS: As-built Drawings. Doc. Review
7 - Trenching CHAR(AMP) Excavation (1)
ACTION (Hold, Monitor, Witness): H
DETAIL: Excavation methodology
FREQUENCY: Daily
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016)
RECORDS: Prestart RCP
7 - Trenching CHAR(AMP) Excavation (2)
ACTION (Hold, Monitor, Witness): M
DETAIL: Trench Profile - Width
FREQUENCY: Daily / as trenching takes place. Different depth methodology
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
RECORDS: Construction Photos
7 - Trenching CHAR(AMP) Excavation (3)
ACTION (Hold, Monitor, Witness): W
DETAIL: Trench Profile - Depth
FREQUENCY: Daily / as trenching takes place.
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
RECORDS: FH Drainage Line Record / Construction Photos
7 - Trenching CHAR(AMP) Excavation (4)
ACTION (Hold, Monitor, Witness): M
DETAIL: Trench Base
FREQUENCY: Every 10m
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Scalar testing
CONFORMANCE CRITERIA: Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2.
RECORDS: Test reports / Construction Photos
8 - Bedding for Concrete Pipe Laying CHAR(AMP) Manhole CHAR(AMP) Cesspit
ACTION (Hold, Monitor, Witness): W
DETAIL: Placing and compaction of Bedding Material.
FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
CONFORMANCE CRITERIA: Bedding CHAR(AMP) Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725
RECORDS: FH Drainage Line Record / Construction Photos
9 - Pipe Position Tolerance
ACTION (Hold, Monitor, Witness): M
DETAIL: -
FREQUENCY: At any point of pipe
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): -
CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design.
RECORDS: FH Drainage Line Record, Survey Data.
10 - Trench Backfill - Placing CHAR(AMP) Compacting
ACTION (Hold, Monitor, Witness): M
DETAIL: Placing and compacting of Trench Backfill Material
FREQUENCY: Throughout Trench Backfilling operation.
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm ATAP40 for subbase/basecourse.
RECORDS: Construction Photos
13 - Subsoil Material Compliance (1)
ACTION (Hold, Monitor, Witness): H
DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD010
FREQUENCY: Upon delivery to site
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
RECORDS: Delivery docket
13 - Subsoil Material Compliance (2)
ACTION (Hold, Monitor, Witness): H
DETAIL: Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate
FREQUENCY: -
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Sand
RECORDS: Delivery docket
14 - Trenching (1)
ACTION (Hold, Monitor, Witness): H
DETAIL: Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade
FREQUENCY: 10m intervals
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet.
RECORDS: Photo / subsoil log
14 - Trenching (2)
ACTION (Hold, Monitor, Witness): H
DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
FREQUENCY: 10m intervals
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
RECORDS: Photo / subsoil log
15 - Bedding, pipe installation and Backfill (1)
ACTION (Hold, Monitor, Witness): W
DETAIL: Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench.
FREQUENCY: 10m intervals
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
RECORDS: Photo / subsoil log
15 - Bedding, pipe installation and Backfill (2)
ACTION (Hold, Monitor, Witness): W
DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
FREQUENCY: 10m intervals
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
CONFORMANCE CRITERIA: Consistency with Subsoil Details
RECORDS: Photos
15 - Bedding, pipe installation and Backfill (3)
ACTION (Hold, Monitor, Witness): W
DETAIL: Backfill by tipping AP20 as bedding CHAR(AMP) ATAP40 as pavement structure into the trench
FREQUENCY: -
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
CONFORMANCE CRITERIA: Ensure good coverage
RECORDS: Photos
16 - Catchpit Connection (1)
ACTION (Hold, Monitor, Witness): W
DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
FREQUENCY: As required
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
CONFORMANCE CRITERIA: Consistency with Subsoil Details
RECORDS: Photo
16 - Catchpit Connection (2)
ACTION (Hold, Monitor, Witness): W
DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
FREQUENCY: As required
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
CONFORMANCE CRITERIA: Consistency with Subsoil Details
RECORDS: Photos
17 - As-Built Drawings
ACTION (Hold, Monitor, Witness): W
DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction'
FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
CONFORMANCE CRITERIA: As Built and GIS Data
RECORDS: Redline As-Built Drawings, scanned as .pdf files.